## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Post - S - Hardware Installation |  |  |  |  | Yes | Post - S - Hardware Installation | 06624c21-8217-47a5-b64c-8e350ba60fe4
checkpoint-status |  |  | checkpoint | Area accessible and ready to install the hardware
checkpoint-status |  |  | checkpoint | All hardware installation completed correctly within tolerance in respective area (Photos attached)
holdpoint |  |  | signoff | Raise Remedial/ Main Contractor Signoff
checklist-flat |  |  | checklist | PRE - S - Insulation |  |  |  |  | Yes | PRE - S - Insulation | 0dd5891a-e7d6-47a2-a51a-0b176a1eacbe
checkpoint-status |  |  | checkpoint | All materials checked & aligning with consented design & specifications prior to install
checkpoint-status |  |  | checkpoint | Correct product & R value as per specification
checkpoint-status |  |  | checkpoint | All Insulation completed correctly to specification & within tolerance in respective area(s)
checklist-flat |  |  | checklist | H - S - Bathroom Checks |  |  |  |  | Yes | H - S - Bathroom Checks | 20ef8dc1-b7cd-474c-a250-dbbc787f6744
checkpoint-status |  |  | checkpoint | Area & substrate acceptable
checkpoint-status |  |  | checkpoint | Vanity check (photos attached)
checkpoint-status |  |  | checkpoint | Mirror check (Photos attached)
checkpoint-status |  |  | checkpoint | Toilet roll holder check (Photos attached)
checkpoint-status |  |  | checkpoint | All relevant bathroom checks completed correctly within tolerance in respective area
holdpoint |  |  | signoff | Raise Remedial/ Main Contractor Signoff
checklist-flat |  |  | checklist | Post - S - Skirting/ Architraves & Trims |  |  |  |  | Yes | Post - S - Skirting/ Architraves & Trims | 2f2f9505-717f-48c6-a837-5120a444ef00
checkpoint-status |  |  | checkpoint | Architraves/ skirtings & trims are the correct size and profile
checkpoint-status |  |  | checkpoint | Skirting boards have been properly scribed, sanded, glued and mitred
checkpoint-status |  |  | checkpoint | Architraves/skirtings & trims have been installed with consistent even margins
checkpoint-status |  |  | checkpoint | Skirting/Architraves & trim work completed - specified level of finish achieved
checklist-flat |  |  | checklist | CST - S - Completion Documents |  |  |  |  | Yes | SYS - CST - S - Completion Documents (old version) | 3f1842d4-62eb-4754-830e-228569698cf0
checkpoint-status |  |  | checkpoint | All relevant Compliance Documentation completed and attached above
button | d7cd6780-ddae-5a5d-b508-bd4a6e7eb94a |  | button | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached | Yes, N/A
label | df75f841-f7cb-53cb-911f-3d81d7f8935a |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | Post - S - Handrails |  |  |  |  | Yes | Post - S - Handrails | 45c12a38-ad6d-4699-abec-9913e77c11db
checkpoint-status |  |  | checkpoint | Area & substrate acceptable
checkpoint-status |  |  | checkpoint | All handrails install completed correctly within tolerance in respective area
holdpoint |  |  | signoff | Raise Remedial/ Main Contractor Signoff
checklist-flat |  |  | checklist | POST - S - Internal Lining - Walls |  |  |  |  | Yes | POST - S - Internal Lining - Walls | 5605a3d1-c84f-4be3-9180-5b524a0fae4d
checkpoint-status |  |  | checkpoint | All preline services & passive fire (where required) completed, area accessible and substrate acceptable
checkpoint-status |  |  | checkpoint | Consider bracing, adhesive/sealant & lining layer(s) requirements (consider fire stopping between layers)
text | e4e5cd18-a5c0-5fe9-acd3-4d39e1428da9 |  | textbox | Specific products used (photos Required)
checkpoint-status |  |  | checkpoint | Services/penetrations, correctly formed & located (consider cut-out tolerances where applicable)
checkpoint-status |  |  | checkpoint | Correct fixing pattern/sealant (consider fire)/adhesive/layers installed to align with consented design and specifications
checkpoint-status |  |  | checkpoint | Any bracing elements completed to design specification
checkpoint-status |  |  | checkpoint | All lining(s) completed correctly to specification & level of finish acceptable in respective area(s)
checklist-flat |  |  | checklist | ST - S - Roof structure - Timber Trusses |  |  |  |  | Yes | ST - S - Roof structure - Timber Trusses | 5a19a990-120b-4048-9682-94f24bfbe2a6
checkpoint-status |  |  | checkpoint | Truss hardware completed as specified
checkpoint-status |  |  | checkpoint | All fixings in place
checkpoint-status |  |  | checkpoint | Truss seating checked and accurate
checkpoint-status |  |  | checkpoint | Tile battens installed and acceptable
checkpoint-status |  |  | checkpoint | Underlay completed and acceptable
checkpoint-status |  |  | checkpoint | Pre-tile checks completed and no issues identified
checkpoint-status |  |  | checkpoint | Load tiles completed and acceptable
checkpoint-status |  |  | checkpoint | Installation and recheck completed and no issues identified
checkpoint-status |  |  | checkpoint | Lay capping completed and acceptable
checkpoint-status |  |  | checkpoint | Ridges installed and acceptable
checkpoint-status |  |  | checkpoint | Facia gutters installed and acceptable
checkpoint-status |  |  | checkpoint | Trusses are installed correctly and acceptable
checklist-flat |  |  | checklist | Post - S - Internal door installation |  |  |  |  | Yes | Post - S - Internal door installation | a0597d30-3192-4ae3-86ec-3f8765083d0f
checkpoint-status |  |  | checkpoint | Door Number(s) / Location checked and accurate
checkpoint-status |  |  | checkpoint | Floor clearance - Adequate for proposed floor coverings
checkpoint-status |  |  | checkpoint | Fixings - Consider Jamb/Hinges, all installed & secure (Size & type)
checkpoint-status |  |  | checkpoint | Door leaf to jamb gaps parallel & correct (Consider paint thickness(s))
checkpoint-status |  |  | checkpoint | Door opening as required & is plumb
checkpoint-status |  |  | checkpoint | All doors installed, damage free & completed correctly to specification in respective area(s)
checklist-flat |  |  | checklist | POST - S - Internal Lining - Ceilings |  |  |  |  | Yes | POST - S - Internal Lining - Ceilings | a65427bd-6913-454a-bbd0-f57e4579e2ec
checkpoint-status |  |  | checkpoint | All preline services & passive fire (where required) completed, area accessible and substrate acceptable
checkpoint-status |  |  | checkpoint | Consider bracing, adhesive/sealant & lining layer(s) requirements (consider fire stopping between layers)
checkpoint-status |  |  | checkpoint | Services/Penetrations, correctly formed & located (consider cutout tolerances and access hatches (location & size) where applicable)
checkpoint-status |  |  | checkpoint | Correct fixing pattern/sealant (consider fire)/adhesive/layers installed to align with consented design and specifications
checkpoint-status |  |  | checkpoint | Any bracing elements completed to design specification
checkpoint-status |  |  | checkpoint | All lining(s) completed correctly to specification & level of finish acceptable in respective area(s)
checklist-flat |  |  | checklist | CST - S - Completion Documents |  |  |  |  | Yes | CST - S - Completion Documents | af12070a-419a-478d-be0d-3bf8206d478d
checkpoint-status |  |  | checkpoint | All relevant Compliance Documentation completed and attached above
boolean | 3dda2a84-b116-5fea-9b79-78447abce784 |  | tickbox | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
label | 43644670-8879-545c-9f7c-8fa51bc46d4b |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint |  |  | signoff | Request Signoff
checklist-sectioned |  |  | checklist | ST - S - Concrete Pour |  |  |  |  | Yes | ST - S - Concrete Pour | d512f7d0-da36-4be8-b9ec-3b2c0a7611fd
checkpoint-group |  |  | section | Pour Details
checkpoint-status |  |  | checkpoint | Pour details entered
text | c0a17092-db42-5e72-9650-c832b0fa790a |  | textbox | Area to be poured:
text | 7e39235b-bdf3-5a4f-951a-02c668779e9b |  | textbox | Date of pour:
checkpoint-status |  |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-group |  |  | section | Formwork and Embedded Items
checkpoint-status |  |  | checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint-status |  |  | checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint-status |  |  | checkpoint | All surfaces correctly prepared (e.g joints to existing concrete, release agent to formwork etc)
checkpoint-status |  |  | checkpoint | Any control joints/ stop ends installed accurately and correctly braced
checkpoint-group |  |  | section | Reinforcing
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/correct
checkpoint-status |  |  | checkpoint | Splice laps checked/correct
checkpoint-status |  |  | checkpoint | All couplers installed correctly (if reid bar couplers have been used, has epconC8 epoxy been used as specified)
boolean | c212ebe5-fe78-598d-a79e-99b75bfd72db |  | tickbox | Appointment with the engineers confirmed (Enter date & time of the appointment)
boolean | 99ac254c-19c5-58fc-922d-d0ab98f12e38 |  | tickbox | Reidbar – coupler and flange nut installations are inspected by the MV Engineer
checkpoint-status |  |  | checkpoint | IMBMS couplers testing carried out for Village Podiums in the form of tensile testing in accordance with NZS3101.1.2006 and results acceptable
checkpoint-status |  |  | checkpoint | All starter bars are installed correctly (location, size and spacing )
checkpoint-status |  |  | checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Welding certificates sited and attached
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
checkpoint-group |  |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status |  |  | checkpoint | Waterproofing elements have been correctly installed and checked
checkpoint-status |  |  | checkpoint | Relevant service requirements completed (locations checked and accurate)
checkpoint-status |  |  | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint-status |  |  | checkpoint | Ryman inspection completed - Approval given to pour concrete
checkpoint-group |  |  | section | Concrete Supplier Specifics
checkpoint-status |  |  | checkpoint | Concrete Supplier details entered
text | 93100df6-ef7c-5738-b8f2-573c46b46b37 |  | textbox | Supplier Name:
text | 48e0decc-a99a-57d7-b9ef-c68833f73820 |  | textbox | Specified concrete strength: | mPA
text | 166287bb-8604-5fa7-85b7-5a6fc008671a |  | textbox | Concrete strength ordered: | mPA
text | 56c4a9bf-c017-59a8-99d6-0a2a2b48a1b3 |  | textbox | Concrete quantity ordered: | m3
button | 8cf1725d-dd87-5ee5-a7d6-0bccc023b935 |  | button | Test blocks booked | Yes, No, N/A
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-group |  |  | section | Placement Method
checkpoint-status |  |  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
checkpoint-status |  |  | checkpoint | Heights and falls checked/confirmed before placement
button | 4af5c14f-6c99-5676-a0fb-4e08cfad49cf |  | button | Is the cover correct to specification | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Heights and falls checked/ confirmed after placement
checkpoint-status |  |  | checkpoint | Any curing compound applied correctly
checkpoint-status |  |  | checkpoint | Concrete placement completed - specified level of finish achieved
checkpoint-group |  |  | section | Post Pour Checks/Sign Off
checkpoint-status |  |  | checkpoint | Any remedial work completed
holdpoint |  |  | signoff | Raise remedial/ Request Signoff
checkpoint-status |  |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checklist-flat |  |  | checklist | FC - S - Windows, Sliders and Sealants |  |  |  |  | Yes | FC - S - Windows, Sliders and Sealants | d521ecf0-b22e-4bd9-a4a3-074cf068787a
checkpoint-status |  |  | checkpoint | Fixings and clearance around opening min 6mm & max 18mm and PEF rod/air seal are within acceptable tolerance level
checkpoint-status |  |  | checkpoint | Check taping around, before installing the windows and sliders
checkpoint-status |  |  | checkpoint | Packers to be correctly used and set back to allow continuous air seal
checkpoint-status |  |  | checkpoint | Jambs level and straight for finishing lines on the side
checkpoint-status |  |  | checkpoint | Door and window jambs flush to GIB Board
checkpoint-status |  |  | checkpoint | Check air seal is provided at the rear of the window reveal
checkpoint-status |  |  | checkpoint | All joints detailed as per attached Detail Document
checkpoint-status |  |  | checkpoint | All framing completed correctly within tolerance in respective area
checkpoint-status |  |  | checkpoint | Sill support fixing bars installed for all joinery within acceptable tolerance level
checkpoint-status |  |  | checkpoint | All windows, sliders and sealant installation completed to specification & within tolerance in respective area(s)
checklist-flat |  |  | checklist | FC - S - External Envelope |  |  |  |  | Yes | FC - S - External Envelope | e9d804e8-ad96-4ec2-a63a-84771cd8517a
checkpoint-status |  |  | checkpoint | Eco ply taped nailing checked
label | 18fc9198-ff3e-50ad-a982-3e762aa0fe4d |  | note | Supplied & installed by others
checkpoint-status |  |  | checkpoint | RAB board Fixing and spacings checked in accordance with manufacturers specs (Photos attached)
checkpoint-status |  |  | checkpoint | Fire strip installed (Photos attached)
checkpoint-status |  |  | checkpoint | Soffit checked and accurate (Photos attached)
checkpoint-status |  |  | checkpoint | Garage reveals checked and accurate (Photos attached)
checkpoint-status |  |  | checkpoint | DPC installed checked and accurate (Photos attached)
holdpoint |  |  | signoff | Request sign off
checklist-flat |  |  | checklist | ST - S - Timber Framing |  |  |  |  | Yes | ST - S - Timber Framing | f2ac52cb-25d5-46f1-9a09-c92b4f32c0c3
checkpoint-status |  |  | checkpoint | Dimensions / locations checked and accurate
checkpoint-status |  |  | checkpoint | All frames are square / Frames are plumb and level
checkpoint-status |  |  | checkpoint | Fixings are correct
checkpoint-status |  |  | checkpoint | Installed in correct level, plumb, correct pitch and braced
checkpoint-status |  |  | checkpoint | Any bracing requirements installed
checkpoint-status |  |  | checkpoint | All framing completed correctly within tolerance in respective area
checklist-flat |  |  | checklist | POST - S - Stopping |  |  |  |  | Yes | POST - S - Stopping | fde6b03c-4906-487a-961d-a048e7fc68b9
checkpoint-status |  |  | checkpoint | Consider fire stopping between layers of lining & apply compound(s) as specified
checkpoint-status |  |  | checkpoint | Openings/penetrations/corners & bulkheads, correctly formed (consider tolerances where applicable)
checkpoint-status |  |  | checkpoint | Consider square stopping, slimlines, joints checked & acceptable
checkpoint-status |  |  | checkpoint | Correct compound(s) used to align with consented specifications
checkpoint-status |  |  | checkpoint | Adequate drying time between coats, no visible bubbling/deforms & each coat is sanded as applicable
checkpoint-status |  |  | checkpoint | Light check completed to ensure no sheet joins stand out
checkpoint-status |  |  | checkpoint | Stopping work completed - specified level of finish achieved