## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Plastered Nibs/Spandrel Beams |  |  |  |  | Yes | Plastered Nibs/Spandrel Beams QA | 28c25f36-d27c-42c7-b776-deded2969f5b
checkpoint-status |  |  | checkpoint | Area Accessible
checkpoint-status |  |  | checkpoint | Substrate acceptable and ok to begin work
checkpoint-status |  |  | checkpoint | All nibs/ beams prepared for plaster
checkpoint-status |  |  | checkpoint | Saddle flashing installed to deck ends (photos attached)
checkpoint-status |  |  | checkpoint | Falls set to 5 degrees as per plan - 20mm Fall over 200mm completed by others
checkpoint-status |  |  | checkpoint | Corner and drip edge flashings installed correctly
checkpoint-status |  |  | checkpoint | Plaster installed as per spec and painted (photos attached)
checkpoint-status |  |  | checkpoint | All cladding completed correctly (photos attached)
checkpoint-status |  |  | checkpoint | All works completed as per specifications
holdpoint |  |  | signoff | Request Sign Off
checklist-flat |  |  | checklist | Cavity Battens |  |  |  |  | Yes | Cavity Battens QA | 52cdf5e5-16b7-49d0-b013-f93d3a8673ca
checkpoint-status |  |  | checkpoint | 20mm Cavity poly battens installed (photos attached)
checkpoint-status |  |  | checkpoint | Correct fixings as per the specifications
checkpoint-status |  |  | checkpoint | Specified Battens installed
checkpoint-status |  |  | checkpoint | Associated STO Flashings installed as per specifications (photos attached)
holdpoint |  |  | signoff | Request Sign Off
checklist-flat |  |  | checklist | Sto Poren Panel Cladding |  |  |  |  | Yes | Sto Poren Panel Cladding QA | add4e0fc-f00c-4c9d-a015-a2449beabe0d
checkpoint-status |  |  | checkpoint | Area Accessible
checkpoint-status |  |  | checkpoint | Substrate acceptable and ok to begin work
checkpoint-status |  |  | checkpoint | Installation of foot tray, windows flashings and battens completed (photos attached)
checkpoint-status |  |  | checkpoint | Appropriate fixings are used at correct centres for STO Poren cladding
checkpoint-status |  |  | checkpoint | All cladding completed correctly
checkpoint-status |  |  | checkpoint | Meshcoat to plaster, banding installed (photos attached)
checkpoint-status |  |  | checkpoint | Topcoat and painted (photos attached)
checkpoint-status |  |  | checkpoint | All works completed as per specifications
holdpoint |  |  | signoff | Request Sign Off
checklist-flat |  |  | checklist | Completion Documents |  |  |  |  | Yes | Completion Documents | f878351e-cc1c-4dcf-b46b-3d0d1106b302
checkpoint-status |  |  | checkpoint | All relevant Compliance Documentation completed and attached above
boolean | deeabf19-1ce1-5bd2-bf49-a51146e3f250 |  | tickbox | LBP Memorandum/ Record of works filled out, signed and attached
boolean | 04a760f7-6ae0-50bd-9631-06df0e9ab428 |  | tickbox | Any Additional Compliance Documentation - Completed and Attached
label | dc441e08-38c3-58ad-96b5-139b76eb1dc2 |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint |  |  | signoff | Request Signoff