## Breakdown
PlasterWorks - 045 Kevin Hickman (Riccarton Park)
Stage 401
B02 & B03 Tunnel/Ramp
Elevation A
|  |  |  | Exterior Plastering | Pre-populate | FC - S - External Plaster - Nibs & Beams
Elevation B
|  |  |  | Exterior Plastering | Pre-populate | FC - S - External Plaster - Nibs & Beams
Elevation C
|  |  |  | Exterior Plastering | Pre-populate | FC - S - External Plaster - Nibs & Beams
Elevation E
|  |  |  | Exterior Plastering | Pre-populate | FC - S - External Plaster - Nibs & Beams
Compliance Documents
|  | Stage 401 - B02 & B03 Tunnel/Ramp | Pre-populate | CST - S - Completion Documents

## Checklist
Type | Name | Value
checklist-flat | FC - S - External Plaster - Nibs & Beams
checkpoint | All nibs/ beams prepared for plaster checked and acceptable
checkpoint | Saddle flashing installed to deck ends, checked and accurate
checkpoint | Falls set to 5 degrees as per plan - 20mm Fall over 200mm checked and accurate
checkpoint | Corner and drip edge flashings installed correctly and acceptable
checkpoint | Plaster installed as per spec and painted, checked and acceptable
checkpoint | All cladding works completed and acceptable
Type | Name | Value
checklist-flat | CST - S - Completion Documents
checkpoint | All relevant Compliance Documentation completed and attached above
button | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
label | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | Request Signoff