## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | FC - S - RAB |  |  |  |  | Yes | FC - S - RAB | 116d9728-a42c-42b3-afca-97cdb83f85fd
checkpoint-status |  |  | checkpoint | Fixing and spacings checked in accordance with manufacturers specs
checkpoint-status |  |  | checkpoint | White MS sealant for air seals between RAB board and concrete horizontal and vertical joints
checkpoint-status |  |  | checkpoint | 3M taping around windows and external corners and vertical joints and horizontal flashing checked
checkpoint-status |  |  | checkpoint | Vaproshield to interfloor installed after vertical taping
checkpoint-status |  |  | checkpoint | Bracing checked and accurate
checkpoint-status |  |  | checkpoint | Penetrations and punctures sealed with flashing tape
checkpoint-status |  |  | checkpoint | Sealing joints over internal and external joints
checkpoint-status |  |  | checkpoint | Battern on RAB Board for cladding fixings
checkpoint-status |  |  | checkpoint | All RAB board installation completed to specification & within tolerance in respective area(s)
checklist-flat |  |  | checklist | FC - S - External Envelope |  |  |  |  | Yes | FC - S - External Envelope | 11934edb-792e-4862-9dec-ccb6ee51cffb
checkpoint-status |  |  | checkpoint | Eco ply taped nailing checked
label | 5fde8d81-8d51-5e03-98ef-a0a52e071262 |  | note | Supplied & installed by others
checkpoint-status |  |  | checkpoint | RAB board Fixing and spacings checked in accordance with manufacturers specs (Photos attached)
checkpoint-status |  |  | checkpoint | Fire strip installed (Photos attached)
checkpoint-status |  |  | checkpoint | Soffit checked and accurate (Photos attached)
checkpoint-status |  |  | checkpoint | Garage reveals checked and accurate (Photos attached)
checkpoint-status |  |  | checkpoint | DPC installed checked and accurate (Photos attached)
holdpoint |  |  | signoff | Request sign off
checklist-sectioned |  |  | checklist | FC - S - Roofing |  |  |  |  | Yes | FC - S - Roofing | 4b2de559-e626-40ad-9e0a-d00c988a559c
checkpoint-group |  |  | section | Pre-installation checks
checkpoint-status |  |  | checkpoint | Scaffolding in place and tagged
checkpoint-status |  |  | checkpoint | Edge protection and safety nets installed
checkpoint-status |  |  | checkpoint | Correct Purlin / Steelwork heights
checkpoint-status |  |  | checkpoint | Correct Precast wall heights
checkpoint-status |  |  | checkpoint | Observations
checkpoint-group |  |  | section | Plywood Gutter Substrate
checkpoint-status |  |  | checkpoint | Plywood laid a minimum 0.5 degrees
checkpoint-status |  |  | checkpoint | Plywood surface smooth finish CD minimum 1.75mm H3 no knots
checkpoint-status |  |  | checkpoint | Plywood laid with 2mm gaps
checkpoint-status |  |  | checkpoint | Plywood fastened with stainless steel screws recessed 2mm
checkpoint-status |  |  | checkpoint | Outlets installed correctly 73-75mm above plywood
checkpoint-status |  |  | checkpoint | Observations
checkpoint-group |  |  | section | Steel Tray Substrate
checkpoint-status |  |  | checkpoint | Metal profile installed upside down with fastenings spaced correctly
checkpoint-status |  |  | checkpoint | Flashings installed on hips and valleys
checkpoint-status |  |  | checkpoint | Insulation protected from crushing (edge of gutter, timber edging, etc.)
checkpoint-status |  |  | checkpoint | Outlets framed and plywood routed out
checkpoint-status |  |  | checkpoint | Unused Roofing Iron Secured
checkpoint-status |  |  | checkpoint | Observations
checkpoint-group |  |  | section | Insulation panels
checkpoint-status |  |  | checkpoint | Sheets installed in brick-bond pattern
checkpoint-status |  |  | checkpoint | No gaps between sheets
checkpoint-status |  |  | checkpoint | Adhesive applied evenly and at correct amount
checkpoint-status |  |  | checkpoint | Sheets held down for correct length of time
checkpoint-status |  |  | checkpoint | Roof is confirmed uniform and flat
checkpoint-status |  |  | checkpoint | Observations
checkpoint-group |  |  | section | Membrane
checkpoint-status |  |  | checkpoint | Insulation panels are acceptable level of cleanliness
checkpoint-status |  |  | checkpoint | Membrane color and thickness confirmed correct
checkpoint-status |  |  | checkpoint | Membrane penetrations have been sealed and are watertight
checkpoint-status |  |  | checkpoint | All welded seams and proprietary items to be seam probed
checkpoint-status |  |  | checkpoint | Observations
checklist-flat |  |  | checklist | FC - S - Eyebrow - Canopy |  |  |  |  | Yes | FC - S - Eyebrow - Canopy | 5cc90657-0958-4e99-a461-9a622c20bf20
checkpoint-status |  |  | checkpoint | Setout completed, checked & accurate (no clashes & wall locations clearly marked)
checkpoint-status |  |  | checkpoint | Framing Dimensions / locations checked & accurate (openings considered where applicable)
checkpoint-status |  |  | checkpoint | All frames have been installed square, straight and plumb
checkpoint-status |  |  | checkpoint | DPC installed (if required) correctly
checkpoint-status |  |  | checkpoint | Fixings are correct to specification including any seismic/bracing requirements (attach relevant photos)
checkpoint-status |  |  | checkpoint | All Nogs (Service/Specialty) & penetrations - installed, checked & correct (consider acoustic & fire rating requirements)
checkpoint-status |  |  | checkpoint | All timber framing completed correctly to specification & within tolerance in respective area(s)
checklist-flat |  |  | checklist | FC - S - Windows, Sliders and Sealants |  |  |  |  | Yes | FC - S - Windows, Sliders and Sealants | 9cf5629f-9a87-4e05-b536-fc34f7f2599e
checkpoint-status |  |  | checkpoint | Fixings and clearance around opening min 6mm & max 18mm and PEF rod/air seal are within acceptable tolerance level
checkpoint-status |  |  | checkpoint | Check taping around, before installing the windows and sliders
checkpoint-status |  |  | checkpoint | Packers to be correctly used and set back to allow continuous air seal
checkpoint-status |  |  | checkpoint | Jambs level and straight for finishing lines on the side
checkpoint-status |  |  | checkpoint | Door and window jambs flush to GIB Board
checkpoint-status |  |  | checkpoint | Check air seal is provided at the rear of the window reveal
checkpoint-status |  |  | checkpoint | All joints detailed as per attached Detail Document
checkpoint-status |  |  | checkpoint | All framing completed correctly within tolerance in respective area
checkpoint-status |  |  | checkpoint | Sill support fixing bars installed for all joinery within acceptable tolerance level
checkpoint-status |  |  | checkpoint | All windows, sliders and sealant installation completed to specification & within tolerance in respective area(s)
checklist-flat |  |  | checklist | FC - S - Flashing installation |  |  |  |  | Yes | FC - S - Flashing installation | a46d64cd-9024-4d41-8cd3-3d8c775ece1b
checkpoint-status |  |  | checkpoint | Head flashing installed with sealant at windows and doors (STO system)
checkpoint-status |  |  | checkpoint | Rainshield installed between joinery and lintel (brick)
checkpoint-status |  |  | checkpoint | DPC and WANZ bar installed at the bottom of the joinery (see fixing) as per manufacturer's spec
checkpoint-status |  |  | checkpoint | Aluminium window jamb side flashings are installed
checkpoint-status |  |  | checkpoint | All flashing installed at windows and doors to specification & within tolerance in respective area(s)
checklist-flat |  |  | checklist | FC - S - Exterior Timber Framing |  |  |  |  | Yes | FC - S - Exterior Timber Framing | e9f83a96-c47d-4c0a-a4d6-d94bd364c54c
checkpoint-status |  |  | checkpoint | Setout completed, checked & accurate (no clashes & wall locations clearly marked)
checkpoint-status |  |  | checkpoint | Framing Dimensions / locations checked & accurate (openings considered where applicable)
checkpoint-status |  |  | checkpoint | All frames have been installed square, straight and plumb
checkpoint-status |  |  | checkpoint | DPC installed (if required) correctly
checkpoint-status |  |  | checkpoint | Fixings are correct to specification including any seismic/bracing requirements (attach relevant photos)
checkpoint-status |  |  | checkpoint | All Nogs (Service/Specialty) & penetrations - installed, checked & correct (consider acoustic & fire rating requirements)
checkpoint-status |  |  | checkpoint | All timber framing completed correctly to specification & within tolerance in respective area(s)