## Breakdown
Keith Park (Pro-Floors) | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5
B09 & B10 Ramp
Civil
Excavation
|  |  |  | Bulk Excavation |  | Prepopulate | Bulk Excavation
Foundation
|  |  |  | Basement Backfilling |  | Prepopulate | Backfilling
|  |  | Completion Documents |  |  | Prepopulate | Completion Documents

## Checklist
checklist-flat | C - S - Bulk Excavation
checkpoint | Excavation depth determined using appropriate RL's (Check relevant drawings and revisions)
checkpoint | Confirm location and isolation of relevant services
checkpoint | Batters formed correctly
checkpoint | Trenches/ pits / hazardous areas appropriately isolated
checkpoint | Soft spots identified and appropriate remedial completed
checkpoint | Hardfill/ blinding installed correctly to required specification
checkpoint | Excavation completed - Correct locations and RL's achieved
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | F - S - Backfilling
checkpoint | Waterproofing membrane installed
checkpoint | Area clean of debris
checkpoint | Backfill completed correctly and heights checked/ correct
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | CST - S - Completion Documents
checkpoint | All relevant Compliance Documentation completed and attached above
bool | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
label | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | Request Signoff
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS