## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Lift Pit Installation |  |  |  |  | Yes | Lift Pit Installation | 0b7f672c-aeef-45d0-90ca-2a68a0f0be87
checkpoint-status |  |  | checkpoint | Set-out completed, checked and accurate
checkpoint-status |  |  | checkpoint | Excavation location and depth accurate
checkpoint-status |  |  | checkpoint | Bedding depth and material correct
checkpoint-status |  |  | checkpoint | Backfill completed and compacted as per specifications
checkpoint-status |  |  | checkpoint | Backfill completed correctly and heights checked/correct
checklist-flat |  |  | checklist | Excavation |  |  |  |  | Yes | Excavation | 109cec7c-b739-4cad-9529-bbbd08640451
checkpoint-status |  |  | checkpoint | Excavation to subgrade as per surveyor RL heights and Design/Instruction
checklist-flat |  |  | checklist | Bulk Excavation |  |  |  |  | Yes | Bulk Excavation | 23dcf94f-f6a9-433c-a3cc-7cf98eb88b01
checkpoint-status |  |  | checkpoint | Excavation depth determined using appropriate RL's (Check relevant drawings and revisions)
checkpoint-status |  |  | checkpoint | Confirm location and isolation of relevant services
checkpoint-status |  |  | checkpoint | Batters formed correctly
checkpoint-status |  |  | checkpoint | Trenches/ pits / hazardous areas appropriately isolated
checkpoint-status |  |  | checkpoint | Soft spots identified and appropriate remedial completed
checkpoint-status |  |  | checkpoint | Hardfill/ blinding installed correctly to required specification
checkpoint-status |  |  | checkpoint | Excavation completed - Correct RL's achieved
checklist-flat |  |  | checklist | Manhole Installation |  |  |  |  | Yes | Manhole Installation | 300abfe0-7538-4eac-97f4-7116ac41881b
checkpoint-status |  |  | checkpoint | Set-out completed, checked and accurate
checkpoint-status |  |  | checkpoint | Excavation location and depth accurate
checkpoint-status |  |  | checkpoint | Bedding depth and material correct
checkpoint-status |  |  | checkpoint | Manhole installed to specified height and invert level
checkpoint-status |  |  | checkpoint | Manhole risers & steps installed and joints sealed as specified
checkpoint-status |  |  | checkpoint | Manhole benching completed and acceptable
checkpoint-status |  |  | checkpoint | Concrete manhole cover installed and sitting correctly with hole covered if required
checkpoint-status |  |  | checkpoint | Cast Iron lid installed and sitting at correct height
checkpoint-status |  |  | checkpoint | Manhole installation completed as per the specifications
checkpoint-status |  |  | checkpoint | Backfill completed & compacted as per the specifications
checklist-flat |  |  | checklist | Completion Documentation |  |  |  |  | Yes | Completion Documentation | 39b25319-562b-4a79-91d8-bcfe521f4a72
checkpoint-status |  |  | checkpoint | Producer Statements attached (PS3)
checkpoint-status |  |  | checkpoint | Other documentation attached - As-Built Drawings etc.
checklist-flat |  |  | checklist | Footpaths checklist |  |  |  |  | Yes | Footpaths checklist | 4b2ae070-10fc-4746-b9bd-fb5915bbba8b
checkpoint-status |  |  | checkpoint | Provide contractor with approved for construction drawings at time of engagement that show heights, detail finish
checkpoint-status |  |  | checkpoint | Landscape Prep
checkpoint-status |  |  | checkpoint | Surveyor engaged to mark out
checkpoint-status |  |  | checkpoint | Lighting Ducts installed by others
checkpoint-status |  |  | checkpoint | Irrigation Ducting in place as per design plans
checkpoint-status |  |  | checkpoint | Footpaths prepped to heights as provided by surveyor
checkpoint-status |  |  | checkpoint | Paver edging completed as per design drawings
checkpoint-status |  |  | checkpoint | Footpath prepped with mesh
checkpoint-status |  |  | checkpoint | Footpath poured
checkpoint-status |  |  | checkpoint | Footpath sawcut every 5 metres
holdpoint |  |  | signoff | Request sign off
checklist-flat |  |  | checklist | Subsoil Drainage |  |  |  |  | Yes | Subsoil Drainage | 4b74545f-8360-4955-8b4e-f8186c67eb44
checkpoint-status |  |  | checkpoint | Set-out completed, checked and accurate
checkpoint-status |  |  | checkpoint | Subsoil Drainage location and depth accurate
checkpoint-status |  |  | checkpoint | Bedding depth and material correct
checkpoint-status |  |  | checkpoint | Correct pipe (size, material & class) laid to specified level, grade and jointed as specified
checkpoint-status |  |  | checkpoint | Subsoil drainage installation completed as per the specifications
checkpoint-status |  |  | checkpoint | Backfill completed - correct materials and compaction methodology used - specified compaction achieved
checklist-flat |  |  | checklist | Roading checklist |  |  |  |  | Yes | Roading checklist | 5c46a934-4dc0-41ff-b1ec-d74f5bffc971
checkpoint-status |  |  | checkpoint | Provide contractor with approved for construction drawings at time of engagement that show RL`s, kerb types and locations, subsoil locations
checkpoint-status |  |  | checkpoint | Surveyor engaged to mark out
checkpoint-status |  |  | checkpoint | 150mm ducts laid if needed
checkpoint-status |  |  | checkpoint | Subsoils laid if needed
checkpoint-status |  |  | checkpoint | Kerbs prepped to heights as provided by surveyor
checkpoint-status |  |  | checkpoint | Kerbs poured as per detailed approved construction drawings
checkpoint-status |  |  | checkpoint | Crossings installed as per drawings supplied
checkpoint-status |  |  | checkpoint | Beam Test
checkpoint-status |  |  | checkpoint | Asphalt laid
checkpoint-status |  |  | checkpoint | Line Marking
holdpoint |  |  | signoff | Request sign off
checklist-flat |  |  | checklist | Rodding Eye |  |  |  |  | Yes | Rodding Eye | 7089a042-17f3-4db6-a912-7dd925e41825
checkpoint-status |  |  | checkpoint | Set-out completed, checked and accurate
checkpoint-status |  |  | checkpoint | Rodding eye installation completed to required specifications
boolean | eb85e685-1620-5caf-b382-8da9dc19f9c2 |  | tickbox | Correct rodding eye (size, material & class) installed
boolean | 21a1ef95-80b8-50b9-881b-38a7e9d43fdc |  | tickbox | Laid to specified level
boolean | c70bc6bd-629a-5770-b092-11b4cbbcf93f |  | tickbox | Installed in correct location
checklist-flat |  |  | checklist | Backfilling |  |  |  |  | Yes | Backfilling | bf9dc5b7-38c8-4f5d-bb36-7d6087ad721c
checkpoint-status |  |  | checkpoint | Waterproofing membrane installed
checkpoint-status |  |  | checkpoint | Area clean of debris
checkpoint-status |  |  | checkpoint | Backfill completed correctly and heights checked/ correct
checklist-flat |  |  | checklist | Completion Documents (B07) |  |  |  |  | Yes | Completion Documents (B07) | c627a5f3-1e93-4a23-86df-e111e48e9814
checkpoint-status |  |  | checkpoint | All relevant Compliance Documentation completed and attached above
button | a677c18b-6bda-54d4-a92b-b84577baa44b | DataPoint is missing 'button' values | button | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
button | 7379cfd8-cbed-5323-bcff-11926de7f28b | DataPoint is missing 'button' values | button | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | Installation |  |  |  |  | Yes | Installation | f3e1eabf-d4be-41e8-b496-c79050bb2770
checkpoint-status |  |  | checkpoint | Installation of Aggregate as per design/instruction
checkpoint-status |  |  | checkpoint | Installation of subsoils as per design/instruction
checkpoint-status |  |  | checkpoint | Installation of Rodding Eyes as per design/instruction