## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 71528d6d-487b-4c3d-8c38-95e2f5354310 |  | checklist | QA - First Fix |  |  |  |  | Yes | QA - First Fix | 122895a3-77c4-44d5-9ff2-d8a08a5a3932
checkpoint-status | 529af275-4777-43eb-8ccc-c55aab28c1a4 |  | checkpoint | Area & substrate acceptable
checkpoint-status | 410eb875-7b55-4d9c-bf6d-825ce11d29ed |  | checkpoint | Pvc waste installed
checkpoint-status | ba34e552-57a9-42e3-a744-535f4169c4a5 |  | checkpoint | Pvc flood test
checkpoint-status | e44c5a76-5e25-4415-97d6-519c45c5be46 |  | checkpoint | Pvc sound lagged
checkpoint-status | f3a3eb9f-7c70-45ee-bbc0-749356b1759f |  | checkpoint | Shower installed
checkpoint-status | e5376e86-e882-43c0-9c51-d58b22a7ef53 |  | checkpoint | Heating system piping installed
checkpoint-status | 9ca91431-3176-4aed-8d85-aff1191e4d9d |  | checkpoint | Basin feeds in correct location
checkpoint-status | 7285814f-0bfe-47e3-819d-b002e4f9e149 |  | checkpoint | Inspection opening - plug removed and cap returned to place
checkpoint-status | 145f34f1-c441-4d6b-8c81-434c17452e95 |  | checkpoint | Toilet feed in correct location
checkpoint-status | c37e8b86-e609-47f2-bae0-9bd465e47c0e |  | checkpoint | Feeds tested to 1500 Kpa
checkpoint-status | 58046566-48b6-4fae-aa22-985d5fd3f5a4 |  | checkpoint | Fire wraps sealed at floor level
checkpoint-status | 23c978ed-67df-4d78-92f3-25f140a69df2 |  | checkpoint | Penetrations logged in register
checkpoint-status | 52ca2589-e047-41b2-afd7-378bcc43e620 |  | checkpoint | Rubbish removed
checkpoint-status | 13aeeb3c-4d35-43db-ab68-c72292a0c349 |  | checkpoint | Pipe securely clipped
checkpoint-status | 28629cc6-2011-447d-a667-69b91482a6ae |  | checkpoint | Shower tray protective box installed
checkpoint-status | 8831db16-f91a-4efb-a001-d17511b088f1 |  | checkpoint | Council inspection passed and attached
checkpoint-status | 680d7e87-2f1e-40f3-a547-53d0f0189065 |  | checkpoint | Area is left clean and tidy (attach photo)
checkpoint-status | 1cba5810-d1e8-4ad8-b444-d1c9c572399f |  | checkpoint | First Fix completed reviewed and approved
checklist-flat | 0e39baef-72d0-4aad-bb2d-9e43155eec9f |  | checklist | QA - Coldwater Checklist |  |  |  |  | Yes | QA - Coldwater Checklist | 23c9cb9e-25d3-4814-8887-87d0cb69184a
checkpoint-status | 4623581a-f886-44eb-9cd0-9d100bfa3e28 |  | checkpoint | Connections welded/crimped correctly
checkpoint-status | bd0d63c5-d1ab-4af1-8f12-9bc3a283ee1e |  | checkpoint | Clip spacing to manufacturer's specs horizontal/ vertical
checkpoint-status | 8cd32b00-f57e-4fbb-9052-cdab949ff325 |  | checkpoint | Lagging installed and neat
checkpoint-status | ce80d239-3a7a-40c8-a4e1-9d748f2b57e7 |  | checkpoint | Labels installed
checkpoint-status | 32de8797-cd8b-4051-ad0d-19543988f3cd |  | checkpoint | Correct valves fitted correctly
checklist-sectioned | 3179eefa-9802-4a95-afe0-2a8da41fa658 |  | checklist | Basement Underslab |  |  |  |  | Yes | QA - Basement Underslab | 32ea0ea8-e26a-4991-8c3b-d65265e0a614
checkpoint-group | f7de560d-518c-43b8-a873-788559153d57 |  | section | Area Prestart / Acceptance & Drawings
checkpoint-status | 4791534c-b414-4ef4-b5a7-ee5cb72c00b3 |  | checkpoint | Area ready for works (grids setout, area accessible and approval to start)
text | a0a4b47e-71b8-5661-a3d8-8cc9a83b2764 |  | textbox | Zone / Area
checkpoint-status | b8826527-babb-4785-b562-68b1e8f0712c |  | checkpoint | Current Dimensioned Slab Set Out Drawings numbers and revisions recorded
checkpoint-group | 0bc7423e-e1a8-431b-bf8b-26deb9217f17 |  | section | Under Slab Pipe install
checkpoint-status | a55b45fd-b90e-476f-aa9a-5418269fd95d |  | checkpoint | Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
text | 4b444d90-e2a1-5ec2-bd5b-cb1ee66481a2 |  | textbox | Start Invert
text | 923d3447-d4c3-5c48-a778-9e23f757f8e1 |  | textbox | Finish Invert
text | b82a1c9e-96ba-5cb8-8acd-db7b499221c6 |  | textbox | Grade of Pre-Line %
text | 991dcb84-2e2d-5fbf-bb07-b0b24e2721b6 |  | textbox | Product Type
checkpoint-status | 7e1691f0-7ae1-4b1b-81f6-e57823215efa |  | checkpoint | Pipe supported
checkpoint-status | 04034572-a19f-4e70-b415-d51484134aca |  | checkpoint | Install Tests completed, reviewed & approved
text | 9e67ffd2-11a1-59af-a6f4-1fd5f7780af6 |  | textbox | Test method used
text | 98ce85c5-cb0f-540b-ae4b-b48c35523c27 |  | textbox | Duration
checkpoint-status | 88ee376b-f602-494e-93e6-80bb5d876c5e |  | checkpoint | Local Authority Inspection Passed
text | fa386568-cbba-5179-aa85-56010678a888 |  | textbox | Witnessed by
text | fd553973-4fdd-539d-92e7-896caca5fcd5 |  | textbox | Representing (Company)
text | e53bb4fd-dd76-5f3d-9c24-463e16779382 |  | textbox | Date
checkpoint-status | a4825606-c905-4c4e-b3b3-56e60714eb66 |  | checkpoint | All relevant test plugs removed where applicable
checkpoint-status | 175b8e8d-660d-4aaf-855a-09aa6a0e8af1 |  | checkpoint | Open ends sealed
checkpoint-status | ce974b23-3635-401b-a635-83159bfbb208 |  | checkpoint | General photos, comments and observations
checkpoint-status | b263d377-56ce-4138-955b-f4239c0d128d |  | checkpoint | Pipe Laying Completed
text | 543558a3-25b5-55db-8df7-620781346577 |  | textbox | Laid by
boolean | 5470c0ab-6f87-5b3e-b6ec-57b03f310600 |  | tickbox | Bedding Sound
boolean | 846a13a3-22f1-5ed3-8b13-7f85271f5ad7 |  | tickbox | Soil Removed
boolean | 38a32a0a-59f4-5057-9b55-d8dc6d4b6d94 |  | tickbox | Trench Compacted
boolean | 2de3b2fd-6d42-5fe5-b46c-506e4da898c5 |  | tickbox | Hard Filled
checkpoint-group | 13d158ea-33a1-4615-8457-73d1a7647569 |  | section | Area Completion/Signoff
checkpoint-status | 38e3778b-c47b-4bb8-a000-03c378beef91 |  | checkpoint | Specified Protection Around All feeds/pipes penetrating slab
checkpoint-status | 66743871-abd8-4a3f-a684-fb03461291fd |  | checkpoint | All Measurements Double Checked
checkpoint-status | 435c24f6-a5e2-4154-964c-98e1ad0a1df6 |  | checkpoint | As-Built Drawings recorded (drawing & revision number(s)
checkpoint-status | 5a1ec7ff-6735-452b-b537-86fde920c084 |  | checkpoint | All relevant under slab works completed, reviewed and approved
text | d0f41b6c-68b8-5c76-8c0c-e6b870c8097d |  | textbox | Completion Date
checklist-flat | fc276c0b-c445-4fc4-8277-98502a046394 |  | checklist | QA - Second Fix |  |  |  |  | Yes | QA - Second Fix | 53843b8e-3f12-4ca0-b386-2e4274b21dc7
checkpoint-status | d2ed13b1-46b6-4ea4-878e-b40504c908bd |  | checkpoint | Area & substrate acceptable
checkpoint-status | c096f5a8-f250-4e5a-8647-2178d8c6aa55 |  | checkpoint | Seal around toilets/basins
checkpoint-status | 96710b09-9bda-4179-a820-8515dca7b098 |  | checkpoint | Basin waste checked for leaks
checkpoint-status | 55582ed6-8d02-407e-bba9-01311db0c4f1 |  | checkpoint | Toilet flushing correctly - No Leaks
checkpoint-status | eac6b453-b1d4-4586-8d25-8367fdc40776 |  | checkpoint | Shower doors installed
checkpoint-status | b8a25e97-285f-405e-801e-0698fa567729 |  | checkpoint | Kitchen tap installed
checkpoint-status | 48fd8543-5dff-4705-a29f-034a07981a79 |  | checkpoint | Kitchen sink waste checked for leaks
checkpoint-status | 8680fff9-e2f4-4027-a7b5-1ee048d8eb8f |  | checkpoint | HWC installed
checkpoint-status | f77c1c93-4d5e-4fe2-a73f-eccb20d33e06 |  | checkpoint | Floor drains cleared
checkpoint-status | 0318caff-f755-406b-baea-e295a1cb4d4e |  | checkpoint | Plugs supplied
checkpoint-status | dc20e17f-6a38-4a59-bab0-a6ab4e396e18 |  | checkpoint | Temp valve set to 50 degrees
checkpoint-status | 8e467227-58f6-47e5-a35c-9c1562cfee9e |  | checkpoint | Rubbish removed
checkpoint-status | ffae6f7b-b141-40b0-a27a-d32541e44f20 |  | checkpoint | Area is left clean and tidy (attach photo)
checkpoint-status | 2a741513-47d3-4074-8a5b-9363da777a8f |  | checkpoint | Second Fix completed reviewed and approved
checklist-sectioned | 13306092-b985-4ac7-9ade-538bb185b7f3 |  | checklist | QA - Apartment Water Supply |  |  |  |  | Yes | QA - Apartment Water Supply | 64e3f76b-13af-44b8-b773-3ffe66a1e8fb
checkpoint-group | be50ed23-5c29-416a-980d-90ea0d0e8d4c |  | section | Water Suppy
checkpoint-status | 7a0c40d3-fedf-4aef-a089-a63bc057ffce |  | checkpoint | Pipe Work Secured in ceiling
checkpoint-status | 24fd8218-a696-4726-88ce-3e104d8794a0 |  | checkpoint | Pipe Work Secured in wall
checkpoint-status | d8c430a6-bf94-4e29-9e37-2069ee996d17 |  | checkpoint | Pipe Work Siliconed
checkpoint-status | 84a3bb03-57a4-43b4-836a-f8f61189694a |  | checkpoint | Check for Crossovers
checkpoint-status | 65bf4e63-8291-4fc5-a522-300b3c014aab |  | checkpoint | Pressure Test 1500 KPA or product/job spec
checkpoint-status | 1e18bc98-fb5f-404b-84ea-816cd6422158 |  | checkpoint | Visual check & photos attached
checkpoint-status | d9747fb1-aa57-4acf-a5a1-012e940a88c7 |  | checkpoint | Check all joints
checkpoint-status | 095ddcce-c131-4d55-9a04-7f853b84df43 |  | checkpoint | Shower/bath outlet Crimp
boolean | ed4f5054-3337-51c9-aeee-a8186c5752ac |  | tickbox | photo uploaded
checkpoint-group | 3bad4779-e795-4dcf-a11f-037aef1432b3 |  | section | Pre-line Inspection
checkpoint-status | 7230ee3e-d843-4d6a-8e4c-8533f14d1d5a |  | checkpoint | Nogs in correct Location
checkpoint-status | 9757cc2a-36e0-4f5f-b17e-75a55eaec64b |  | checkpoint | Cylinder seismic nogs in place
checkpoint-status | ce37a76b-b281-42de-bac0-2347220ad59e |  | checkpoint | Vanity, shower, toilet nogs
checkpoint-status | 9147b029-fece-46b5-af71-5033d71f6ae4 |  | checkpoint | Shower mixer - Depths allowance for tiles, nogs square to wall
checkpoint-status | 04697d2f-c4f5-4fcb-8288-a9234a7994b3 |  | checkpoint | Mixers straight
checkpoint-status | c98c0733-5940-403a-b3b0-f41ace20e0af |  | checkpoint | Vanity Wingbacks
checkpoint-status | 1ee83dbc-8ede-445e-af70-93d3e4fcea7b |  | checkpoint | Outlets straight
checkpoint-status | 61f8cc80-47ca-4bf9-a014-3fe15d8cfdbb |  | checkpoint | Outlets correct length
checkpoint-status | dda20e4e-9643-454a-9326-34d320c4e5a2 |  | checkpoint | HWC water feeds
checkpoint-status | 487598a6-8d9e-4870-912b-ba2960e132f0 |  | checkpoint | Capped Off
checkpoint-status | 36a6d184-5096-4b75-b365-3fda504f1cca |  | checkpoint | Rubbish removed
checkpoint-status | 1360d22b-b97c-4dfe-ab0d-6ff6b3a996cf |  | checkpoint | Protective covers in place
label | 2eb3711e-6c57-58c2-a267-18f2a2cb4694 |  | note | Attach photos of completed area
checkpoint-status | 5720df9f-4765-4f58-883a-8064a4a4c1db |  | checkpoint | Pre Line Inspection Passed - Foreman
holdpoint | 4ffe7272-32fb-4b81-9378-c4bbcb0ade57 |  | signoff | Add Signature
checkpoint-status | fb75fc91-9fc3-40e6-bfff-2f4eb6221892 |  | checkpoint | Pre Line Inspection Passed - Witness
holdpoint | dbd5ed62-cc1f-4e69-abae-ec76a024586a |  | signoff | Add Signature
checklist-flat | 06d8d6f0-bdbd-4f27-9231-fc3c0aab4e7b |  | checklist | Hot Water |  |  |  |  | Yes | QA - Hotwater Checklist | f152b00f-9190-4f31-bfae-1d15f4263ac2
checkpoint-status | ed30d69b-904f-49f1-8f7f-b0419bee24d0 |  | checkpoint | Connections welded/crimped correctly
checkpoint-status | d16e7bea-afb6-4323-8032-1c70db9851d1 |  | checkpoint | Clip spacing to manufacturer's specs horizontal/ vertical
checkpoint-status | e95d2341-114d-4359-8ae8-381232c7dae1 |  | checkpoint | Lagging installed and neat
checkpoint-status | b5a84dc2-90f4-4b5b-a1a9-ae12ea80a677 |  | checkpoint | Labels installed
checkpoint-status | ed83bdc7-b033-4feb-955f-7c7b66ab9aa4 |  | checkpoint | Correct valves fitted correctly
checklist-sectioned | b62c94dc-55d3-4d9b-b983-c98a9b4cc46d |  | checklist | QA - Waste / Stacks |  |  |  |  | Yes | QA - Waste / Stacks | fa7c145a-7c40-473c-9fa6-b090f345716f
checkpoint-group | d9ea1acb-9282-4e8e-8c29-810e3045e1eb |  | section | Area Prestart / Acceptance & Drawings
checkpoint-status | 34a5455c-9214-45e8-ab12-a1f6e38c1ec9 |  | checkpoint | Area Prestart / Acceptance & Drawings
text | 49127648-f6ff-5724-9376-e26c93ed01a8 |  | textbox | Zone / Area
checkpoint-status | d3c4f5d3-4f56-49fb-8598-c1ddb6cd494c |  | checkpoint | Area ready for works
checkpoint-status | 1c917d0f-2ed9-4e6a-ac6b-4f871914fefb |  | checkpoint | Current Dimensioned Slab Set Out Drawings numbers and revisions recorded
checkpoint-group | 9e073d73-ec5a-4e53-be79-4bb02d82614b |  | section | Pipe install
checkpoint-status | eaf40797-5b5c-451c-8041-4e700e727faa |  | checkpoint | IE's - Test points installed correct locations (ASNZS 3500)
checkpoint-status | c294bb27-5261-46f6-a031-24193ffd1496 |  | checkpoint | Pipeout completed
checkpoint-status | a6fb6e0b-7496-4542-a746-9e52b8c0f3c2 |  | checkpoint | Correct labels
checkpoint-status | db86329d-98c6-4857-8f7e-b8fde9d16e6e |  | checkpoint | Acoustic lagging
text | 6a0ee72d-405b-5056-91e4-a7c79cb9e28c |  | textbox | Product Type
checkpoint-status | 94cbd4df-0188-4ec4-8d5e-b73530d49ac6 |  | checkpoint | Correct Pipe supports completed
checkpoint-status | 2e514960-5977-48a6-bc13-13db34bde47a |  | checkpoint | Seismic bracing completed
checkpoint-status | 0077586d-8a37-4d19-8a79-dc9867771cf3 |  | checkpoint | Vent installed
checkpoint-status | d65ed88b-3db1-4e8d-a80f-706c82ddf555 |  | checkpoint | Correct fall
checkpoint-status | 796bd44b-6508-4456-bfdb-75c3cafd8faf |  | checkpoint | Flood Test in accordance with ASNZ 3500
text | 3571b86a-2ded-55ab-9bd2-d70d1202f3c4 |  | textbox | Witnessed by
text | 703ab891-547e-5cbf-85d2-a95e2bd0f4fc |  | textbox | Representing (Company)
text | 98a6e704-f189-527e-a89a-f322ed541da0 |  | textbox | Date
holdpoint | 5ccdcd5f-1d69-4529-ac88-5d24e2a05dca |  | signoff | Request sign off
checkpoint-status | b4fd110d-f0fa-4e83-bfad-68def72a7235 |  | checkpoint | All relevant test plugs removed where applicable
checkpoint-status | 7d9f32d0-8e66-4945-a97c-0d8eee737bb9 |  | checkpoint | Open ends sealed
checkpoint-status | 57e1bc1e-560f-4a69-962d-59698a4ce456 |  | checkpoint | General photos, comments and observations
checkpoint-status | 2bfcb8f4-99c0-4bec-a7c9-7ada6b8a5a1d |  | checkpoint | Pipe Install Completed
text | e7c0331c-8da6-5db1-bf25-db6724a5c7b2 |  | textbox | Installed by
checkpoint-group | d4072788-8075-4cdf-a880-7e9bd9972316 |  | section | Area Completion/Sign Off
checkpoint-status | 9a9a0c7d-033a-4934-b066-42876bb872b8 |  | checkpoint | Specified Protection Around All feeds/pipes penetrating slab
checkpoint-status | bb95c22d-2b63-4898-b57e-c138456079f8 |  | checkpoint | All Measurements Double Checked
checkpoint-status | dee15791-b4e9-4957-9575-9aee5e438644 |  | checkpoint | As-Built Drawings recorded (drawing & revision number(s)
text | 4359ee92-9f4a-581c-81c6-101142452cd6 |  | textbox | Completion Date
checklist-flat | 97eef07e-cddb-4d48-a0dd-9af8c755cb2e |  | checklist | Hotwater Plant, Pumps & Tempering Valves |  |  |  |  | Yes | QA - Hotwater Plant, Pumps & Tempering Valves | ff1e66ac-2d53-4cef-850e-f4fd2852fe6b
checkpoint-status | 5a5b5a5b-554e-4706-9b53-c8c33d34d93f |  | checkpoint | Flush all lines and strainer including rinnais
checkpoint-status | d4cf8fa7-d2ba-44aa-abcc-81caf068701b |  | checkpoint | All safety valves installed
checkpoint-status | 9775ef08-9a8e-4019-aaf6-cb101cd0073c |  | checkpoint | Seismic restraint fitted
checkpoint-status | fc247d11-6a93-4e1c-bfdc-e704d2d14b6b |  | checkpoint | Check condensate drains from Rheem gas boilers
checkpoint-status | 31393023-c2a4-4600-b8f3-29ea8f17f7de |  | checkpoint | Check All Connectors For Leaks
checkpoint-status | 06a3b889-2eb3-41aa-9f79-9d67cc11b254 |  | checkpoint | Check all valves and connections for leaks
checkpoint-status | 7a216685-585f-44b8-8853-ceb9c7181d29 |  | checkpoint | Operate cold water expansion valves / check operation
checkpoint-status | 470f6742-0418-48d9-bede-fdcbbdb856fc |  | checkpoint | Set limiting valve
checkpoint-status | c4768bd1-2dbc-4fa9-b8d4-b470e4efaa41 |  | checkpoint | Test TPR valve
checkpoint-status | adb68e70-2ed1-4817-9b07-9de1300decfb |  | checkpoint | Check for crossovers
checkpoint-status | 1ef07ef3-6722-459a-91fe-4e6202dbe7ea |  | checkpoint | Check HWC For Correct Valve Installation
checkpoint-status | 4a0c9d31-c92e-407e-9c7e-a9509e2706ee |  | checkpoint | Lagging completed
checkpoint-status | 3976cc51-c619-4489-8d6b-311e7bf28a1a |  | checkpoint | Check All Hot/Cold Pipes For Correct Position
checkpoint-status | 485ba2e9-81a7-4afa-81c9-84471db1071a |  | checkpoint | Set tempering valve temperature
checkpoint-status | 74c32904-4bde-4c9c-8ecb-b7f8f91b7425 |  | checkpoint | Set Rheem gas water heaters
checkpoint-status | 65b95c2a-f2ea-49fc-8504-599278a62103 |  | checkpoint | Set thermostat temperature
checkpoint-status | 7f60907c-5d71-42e4-bdd0-8022fb61780b |  | checkpoint | Set Bleed air from primary pumps
checkpoint-status | 8da5b382-c525-4b1d-a450-bfd90fdad12c |  | checkpoint | Bleed air from circulating pump
checkpoint-status | bfa55161-b7df-45ee-a776-4c2c2accb6f8 |  | checkpoint | Set all return thermostatic balancing valves
checkpoint-status | 10939513-f525-4f2a-8261-eed3008f8c5e |  | checkpoint | Test gas for soundness & check working pressure
checkpoint-status | d4acbee7-17d5-459a-9d08-f0237f140456 |  | checkpoint | Water temperature in Hot water cylinders
checkpoint-status | b69705cb-9b52-4cf9-93f0-65956f632e81 |  | checkpoint | Installers name & date works completed
holdpoint | c0ce7d76-9d13-4dc2-af17-a0776fdb0a6e |  | signoff | Request Signoff