## Project Breakdown
Regal Tiling - 045 Riccarton Park (Kevein Hickman)
Stage 06 - THB 08 - 09
THB 09
TH 21
|  |  |  | Kitchen |  | Prepopulate | POST - S - Tiling
|  |  |  | Bathroom |  | Prepopulate | POST - S - Tiling
|  |  |  | Undertile heating Bathroom |  | Prepopulate | POST - S - Underfloor heating
|  |  |  | WC |  | Prepopulate | POST - S - Tiling
TH 22
|  |  |  | Bathroom |  | Prepopulate | POST - S - Tiling
|  |  |  | Undertile heating Bathroom |  | Prepopulate | POST - S - Underfloor heating
|  |  |  | Kitchen |  | Prepopulate | POST - S - Tiling
|  |  |  | WC |  | Prepopulate | POST - S - Tiling
THB 08
TH 24
|  |  |  | Kitchen |  | Prepopulate | POST - S - Tiling
|  |  |  | Bathroom |  | Prepopulate | POST - S - Tiling
|  |  |  | Undertile heating Bathroom |  | Prepopulate | POST - S - Underfloor heating
|  |  |  | WC |  | Prepopulate | POST - S - Tiling
TH 26
|  |  |  | Kitchen |  | Prepopulate | POST - S - Tiling
|  |  |  | Bathroom |  | Prepopulate | POST - S - Tiling
|  |  |  | Undertile heating Bathroom |  | Prepopulate | POST - S - Underfloor heating
|  |  |  | WC |  | Prepopulate | POST - S - Tiling
TH 28
|  |  |  | Kitchen |  | Prepopulate | POST - S - Tiling
|  |  |  | Bathroom |  | Prepopulate | POST - S - Tiling
|  |  |  | Undertile heating Bathroom |  | Prepopulate | POST - S - Underfloor heating
|  |  |  | WC |  | Prepopulate | POST - S - Tiling
TH 30
|  |  |  | Kitchen |  | Prepopulate | POST - S - Tiling
|  |  |  | Bathroom |  | Prepopulate | POST - S - Tiling
|  |  |  | Undertile heating Bathroom |  | Prepopulate | POST - S - Underfloor heating
|  |  |  | WC |  | Prepopulate | POST - S - Tiling
Completion Documents
|  | Stage 06 |  | Prepopulate | CST - S - Completion Documents

## Checklist
Type | Name | Value
checklist-flat | POST - S - Underfloor heating
checkpoint | Wiring on the floor completed correctly
checkpoint | Self leveling coverage completed and acceptable
checkpoint | Underfloor heating completed - specified level of finish achieved
Type | Name | Value
checklist-flat | POST - S - Tiling
checkpoint | Matching batches of tiles installed
checkpoint | Correct tile adhesive applied as per spec
checkpoint | Trims/ transition bars and any other finishing completed
checkpoint | Epoxy/ grouting correct colours applied and acceptable
checkpoint | Silicone correct colours applied and acceptable
checkpoint | Fully cleaned and no grout residue on tiles
checkpoint | Tiling completed - specified level of finish achieved and area left clean and tidy
Type | Name | Value
checklist-flat | CST - S - Completion Documents
checkpoint | All relevant Compliance Documentation completed and attached above
button | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
label | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | Request Signoff