## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | FC - R - Passive fire |  |  |  |  | Yes | FC - R - Passive fire | 0130c3f6-005f-4a70-acaa-33a39b163862
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Passive Fire works completed and acceptable
checklist-flat |  |  | checklist | FC - R - Flashing installation |  |  |  |  | Yes | FC - R - Flashing installation | 050fe7de-bde0-4f30-9c31-9ae47253cf50
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Flashing installation completed and acceptable
checklist-flat |  |  | checklist | BC Amendment - |  |  |  |  | Yes | Add Council BC Amendment Checklist | 0c643acd-5a0e-4d88-a875-a0cb6b9c3d02
checkpoint-status |  |  | checkpoint | Building consent amendment status (Pass once approved & all information is attached including observations, correspondence & close out evidence)
label | 1bedacd3-6b5f-4992-a86f-0bc9d9b6b8d1 |  | note | PASS above checkpoint when amendment is approved
text | ea854fd3-af05-48c5-bfa5-3e028dec370f |  | textbox | Date of application
text | d21b869b-2ba4-4733-aa29-f089e8181cd7 |  | textbox | Reason for application
text | ff307bc0-8fde-4687-b56a-40ab8b9f7a44 |  | textbox | Date of approval / acceptance
text | 0f1f687d-0c1e-4559-a110-6c98e391fbf7 |  | textbox | Inspection Type Code (If applicable e.g. Site meeting IME)
boolean | e8fabf7c-ccf7-440c-b609-de2d1f07b6a2 |  | tickbox | Council approval of amendment attached
text | 55ca00ed-390e-4a18-a763-6068c93a9d27 |  | textbox | Update building consent number (including amendment)
boolean | 0fafd961-e3e4-4a1e-9ba2-fe2febe04e12 |  | tickbox | Latest building consent including amendment has been attached in the "Latest Building Consent" folder to supersede the previous consent
label | 055902f6-5e50-4523-a80b-dd0f8944dd2b |  | note | Ensure this amendment and relevant changes are communicated to any relevant parties
checklist-flat |  |  | checklist | ST - R - Blockwork |  |  |  |  | Yes | ST - R - Blockwork | 134c387f-c75e-4205-ba56-1c7a1054763e
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Blockwork walls completed and acceptable
checklist-flat |  |  | checklist | FC - R - Tapes and VaproShield |  |  |  |  | Yes | FC - R - Tapes and VaproShield | 16b00d1b-b151-4a2a-8afc-079ca29931d0
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Tapes/VaproShield works completed and acceptable
checklist-flat |  |  | checklist | F - R - Underground services |  |  |  |  | Yes | F - R - Underground services | 18b52d82-b8fd-4a13-b302-bf019aa844a5
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All underground services installation completed as per the specifications
checklist-flat |  |  | checklist | FC - R - Water Test |  |  |  |  | Yes | FC - R - Water Test | 196257d7-fe08-42d8-b4a1-475fef915a93
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Water Test completed and acceptable
checklist-flat |  |  | checklist | FC - R - Brick Works |  |  |  |  | Yes | FC - R - Brick Works | 19fdb202-29a7-4567-ae37-c6f641cdfc42
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Brick works completed and acceptable
checklist-flat |  |  | checklist | ST - R - Precast Balcony Installation |  |  |  |  | Yes | ST - R - Precast Balcony Installation | 1a2eb16e-64a2-4107-9bca-7453f4402303
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Joints grouted with Sika 212 and PEF rod.
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Balcony Installation completed and acceptable
checklist-flat |  |  | checklist | ST - R - Concrete Pour |  |  |  |  | Yes | ST - R - Concrete Pour | 1b491961-41bd-448d-a13e-a15d588be624
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Concrete pour completed and acceptable
checklist-flat |  |  | checklist | Minor Variation - |  |  |  |  | Yes | Add Council Minor Variation Checklist | 1bca01c5-7e00-47d1-95bb-e42c7c0ecbf0
checkpoint-status |  |  | checkpoint | Minor variation status (Pass once approved & all information is attached including observations, correspondence & close out evidence)
label | abefa70f-bf7c-4063-9f45-320e8d06e19f |  | note | PASS above checkpoint when variation is approved
label | 1fe9bcf0-4962-4df1-9e77-fe0563112553 |  | note | If minor variation is a FAIL - document why below and follow appropriate corrective actions
text | 1630c331-1d54-426d-ae50-eccc6e60fdda |  | textbox | Date of application
text | 30897ede-6546-4d54-8116-91a3930ab857 |  | textbox | Reason for application
text | 601ebe19-3baf-4095-a027-2ba3856505a0 |  | textbox | Date of approval / acceptance
text | 7e9217ff-a504-4aae-837d-b0be114f946d |  | textbox | Inspection Type Code (If applicable e.g. Site meeting IME)
boolean | d2cc6a6c-761c-4e40-b5a1-32e92e510b05 |  | tickbox | Council approval of minor variation attached
checklist-flat |  |  | checklist | CST - R - Foundation Consent |  |  |  |  | Yes | CST - R - Foundation Consent | 1ee89dd4-6681-413f-bc2d-58036c58d895
checkpoint-status |  |  | checkpoint | Record of title
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Pre-cast concrete
boolean | 1d889686-54d4-5067-a3b4-49d09b6bae0f |  | tickbox | Producer Statement Design(PS1): Prestressed concrete beams and floor units
boolean | 6a7c54e0-5e1b-59c3-9a3a-de8f22152895 |  | tickbox | Producer Statement Construction(PS3): Prestressed concrete beams and floor units
boolean | f27aeff0-5b9b-537e-ae9f-ffe24c5a479a |  | tickbox | Producer Statement Review(PS4): Prestressed concrete beams and floor units
boolean | 733267cb-35a0-5f4c-a5b5-320f268dd043 |  | tickbox | Shop drawings for concrete beams and floor units
checkpoint-status |  |  | checkpoint | Producer Statement Construction(PS3): sub-soil drainage
checkpoint-status |  |  | checkpoint | Waterproofing
boolean | 9e0067cd-fd62-5a6a-af05-2949642de6c8 |  | tickbox | Producer Statement Construction(PS3): Waterproofing Membrane
boolean | 4be3c9d6-69b4-5da0-b8c0-aac76c8beac2 |  | tickbox | Manufacturer's warranty for waterproofing membrane
checkpoint-status |  |  | checkpoint | Mill certificates
checkpoint-status |  |  | checkpoint | Concrete dockets
checkpoint-status |  |  | checkpoint | Producer Statement Review(PS4): Engineer's observation
checkpoint-status |  |  | checkpoint | Surveyor certificate for siting
checklist-flat |  |  | checklist | ST - R - Timber Framing |  |  |  |  | Yes | ST - R - Timber Framing | 20b6083d-2ebb-4ee5-aed0-cee1002a397f
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Timber frame installation completed and acceptable
checklist-sectioned |  |  | checklist | Pour: |  |  |  |  | Yes | ST - R - Concrete Pour - Ryman Owned | 22041f91-29d2-4fe0-8148-c50a7eb178d8
checkpoint-group |  |  | section | Pour Details
checkpoint-status |  |  | checkpoint | Pour details entered
text | 6606d8f9-6e51-56b0-81f9-e2b307fd43a5 |  | textbox | Area to be poured:
text | c0c9e041-b654-579c-a600-24247908ba38 |  | textbox | Date of pour:
checkpoint-status |  |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-group |  |  | section | Formwork and Embedded Items
checkpoint-status |  |  | checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint-status |  |  | checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint-status |  |  | checkpoint | All surfaces correctly prepared (e.g joints to existing concrete, release agent to formwork etc)
checkpoint-status |  |  | checkpoint | Any control joints/ stop ends installed accurately and correctly braced
checkpoint-group |  |  | section | Reinforcing
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/correct
checkpoint-status |  |  | checkpoint | Splice laps checked/correct
checkpoint-status |  |  | checkpoint | All couplers installed correctly (if reid bar couplers have been used, has epconC8 epoxy been used as specified)
boolean | a13002fa-0efe-5c27-934c-9f83d8673a57 |  | tickbox | Appointment with the engineers confirmed (Enter date & time of the appointment)
boolean | d5ca34c8-2fe2-563b-a388-3fccd74edea5 |  | tickbox | Reidbar – coupler and flange nut installations are inspected by the MV Engineer
checkpoint-status |  |  | checkpoint | IMBMS couplers testing carried out for Village Podiums in the form of tensile testing in accordance with NZS3101.1.2006 and results acceptable
checkpoint-status |  |  | checkpoint | All starter bars are installed correctly (location, size and spacing )
checkpoint-status |  |  | checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Welding certificates sited and attached
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
checkpoint-group |  |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status |  |  | checkpoint | Waterproofing elements have been correctly installed and checked
checkpoint-status |  |  | checkpoint | Relevant service requirements completed (locations checked and accurate)
checkpoint-status |  |  | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint-status |  |  | checkpoint | Ryman inspection completed - Approval given to pour concrete
checkpoint-group |  |  | section | Concrete Supplier Specifics
checkpoint-status |  |  | checkpoint | Concrete Supplier details entered
text | a5092c68-fa64-5925-b258-e4ec38eb8ee9 |  | textbox | Supplier Name:
text | d05bf3fa-cf86-57f3-8474-a52cdb897efe |  | textbox | Specified concrete strength: |  |  | mPA
text | 496921f3-e309-59c4-a135-2769644f253e |  | textbox | Concrete strength ordered: |  |  | mPA
text | be2a154e-af92-5396-901e-4ade853337ac |  | textbox | Concrete quantity ordered: |  |  | m3
button | 5e3b16e4-4ea9-5579-a49c-b612ba4b1a1e |  | button | Test blocks booked | Yes, No, N/A
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-group |  |  | section | Placement Method
checkpoint-status |  |  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
checkpoint-status |  |  | checkpoint | Heights and falls checked/confirmed before placement
button | 8a6c721f-9195-5cb1-972f-6541fe36b7ee |  | button | Is the cover correct to specification | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Heights and falls checked/ confirmed after placement
checkpoint-status |  |  | checkpoint | Any curing compound applied correctly
checkpoint-status |  |  | checkpoint | Concrete placement completed - specified level of finish achieved
checkpoint-group |  |  | section | Post Pour Checks/Sign Off
checkpoint-status |  |  | checkpoint | Any remedial work completed
holdpoint |  |  | signoff | Raise remedial/ Request Signoff
checkpoint-status |  |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checklist-flat |  |  | checklist | Building Consent - |  |  |  |  | Yes | Add Council BC Upload Checklist | 254f87ac-4f40-4f00-8e60-01cbe5838bf6
checkpoint-status |  |  | checkpoint | Latest building consent attached (superseded and attached as required)
checklist-flat |  |  | checklist | FC - R - Balustrades Installation |  |  |  |  | Yes | FC - R - Balustrades Installation | 25703f2c-c19a-4186-b046-b9f189740488
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Balustrades installation completed and acceptable
checklist-flat |  |  | checklist | FC - R - Eyebrow - Canopy |  |  |  |  | Yes | FC - R - Eyebrow - Canopy | 27dbc8c1-d638-44a9-aff8-ccfdb6e894da
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Exterior Tiling works completed and acceptable
checklist-flat |  |  | checklist | C - R - Service Trenches - Common Service Trenches |  |  |  |  | Yes | C - R - Service Trenches - Common Service Trenches | 2cb0e639-0470-402a-8ec5-b1c59f675d72
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Common service trench works completed as per the specifications
checklist-flat |  |  | checklist | C - R - Manhole Installation |  |  |  |  | Yes | C - R - Manhole Installation | 3034fc32-aa07-408b-ad3c-0a41917d0fb7
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Manhole Installation completed as per the specifications
checklist-flat |  |  | checklist | F - R - Shell Beam Installation |  |  |  |  | Yes | F - R - Shell Beam Installation | 33210fa6-db69-4c0d-9df0-9aeb91b2709d
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Shell Beam installation completed as per the specifications
checklist-flat |  |  | checklist | ST - R - Intumescent Painting |  |  |  |  | Yes | ST - R - Intumescent Painting | 3b6cbd8a-b1b5-4949-ac25-88d07d6f0178
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Intumescent Painting completed and acceptable
checklist-flat |  |  | checklist | ST - R - Stair Installation |  |  |  |  | Yes | ST - R - Stair Installation | 3ce6915d-38ef-4ad0-a5a9-f176d9ddb7a1
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Stair Installation completed and acceptable
checklist-flat |  |  | checklist | FC - R - Lintels |  |  |  |  | Yes | FC - R - Lintels | 509e17b1-b599-4060-8fb5-3e0eab33628a
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Lintels completed and acceptable
checklist-flat |  |  | checklist | CST - R - Fire Consent |  |  |  |  | Yes | CST - R - Fire Consent | 51465c26-e8f4-42df-9dad-ff5b06d427f0
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Electrical
boolean | 7275e5ae-b5f1-570a-b18a-40b3ef56d240 |  | tickbox | Electrical compliance and safety certificate
boolean | 2ac96d6f-8d62-5a22-916e-64ed2d287400 |  | tickbox | record of inspections for high risk works
checkpoint-status |  |  | checkpoint | Fire rated (Intumescent) Coatings to Structural Steel
boolean | 2d7cce77-f25b-50de-9ad0-e8a1aa961ed7 |  | tickbox | Producer Statement Construction(PS3 - AC2334): Intumescent coatings to structural steel from approved applicator
boolean | e22db09e-38c9-5afc-98ed-c432e9091f15 |  | tickbox | Suppliers material schedule - products used and thicknesses applied
boolean | b44a25b4-c45f-5193-b8f6-2b08f3b0edd0 |  | tickbox | Floor plan of intumescent coating locations
checkpoint-status |  |  | checkpoint | Fire Rated and Stopping Systems
boolean | 29751076-253d-5ecf-b825-fe15e3ac864b |  | tickbox | Producer Statement Construction(PS3): Fire stopping of penetrations(collars, wraps, sealants) for Plumbing, Mechanical, Ventilation and Communication services
boolean | 1e5ed607-d406-5af1-bf6e-b701376044d9 |  | tickbox | Fire rated penetration Schedule: Plumbing, Mechanical, Ventilation and Communication Services
boolean | bf65fa1d-c5e3-5ff0-88b5-363b37b4e631 |  | tickbox | As built plans: penetrations
boolean | bd71e54a-0a14-5b80-a011-c5d3568cc844 |  | tickbox | Producer Statement Construction(PS3): Installed fire rated constructions; fire rated walls, partitions, floors and ceilings to show fire rating
boolean | bac5c294-297c-5c99-8099-9150aff07f8a |  | tickbox | Fire door declaration documentation and register of door sets by the manufacturer (refer NZS4520: 2010 clause 6.4.3
checkpoint-status |  |  | checkpoint | Sprinkler systems
boolean | aa546a0b-fc55-59ad-89c6-c48e2a69f675 |  | tickbox | Producer Statement Construction(PS3): Automatic sprinkler system (in compliance with NZS4514:2013)
boolean | 8f67f952-6355-571f-9371-9d8ac2ae9c4a |  | tickbox | Accredited inspection company's automatic sprinkler system certification confirming compliance with NZS4514:2013
boolean | 3bf81012-13c9-5479-84f7-2ee20cabf5cb |  | tickbox | As built documentation; sprinkler block plan, equipment manufacture register
checkpoint-status |  |  | checkpoint | Manual and Automatic fire alarms
boolean | a2637a92-80eb-5c14-bdb6-b7f0c18c915b |  | tickbox | Producer Statement construction(PS3): Manual/automatic fire alarm in compliance with NZS4512:2010
boolean | af015870-bffb-5a2b-b472-7ece730029f4 |  | tickbox | Accredited inspection company's fire alarm certification confirming compliance with NZS4512:2010 (new system)
boolean | 98b5f26d-0b73-5f65-b425-02cf648fd41f |  | tickbox | As built documentation; zone index plan, operation manual and maintenance manual
checkpoint-status |  |  | checkpoint | Riser Mains for use by fire services
boolean | 3b96cd8f-4c94-55e3-887e-68776c2e5cef |  | tickbox | Producer Statement Construction(PS3): fire hydrant riser confirming compliance with NZS4510:2008
boolean | d6a3a496-eeb4-5c91-9f48-15bb3bd5512d |  | tickbox | Certificate of Compliance or Verification Report for fire hydrant riser confirming compliance with NZS4510:2008
boolean | d12ff07e-a260-56a9-8661-46185511c4d7 |  | tickbox | As built documentation; fire hydrant schematic as built
checkpoint-status |  |  | checkpoint | Emergency Lighting systems
boolean | e81bf930-e5be-50a3-83a1-b0fffe013811 |  | tickbox | Producer Statement Construction(PS3): Emergency lighting from electrical contractor confirming compliance with NZBC F6
boolean | 622005ff-c43c-560a-8b6e-b6ec96387204 |  | tickbox | Producer Statement Review(PS4): Emergency Lighting from council approved electrical engineer confirming compliance with NZBC F6
boolean | b09e691a-915b-559f-aed0-befcff94e6b4 |  | tickbox | Duration test results for emergency light fitting from electrical contractor or IQP
boolean | fbf61a03-fa83-546e-a8e7-8a3d45126a64 |  | tickbox | Lux test results for the emergency lighting system
boolean | d3fd61e7-27ef-5405-a73d-5527160da33d |  | tickbox | As built plan with model of systems installed
boolean | 58fd68d0-af54-527e-bcc8-7820967fb6ad |  | tickbox | Electrical work certificate
checkpoint-status |  |  | checkpoint | Fire separation that forms part of the means of escape from fire
boolean | 6f517eb1-9b45-5d13-93b1-e821a26fe1eb |  | tickbox | As built plans confirming final location of Fire separation that forms part of the means of escape from fire
checkpoint-status |  |  | checkpoint | Smoke separation that forms part of the means of escape from fire
boolean | d78d496f-6615-5111-9dcc-35cbcade9a67 |  | tickbox | As built plans confirming final location of walls forming a protected path in a building, smoke resistant lift lobby, smoke stop door, smoke cell
checkpoint-status |  |  | checkpoint | interfaced fire or smoke doors on windows
boolean | 89ae1038-bdcc-5f4c-9a12-0962f744578e |  | tickbox | Producer Statement Construction(PS3): installation of magnetic door holders
boolean | 796930c0-68fd-59db-b3de-6fee43557443 |  | tickbox | As built documentation; location of systems, the make of the systems, operation manuals and maintenance manuals
checkpoint-status |  |  | checkpoint | final exits
boolean | ec41fce7-00d9-58cb-9e0f-578ab6325ed5 |  | tickbox | as built plans confirming location of final exit (include info on if any doors are automatic or access controlled)
checkpoint-status |  |  | checkpoint | Signs for all systems
boolean | 83d82476-39b7-540b-a3d8-78fe5b4e2a45 |  | tickbox | SS 1/1: Sign showing maximum storage heights
boolean | a66d37ef-56ed-5f71-9b3b-b600945931ff |  | tickbox | SS 2/1: Sign showing how to operate a fire alarm call point
boolean | 798f2872-0638-5e6d-a5ed-1c977e731b8a |  | tickbox | SS 3/1: Sign showing location of accessible automatic
boolean | 1d5766bb-be89-56e5-8061-353418274dd5 |  | tickbox | SS 3/2: Sign showing and automatic closing fire or smoke door
boolean | 9a22c96e-a252-5bc3-8fc2-b0943b52bea1 |  | tickbox | SS 3/2: Sign showing location of an emergency door release on access control doors
boolean | 98df7bc4-88a0-5038-a84a-f2036ee3dc4d |  | tickbox | SS 8/1: Sign showing location of accessible lift
boolean | cdb35993-6ac1-5fa1-8da1-3ca5394d92bd |  | tickbox | Sign showing not to use the lift in event of fire
boolean | 885e2b61-11f9-570d-87d1-6e52bc3c2341 |  | tickbox | Sign showing lift load ratings
boolean | 3cf1f666-b969-58ac-9fff-6d39f1a81a7d |  | tickbox | SS 8/3: Sign showing hazards to escalators and moving walks
checkpoint-status |  |  | checkpoint | Fire safety construction review
boolean | 6a3b7bcd-8fb8-56f2-ad91-f6f3884f38c0 |  | tickbox | Producer Statement Review(PS4): council approved fire engineer to confirm systems conform with the relevant NZBC clauses and fire reports
checkpoint-status |  |  | checkpoint | Application for compliance schedule (AC2102)
checkpoint-status |  |  | checkpoint | Confirmation of performance standards for specified systems (AC2150)
checklist-sectioned |  |  | checklist | Code Compliance Certificate |  |  |  |  | Yes | Add Code Compliance Certificate (CCC) Checklist | 52b86f81-9249-4474-80f3-d6e9de5e3a9e
checkpoint-group |  |  | section | Code Compliance Certificate Lodgement
checkpoint-status |  |  | checkpoint | Code Compliance Certificate lodgement form completed/received and attached
label | d4808040-1f76-4d19-bbc4-16231af57732 |  | note | Attach confirmation of CCC lodgement and PASS above checkpoint when CCC has been applied for
folder-normal |  | Not allowed as a child of checklist-sectioned. | folder-normal | Code Compliance Certificate RFI's
checkpoint-group |  |  | section | Code Compliance Certificate Approval
checkpoint-status |  |  | checkpoint | Final Code Compliance Certificate (approved & attached)
label | 718b03c8-007d-47d4-8345-4c2bd04bb57a |  | note | Attach approved Code Compliance Certificate and PASS above checkpoint when CCC has been approved
checklist-flat |  |  | checklist | ST - R - Roof structure - Timber Trusses |  |  |  |  | Yes | ST - R - Roof structure - Timber Trusses | 55370094-667e-42da-b80a-0c6d7d509428
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All timber trusses correctly installed in respective area and acceptable
checklist-flat |  |  | checklist | FC - R - Exterior Timber Framing |  |  |  |  | Yes | FC - R - Exterior Timber Framing | 56a91844-3fed-49fc-8acb-33be69fb9025
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Exterior Timber Framing works completed and acceptable
checklist-flat |  |  | checklist | CST - R - Mechanical Constant |  |  |  |  | Yes | CST - R - Mechanical Constant | 5bcc041a-637d-43f6-809d-b2505aac964c
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Electrical
boolean | 895528c1-bb26-53e9-8f10-7460bdcddcc3 |  | tickbox | Electrical compliance and safety certificate
boolean | 2e28d945-5fbb-5360-8e9a-e62119db5e8c |  | tickbox | record of inspections for high risk works
checkpoint-status |  |  | checkpoint | Automatic doors
boolean | ba1143ce-a297-5572-811d-a237beae5733 |  | tickbox | Producer Statement Construction(PS3): automatic door installation and failsafe override
boolean | 4e1ff6bb-b872-5142-aa9b-05c787454f29 |  | tickbox | As built documentation; plans, operation and maintenance manual
checkpoint-status |  |  | checkpoint | Access controlled doors
boolean | 6f24b19d-932c-5695-a733-6e3d1de09b9a |  | tickbox | Producer Statement Construction(PS3): installation of access control to doors and failsafe override
boolean | ae8de55a-92d3-5285-a44a-f0365e992d99 |  | tickbox | As built documentation; location of systems, the make of the systems and operation manuals
checkpoint-status |  |  | checkpoint | Escape route pressurization systems
boolean | a102d3e8-5969-5c2f-9c2d-4488b9cac5a1 |  | tickbox | Producer Statement Construction(PS3): Installation of escape route pressurization systems from approved mechanical contractor
boolean | 3d3a37e2-9402-51c0-b30e-df69208c8cac |  | tickbox | Producer Statement Review(PS4): Installation of escape route pressurization systems from approved mechanical contractor
boolean | 6d61a850-5ded-524b-bb74-f3c6cf66491a |  | tickbox | test/commissioning results verifying measured airflow rates meet design and interface with alarm system
boolean | 239e9dfd-3881-5939-b5aa-315f0aed2944 |  | tickbox | As built documentation; equipment schedules and make of systems, operation and maintenance manuals
boolean | 7784af1c-aeb3-5f21-a3bc-13e0ec14eeec |  | tickbox | Electrical work certificate
checkpoint-status |  |  | checkpoint | Passenger Carrying Lifts
boolean | 09a92cdd-11d8-5083-b69b-bd9db1518b92 |  | tickbox | Codemark construction certification and inspection/maintenance sheets
checkpoint-status |  |  | checkpoint | Mechanical ventilation or air conditioning system
boolean | e85d6a17-f0ef-505a-9dd9-813a82398124 |  | tickbox | Producer Statement Construction(PS3): Kitchen extract system (compliance with NZBC G4)
boolean | 19b628d2-251d-5c39-8932-87b9cf6bc94e |  | tickbox | Producer Statement Construction(PS3): Confirmation from mechanical contractor the systems comply with NZBC G4
boolean | 5cbdde31-8fd8-5148-8d39-d17f9dee3438 |  | tickbox | Producer Statement Review(PS4): Confirmation from council approved mechanical engineer that the systems comply with NZBC G4
boolean | 45cc4ee0-5240-577c-b2c6-587c753b9128 |  | tickbox | Producer Statement Review(PS4): Installation of seismic restraints in accordance with NZS 4219:2009:"Seismic Performance of Engineering Systems in Buildings"
boolean | 509077cc-7a0a-589c-8993-715a18c3ff73 |  | tickbox | test/commissioning results verifying measured airflow rates meet design and interface with alarm system
boolean | 8a61ad2a-ed78-5db2-89ac-942f8f79b6f5 |  | tickbox | As built documentation; equipment schedules and make of systems, operation and maintenance manuals
checkpoint-status |  |  | checkpoint | Application for compliance schedule (AC2102)
checkpoint-status |  |  | checkpoint | Confirmation of performance standards for specified systems (AC2150)
checklist-flat |  |  | checklist | F - R - Survey Certificates |  |  |  |  | Yes | F - R - Survey Certificates | 5d389030-5a28-40d1-aa27-89d019e5d71b
checkpoint-status |  |  | checkpoint | survey certificates for correct building height/location/setout attached
checklist-flat |  |  | checklist | F - R - Sheet Piling |  |  |  |  | Yes | F - R - Sheet Piling | 6002bf65-8bce-4f54-accf-bd23189bb860
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Sheet pile installation completed and acceptable
checklist-flat |  |  | checklist | C - R - Service Trenches - Pulling Pits |  |  |  |  | Yes | C - R - Service Trenches - Pulling Pits | 65337357-797c-403b-bbbc-529b6d0d6958
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Pulling Pits trench works completed as per the specifications
checklist-flat |  |  | checklist | C - R - Demolition |  |  |  |  | Yes | C - R - Demolition | 65a8bc0c-9e27-425b-ac02-9c69ed1fe8c2
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Demolition completed and acceptable
checklist-flat |  |  | checklist | C - R - Asbestos Removal |  |  |  |  | Yes | C - R - Asbestos Removal | 67076773-a495-4cd3-8720-c805b350bfa6
checkpoint-status |  |  | checkpoint | Asbestos Removal Control Plan (ARCP) reviewed and attached
checkpoint-status |  |  | checkpoint | Demolition Survey reviewed and attached
checkpoint-status |  |  | checkpoint | Background Air Monitoring Results (BGAM) reviewed and attached
checkpoint-status |  |  | checkpoint | Clearance Certificates reviewed and attached
checkpoint-status |  |  | checkpoint | All asbestos removed and approval given to progress with work
checklist-flat |  |  | checklist | CST - R - Site Inspection Details |  |  |  |  | Yes | CST - R - Site Inspection Details | 739e75ff-6d24-4bc4-9195-b661b583ce62
checkpoint-status |  |  | checkpoint | Specific site works location
checkpoint-status |  |  | checkpoint | Contractor QA reviewed and approved
checkpoint-status |  |  | checkpoint | Have the consented drawings been followed?
checkpoint-status |  |  | checkpoint | General comments, photos, and observations during inspection
checkpoint-status |  |  | checkpoint | Works completed to required specifications - Engineer signoff
checklist-flat |  |  | checklist | FC - R - STO Poly Plaster |  |  |  |  | Yes | FC - R - STO Poly Plaster | 754505af-d6f8-42dd-b1bf-0e57f2f53148
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | STO Poly Plaster works completed and acceptable
checklist-flat |  |  | checklist | C - R - Bulk Excavation |  |  |  |  | Yes | C - R - Bulk Excavation | 7b3db03c-bbe8-4644-9019-ac3918fdc70d
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Excavation completed - Correct locations and RL's achieved
checklist-flat |  |  | checklist | FC - R - Balconies |  |  |  |  | Yes | FC - R - Balconies | 81d94ad3-4c83-4b00-a796-ee88b78cd3fd
checkpoint-status |  |  | checkpoint | Waterproofing and flashing checked and acceptable
checkpoint-status |  |  | checkpoint | All screed to nib and deck falls checked and accurate
checkpoint-status |  |  | checkpoint | Soffit Checked and accurate
checkpoint-status |  |  | checkpoint | Flood test completed and acceptable
checkpoint-status |  |  | checkpoint | Installation of deck tiles completed and acceptable
checkpoint-status |  |  | checkpoint | All works on balcony are completed to required specification.
checklist-flat |  |  | checklist | Compliance Documentation - BCN/2020/3836 |  |  |  |  | Yes | Add Civil Consent BCN/2020/3836 (V2) | 82279fa3-73a3-40f7-a7aa-2c63d2e91273
checkpoint-status |  |  | checkpoint | All documents received, reviewed, attached and approved
label | 4e86d38e-ef10-45b7-9f51-87ad57c28e1d |  | note | "Pass" once all relevant compliance documentation is received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Energy work certificate
holdpoint |  |  | signoff | REQUEST COMPLETION DOCUMENT
checkpoint-status |  |  | checkpoint | Civil consultant's site inspection records - Woods
holdpoint |  |  | signoff | REQUEST COMPLETION DOCUMENT
checkpoint-status |  |  | checkpoint | Producer Statement Construction Review (PS4) Civil engineer - Woods
holdpoint |  |  | signoff | REQUEST COMPLETION DOCUMENT
checkpoint-status |  |  | checkpoint | Geotech engineer's site inspection records - Tonkin & Taylor
holdpoint |  |  | signoff | REQUEST COMPLETION DOCUMENT
checkpoint-status |  |  | checkpoint | Producer Statement Construction Review (PS4) Geotechnical - Tonkin & Taylor
holdpoint |  |  | signoff | REQUEST COMPLETION DOCUMENT
checkpoint-status |  |  | checkpoint | Water reticulation - pipework testing: form B-084
holdpoint |  |  | signoff | REQUEST COMPLETION DOCUMENT
checkpoint-status |  |  | checkpoint | Backflow prevention device: Provide IQP Test Report
holdpoint |  |  | signoff | REQUEST COMPLETION DOCUMENT
checkpoint-status |  |  | checkpoint | Foulwater and stormwater drains layouts
holdpoint |  |  | signoff | REQUEST COMPLETION DOCUMENT
checkpoint-status |  |  | checkpoint | Pressure Sewer System - Provide completed form B-082
holdpoint |  |  | signoff | REQUEST COMPLETION DOCUMENT
checkpoint-status |  |  | checkpoint | Any additional compliance documents
checklist-flat |  |  | checklist | FC - R - Anchor Points - Anchor Point Installation |  |  |  |  | Yes | FC - R - Anchor Points - Anchor Point Installation | 84792489-f833-4c50-ace1-05389072fe9b
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Anchor point installation completed and acceptable
checklist-flat |  |  | checklist | CST - R - Piling Consent |  |  |  |  | Yes | CST - R - Piling Consent | 855737cd-7b04-4600-8256-43efdec7d50b
checkpoint-status |  |  | checkpoint | Record of Title
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Construction Review
boolean | 8d3f0588-92ec-5964-a5f9-4458572517b1 |  | tickbox | Producer Statement Review(PS4): Geotechnical
boolean | b84a773d-9246-51da-a524-c162750101e2 |  | tickbox | Producer Statement Review(PS4): Compaction of hardfill
boolean | bc25e5b8-109b-5b24-b463-60f52393601a |  | tickbox | Producer Statement Review(PS4): Drain Bridging
boolean | f7e1ad34-8c0c-5568-9eeb-7809e7af3412 |  | tickbox | Producer Statement Review(PS4): Engineer's observation
checkpoint-status |  |  | checkpoint | Producer Statement Construction(PS3): Piling
checkpoint-status |  |  | checkpoint | Pile records and cards
checkpoint-status |  |  | checkpoint | Surveyor certificate for siting
checkpoint-status |  |  | checkpoint | Mill certificates
checkpoint-status |  |  | checkpoint | Concrete dockets
checklist-flat |  |  | checklist | ST - R - Roof structure - Steel |  |  |  |  | Yes | ST - R - Roof structure - Steel | 87839c93-2646-43dc-ad8d-fd79ec95a1f6
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All structural steel correctly installed in respective area and acceptable
checklist-flat |  |  | checklist | F - R - Waterproofing |  |  |  |  | Yes | F - R - Waterproofing | 8df3bc4c-3763-4396-b27c-8965db473599
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All waterproofing works completed as per the specifications
checklist-flat |  |  | checklist | FC - R - Roofing |  |  |  |  | Yes | FC - R - Roofing | 9220c7ac-db61-464d-88d8-a9b670ca3860
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Roofing installation completed and acceptable
checklist-flat |  |  | checklist | F - R - Underslab plumbing |  |  |  |  | Yes | F - R - Underslab plumbing | 9a80f6e3-f9a0-4ea0-9a35-e821c3bed321
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All underslab plumbing installation completed as per the specifications
checklist-flat |  |  | checklist | ST - R - Precast Wall Panel Installation |  |  |  |  | Yes | ST - R - Precast Wall Panel Installation | 9d47c2eb-4318-45ab-9a39-d85ea2990007
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Wall Panel Installation completed and acceptable
checklist-flat |  |  | checklist | CST - R - Fitout Consent |  |  |  |  | Yes | CST - R - Fitout Consent | 9dc9dbf1-fbdf-4697-b623-e1f5620b9299
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP records
checkpoint-status |  |  | checkpoint | Waterproofing
boolean | 5e013704-e893-54d7-97f5-781b3daa3e9b |  | tickbox | Producer Statement Construction(PS3): Waterproofing Membrane
boolean | 84ece43b-93a3-58f4-97e5-88f7952c99be |  | tickbox | Manufacturer's warranty for waterproofing membrane
checkpoint-status |  |  | checkpoint | Surface Coatings
boolean | cc371c1c-2abf-5a1a-a0c3-fcab43dffda3 |  | tickbox | Producer Statement Construction(PS3): surface finishes complying with (material categories 1-3 – NZBC clause C3.4(a)
boolean | fe6b3db7-2c97-5e8f-8471-bf945839dff0 |  | tickbox | Producer Statement Construction(PS3): floor surface materials complying with (NZBC clause C3.4(b))
checkpoint-status |  |  | checkpoint | Acoustic testing
boolean | f7546549-8beb-5f88-ac58-e4ec15df552d |  | tickbox | Report/Test certificates from council approved acoustic engineer confirming compliance with NZBC G6
checkpoint-status |  |  | checkpoint | Balustrades
boolean | 488fa40f-5fa7-567c-b6a5-c702c935356d |  | tickbox | Producer Statement Construction(PS3) for balustrade installation
checkpoint-status |  |  | checkpoint | Producer Statement Construction(PS3) for proprietary products
checklist-flat |  |  | checklist | FC - R - External Plaster - Nibs & Beams |  |  |  |  | Yes | FC - R - External Plaster - Nibs & Beams | 9eb5f5d3-8fb8-49dc-923f-880e5d2b911c
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | External Plaster works for Nibs & Beams completed and acceptable
checklist-flat |  |  | checklist | C - R - Detailed Excavation |  |  |  |  | Yes | C - R - Detailed Excavation | 9ece9072-3794-44cf-a8ee-5a1ad46f2acd
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Excavation completed - Correct locations and RL's achieved
checklist-flat |  |  | checklist | FC - R - RAB Board |  |  |  |  | Yes | FC - R - RAB Board | 9f17d2cc-74ea-49dc-9f75-5d9395742318
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | RAB Board works completed and acceptable
checklist-flat |  |  | checklist | ST - R - Precast Shell Beam Lintel Installation |  |  |  |  | Yes | ST - R - Precast Shell Beam Lintel Installation | a62eeaa8-cd9a-4b71-95aa-bb1a35b77612
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Shell Beam Lintel Installation completed and acceptable
checklist-flat |  |  | checklist | C - R - Pipe Laying - Wastewater |  |  |  |  | Yes | C - R - Pipe Laying - Wastewater | a957b79a-c8f9-4e79-a7b2-498ca3914a2b
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Wastewater pipe laying completed as per the specifications
checklist-flat |  |  | checklist | FC - R - Anchor Points - Static line installation |  |  |  |  | Yes | FC - R - Anchor Points - Static line installation | ab161b25-99ef-4704-8aee-374b7c0a7889
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Static line installation completed and acceptable
checklist-flat |  |  | checklist | FC - R - Envelope Penetrations |  |  |  |  | Yes | FC - R - Envelope Penetrations | ad6434b6-1d9c-4707-88f8-948ee662396e
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Envelope Penetrations completed and acceptable
checklist-flat |  |  | checklist | FC - R - Louvres Installation |  |  |  |  | Yes | FC - R - Louvres Installation | afc514b3-e562-415e-8315-2d249b1a58d6
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Balustrades installation completed and acceptable
checklist-flat |  |  | checklist | Add Passive Fire Documents |  |  |  |  | Yes | Add Passive Fire Documents | b4d63cc6-67e0-48ce-8315-97a081a62712
checkpoint-status |  |  | checkpoint | All documents available, checked and referenced
checklist-flat |  |  | checklist | FC - R - Symonite Alucobond Cladding System |  |  |  |  | Yes | FC - R - Symonite Alucobond Cladding System | b5c96c02-b237-4a63-bf1b-4e864aa5e412
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Exterior Tiling works completed and acceptable
checklist-flat |  |  | checklist | C - R - Connection to public systems |  |  |  |  | Yes | C - R - Connection to public systems | b6c3c424-1cb5-4612-8f0f-50fc827f9a46
checkpoint-status |  |  | checkpoint | Approval to connect given by relevant Authority (AC, Watercare, Vector, etc)
checkpoint-status |  |  | checkpoint | Area signed off by engineer
checkpoint-status |  |  | checkpoint | Pipe line connected in accordance with requirements, checked and accurate
checklist-flat |  |  | checklist | CST - R - Hydraulic Consent |  |  |  |  | Yes | CST - R - Hydraulic Consent | b8ded697-3a83-4c2c-95d6-5572b289506c
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Plumbing
boolean | fad87455-eb8b-5917-af71-edbaaf2e85d6 |  | tickbox | Producer Statement Construction (PS3): Plumbing
boolean | 81d859da-fb64-5f4b-b854-875601b84a00 |  | tickbox | Confirmation of water saving devices
boolean | 8c6dd7cf-c9ee-531a-bf6d-4028c6fbdfa8 |  | tickbox | Plumbing under slab as built plan
boolean | 1d74770b-bed1-543d-b8ef-75088112e2c2 |  | tickbox | Producer Statement Review(PS4): hydraulic systems of the building from a council approved engineer
checkpoint-status |  |  | checkpoint | Gas-fitting Work Certificate
checkpoint-status |  |  | checkpoint | Automatic Backflow Preventers Connected to Potable Water supply
boolean | 0e342236-2d88-5f61-ad36-1c9d673c1c63 |  | tickbox | Backflow prevention - PS3 and test certificates showing location and type of devices
checkpoint-status |  |  | checkpoint | Application for compliance schedule (AC2102)
checkpoint-status |  |  | checkpoint | Confirmation of performance standards for specified systems (AC2150)
checklist-flat |  |  | checklist | PRE - R - PRE-line |  |  |  |  | Yes | PRE - R - PRE-line | b8ffc319-1213-4f9d-b879-f065e7e54f9b
checkpoint-status |  |  | checkpoint | PRE-line works completed and acceptable. Trades QA received, reviewed, attached and approved for all pre-line trades. Approved to line the area.
button | 3eb49f18-5ba5-5a75-9b50-d4e7ce9483d3 |  | button | Timber frame installation completed and acceptable | Yes, N/A
button | dd298649-a257-5191-b84a-9dbc88c189f0 |  | button | Steel Stud frame installation completed and acceptable | Yes, N/A
button | b9ccdc01-f66c-5de6-a6cc-e15da4571c70 |  | button | Electrical First Fix completed and acceptable | Yes, N/A
button | e5b4228e-3244-516e-a1f6-c2995d5ff48a |  | button | Plumbing First Fix completed and acceptable | Yes, N/A
button | bcfed2cb-4484-5754-aae7-78b2817c5661 |  | button | Security, Comms and Data First Fix completed and acceptable | Yes, N/A
button | 5c6d14b8-1e16-534a-b46f-1abd1e6de30e |  | button | HVAC First Fix completed and acceptable | Yes, N/A
button | f59051c6-7b1e-5adc-b444-30f836cb8a22 |  | button | Fire Security First Fix completed and acceptable | Yes, N/A
button | 0a354587-79ab-5329-ae3c-f90ca6404016 |  | button | Under floor heating First Fix (including screeding and soundproofing of the bathrooms/ wc) completed and acceptable | Yes, N/A
button | ff44d26b-5a59-51d3-b104-63c07eb1f21b |  | button | Kitchen extract First Fix completed and acceptable | Yes, N/A
button | f14a2852-1925-5b50-a0b4-7586ff8032ef |  | button | Insulation installation completed and acceptable | Yes, N/A
button | b655f24c-5e89-503d-95e6-d0738a8ab60b |  | button | Passive fire installation completed and acceptable | Yes, N/A
button | 28c61b25-bd67-5d53-9fe3-10abd74bdb8b |  | button | Suspended ceiling grids installation completed and acceptable | Yes, N/A
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checklist-flat |  |  | checklist | Council Inspection - |  |  |  |  | Yes | Add Council Inspection Checklist (V2) | bb8d764e-6715-4ac9-bef8-249ad6393b50
checkpoint-status |  |  | checkpoint | Inspection completed, attached and any relevant observations closed out
label | 2d8a788d-2b5e-4656-ab5e-0d716310f606 |  | note | Pass once all information is attached including observations with evidence of closeout
text | f713d72a-a804-45e0-8fd1-25ce4e2beed7 |  | textbox | Date of Inspection:
text | 27fff276-098e-4848-aa62-a120f0e8cf9b |  | textbox | Type of Inspection:
text | 31f12e5f-2b14-4af1-b5f0-384970a844fe |  | textbox | Area inspection relates to
select | d18e264f-d0aa-43aa-9056-9495ad0c81f2 |  | dropdown | Inspection Outcome | Pass, Fail, Partial Pass, N/A
boolean | a165bb6e-b16c-4fb1-96a5-2b5abed9a7d5 |  | tickbox | Council Inspection attached
button | 3853dca0-11b4-44c8-a86f-7866e5dc9824 |  | button | All Relevant Observation Closeout evidence attached below if applicable (Pass once completed) | Pass,N/A
text | b168ffe6-579a-40ee-aee1-89a04daecc47 |  | textbox | Failed Comments & Required Action
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | CST - R - Structural Consent |  |  |  |  | Yes | CST - R - Structural Consent | bbb5f1c7-e70a-4730-b60f-857b1fc4aa34
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Pre-cast concrete
boolean | ece430e5-f9ec-510f-ad04-e4740d69c13a |  | tickbox | Producer Statement Design(PS1): Prestressed beams, walls, stairs, columns and floor units
boolean | bc9d5253-efbe-57b0-b4df-d1aa07485610 |  | tickbox | Producer Statement Construction(PS3): Prestressed beams, walls, stairs, columns and floor units
boolean | 54318a46-95bb-5243-92f3-ab6a8e550b67 |  | tickbox | Producer Statement Review(PS4): Prestressed beams, walls, stairs, columns and floor units
checkpoint-status |  |  | checkpoint | Structural Steel
boolean | 9d874293-49ce-5343-b4a0-efa9b97ce157 |  | tickbox | Producer Statement Construction(PS3): Corrosion Protection
boolean | 58e2a82b-2a41-5b6a-a383-cedcf0829371 |  | tickbox | ITPs approved by structural engineer
boolean | f86b7260-b6d5-55c5-b6e5-05380abdf34b |  | tickbox | weld inspection and test records
checkpoint-status |  |  | checkpoint | Fire rated (Intumescent) Coatings to Structural Steel
boolean | 37661126-cbc9-5d11-8ed2-2b70c6a6db47 |  | tickbox | Producer Statement Construction(PS3 - AC2334): Intumescent coatings to structural steel from approved applicator
boolean | 8f34da1d-46e7-5145-b29f-709b9788bc9f |  | tickbox | Suppliers material schedule - products used and thicknesses applied
boolean | 018dbfd9-e802-5b83-87b5-dd336c93d4f1 |  | tickbox | Floor plan of intumescent coating locations
checkpoint-status |  |  | checkpoint | Trusses
boolean | df39207e-d30d-562c-b536-6b73c26b922a |  | tickbox | Producer Statement Design(PS1): Layout Plan for timber roof trusses
boolean | c635024d-5303-54c4-aec2-d32a2b111b7c |  | tickbox | Producer Statement Construction(PS3): for timber roof trusses
checkpoint-status |  |  | checkpoint | Construction Review (Structural)
boolean | a5a7a475-92f3-5d99-a56b-3d289cdcca1b |  | tickbox | Producer Statement Construction Review(PS4): Certification of work in accordance with design, drawings, specifications and material codes
boolean | f9e5be4b-dd1d-5b4b-bae3-8c827f72f737 |  | tickbox | Producer Statement Construction Review(PS4): excavation near boundary and site observation notes
boolean | 1f5b94db-fcaf-5aed-94a2-4d5b519799cc |  | tickbox | Producer Statement Construction Review(PS4): Raft slab and site observation notes
boolean | 01fb8989-70ed-534f-a8a6-2f470fb42a89 |  | tickbox | Producer Statement Construction Review(PS4): Swimming pool and site observation notes
boolean | 2d197b34-3abf-570e-a4b2-1d01c2672974 |  | tickbox | Producer Statement Construction Review(PS4): Type A or B masonry and site observation notes
boolean | 86ac2184-32f6-5389-a367-54b62f9c066a |  | tickbox | Producer Statement Construction Review(PS4): Underpinning and site observation notes
boolean | d66e2334-5d96-5011-be97-5720c8122343 |  | tickbox | Producer Statement Construction Review(PS4): Structural steel including connections and site observation notes
boolean | 2f36a349-80de-578e-8e0d-d78457e9782b |  | tickbox | Producer Statement Construction Review(PS4): Timber pole retaining wall and site observation notes
boolean | 0906e1af-8f41-52f9-b48f-c2ed9d7fc071 |  | tickbox | Producer Statement Construction Review(PS4): reinforced concrete foundations and site observation notes
boolean | 596ddefc-6799-529f-a562-f245ea91ab86 |  | tickbox | Producer Statement Construction Review(PS4): Suspended concrete slab and site observation notes
boolean | b0ad8bc4-82ed-58b5-a169-6eba976d184f |  | tickbox | Producer Statement Construction Review(PS4): Precast elements and site observation notes
boolean | 136d4548-74d6-5012-9559-5cef2eef0e30 |  | tickbox | Structural engineer's variations and contractor advice notes
checkpoint-status |  |  | checkpoint | Surveyor certificate for finished floor levels
checklist-flat |  |  | checklist | FC - R - Windows and Sliders |  |  |  |  | Yes | FC - R - Windows and Sliders | bc49d76a-f735-4bf6-a4bb-f57eb5cd92d2
checkpoint-status |  |  | checkpoint | Check clearance around opening min 6mm/ max 18mm
checkpoint-status |  |  | checkpoint | Packers to be correctly used and set back to allow continuous air seal
checkpoint-status |  |  | checkpoint | Check air seal is provided at the rear of the window reveal
holdpoint |  |  | signoff | Raise remedial/ request signoff
checkpoint-status |  |  | checkpoint | Window and slider installation completed and acceptable
checklist-flat |  |  | checklist | ST - R - Insitu Stitch Joints |  |  |  |  | Yes | ST - R - Insitu Stitch Joints | c452f44e-3e46-423d-b8ab-bcfa049f2c0c
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Insitu Stitch Joints concrete pour completed and acceptable
checklist-flat |  |  | checklist | Handover |  |  |  |  | Yes | H - R - Handover | c7c4d338-196d-469f-937c-e8a02865a00c
checkpoint-status |  |  | checkpoint | Hardware/Fittings
checkpoint-status |  |  | checkpoint | Plumbing
checkpoint-status |  |  | checkpoint | Electrical
checkpoint-status |  |  | checkpoint | Joinery/Doors
checkpoint-status |  |  | checkpoint | Decorating
checkpoint-status |  |  | checkpoint | Flooring
checkpoint-status |  |  | checkpoint | Other
checkpoint-status |  |  | checkpoint | Upload Related Ryman Fitout quality inspection record (QT-012)
checklist-flat |  |  | checklist | ST - R - Precast Spandrel Panel Installation |  |  |  |  | Yes | ST - R - Precast Spandrel Panel Installation | cad4f97f-2e8e-4a20-8654-275a866cff06
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Spandrel Panel Installation completed and acceptable
checklist-flat |  |  | checklist | CST - R - Civil Consent |  |  |  |  | Yes | CST - R - Civil Consent | cd7dc171-9a02-4baa-a3ed-8f14b9e8e1fe
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Drainage
boolean | 6ff12d23-1b7f-58ef-ba09-4f26463eab17 |  | tickbox | Producer Statement Construction(PS3): sub-soil drains
boolean | 37e98f60-1ae6-5e36-b881-6f5e84f326f4 |  | tickbox | Producer Statement Construction(PS3): drainage
boolean | d0724420-990c-5c59-9d0e-ff185b771413 |  | tickbox | Drainage as built plan
boolean | f8fc99a3-a297-5021-97a9-ce7892a142c9 |  | tickbox | Producer Statement Construction(PS3): Stormwater Management
boolean | 12bb81d3-9868-5675-92a4-a229abeb3a52 |  | tickbox | Producer Statement Review(PS4): Stormwater management approved by council Engineer
boolean | 2e3c6b50-252b-5a65-a66a-53df4ded27b0 |  | tickbox | Operations and Maintenance manual for stormwater management systems
boolean | e8d8003c-3971-5919-99cf-fd7cbe909ea6 |  | tickbox | Backflow test Certificate | Yes,No,N/A
checkpoint-status |  |  | checkpoint | Drainage Pump Systems
boolean | f70d46ea-0a63-513b-9d52-cdb0a7119c3e |  | tickbox | Producer Statement Construction(PS3): installation of drainage pump system
boolean | 29182a2c-a194-55b8-b7ed-d3f8f4cd9f79 |  | tickbox | Manufacturer's warranty for pump system
boolean | 84d2a298-25dd-5caf-bcfb-e8ec78103097 |  | tickbox | Maintenance agreement for pump system
checkpoint-status |  |  | checkpoint | On-Site wastewater Systems
boolean | a0b14624-89fc-59e4-ae9c-0697d02710e5 |  | tickbox | Producer Statement Construction(PS3): wastewater treatment and disposal system
boolean | ba3e6761-a145-5fcd-b638-a4a2b39a535c |  | tickbox | Plan showing location of treatment and disposal of systems
boolean | fecf0cb0-8a49-50a6-9a02-cce58790addc |  | tickbox | Producer Statement Review(PS4): System of onsite treatment and disposal of wastewater
boolean | 2f1c7027-bcc2-5683-a7cf-82882ef62aa4 |  | tickbox | Maintenance agreement for on-site wastewater treatment and disposal system
checkpoint-status |  |  | checkpoint | Development Engineering
boolean | 8be00230-678d-5171-893f-eba36f35d6d1 |  | tickbox | Written approval of works completed within 2m of public waste water drainage
boolean | 1bd4fd86-98b4-5c34-955b-6f50173d19d7 |  | tickbox | Engineering Approval Completion Certificate for ENG
checkpoint-status |  |  | checkpoint | Watercare Services/Viola Approval
boolean | 2ec4f456-6b73-557d-a032-3e1be28ff148 |  | tickbox | Certificate of connection for both incoming and outgoing water to the public system
boolean | 6de46545-1956-560a-9cbd-45d15e56ca78 |  | tickbox | Written approval of completed works
checklist-flat |  |  | checklist | FC - R - Soffits |  |  |  |  | Yes | FC - R - Soffits | d9916172-8057-4f16-929c-a58b1d0efaa7
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Soffit works completed and acceptable
checklist-flat |  |  | checklist | FC - R - Cladding Sealant |  |  |  |  | Yes | FC - R - Cladding Sealant | dd8d63f3-ff38-4986-a213-083bb0bf03a7
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Cladding sealant completed and acceptable
checklist-flat |  |  | checklist | F - R - Backfilling |  |  |  |  | Yes | F - R - Backfilling | e028194c-cfef-4c2a-a246-100dd9c3b078
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Backfilling completed as per the specifications
checklist-flat |  |  | checklist | ST - R - Precast Wall Bracket Installation |  |  |  |  | Yes | ST - R - Precast Wall Bracket Installation | e3cb2050-f3c7-4342-9676-782662e81b15
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Wall Bracket Installation completed and acceptable
checklist-flat |  |  | checklist | F - R - Crane Piling |  |  |  |  | Yes | F - R - Crane Piling | e40535e8-3646-40aa-8e58-65cee8469c36
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Crane Piling completed and acceptable
checklist-flat |  |  | checklist | FC - R - Air conditioning |  |  |  |  | Yes | FC - R - Air conditioning | e4b9972a-2bfb-4082-9051-cb02d7c581c6
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Exterior Tiling works completed and acceptable
checklist-flat |  |  | checklist | CST - R - Restricted Building Works Consent |  |  |  |  | Yes | CST - R - Restricted Building Works Consent | e6635c39-0458-4c9c-bf29-fae68cca9f0d
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Record of works
boolean | 90c3e8a5-bc73-514a-b939-217d0b2c1fff |  | tickbox | Foundations
boolean | e2b333e2-3426-5c58-852e-1dfeeb373b8e |  | tickbox | Slab or subfloor framing
boolean | d92d6a3c-a7e5-5139-a2fc-4e43de8f75c5 |  | tickbox | Blockwork
boolean | aa9c7d38-3784-5ec1-9882-ac68d05f2bf6 |  | tickbox | Walls
boolean | f81869a3-c9b3-5982-a36c-dff13e040ae3 |  | tickbox | Roof
boolean | 916abf89-0d99-5183-ac0a-4f1db34e1988 |  | tickbox | Columns and Beams
boolean | e2207f9a-8f9b-5181-baf3-fe96ae0edae5 |  | tickbox | Bracing
boolean | cfa0208e-1d30-5b38-abaa-abd7cf10cb97 |  | tickbox | Damp proofing
boolean | d004563c-0ab4-57b4-80c3-fca74d253231 |  | tickbox | Roof cladding or roof cladding system
boolean | 863a84a8-c902-5170-ae0f-8675c86f0cee |  | tickbox | Ventilation system
boolean | 73e48a95-3c80-551f-b0fd-11959b0d2e45 |  | tickbox | Wall cladding or wall cladding system
boolean | 1071cff2-c945-5d5f-af25-5b193dda4800 |  | tickbox | Waterproofing
checkpoint-status |  |  | checkpoint | Record of warranties
checklist-flat |  |  | checklist | FC - R - Exterior Tiling |  |  |  |  | Yes | FC - R - Exterior Tiling | e669e6ed-e639-4aba-a8c2-84b2b68d3019
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Exterior Tiling works completed and acceptable
checklist-flat |  |  | checklist | CST - R - Demolition Consent |  |  |  |  | Yes | CST - R - Demolition Consent | e6a27124-6f71-4f98-b696-1b377e40b2af
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection passed
checkpoint-status |  |  | checkpoint | Summary Sheet - Site inspection records
checkpoint-status |  |  | checkpoint | Summary Sheet - LBP Records
checkpoint-status |  |  | checkpoint | Asbestos - Asbestos Clearance Certificates & PS3
checkpoint-status |  |  | checkpoint | Demolition - PS3
checklist-flat |  |  | checklist | FC - R - Anchor Points - Intermediate, Corner and End Plate Installation |  |  |  |  | Yes | FC - R - Anchor Points - Intermediate, Corner and End Plate Installation | ec33cc28-d7fe-4b67-8c44-41d583b4aadb
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Intermediate, Corner and End Plate installation completed and acceptable
checklist-flat |  |  | checklist | F - R - Piling |  |  |  |  | Yes | F - R - Piling | ec63d5d5-202a-4311-a785-d5def84499a2
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Piling completed as per the specifications
checklist-flat |  |  | checklist | ST - R - Precast Edge Beams Installation |  |  |  |  | Yes | ST - R - Precast Edge Beams Installation | ecb2e992-b5b4-4a65-998d-5b21d0cf8ee0
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Edge Beams Installation completed and acceptable
checklist-flat |  |  | checklist | FC - R - Ecoply Board |  |  |  |  | Yes | FC - R - Ecoply Board | f0d30980-66c1-46e8-a142-9b71685d2a19
checkpoint-status |  |  | checkpoint | Fixing and spacings checked in accordance with manufacturers specs.
checkpoint-status |  |  | checkpoint | Bracing checked and accurate
checkpoint-status |  |  | checkpoint | Penetrations and punctures sealed with flashing tape
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Ecoply board installation completed and acceptable
checklist-flat |  |  | checklist | CST - R - Council Inspection |  |  |  |  | Yes | CST - R - Council Inspection | f1055187-b866-4425-b454-8d5618c32ff8
checkpoint-no-status |  |  | checkpoint | Inspection Details:
text | 5a3c1a62-940f-540c-87b7-956efdfdfe1a |  | textbox | Date of Inspection
text | 66ff6ccf-4bd8-579e-9110-cd153fe8b46c |  | textbox | Type of Inspection
text | be59bfc8-a8f0-5f52-a984-0582e3f32ad8 |  | textbox | Area Inspection relates to
select | 010dac22-5197-5dea-96ff-91495be452cb |  | dropdown | Inspection outcome | Pass, Partial Pass, Fail
boolean | 17fb5b53-8735-5316-962b-988f1e618a0e |  | tickbox | Council inspection attached
checkpoint-status |  |  | checkpoint | Relevant Observation Closeout evidence attached below if applicable (pass once completed)
text | e89cf5fe-4960-592d-a7f3-7c382edf9135 |  | textbox | Failed comments and Required Action
checklist-flat |  |  | checklist | ST - R - Rib & Infill Installation |  |  |  |  | Yes | ST - R - Rib & Infill Installation | f220b0a2-97cc-414b-accf-f1bf5f7bf08d
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Rib & Infill Installation completed and acceptable
checklist-flat |  |  | checklist | FC - R - Down Pipes |  |  |  |  | Yes | FC - R - Down Pipes | f6a3ef5e-89b7-48ce-be74-5c8514f890e6
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Downpipe installation completed and acceptable
checklist-flat |  |  | checklist | CST - R - Façade Consent |  |  |  |  | Yes | CST - R - Façade Consent | fc02aa2f-1136-493d-b452-d8f9b8e6c783
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Exterior
boolean | d421da1d-3c2f-5f1b-a35e-a9cf6213cdeb |  | tickbox | Producer Statement Construction(PS3): Plaster system and manufacturer's product warranty
boolean | 866469a8-31ae-52a5-9080-85bf2c436c96 |  | tickbox | Producer Statement Construction(PS3): Brick work and manufacturer's product warranty
checkpoint-status |  |  | checkpoint | Glazing and external joinery
boolean | bdaa5e83-29e7-576a-8ea8-09e8ea73fb42 |  | tickbox | Producer statement for aluminium joinery complying with NZS4211:2008
boolean | ca8a1ad6-c543-5915-b0a2-764926ec9e83 |  | tickbox | Producer Statement Construction(PS3): safety glazing in compliance with NZS4211:2008
boolean | bf997a6f-db0f-5ae9-a134-5679c707e95d |  | tickbox | Producer Statement Design(PS1) from joinery manufacturer
boolean | d1408223-f563-52d9-b9f4-8a9b5278f441 |  | tickbox | Producer statement for fire rated windows confirming compliance with NZS4232
checkpoint-status |  |  | checkpoint | Waterproofing
boolean | 8409f639-3d5d-5612-a334-ed030118ea21 |  | tickbox | Producer Statement Construction(PS3): Roof membrane and Manufacturer's product warranty
boolean | f820dbb6-bd39-5942-bffb-66ac8c8f306e |  | tickbox | Producer Statement Construction(PS3): Deck Membrane and manufacturer's product warranty
boolean | fc3f2565-9c2d-5dde-a589-08730bdeb911 |  | tickbox | Producer Statement Construction(PS3): Tanking membrane and manufacturer's product warranty
checkpoint-status |  |  | checkpoint | Roof abseil and fall arrest system
boolean | 7ea60a3c-d460-5985-9eb9-33ba39545166 |  | tickbox | Producer Statement Design(PS1): installation of roof abseil and/or fall arrest system
boolean | 38e3d5fa-5a5c-5d19-b1da-e50b0d174291 |  | tickbox | Producer Statement Construction(PS3): installation of roof abseil and/or fall arrest system
boolean | d1362f89-3ad1-547e-955d-159ffbf64fed |  | tickbox | Producer Statement Review(PS4): installation of roof abseil and/or fall arrest system
checkpoint-status |  |  | checkpoint | Balustrades
boolean | 667b2fb1-7b76-53fe-9bfc-f7bd7d1f9671 |  | tickbox | Producer Statement Construction (PS3) for the balustrade installation
checkpoint-status |  |  | checkpoint | Façade systems
boolean | b40b72d5-ce4f-546d-be72-76d4e50b6531 |  | tickbox | Producer Statement Review(PS4): from council approved façade engineer for façade system
boolean | e0c4d4c6-88e3-5436-913f-9f927aa7e77c |  | tickbox | Written report from council approved façade engineer for façade system (supporting the PS4)
boolean | 1f72daa2-bc90-53d0-baf7-8aa76c6bef03 |  | tickbox | Producer Statement Construction(PS3): installation of the façade system
boolean | bdd7aec1-87e9-5bec-b828-68ca843ad6eb |  | tickbox | Façade System Maintenance Manual
boolean | 2f159fa4-95e0-5937-98df-e3c4507987ec |  | tickbox | Warranties/Guarantees from main and sub-contractors
checklist-flat |  |  | checklist | C - R - Pipe Laying - Stormwater |  |  |  |  | Yes | C - R - Pipe Laying - Stormwater | fc4afb3b-dc49-43c5-9bea-beaeb4bb43cd
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Stormwater pipe laying completed as per the specifications