## Checklist
checklist | POST - S - Plumbing Second Fix
section | Preinstall QA
checkpoint | Permission to begin work obtained
checkpoint | Drawings correct issue and construction set
Checkpoint | Area is left clean and tidy and work can begin
Checkpoint | Fit-off materials match schedule or drawings
Checkpoint | Setouts/min clearances as per specification
Checkpoint | Water pipework maintained test throughout
Checkpoint | No debris in floor wastes or subs
Section | Water Supplies
Checkpoint | Toilet full flush and half flush working as required. Visual check for leaks on pan cone and close coupled connection
Checkpoint | Vanity basin mixer working to required flow rate and overflow able to keep up with flow rate from mixer
Checkpoint | Sink overflow able to keep up with flow rate from mixer
Checkpoint | Dishwasher commissioned
Checkpoint | Showers - Mixer working to required flow rate and shower hoses fitted with non-returns
Section | Hot water cylinder
Checkpoint | Trap installed on tray if required
Checkpoint | HWC relief lines have 25mm clearance
Checkpoint | Restraints installed
Checkpoint | Hot water set to Min 60°
Checkpoint | Tempering valve set to required temperature
Checkpoint | Timber blocks installed
Section | Finishing
Checkpoint | Flanges installed on all pipework penetrations
Checkpoint | All soil pipes are connected to sanitary sewer
Checkpoint | No crossovers, hot on left and cold on right on all mixers
Checkpoint | All fixtures are siliconed down and splash sealed
Checkpoint | Hose taps are complete with Vacuum Breakers
Checkpoint | Area is left clean and tidy
Checkpoint | Work is 100% competed to required specifications
holdpoint | Raise remedial/Request signoff