## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | C - R - Connection to public systems |  |  |  |  | Yes | C - R - Connection to public systems | 01f80219-3149-4a5f-b8e7-4e6dfb6205ef
checkpoint-status |  |  | checkpoint | Approval to connect given by relevant Authority (AC, Watercare, Vector, etc)
checkpoint-status |  |  | checkpoint | Area signed off by engineer
checkpoint-status |  |  | checkpoint | Pipe line connected in accordance with requirements, checked and accurate
checklist-flat |  |  | checklist | FC - R - Water Test |  |  |  |  | Yes | FC - R - Water Test | 02981f98-dc95-4253-acbf-bdc63d97483b
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Water Test completed and acceptable
checklist-flat | b7353c3f-2613-42dc-a1c4-90669fd48e1b |  | checklist | Minor Variation - |  |  |  |  | Yes | Add Council Minor Variation Checklist | 054e47eb-e59d-464e-abea-a82ebb016bf2
checkpoint-status | ed8928c6-cc30-4efd-9718-3c1ee68b671c |  | checkpoint | Minor variation status (Pass once approved & all information is attached including observations, correspondence & close out evidence)
label | d83c76ad-c2c4-422a-b3d0-5e46ac4be24f |  | note | PASS above checkpoint when Council variation is approved
label | ab21c4bc-c773-43ee-88d7-f338c674ee92 |  | note | If minor variation is a FAIL - document why below and follow appropriate corrective actions
text | e716f58a-4420-4e11-91ae-f4fef0f7ba87 |  | textbox | Date of application
text | 6931f74e-964b-42b5-905c-440c2ce0001a |  | textbox | Reason for application
text | 4ce69a81-cba4-4eac-b963-ff28392bbaf5 |  | textbox | Date of approval / acceptance
text | 78d9159e-0896-4188-a542-fa6b1bf43aaa |  | textbox | Inspection Type Code (If applicable e.g. Site meeting IME)
boolean | d24858c1-85f5-44b8-99c0-818a707a7f19 |  | tickbox | Council approval of minor variation attached
checklist-flat |  |  | checklist | C - R - Service Trenches - Pulling Pits |  |  |  |  | Yes | C - R - Service Trenches - Pulling Pits | 0af534f4-a1ac-4a28-ace2-3fcc6e3e1281
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Pulling Pits trench works completed as per the specifications
checklist-flat |  |  | checklist | ST - R - Precast Spandrel Panel Installation |  |  |  |  | Yes | ST - R - Precast Spandrel Panel Installation | 0c34121d-0005-47ee-9cf4-357a3d9eb815
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Spandrel Panel Installation completed and acceptable
checklist-flat |  |  | checklist | ST - R - Roof structure - Timber Trusses |  |  |  |  | Yes | ST - R - Roof structure - Timber Trusses | 0e4a9956-340e-42c0-83fb-90d6c9bff706
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All timber trusses correctly installed in respective area and acceptable
checklist-flat |  |  | checklist | FC - R - Louvres Installation |  |  |  |  | Yes | FC - R - Louvres Installation | 10b05dc3-3fc8-4670-9ec8-7945c1ce2c3c
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Balustrades installation completed and acceptable
checklist-flat |  |  | checklist | FC - R - Tapes and VaproShield |  |  |  |  | Yes | FC - R - Tapes and VaproShield | 13985943-e99d-4714-8324-61ca70a1d2b9
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Tapes/VaproShield works completed and acceptable
checklist-flat |  |  | checklist | FC - R - Envelope Penetrations |  |  |  |  | Yes | FC - R - Envelope Penetrations | 1a6b922a-7fc5-4c89-ba40-296a055982bc
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Envelope Penetrations completed and acceptable
checklist-flat |  |  | checklist | PRE - R - PRE-line |  |  |  |  | Yes | PRE - R - PRE-line | 1ad7f9db-d4f8-492c-a971-e3664981c86f
checkpoint-status |  |  | checkpoint | PRE-line works completed and acceptable. Trades QA received, reviewed, attached and approved for all pre-line trades. Approved to line the area.
button | fee0c156-969f-59f1-9206-3094429b9c6e |  | button | Timber frame installation completed and acceptable | Yes, N/A
button | 7c7aef0a-9d65-5329-a9e8-06279619d673 |  | button | Steel Stud frame installation completed and acceptable | Yes, N/A
button | 532b1a28-8482-5f62-8aaf-6c43e3627da1 |  | button | Electrical First Fix completed and acceptable | Yes, N/A
button | 43fd1d26-6df4-5366-881d-ca544910a275 |  | button | Plumbing First Fix completed and acceptable | Yes, N/A
button | bb0f768b-939e-5bad-a462-a57403530307 |  | button | Security, Comms and Data First Fix completed and acceptable | Yes, N/A
button | 59aa9ec4-6f4c-59f0-a05c-0e6e45f1acf4 |  | button | HVAC First Fix completed and acceptable | Yes, N/A
button | 85e23c26-7ad3-569b-a151-47e572154a10 |  | button | Fire Security First Fix completed and acceptable | Yes, N/A
button | 1fe4da37-a860-58fb-9117-c9c7d91dc6f3 |  | button | Under floor heating First Fix (including screeding and soundproofing of the bathrooms/ wc) completed and acceptable | Yes, N/A
button | 7e1bc980-1942-5455-bb36-823fb6cbe398 |  | button | Kitchen extract First Fix completed and acceptable | Yes, N/A
button | eadf2590-bf75-5739-9ab2-055dd2ce003e |  | button | Insulation installation completed and acceptable | Yes, N/A
button | bffcf7e7-7491-567f-a3cf-2177394f8d7f |  | button | Passive fire installation completed and acceptable | Yes, N/A
button | 18b2e3a0-431d-53df-9f1b-51eeb59ddfc5 |  | button | Suspended ceiling grids installation completed and acceptable | Yes, N/A
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checklist-flat |  |  | checklist | CST - R - Fitout Consent |  |  |  |  | Yes | CST - R - Fitout Consent | 23aa50cf-007c-4a49-9151-84db109cc287
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP records
checkpoint-status |  |  | checkpoint | Waterproofing
boolean | 6a56a4ed-3223-5641-9d83-0a95be008fa2 |  | tickbox | Producer Statement Construction(PS3): Waterproofing Membrane
boolean | b951c2f2-e7fb-5231-a76a-70edd18346c2 |  | tickbox | Manufacturer's warranty for waterproofing membrane
checkpoint-status |  |  | checkpoint | Surface Coatings
boolean | fa07c014-75d0-5d05-9403-2abf7b443e67 |  | tickbox | Producer Statement Construction(PS3): surface finishes complying with (material categories 1-3 – NZBC clause C3.4(a)
boolean | 528c7fe6-9e0c-5006-b9c4-fedfdd7c76ab |  | tickbox | Producer Statement Construction(PS3): floor surface materials complying with (NZBC clause C3.4(b))
checkpoint-status |  |  | checkpoint | Acoustic testing
boolean | 4a1f1505-fc1b-5b6b-92ce-b62b5a071014 |  | tickbox | Report/Test certificates from council approved acoustic engineer confirming compliance with NZBC G6
checkpoint-status |  |  | checkpoint | Balustrades
boolean | fa0322fe-2f8a-5c93-b722-008fd836d9a6 |  | tickbox | Producer Statement Construction(PS3) for balustrade installation
checkpoint-status |  |  | checkpoint | Producer Statement Construction(PS3) for proprietary products
checklist-flat |  |  | checklist | ST - R - Stair Installation |  |  |  |  | Yes | ST - R - Stair Installation | 24830c3e-0866-480d-9876-05d1e1c11b9c
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Stair Installation completed and acceptable
checklist-flat |  |  | checklist | F - R - Piling |  |  |  |  | Yes | F - R - Piling | 25fb667c-ce8a-4b49-bcea-ac49767813d6
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Piling completed as per the specifications
checklist-flat |  |  | checklist | ST - R - Precast Wall Panel Installation |  |  |  |  | Yes | ST - R - Precast Wall Panel Installation | 28fc58c4-0324-4a6a-9344-faad9362e605
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Wall Panel Installation completed and acceptable
checklist-flat |  |  | checklist | CST - S - Completion Documents |  |  |  |  | Yes | CST - S - Completion Documents | 2bd04e2e-ebeb-49db-95b9-a74cef3a6255
checkpoint-status |  |  | checkpoint | All relevant Compliance Documentation completed and attached above
boolean | 605fc304-cf92-5a06-84f8-77cc522fce42 |  | tickbox | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
label | b369d82f-b1f1-53eb-93c3-a29308e49aeb |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | FC - R - Down Pipes |  |  |  |  | Yes | FC - R - Down Pipes | 2d74b8f0-7d14-46c4-8d7b-2d9626a9fe5b
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Downpipe installation completed and acceptable
checklist-flat |  |  | checklist | C - R - Demolition |  |  |  |  | Yes | C - R - Demolition | 2e0a0880-7e75-4af3-adf9-bc9b1045da11
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Demolition completed and acceptable
checklist-flat |  |  | checklist | C - R - Pipe Laying - Wastewater |  |  |  |  | Yes | C - R - Pipe Laying - Wastewater | 34614409-3861-4532-bdf7-bb61a34e316b
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Wastewater pipe laying completed as per the specifications
checklist-flat |  |  | checklist | Council Inspection - |  |  |  |  | Yes | Add Council Inspection Checklist | 35321fc8-3347-442e-a3ad-52b253b4dc3c
checkpoint-status |  |  | checkpoint | Inspection completed, attached and any relevant observations closed out (Pass once all information is attached including observations with evidence of closeout)
text | e716f58a-4420-4e11-91ae-f4fef0f7ba87 |  | textbox | Date of inspection:
text | 78d9159e-0896-4188-a542-fa6b1bf43aaa |  | textbox | Inspection Type Code:
text | 6931f74e-964b-42b5-905c-440c2ce0001a |  | textbox | Area inspection relates to
select | ca58c4ad-f5b3-41c0-ae49-ce6c1c3289f9 |  | dropdown | Inspection Outcome | Pass,Fail,Partial Pass,N/A
boolean | d24858c1-85f5-44b8-99c0-818a707a7f19 |  | tickbox | Council inspection attached
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All Relevant Observation Closeout evidence attached here if applicable (Pass once completed)
text | 659f0de8-c7a9-45fe-9851-606ecd798dd2 |  | textbox | Outstanding Information Required
checklist-flat |  |  | checklist | FC - R - Symonite Alucobond Cladding System |  |  |  |  | Yes | FC - R - Symonite Alucobond Cladding System | 3574e4e0-c0b9-4c83-94e9-6cae73f1bf4f
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Exterior Tiling works completed and acceptable
checklist-flat |  |  | checklist | FC - R - STO Poly Plaster |  |  |  |  | Yes | FC - R - STO Poly Plaster | 35a1c5e4-1dad-4088-9a83-ff03608a92d9
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | STO Poly Plaster works completed and acceptable
checklist-flat |  |  | checklist | ST - R - Roof structure - Steel |  |  |  |  | Yes | ST - R - Roof structure - Steel | 35d5b7c9-0cd9-4caa-acc7-43206e849057
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All structural steel correctly installed in respective area and acceptable
checklist-flat |  |  | checklist | C - R - Detailed Excavation |  |  |  |  | Yes | C - R - Detailed Excavation | 3722c34e-f2e4-407a-a8dc-57e3475236a8
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Excavation completed - Correct locations and RL's achieved
checklist-flat |  |  | checklist | CST - R - Fire Consent |  |  |  |  | Yes | CST - R - Fire Consent | 410ee663-228d-43a2-86d7-951454f3af40
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Electrical
boolean | 9a3c1ab4-719a-502d-8f3b-ef008149deb3 |  | tickbox | Electrical compliance and safety certificate
boolean | fa0cfa4b-ddf1-51e6-9411-09701a918ce4 |  | tickbox | record of inspections for high risk works
checkpoint-status |  |  | checkpoint | Fire rated (Intumescent) Coatings to Structural Steel
boolean | 309391b4-5f16-527d-9c77-eb75c0a8e6cb |  | tickbox | Producer Statement Construction(PS3 - AC2334): Intumescent coatings to structural steel from approved applicator
boolean | 77e5e8e3-3cee-58de-bc64-a85957c55f37 |  | tickbox | Suppliers material schedule - products used and thicknesses applied
boolean | c37c33b0-fc33-527e-b4a0-3ca9f0823d05 |  | tickbox | Floor plan of intumescent coating locations
checkpoint-status |  |  | checkpoint | Fire Rated and Stopping Systems
boolean | c5519803-e023-5d6e-a963-f84a65f0a34a |  | tickbox | Producer Statement Construction(PS3): Fire stopping of penetrations(collars, wraps, sealants) for Plumbing, Mechanical, Ventilation and Communication services
boolean | e01b8d37-af53-5c6e-a97b-14b213b5127c |  | tickbox | Fire rated penetration Schedule: Plumbing, Mechanical, Ventilation and Communication Services
boolean | 6b87ba84-904f-56c7-b761-c246cef9e158 |  | tickbox | As built plans: penetrations
boolean | fa3f299e-2f0b-5828-8711-75dd20443bd3 |  | tickbox | Producer Statement Construction(PS3): Installed fire rated constructions; fire rated walls, partitions, floors and ceilings to show fire rating
boolean | 97fd1510-bcf2-52c1-8fa9-b72f065cee74 |  | tickbox | Fire door declaration documentation and register of door sets by the manufacturer (refer NZS4520: 2010 clause 6.4.3
checkpoint-status |  |  | checkpoint | Sprinkler systems
boolean | 35ac9cd6-fa96-5772-b7a9-0c6f8833a887 |  | tickbox | Producer Statement Construction(PS3): Automatic sprinkler system (in compliance with NZS4514:2013)
boolean | 52382401-e6af-5f9a-b941-4eb3241656d3 |  | tickbox | Accredited inspection company's automatic sprinkler system certification confirming compliance with NZS4514:2013
boolean | d8e73614-b997-5c28-9138-56d6a3c7e951 |  | tickbox | As built documentation; sprinkler block plan, equipment manufacture register
checkpoint-status |  |  | checkpoint | Manual and Automatic fire alarms
boolean | 76270458-5074-5500-96a7-5bd877c5e03a |  | tickbox | Producer Statement construction(PS3): Manual/automatic fire alarm in compliance with NZS4512:2010
boolean | 18180996-2b5f-56ad-9809-fbfee6293cc5 |  | tickbox | Accredited inspection company's fire alarm certification confirming compliance with NZS4512:2010 (new system)
boolean | 6e5cd940-4543-520e-850b-e9abcd402339 |  | tickbox | As built documentation; zone index plan, operation manual and maintenance manual
checkpoint-status |  |  | checkpoint | Riser Mains for use by fire services
boolean | bdbcfe90-d09c-5c61-8b85-7c026e5bf1ca |  | tickbox | Producer Statement Construction(PS3): fire hydrant riser confirming compliance with NZS4510:2008
boolean | 863d20be-1986-532e-8205-be29abc13064 |  | tickbox | Certificate of Compliance or Verification Report for fire hydrant riser confirming compliance with NZS4510:2008
boolean | 78df07f3-e760-5a6f-9c21-6abc9aee1caa |  | tickbox | As built documentation; fire hydrant schematic as built
checkpoint-status |  |  | checkpoint | Emergency Lighting systems
boolean | 47c7281c-3c93-54f0-b5f6-0edc29d61763 |  | tickbox | Producer Statement Construction(PS3): Emergency lighting from electrical contractor confirming compliance with NZBC F6
boolean | e8224793-8fd7-5360-b298-58b3556f5a13 |  | tickbox | Producer Statement Review(PS4): Emergency Lighting from council approved electrical engineer confirming compliance with NZBC F6
boolean | 2bf3f617-9a20-56fd-83a9-80667e6f0178 |  | tickbox | Duration test results for emergency light fitting from electrical contractor or IQP
boolean | 876239de-17c9-566d-a3cd-af84211c410e |  | tickbox | Lux test results for the emergency lighting system
boolean | ad4a545f-355f-59e9-b3e1-aa917014bb03 |  | tickbox | As built plan with model of systems installed
boolean | f542ed85-daae-5e53-906f-6e524fcd3024 |  | tickbox | Electrical work certificate
checkpoint-status |  |  | checkpoint | Fire separation that forms part of the means of escape from fire
boolean | 26668b9c-01c5-5268-9974-be754541901a |  | tickbox | As built plans confirming final location of Fire separation that forms part of the means of escape from fire
checkpoint-status |  |  | checkpoint | Smoke separation that forms part of the means of escape from fire
boolean | fb9391ce-5e58-51ee-a840-0ee006d0bd80 |  | tickbox | As built plans confirming final location of walls forming a protected path in a building, smoke resistant lift lobby, smoke stop door, smoke cell
checkpoint-status |  |  | checkpoint | interfaced fire or smoke doors on windows
boolean | 2709ca68-54f8-5d21-9f6e-69b826d1892f |  | tickbox | Producer Statement Construction(PS3): installation of magnetic door holders
boolean | 09bc05ce-aa52-5503-af8e-e7a57d71daa1 |  | tickbox | As built documentation; location of systems, the make of the systems, operation manuals and maintenance manuals
checkpoint-status |  |  | checkpoint | final exits
boolean | f925b7ca-ab4d-519a-b392-2cf00c376db8 |  | tickbox | as built plans confirming location of final exit (include info on if any doors are automatic or access controlled)
checkpoint-status |  |  | checkpoint | Signs for all systems
boolean | 4c18dc29-b40f-5e79-b870-d38ecdfd32f8 |  | tickbox | SS 1/1: Sign showing maximum storage heights
boolean | b27b0da2-e13c-560a-b1ad-12ccc0535bab |  | tickbox | SS 2/1: Sign showing how to operate a fire alarm call point
boolean | 18beffdf-7490-542d-8186-90ed819bb9c0 |  | tickbox | SS 3/1: Sign showing location of accessible automatic
boolean | 1125edf9-0050-5013-a8e0-e4605a32e7da |  | tickbox | SS 3/2: Sign showing and automatic closing fire or smoke door
boolean | abb46ab3-c8f7-5865-b0d6-dbbd580092c3 |  | tickbox | SS 3/2: Sign showing location of an emergency door release on access control doors
boolean | 0f747c56-d4ec-5ab2-9aa9-6bfd2cba1ecb |  | tickbox | SS 8/1: Sign showing location of accessible lift
boolean | 280ff417-1cd6-517e-9302-49820c4112bb |  | tickbox | Sign showing not to use the lift in event of fire
boolean | 8b447db2-8c6c-5e88-a4ee-f93570362ba4 |  | tickbox | Sign showing lift load ratings
boolean | 1bbafa76-bf15-5dbb-975b-1b173d25aa27 |  | tickbox | SS 8/3: Sign showing hazards to escalators and moving walks
checkpoint-status |  |  | checkpoint | Fire safety construction review
boolean | fb1766bf-1e31-5119-b581-3daf5a4b360b |  | tickbox | Producer Statement Review(PS4): council approved fire engineer to confirm systems conform with the relevant NZBC clauses and fire reports
checkpoint-status |  |  | checkpoint | Application for compliance schedule (AC2102)
checkpoint-status |  |  | checkpoint | Confirmation of performance standards for specified systems (AC2150)
checklist-flat | 5237afd2-217a-4219-a896-6760325801ee |  | checklist | Foundation & Basement Structure Consent |  |  |  |  | Yes | Add Foundation & Basement Structure Consent Checklist | 41e16dea-cdf1-4133-b33c-e1b25d0c5d37
checkpoint-status | 7f187b80-834b-4fb1-8fa1-f0a2759202f6 |  | checkpoint | Record of Title
holdpoint | 38f044b6-8060-4eda-b636-f2ed02d17d6f |  | signoff | Request for document
checkpoint-status | 3f782a10-884a-4dd4-89fe-2d7239a7196d |  | checkpoint | Passed final inspection
holdpoint | 956a4fc9-e5f8-4227-af75-d7d77e74794e |  | signoff | Request for document
checkpoint-status | 6b5728f2-8277-41df-98a2-f0be72895122 |  | checkpoint | Summary sheet from consent book site inspection records
holdpoint | b9692ad9-7974-44e7-b833-1cb5c848e637 |  | signoff | Request for document
checkpoint-status | 796f64b6-8659-414d-8873-2cf730512d0f |  | checkpoint | Summary sheet from consent book LBP records
holdpoint | 9537d6e9-8e1a-4cae-9291-1965fc31d834 |  | signoff | Request for document
checkpoint-status | 53302cc4-5504-429c-b44f-8e2168b256dd |  | checkpoint | Electrical: documents reviewed and attached
boolean | aa5fc7cd-741f-5158-9e6f-f810a1c39dda |  | tickbox | Electrical Compliance and Safety Certificate
boolean | 500abc8f-7445-5b96-84ce-9bfe0a0bed67 |  | tickbox | Record of inspections (For all high-risk works)
holdpoint | 0ceb2902-ba8d-42dc-9686-159747943365 |  | signoff | Request for document
checkpoint-status | 7b1b6f0e-5e0b-4b67-9e74-025af213ae7a |  | checkpoint | Surveyors Certificate: documents reviewed and attached
boolean | 165fbe43-046b-5a4b-a4ec-d942120f6a4c |  | tickbox | Siting
boolean | cd42cbb0-1640-597a-bdd7-8589a431cd88 |  | tickbox | Finished Floor Level
holdpoint | 01dd7690-8376-4b8a-a24e-8f13d256c1fb |  | signoff | Request for document
checkpoint-status | 3378cac8-3f34-4374-b5f1-2cecd8a6b2a0 |  | checkpoint | Piling (driven, bored concrete & screw piles): documents reviewed and attached
boolean | e97d13da-6a58-5e33-9b00-96f3c53943dc |  | tickbox | Producer Statement Construction (PS3) for piling
boolean | 50dc700b-a011-5786-baf9-36b836be19a0 |  | tickbox | Pile records
holdpoint | fb071f3e-7539-4f7d-b13a-e54b675d7688 |  | signoff | Request for document
checkpoint-status | 63c80d97-15c9-435c-981a-c2898851ce75 |  | checkpoint | Pre-cast Concrete: documents reviewed and attached
boolean | 939e1704-8b56-5b5e-87aa-5cb5d0f173d6 |  | tickbox | Producer Statement Design (PS1), Producer Statement Construction (PS3) & shop drawings for the precast, pre-stressed concrete beams, walls, stairs, columns and floor units
boolean | 76e56b96-62ae-511a-8429-3f3aaf5afe9b |  | tickbox | Producer Statement Construction (PS3) & shop drawings for the manufacture of precast concrete wall panels and stair units
boolean | b1bb20c6-96d4-5607-bb78-06e3c5aa36a2 |  | tickbox | Producer Statement Constrcution Review (PS4) for the precast, pre-stressed concrete beams, walls, stairs, columns and floor units
holdpoint | 85a7e01a-d2bf-4387-9a7f-8a8ff2f0f64b |  | signoff | Request for document
checkpoint-status | b59dcfe5-454e-4c22-b548-9e195345dbed |  | checkpoint | Structural Steel: documents reviewed and attached
boolean | 6040d09a-1dad-56ac-b793-dc733f28f39d |  | tickbox | Producer Statement Construction (PS3) for Corrosion Protection
boolean | 7785c63e-8fa1-5239-a79c-723e9b98927c |  | tickbox | Records of welding for all structural steel (Inspection and Test Plan approved by the structural engineer and copies of all weld inspection and test records)
boolean | 3e9136be-f04c-59b2-91e1-1d8b0a068b51 |  | tickbox | Producer Statement Construction (PS3) for the onsite welding, along with the appropriate welding certificate
holdpoint | b42b07c0-55fb-4943-825e-416cdc1401b2 |  | signoff | Request for document
checkpoint-status | ed9805e3-ce92-4c8d-84c6-07aaaea4e3fb |  | checkpoint | Waterproofing: documents reviewed and attached
boolean | 5701df29-c8fe-5994-af1d-421a0cff6307 |  | tickbox | Tanking Membrane: Producer Statement Construction (PS3) and Manufacturers Product Warranty
holdpoint | fbffad1a-0bee-48bf-8a1a-92cee9b52ef9 |  | signoff | Request for document
checkpoint-status | b161be7f-e7ad-49a7-859f-c158453e51bc |  | checkpoint | Geotechnical Construction Review: documents reviewed and attached
boolean | ec78a305-7382-5c31-a366-453ea9d45c22 |  | tickbox | Written Report and Producer Statement Construction Review (PS4) from the geotechnical engineer for site and foundation excavations & construction of the building platform, confirming site conditions are consistent with the assumptions made in the engineering design and geotechnical report
holdpoint | 545afd73-5cec-4a5d-85fa-874ed233a285 |  | signoff | Request for document
checkpoint-status | 1ffe0362-6f2a-4402-bb35-7807f4ebcd66 |  | checkpoint | Construction Review (Structural): documents reviewed and attached
boolean | 6ddcccae-1618-5a03-ae70-c059b45b766c |  | tickbox | Producer Statement Construction Review (PS4) certifying the construction of the work has been carried out in accordance the design, drawings, specifications and relevant material codes
boolean | 120608a0-e774-5e4e-9619-a0fbfb4a7edf |  | tickbox | Copies of all the structural engineers site observation records to support the PS4
boolean | 9fc6b51e-bc1c-5a19-bddc-f7f98f78074e |  | tickbox | Copies of all the structural engineers variations and contractor advice notes
holdpoint | 99fb211d-dedc-4656-9aa9-59d528d5cab9 |  | signoff | Request for document
checkpoint-status | 2031f0fa-1df5-4add-a0a2-e4e40a75c9e6 |  | checkpoint | Construction Review: documents reviewed and attached
boolean | 96aff05b-54cb-59ec-b188-80330646332a |  | tickbox | Producer Statement Construction Review (PS4) compaction of hardfill and site observation notes
boolean | b1fe26a6-fc03-594c-99c2-08a33faa3899 |  | tickbox | Producer Statement Construction Review (PS4) drain bridging and site observation notes
boolean | 9ea1e953-1947-5958-bd2f-752be1acfdf5 |  | tickbox | Producer Statement Construction Review (PS4) excavation near boundary and site observation notes
boolean | 778f28fe-1e25-575f-bc88-d20c834305d8 |  | tickbox | Producer Statement Construction Review (PS4) pile driving and site observation notes
boolean | ba57711d-2994-5c9d-a0e5-c78b35165303 |  | tickbox | Producer Statement Construction Review (PS4) raft slab and site observation notes
boolean | c5cc806a-66a9-5f90-bacb-2dabff4c460c |  | tickbox | Producer Statement Construction Review (PS4) swimming pool and site observation notes
boolean | d4dd6402-ddf9-5d7d-99e4-b608e684530e |  | tickbox | Producer Statement Construction Review (PS4) Type A or B Masonry and site observation notes
boolean | 58e67583-d460-5c0d-9f5f-5a040a66f5e7 |  | tickbox | Producer Statement Construction Review (PS4) Underpinning and site observation notes
boolean | 8f2c48cb-2ceb-5fa5-b6c1-2d62916e066c |  | tickbox | Producer Statement Construction Review (PS4) structural steel including connections and site observation notes
boolean | a1bab049-c328-5300-9b8c-cc25f55ab187 |  | tickbox | Producer Statement Construction Review (PS4) timber pole retaining wall and site observation notes
boolean | f444c1b2-6675-53fd-aef0-408aa108521c |  | tickbox | Producer Statement Construction Review (PS4) reinforced concrete foundations and site observation notes
boolean | 86a0c938-ca60-567f-a4eb-c35edb83c543 |  | tickbox | Producer Statement Construction Review (PS4) suspended concrete slab and site observation notes
boolean | 42bb51ee-6d2c-50c1-909a-dfa9c3326541 |  | tickbox | Producer Statement Construction Review (PS4) precast elements and site observation notes
holdpoint | 315b177d-be01-4432-b291-d99889f8f580 |  | signoff | Request for document
checkpoint-status | dcc91a49-19ab-4c65-b3a5-8b0592ab214c |  | checkpoint | Trusses: documents reviewed and attached
boolean | a7021f37-1b77-5c2d-b8d1-7c87f3974860 |  | tickbox | Producer Statement Design (PS1) and layout plan for the timber roof trusses
holdpoint | a8709d57-d0f1-4d56-ab7b-ccc274d97e1b |  | signoff | Request for document
checkpoint-status | 2fec6911-0472-429e-a934-f34476c21d02 |  | checkpoint | Fire Rated (intumescent) Coatings to Structural Steel: documents reviewed and attached
boolean | 46742e4e-b9b7-5b64-a305-fd248567680a |  | tickbox | Producer Statement Construction (PS3 - use AC2334) for Fire Rated (intumescent) Coatings to Structural Steel from an approved applicator.
boolean | 746274ad-816e-57f2-b07a-6090342ec369 |  | tickbox | Copy of the suppliers material schedule listing products used and thicknesses applied
boolean | 2be58100-fab8-585e-8d69-55e4146b304c |  | tickbox | Floor plan identifying location of the intumescent coatings
holdpoint | 45f896d5-5b91-4214-b448-782f721eed31 |  | signoff | Request for document
checkpoint-status | 4c840f10-07ec-4d8e-8291-1a883acfc7b0 |  | checkpoint | Fire rated and stopping systems: documents reviewed and attached
boolean | afd3e395-4ed7-56bd-a1bf-620df404e749 |  | tickbox | Producer Statement Construction (PS3) for fire stopping of penetrations (collars, wraps, sealants): Plumbing, Electrical, Mechanical ventilation & Communication Services
boolean | a1c6ec5b-486a-5b1b-bd8e-3c7445673a08 |  | tickbox | Copy of the fire rated penetration schedule: Plumbing, Electrical, Mechanical ventilation & Communication Services
boolean | 878270e8-b4c2-536e-b8e6-6c14b7013ef9 |  | tickbox | As Built plans showing penetrations
boolean | cd1bb32d-cf53-5e22-8e44-2685f62609fc |  | tickbox | Producer Statement Construction (PS3) for installed fire rated constructions (i.e. fire rated walls, partitions, floors, ceilings) - to show Fire Rating
holdpoint | d5e64062-cd08-4bea-abeb-748b466d8f5b |  | signoff | Request for document
checkpoint-status | 6ccf3085-cafb-4a16-aeaf-9765dc7f8091 |  | checkpoint | Fire Safety Construction Review: documents reviewed and attached
boolean | 927d9bac-f87e-553e-916a-081abd751ec6 |  | tickbox | Producer Statement Construction Review (PS4) from a council approved fire engineer for the fire safety systems confirming compliance with the relevant NZBC clauses and the approved fire report
holdpoint | ecbfffa2-4114-47e5-8ace-eba0e52d7a88 |  | signoff | Request for document
checkpoint-status | f788c245-1e13-4cfd-a1ff-c24db2f3d3a1 |  | checkpoint | Other: documents reviewed and attached
boolean | bbb8e1ed-c036-5607-868b-76bdd03ba52d |  | tickbox | Copies of the ready mixed concrete documentation confirming the mPa strength of the concrete supplied
boolean | e8f0a6ca-a013-51e0-b0bd-590aceea5390 |  | tickbox | Mill certificates
boolean | 1a2d0745-5f9b-553c-bbc8-2e5c52e8c45f |  | tickbox | Producer Statement Construction (PS3) for the sub-soil drains
holdpoint | 78d9d1e9-402b-4351-aa44-d37a86217e03 |  | signoff | Request for document
checkpoint-status | f136a8b9-483f-4952-aa39-6e649c032626 |  | checkpoint | Any additional documents required
holdpoint | e236d1ad-6619-44de-8103-3d798845da62 |  | signoff | Request for document
checkpoint-status | c727bfea-44b9-4ab4-8bac-886be3fb7eaf |  | checkpoint | CCC lodgement form reviewed and attached
holdpoint | d470f965-255a-4bff-84e2-61dbe9dca362 |  | signoff | Request for document
checkpoint-status | 46f9c64c-b504-4f85-9d5d-e8901555fba4 |  | checkpoint | Specified Systems form reviewed and attached
holdpoint | 232dcf74-8c0c-4187-a957-7be75ade94a9 |  | signoff | Request for document
checklist-flat |  |  | checklist | F - R - Sheet Piling |  |  |  |  | Yes | F - R - Sheet Piling | 424c16fa-a678-4edf-99ea-118612b460bc
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Sheet pile installation completed and acceptable
checklist-flat |  |  | checklist | Code of Compliance (CCC) - |  |  |  |  | Yes | Add Council CCC Upload Checklist | 4339919b-6fcd-485c-8ce2-254c0eeaa30a
checkpoint-status |  |  | checkpoint | Final CCC (approved & attached)
checklist-flat |  |  | checklist | C - R - Asbestos Removal |  |  |  |  | Yes | C - R - Asbestos Removal | 461253c6-f97f-407a-b9be-2329faeacb88
checkpoint-status |  |  | checkpoint | Demolition Survey reviewed and attached
checkpoint-status |  |  | checkpoint | Asbestos Removal Control Plan (ARCP) reviewed and attached
checkpoint-status |  |  | checkpoint | Background Air Monitoring Results (BGAM) reviewed and attached
checkpoint-status |  |  | checkpoint | Clearance Certificates reviewed and attached
checkpoint-status |  |  | checkpoint | All asbestos removed and approval given to progress with work
checklist-sectioned | 5cdc2270-9f85-4be5-b77f-c5fdf2b13235 |  | checklist | Constructor Audit - Structural Superstructure - |  |  |  |  | Yes | Add 01 Constructor Audit (Auckland Council Assessment) - Structural Superstructure Checklist (V4) | 46a865f4-b4a0-4576-807b-6ff77812d4a4
checkpoint-group | b13bea60-d883-40ec-869f-4ebd978f9421 |  | section | Superstructure Assessment - Details / Drawings / Documentation
checkpoint-status | fdb29602-81f9-4440-ad50-9a9e1d7804c8 |  | checkpoint | Clearly identify area/element covered in this assessment (Pass once detailed below)
text | 1d15eb54-cc31-49de-a834-a0b34903f909 |  | textbox | Date of assessment (format - dd/mm/yyyy)
text | 0d5f9bcd-d449-42c6-ba7d-36d5f20f95e2 |  | textbox | Detailed breakdown of element(s) including location and grid references relating to this audit
label | a7d0f8c8-e001-4a53-8ee4-35b11f3b30e2 |  | note | Add descripton for what work was carried out on the element. Inspector cannot tell if the beam was erected, coated, welded etc
boolean | e5bd75b6-ba61-40b2-bd85-82573c3b9fc3 |  | tickbox | Attach marked up plan detailing element(s), location and grid references relating to this assessment
checkpoint-status | b114f5d9-93e2-4eea-a787-9ed3328d6648 |  | checkpoint | Description of work being undertaken (PASS once all detailed below are entered)
button | 32765559-2b61-4a4b-acda-383f53aa3c46 |  | button | Does the work being undertaken comply with the issued building consent or approved minor variations or amendments | Yes, No
label | 8e0f195b-ffaf-41e3-9acc-e54bc51fa52b |  | note | If "NO" what are the discrepancies? clearly detail below
text | 11212934-4b67-4568-9579-07ff1fc7ed53 |  | textbox | Latest building consent number, stage and amendments (if applicable)
text | 0c164971-c09c-414d-81ac-436935bac688 |  | textbox | Relevant drawings & revision numbers
boolean | 15b993e5-3efe-4063-95f2-83879222b882 |  | tickbox | Attach all relevant drawings with revision numbers clearly detailed
button | 122a30e0-0bbe-472b-86ba-375abade838f |  | button | Construction drawing revisions match consented drawing revisions | Yes, No
label | 049711f2-62d2-4d7a-8601-41b554ebe185 |  | note | If "NO" what are the discrepancies? (comment below and attach evidence of discrepancies)
button | 8234ff17-121d-4007-a8e9-3aba8f9f3fcb |  | button | Does the installation of this building element compromise any previously assessed/inspected building elements? | Yes, No
label | a4141cf2-6795-450c-8ecd-7b702abd0400 |  | note | Select "NO" if this has been considered & does not compromise any previously assessed/inspected building elements (attach any relevant supporting evidence below)
label | 770d7156-8af4-4dcd-9ebd-df41853f0f53 |  | note | If "YES" explain below (what is compromised, how it it is compromised & how this will be mitigated/managed)
checkpoint-status | 2d321b08-b40c-405f-a7ad-72a7ecdab446 |  | checkpoint | Select "PASS" and progress if all above items have been considered and sufficient supporting documentation attached
checkpoint-group | baf0e4cb-f016-4d30-be3e-c132e02f0956 |  | section | Structural Superstructure Assessment - Council / Consultant Summary
checkpoint-status | f4ba16d2-6f6c-45eb-bf8c-f465d5b4856a |  | checkpoint | Structural superstructure assessment details (Pass once inputted below)
text | 51feebe6-1f3a-4efd-995a-06895dec848c |  | textbox | Describe progress of construction since last audit
button | f5d9061a-a15b-41cf-929a-b69b62eb7251 |  | button | NEW BC AMENDMENTS - has there been any requirement for a new amendment since the last council audit/inspection | Yes, No
text | b5cd2cbe-2306-468a-a3cf-83372f34261d |  | textbox | If yes - detail amendment here including status
button | 533ec2fa-de3d-471c-aa48-817ce88c7b4c |  | button | APPROVED BC AMENDMENTS - have any previously open AMENDMENTS been responded to by Auckland Council since the last audit/inspection | Yes, No, N/A
text | 47c8c76d-42b0-41e5-af3c-f8f18ebd579f |  | textbox | If yes - detail here and ensure latest Building Consent (including amendment) is uploaded into Conqa
button | a37babf9-02e1-4f48-8483-6faeb152ccab |  | button | WIP AMENDMENTS - are there any AMENDMENTS which will maintain a "Work in Progress" status for this audit | Yes, No, N/A
text | 6e7ebbd5-b696-43b0-b228-92a265563165 |  | textbox | If yes - detail amendment here and provide an update on the status
button | d9a509fb-0333-4176-bdb5-939b2603993d |  | button | NEW MINOR VARIATIONS - has there been any requirement for a new minor variation since the last council audit/inspection | Yes, No
text | 11147a05-6b45-4196-87bd-2e3220a127b2 |  | textbox | If yes - detail here including status
button | 63dcbb3f-1b77-429b-b608-d4f7ccd5e33d |  | button | APPROVED MINOR VARIATIONS - have any previously open minor variations been responded to by Auckland Council since the last audit/inspection | Yes, No, N/A
text | 3efd929d-6e4e-461d-8548-e4251b57be80 |  | textbox | If yes - detail here and ensure latest status (including approval) is uploaded into Conqa
button | 3848ecf4-cede-44a7-93a5-39ecf184cd26 |  | button | WIP MINOR VARIATIONS - are there any minor variations which will maintain a "Work in Progress" status for this audit | Yes, No, N/A
text | 60143860-e136-4d57-b86e-c20849af86e8 |  | textbox | If yes - detail variation here and provide an update on the status
checkpoint-status | 9f2155dd-3c33-4438-9835-0205d6d6badc |  | checkpoint | PREVIOUS COUNCIL AUDITS/ INSPECTIONS - Any previous council audit / inspection issues (fails / anomalies) relating to this BC have been addressed & closed out
label | 3f7bc8bd-ce72-403e-b5cb-ae5dcbaa929c |  | note | "Pass" if there are no outstanding issues (fails / anomalies) from previous council audits/inspections relating to this Building Consent
label | 77cf85bd-93e8-4b48-b7f9-e96d8060979e |  | note | "Fail" if outstanding issues (fails / anomalies) remain un actioned/closed from previous inspections / audits and provide context
label | d8ac2897-19ea-47a2-b62f-90092fcbd92e |  | note | Prior to selecting "Pass" and confirming there are no outstanding fails / anomalies, ensure these have been appropriately closed out and the appropriate evidence attached HERE & in the appropriate audit/inspection
checkpoint-status | 357d6535-0b8e-484d-a1a4-a23a3e1b60ad |  | checkpoint | Engineer / Consultant Inspection Summary & Observation Closeout
button | c87f05cf-3e31-472c-a6a6-563a666da957 |  | button | Are the relevant engineers / consultants attending site & achieving the correct level of monitoring | Yes, No, N/A
text | affd552f-48aa-4108-9279-aab40a566cbb |  | textbox | List all engineers / consultants who have been to site since the last Council audit/inspection & describe all elements/work checked by the engineer
button | c6c52ae7-e9d6-41ad-b145-5e09568d767f |  | button | Viewed all engineers reports since last audit undertaken & have identified what elements and areas have been checked by the engineer | Yes, No
label | b9cc8a08-c313-4a29-a1ca-1efd15f3be02 |  | note | "Pass" ABOVE checkpoint if there are no outstanding engineers remedials/observations
label | 65ad8797-b5b3-40e5-9c66-4e640af08e49 |  | note | "Fail" ABOVE checkpoint if outstanding engineers remedials/observations remain unresolved and provide context
button | d8aac606-7c67-41dd-8728-44476dd15263 |  | button | NEW OBSERVATIONS/REMEDIALS - has there been any new engineer / consultant remedials/observations since the last council audit/inspection | Yes, No
text | cf264bae-a822-4862-b8d6-668fbeac3ddf |  | textbox | If yes - detail here including status
button | 3110f445-ee17-4a18-bc6a-ab408156c4de |  | button | APPROVED OBSERVATIONS/REMEDIALS - have any previously open remedial/observations been approved by the appropriate engineer / consultant since the last audit/inspection | Yes, No, N/A
text | d74bfb06-5e48-45e2-ab9b-23246d5c2c0c |  | textbox | If yes - detail here and ensure latest status (including approval) is uploaded into Conqa
button | 27077dff-248a-4f07-8e04-c5edf69771e8 |  | button | WIP OBSERVATIONS/REMEDIALS - are there any remedials/observations which will maintain a "Work in Progress" status for this audit | Yes, No, N/A
text | d7a2273f-2208-440e-86b4-3497786e0aeb |  | textbox | If yes - detail here and provide an update on the status
boolean | 8097a03b-bf6f-48df-8fe2-58f91d1b3ad8 |  | tickbox | All relevant consultant inspections completed since the last Auckland Council audit/inspection attached HERE including any corrective action undertaken with sufficient evidence of close out.
checkpoint-status | da3865b3-458a-4402-94ee-830d551f2f94 |  | checkpoint | ANY OTHER THIRD PARTY CONSULTANTS - Described work / elements checked by others (third party)
text | 08f62631-5e6e-4f8b-ab29-eaea77f846a7 |  | textbox | If applicable, describe any action/remedial items still to be signed off by others
boolean | 84e9e7d9-895c-4135-b6f6-140fc0809752 |  | tickbox | Any relevant third party consultant inspections completed since the last Auckland Council audit/inspection attached HERE including any corrective action undertaken with sufficient evidence of close out.
label | 18d7de02-d06b-4d6a-93e4-d1ac04ce7ce1 |  | note | If required use this checkpoint to detail and other action/remedial items have been signed off or select "N/A" if there has been no requirement for a third party
checkpoint-group | 0781d6e0-3277-4589-b906-745525c87184 |  | section | Main Contractors & Trades QC/QA and supporting documentation
checkpoint-status | 90ff8cba-cfa4-4347-98c7-40b41f463b66 |  | checkpoint | General Site Photos / As Builts
label | 011276ed-142c-40c3-9ab6-f4b69149e010 |  | note | Attach a minimum of 10 site photos giving an overview of the on site progress relating to this Building Consent since the last audit / inspection
label | 0fca93a7-f81f-4153-9558-c7e73247adee |  | note | Attach any relevant progressive as builts / mark ups
checkpoint-status | abfb55aa-18ab-4fc4-9a1d-6fb7b91670f4 |  | checkpoint | FORMWORK - trade / element applicable to this audit
label | 6ba1abeb-aaa8-4a7f-8878-cccd762d8a6d |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | 73f7bec3-e074-46e7-804f-589d8ab4bf6f |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | 286afa27-7567-4444-b85d-f56f8d4e6100 |  | textbox | Overview of progress relating to this trade/element (Formwork) since last audit
label | ee3fab46-f5aa-4cbb-8896-d564e7907433 |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, setout, heights, stability/bracing, DPM / terminations
boolean | 0fac06a4-ab41-4fcc-83f9-d6ece508b300 |  | tickbox | Formwork - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status | 27de4592-2419-454d-a90a-d2945d67f8eb |  | checkpoint | REINFORCING - trade / element applicable to this audit
label | 0c9cd040-ab41-4c37-823a-a535757aaf7a |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | b5b7e31b-4c47-490e-a080-432026d76a07 |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | adb621c5-3e7f-4038-8cad-d8361197882b |  | textbox | Overview of progress relating to this trade/element (Reinforcing) since last audit
label | fdba52a0-2d12-4f26-abee-9474ef44f5f9 |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, detail sheets, reo mill certs, size, grade, laps, bends, cover, starters (size & location), cast in items
label | 50d133a3-d7f2-4dcc-b729-54f0bca64ded |  | note | COMPLIANCE CONSIDERATIONS - PS3, PS4, all reinforcing steel bars/ mesh mill certs or steel grade confirmation from supplier, all reinforcing steel fabricator detail sheets for cages/ bent rebar- must verify rebar sourced from accredited supplier
boolean | b6226eed-9cfd-4d5a-b0ba-72f5018efcde |  | tickbox | Reinforcing - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status | ad4f6bd1-c88d-4134-b6c1-ad8b4f657b5e |  | checkpoint | CONCRETE PLACEMENT - trade / element applicable to this audit
label | 9f79b09b-a14e-41a7-a42c-0d5feaebd90e |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | a1081352-a8b7-4979-9838-a5cafc8fc20a |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | da53f8a9-f77f-4e4f-bef9-f3a33dcce56c |  | textbox | Overview of progress relating to this trade/element (Concrete Placement) since last audit
label | 7b1885c1-bd00-40e6-a06e-40de4d927be4 |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, approval, mPa, slump tests, vibration, finish, curing, concrete batch certs confirming mPa and any additive
label | 2bd2de13-1c29-464e-be00-923a5c0cecbb |  | note | COMPLIANCE CONSIDERATIONS - PS3, PS4, concrete cylinder tests for previous month deliveries (7, 14 and/or 28 days as required)
boolean | eeeccbdb-b8a0-4993-a086-8811013cccfe |  | tickbox | Concrete Placement - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status | f99f3b6e-2650-4ceb-ad4f-8f2ea470c51a |  | checkpoint | BLOCKWORK INC REINFORCING - trade / element applicable to this audit
label | c653f758-0976-4c53-a293-df19c92bb71a |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | 0e2c435a-6511-4d93-a3c1-a574eecab36b |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | 0bd03265-041b-406b-ad48-ab99bf28c7d5 |  | textbox | Overview of progress relating to this trade/element (Blockwork Inc Reinforcing) since last audit
label | b91c8982-812c-4488-838e-e0d624c0b2e8 |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, compliance method, masonry grade, size, setout, level and plumb, heights, wash outs, stretcher or stack bond, Mortar joint sizes (7-13mm), tooled to match proposed finish, bond beams, control joints, Approval, mPa, slump tests, vibration, finish, sealer, concrete batch certs confirming mPa and any additive
label | fc35e658-5f7d-446b-89f3-7390b6376135 |  | note | COMPLIANCE CONSIDERATIONS - PS3, PS4, all reinforcing steel bars/ mesh mill certs or steel grade confirmation from supplier, all reinforcing steel fabricator detail sheets for cages/ bent rebar- must verify rebar sourced from approved supplier, concrete cylinder tests for previous month deliveries (7, 14 and/or 28 days as required)
boolean | 9b60ce17-9c14-4731-85be-6f0b86c1203a |  | tickbox | Blockwork Inc Reinforcing - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status | ac11435e-0b86-4973-be1d-814c85a0a38b |  | checkpoint | PRECAST MANUFACTURE - trade / element applicable to this audit
label | 9d73edab-8294-4300-a2f5-959ebd33768f |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | fccf2bf3-5854-40cc-bfeb-6a7d87cf9aa2 |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | 09338bb9-ee99-498f-a2ac-902f4ec791d4 |  | textbox | Overview of progress relating to this trade/element (Precast Manufacture) since last audit
label | 3144008e-bd59-4d78-b7b9-b0a8d85dc044 |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, mPa, slump tests, vibration, finish, curing, concrete batch certs confirming mPa and any additive, detail sheets, reo mill certs, size, grade, laps, bends, cover, inserts / cast in items, starters (size & location)
label | 68d77fdc-168e-4822-a089-c50366dfb918 |  | note | COMPLIANCE CONSIDERATIONS - PS1, concrete test results (7, 14 and/or 28 days as required), mill certs & steel grade confirmation from accredited supplier, PS3, PS4
boolean | 377368e0-be2a-40a7-89bd-e2d810557ccc |  | tickbox | Precast Manufacture - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status | 4ae69590-e7cd-4ecb-9f7b-71dc160ff7fa |  | checkpoint | PRECAST INSTALLATION - trade / element applicable to this audit
label | 8255afb7-4bee-4cb8-8d44-d7268d838b0f |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | 64f131bf-1908-4586-94ba-8f54d0eb1417 |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | 411a845a-58d5-4603-8ef1-9f421314ccd8 |  | textbox | Overview of progress relating to this trade/element (Precast Installation) since last audit
label | 621fa5e4-4300-4f38-b7be-344839460a41 |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, setout, precast starters (size & length), seating, bracing/propping, alignment/plumb/level, joints/connections
boolean | 671c7d21-6e80-4aa0-8e29-6d286a810edd |  | tickbox | Precast Installation - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status | a9cacdac-7d9d-4823-b8b0-e114f9fbee0f |  | checkpoint | Structural Grouting - trade / element applicable to this audit
label | 750c1595-7e32-4d35-8935-cfe92982a7a8 |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | 0a0259d6-09f4-4668-b4ea-02ad7dea8967 |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | ada2c96e-6a79-4f4a-b61a-c73ececf5a89 |  | textbox | Overview of progress relating to this trade/element (Structural Grouting) since last audit
label | 0218b7dc-213e-492c-a4e2-2c956188945b |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, approval, product alignment with specification, mPa, slump tests, installation
label | 2f3663e0-3251-43a9-997e-c836fc0b3f07 |  | note | COMPLIANCE CONSIDERATIONS - manufacturer's warranty, workmanship warranty, PS3
boolean | 0787cec4-df93-4012-8f81-2442ffd1188d |  | tickbox | Structural Grouting - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status | 93f832d5-3c42-4639-b5d9-ee7be4b3bbc8 |  | checkpoint | Structural Steel - trade / element applicable to this audit
label | f996f7c6-3726-40a9-8573-330419263dce |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | 1d90ffde-f4e9-4b4b-a42c-6e7e895d5d10 |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | 8c3039b2-0b70-41f8-9aa7-7d7f7115e21f |  | textbox | Overview of progress relating to this trade/element (Structural Steel) since last audit
label | 675700a4-16a4-421b-afc9-d9f8059352ac |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, mill certs, fabrication and welding(NDT report, Coatings report) / ONSITE- Delivery dockets, Hold down/Structural connections (setout, size & type), Erection - Location & orientation - Level & Plumb, propped/braced, all connections adequate and to spec & onsite welds, bolt tightening logs
label | 4529c9fa-a966-45fb-b26b-40e3d3dd31a0 |  | note | COMPLIANCE CONSIDERATIONS - PS3, PS4, all steel has mill certs or steel grade confirmation from supplier, all reinforcing steel fabricator detail sheets for cages/ bent rebar- must verify rebar sourced from accredited supplier
boolean | 55155dba-2fa8-4ee5-8bc1-41b71986c9a0 |  | tickbox | Structural Steel - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status | e883e432-f085-4532-88af-113000fa06a2 |  | checkpoint | Intumescent Painting - trade / element applicable to this audit
label | fb1ddf2e-5218-4ce3-80a6-b88ed697eba6 |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | dd4f1044-bd79-4f32-8cfd-a4cd03a29808 |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | fd50fdd4-a808-492b-8830-1fb823269448 |  | textbox | Overview of progress relating to this trade/element (Intumescent Painting) since last audit
label | a5a215db-4271-42d7-876b-ac8da4531feb |  | note | ON SITE KEY CONSIDERATIONS -Design & Specifications, product alignment with specification (incl any testing/certification(s)), substrate & surface conditions, Ambient conditions (atmospheric), Micrometer readings - Coatings report
label | 064b8cb8-28e3-4307-8072-08fc4968249f |  | note | COMPLIANCE CONSIDERATIONS - manufacturer's warranty, workmanship warranty, PS3
boolean | 9bdd6be3-2ed2-4fe5-896e-53e72bd7bbe6 |  | tickbox | Intumescent Painting - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status | 9417c51d-78b6-4a4c-a532-f92a83316709 |  | checkpoint | Tanking/waterproofing - trade / element applicable to this audit
label | b49af962-d2e3-4600-a25a-962ea02f1110 |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | bde40489-a086-46da-848c-c7dc57e106d6 |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | 8c90f1bf-92d1-4695-a7c7-edaa0a47e10c |  | textbox | Overview of progress relating to this trade/element (Tanking/waterproofing) since last audit
label | 4cddea81-fc57-493a-b765-ecedbcfb3893 |  | note | ON SITE KEY CONSIDERATIONS -Design & specifications, Trade details & license, materials/system, manufacturer's specifications, substrate, drainage, installation, joints / control joints, terminations, protection, backfill methodology
label | 50cf5927-5a1c-4682-842d-2c602e13e5d1 |  | note | COMPLIANCE CONSIDERATIONS - manufacturer's warranty, workmanship warranty, PS3, PS4
boolean | d9a423f7-1eb8-4c13-987c-646a12e0c1a7 |  | tickbox | Tanking/waterproofing - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status | a0d91f7a-46e4-4fe2-b731-ed7de42dcc7e |  | checkpoint | Any other trade / element - trade / element applicable to this audit
label | ea0dde6c-2174-42e8-b6f0-7890653f0262 |  | note | "PASS" and detail below if any other trade/element is applicable to this audit. Complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | f64aebe5-2893-47b8-b46e-3fc487f3d0d3 |  | note | "N/A" if no other trade/element is applicable to this audit, comment below if required
text | b32f2383-4e79-40d5-a699-c6ba2ada655d |  | textbox | Overview of progress relating to this trade/element since last audit
boolean | 1b2dd3cb-777f-4aa4-8946-1ed3f2973ce9 |  | tickbox | Any other trade / element - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status | 01885574-81a2-44df-9769-38a8b06a4fc8 |  | checkpoint | Select "PASS" and notify Auckland Council if all above items have been considered and sufficient supporting documentation attached
text | 629f2f58-86ab-4498-bbc7-56e108331ebf |  | textbox | Date this Audit report was sent to Auckland Council
text | 9172d540-f32a-44fd-b49c-742e353c48ab |  | textbox | Inspector(s) from Auckland Council who this was sent to (including email address)
checkpoint-group | 4b64b3be-bddd-47fa-b5b7-2ae905f1e682 |  | section | Close out of Audit
checkpoint-status | 1a5a4279-7440-4245-865a-7a45069360f3 |  | checkpoint | Close out of Audit - Pass once Council Audit is completed and attached with any corrective actions detailed and closed out below
text | 7c585405-8a98-446e-a423-de54a23e31b7 |  | textbox | Date Auckland Council Inspector sent receipt / audit response
boolean | 1cfd6ab8-3dd8-4308-add5-579a0bbb8f68 |  | tickbox | Council Audit completed and attached
text | fc37fdd9-f69d-4dd5-ba10-c145fa83f652 |  | textbox | As detailed in this Council Audit or discussed - next Audit will occur on
checkpoint-status | 8b9040cd-29c7-456d-8f55-106195bde5a8 |  | checkpoint | Any Relevant Observation Closeout evidence attached here if applicable (Pass once completed)
text | e08cfeb3-25ac-4378-be22-2c5a63b7ea14 |  | textbox | Corrective actions required before next audit
label | 4f8d1615-2a78-4c28-aad8-0b2a575ae382 |  | note | These should include a summary list of close outs still to be addressed from any of the above line items and comments made in the council audit or any outstanding from previous audits/inspections relating to this building consent
checklist-flat |  |  | checklist | FC - R - Anchor Points - Intermediate, Corner and End Plate Installation |  |  |  |  | Yes | FC - R - Anchor Points - Intermediate, Corner and End Plate Installation | 4fa86ab3-fc78-49b8-83eb-d5db70bb96c1
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Intermediate, Corner and End Plate installation completed and acceptable
checklist-flat |  |  | checklist | FC - R - Air conditioning |  |  |  |  | Yes | FC - R - Air conditioning | 52cd3272-77be-4a0f-bd7f-6baf62c7932e
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Exterior Tiling works completed and acceptable
checklist-flat |  |  | checklist | C - R - Pipe Laying - Stormwater |  |  |  |  | Yes | C - R - Pipe Laying - Stormwater | 56bff849-c201-4169-be82-3344f0623264
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Stormwater pipe laying completed as per the specifications
checklist-flat |  |  | checklist | F - R - Waterproofing |  |  |  |  | Yes | F - R - Waterproofing | 5b043d3e-cdf5-4c41-8f20-484c30e84daa
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All waterproofing works completed as per the specifications
checklist-flat |  |  | checklist | CST - R - Structural Consent |  |  |  |  | Yes | CST - R - Structural Consent | 5b17fa2c-00cf-49a1-80cc-015705c13f52
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Pre-cast concrete
boolean | 57559ddb-0f65-5cd3-8f4b-58e9ca2c76d6 |  | tickbox | Producer Statement Design(PS1): Prestressed beams, walls, stairs, columns and floor units
boolean | cafcdc76-ac84-5572-a822-c58b6c16bbb1 |  | tickbox | Producer Statement Construction(PS3): Prestressed beams, walls, stairs, columns and floor units
boolean | fa09cfe2-80e7-5021-ae58-e15a286e1e64 |  | tickbox | Producer Statement Review(PS4): Prestressed beams, walls, stairs, columns and floor units
checkpoint-status |  |  | checkpoint | Structural Steel
boolean | 0ead51f8-cd1f-5394-9bdc-2b53beb5f63b |  | tickbox | Producer Statement Construction(PS3): Corrosion Protection
boolean | 50bd65d9-9092-5ef4-86ff-2b0f77c918bf |  | tickbox | ITPs approved by structural engineer
boolean | 899b5c98-308d-5f3f-813b-31198d498609 |  | tickbox | weld inspection and test records
checkpoint-status |  |  | checkpoint | Fire rated (Intumescent) Coatings to Structural Steel
boolean | 17f3bc6d-3ee0-50d6-b911-eeb940b50c6a |  | tickbox | Producer Statement Construction(PS3 - AC2334): Intumescent coatings to structural steel from approved applicator
boolean | aeaaa583-c796-5930-a8f7-119e790716ca |  | tickbox | Suppliers material schedule - products used and thicknesses applied
boolean | 0358701b-fad8-5420-8d41-e5e177b93c53 |  | tickbox | Floor plan of intumescent coating locations
checkpoint-status |  |  | checkpoint | Trusses
boolean | 432aa4e1-336b-5088-9355-4dd2e5acbbf7 |  | tickbox | Producer Statement Design(PS1): Layout Plan for timber roof trusses
boolean | c6178159-8ce1-579a-b3e7-1ebdeb62f150 |  | tickbox | Producer Statement Construction(PS3): for timber roof trusses
checkpoint-status |  |  | checkpoint | Construction Review (Structural)
boolean | d8a651c4-c384-5d3c-a33b-c862ab60d779 |  | tickbox | Producer Statement Construction Review(PS4): Certification of work in accordance with design, drawings, specifications and material codes
boolean | 8ccb7aa8-9741-5a97-9db5-a3bfd3f552bb |  | tickbox | Producer Statement Construction Review(PS4): excavation near boundary and site observation notes
boolean | 01a76d42-13c0-5010-9d78-91fb2451c293 |  | tickbox | Producer Statement Construction Review(PS4): Raft slab and site observation notes
boolean | ca77f557-03bc-57f6-8ecd-14de62e9f191 |  | tickbox | Producer Statement Construction Review(PS4): Swimming pool and site observation notes
boolean | 59bbe433-d402-5dce-94ec-01c3eb4d9154 |  | tickbox | Producer Statement Construction Review(PS4): Type A or B masonry and site observation notes
boolean | eb0ebf92-3574-5003-a079-d8f8713c931a |  | tickbox | Producer Statement Construction Review(PS4): Underpinning and site observation notes
boolean | 1f77c525-8fe3-557a-bdc7-9994cc001eca |  | tickbox | Producer Statement Construction Review(PS4): Structural steel including connections and site observation notes
boolean | d39d8a64-5804-519f-9a4b-c086637cf546 |  | tickbox | Producer Statement Construction Review(PS4): Timber pole retaining wall and site observation notes
boolean | 8e9f48c1-59df-55de-8053-5e23d0bc228a |  | tickbox | Producer Statement Construction Review(PS4): reinforced concrete foundations and site observation notes
boolean | b7b5aeba-58c7-55dc-8731-9f87cba5654f |  | tickbox | Producer Statement Construction Review(PS4): Suspended concrete slab and site observation notes
boolean | e83cae82-2b6b-5d11-9072-f1925c50c996 |  | tickbox | Producer Statement Construction Review(PS4): Precast elements and site observation notes
boolean | 6fabb33f-dd74-5919-ac21-ed7f0e7036a1 |  | tickbox | Structural engineer's variations and contractor advice notes
checkpoint-status |  |  | checkpoint | Surveyor certificate for finished floor levels
checklist-flat |  |  | checklist | FC - R - Brick Works |  |  |  |  | Yes | FC - R - Brick Works | 5c0a0cff-7d82-4a27-8188-ced519016730
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Brick works completed and acceptable
checklist-sectioned |  |  | checklist | FC - R - Scaffold Drop Checklist |  |  |  |  | Yes | FC - R - Scaffold Drop Checklist | 5d053633-ee4f-4922-8d81-5d74b275e1aa
checkpoint-group |  |  | section | Brickwork
checkpoint-status |  |  | checkpoint | Weep holes installed.
checkpoint-status |  |  | checkpoint | Weep holes clean of mortar.
checkpoint-status |  |  | checkpoint | Vent holes installed.
checkpoint-status |  |  | checkpoint | Vent holes clear of mortar.
checkpoint-status |  |  | checkpoint | Mortar finish acceptable – no holes.
checkpoint-status |  |  | checkpoint | Mortar acceptable around vents.
checkpoint-status |  |  | checkpoint | Clean Lintel Cavity.
checkpoint-status |  |  | checkpoint | Vent holes full brick.
checkpoint-status |  |  | checkpoint | No damage to bricks.
checkpoint-status |  |  | checkpoint | Seals completed Nib / Brick. Soffit / Brick.
checkpoint-group |  |  | section | Sto
checkpoint-status |  |  | checkpoint | Seals completed Nib / Brick.
checkpoint-status |  |  | checkpoint | Sto finish good ( not damaged.)
checkpoint-status |  |  | checkpoint | Paint standard acceptable
checkpoint-status |  |  | checkpoint | Soffits complete
checkpoint-group |  |  | section | Windows
checkpoint-status |  |  | checkpoint | Windows are clean
checkpoint-status |  |  | checkpoint | Railside's sealed (good seal)
checkpoint-status |  |  | checkpoint | Transom rubber caps installed (not loose)
checkpoint-group |  |  | section | Misc
checkpoint-status |  |  | checkpoint | Downpipes installed
checkpoint-status |  |  | checkpoint | Roof capped & fascia installed
holdpoint |  |  | signoff | Raise remedial / Request Sign Off
checklist-flat |  |  | checklist | CST - R - Civil Consent |  |  |  |  | Yes | CST - R - Civil Consent | 61c0ec02-9b48-43e8-9f8f-b9367f80b7ac
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Drainage
boolean | 64aefad7-3839-5a3c-be2b-2c5a82dee308 |  | tickbox | Producer Statement Construction(PS3): sub-soil drains
boolean | 39c82f84-50ba-50d2-841b-6a5030d98d21 |  | tickbox | Producer Statement Construction(PS3): drainage
boolean | 499c24d3-d73a-5aaa-afb4-369cbfc3712f |  | tickbox | Drainage as built plan
boolean | 6b0d4bfc-844c-5938-934b-54ea68d92ce1 |  | tickbox | Producer Statement Construction(PS3): Stormwater Management
boolean | 91e58735-66a5-5e23-9f98-d8528bb6607a |  | tickbox | Producer Statement Review(PS4): Stormwater management approved by council Engineer
boolean | b56e99c3-1442-5a07-aa09-54302ca573e7 |  | tickbox | Operations and Maintenance manual for stormwater management systems
boolean | a0b03923-33e2-50fd-b002-9ba4a9f44214 |  | tickbox | Backflow test Certificate | Yes,No,N/A
checkpoint-status |  |  | checkpoint | Drainage Pump Systems
boolean | 88f93c9e-1a48-5385-ac37-7240fe3da335 |  | tickbox | Producer Statement Construction(PS3): installation of drainage pump system
boolean | 4f59b2c8-77a8-5665-a98b-61a8482a6bda |  | tickbox | Manufacturer's warranty for pump system
boolean | 85bf517e-04f4-5267-92ab-b8fa95442858 |  | tickbox | Maintenance agreement for pump system
checkpoint-status |  |  | checkpoint | On-Site wastewater Systems
boolean | 2161b41f-475d-5751-9f64-d20ccdb0a94b |  | tickbox | Producer Statement Construction(PS3): wastewater treatment and disposal system
boolean | 73427198-77ad-57cd-b6e4-704ef8a0421a |  | tickbox | Plan showing location of treatment and disposal of systems
boolean | ee649b80-8693-53c9-9620-2f8fc79d346b |  | tickbox | Producer Statement Review(PS4): System of onsite treatment and disposal of wastewater
boolean | 519b1c48-9fb1-5560-9b89-886039a946bc |  | tickbox | Maintenance agreement for on-site wastewater treatment and disposal system
checkpoint-status |  |  | checkpoint | Development Engineering
boolean | 1356028a-1107-5e4b-9c30-a2334cbb5280 |  | tickbox | Written approval of works completed within 2m of public waste water drainage
boolean | d620bbae-c28a-5d36-83c4-2fbc93743d88 |  | tickbox | Engineering Approval Completion Certificate for ENG
checkpoint-status |  |  | checkpoint | Watercare Services/Viola Approval
boolean | 2fd3b143-e612-555f-a31f-20e23d4ce307 |  | tickbox | Certificate of connection for both incoming and outgoing water to the public system
boolean | 0a924472-0f5f-5861-a6e5-87076e0e3cff |  | tickbox | Written approval of completed works
checklist-flat |  |  | checklist | ST - R - Precast Edge Beams Installation |  |  |  |  | Yes | ST - R - Precast Edge Beams Installation | 631d6a03-308a-479e-b137-11e243c46266
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Edge Beams Installation completed and acceptable
checklist-flat |  |  | checklist | FC - R - Soffits |  |  |  |  | Yes | FC - R - Soffits | 658411ea-51a8-4c90-b014-66cfc6428098
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Soffit works completed and acceptable
checklist-flat |  |  | checklist | F - R - Backfilling |  |  |  |  | Yes | F - R - Backfilling | 65dbfb85-5903-4ee1-bed4-9fa201d3e16a
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Backfilling completed as per the specifications
checklist-flat | 8f738dee-dfd3-4232-bf69-f611bc7625bb |  | checklist | Fitout consent |  |  |  |  | Yes | Add Fitout Consent Checklist | 6758f367-58bc-483f-bf24-ad1d7c8a6214
checkpoint-status | 79a9a9db-c5e4-4630-95ef-8ff753a0892d |  | checkpoint | Record of Title
holdpoint | 9c36c34f-f8b6-4451-801f-363592c2faea |  | signoff | Request for document
checkpoint-status | 4e1683f0-fc0c-4a24-bdb4-38c0a75b6c30 |  | checkpoint | Passed final inspection
holdpoint | 7a285434-8be8-4878-964f-d9a07e3c249d |  | signoff | Request for document
checkpoint-status | d2fb87f7-57d7-46bb-96fd-69e045331c30 |  | checkpoint | Summary sheet from consent book site inspection records
holdpoint | 677360c0-046e-4eb1-aa0e-39572e93c54d |  | signoff | Request for document
checkpoint-status | 5105957a-bf49-45ca-a608-d86d2a816d1b |  | checkpoint | Summary sheet from consent book LBP records
holdpoint | e99aef63-9511-44f9-bfbd-540bbeb2c8f4 |  | signoff | Request for document
checkpoint-status | 4a402035-f324-432e-8b13-161ee48d81b9 |  | checkpoint | Electrical: documents reviewed and attached
boolean | f2e23fd5-9abb-5c4e-b794-2f7bb569a399 |  | tickbox | Electrical Compliance and Safety Certificate
boolean | 10b764a8-8018-57de-9b64-d05a61530a9d |  | tickbox | Record of inspections (For all high-risk works)
holdpoint | 0d120d58-c163-4416-aadd-8b7445a7e01c |  | signoff | Request for document
checkpoint-status | c93a0725-93b5-4c1f-aaea-4d7f4e931924 |  | checkpoint | Plumbing: documents reviewed and attached
boolean | 5b9e30f2-2dd8-50bd-bc89-2890c57626fc |  | tickbox | Producer Statement Construction (PS3) for the plumbing (if not tested onsite by inspector)
boolean | b666cc09-e88e-51c1-957f-754d11fb70ea |  | tickbox | Confirmation / checklist of water saving devices
boolean | 86d6f0a9-c5d4-5745-b25c-0991b35146b6 |  | tickbox | Plumbing under slab as built plan
boolean | e4c02666-b22c-59f7-8165-31cddea050a4 |  | tickbox | Producer Statement Construction Review (PS4) from a council approved engineer for the building hydraulic systems
holdpoint | a1fc3a1b-309b-483b-a39c-d1d098a45176 |  | signoff | Request for document
checkpoint-status | a4ba5258-6b9f-4e0c-a339-cb50aa6b5287 |  | checkpoint | Gas-fitting Work Certificate: documents reviewed and attached
holdpoint | fbcfb136-6a1d-4b9e-9e2a-5446f45001e2 |  | signoff | Request for document
checkpoint-status | 634dec4e-05f4-40fc-a2f3-246b90d3c715 |  | checkpoint | Electrical: documents reviewed and attached
boolean | 2c69e740-9776-556d-8dd0-bb7ff3b0b472 |  | tickbox | Electrical Compliance and Safety Certificate
boolean | 5ab283b5-271e-5ce4-ba35-2cc6cf7ced4b |  | tickbox | Record of inspections (For all high-risk works)
holdpoint | a25f2e57-28f1-4c3a-ba06-962471d45e10 |  | signoff | Request for document
checkpoint-status | bf1ac92d-cdaa-460b-94b9-1e2b07314450 |  | checkpoint | Proprietary Products: documents reviewed and attached
boolean | 96fd431f-4775-5bf0-9538-47b46b9e2175 |  | tickbox | Producer Statement Construction Review (PS4) for seismic restraints
holdpoint | 82e6899c-3153-4f40-8729-6de04487a17f |  | signoff | Request for document
checkpoint-status | 418e966b-1897-405c-ad87-ab1ba887b48b |  | checkpoint | Waterproofing: documents reviewed and attached
boolean | e642d664-b30d-51fb-9f1a-aa75ffe8ca2c |  | tickbox | Tanking Membrane: Producer Statement Construction (PS3) and Manufacturers Product Warranty
holdpoint | 72af2548-dc0a-46fd-b7f3-682de2403d95 |  | signoff | Request for document
checkpoint-status | 22e75b59-6b5d-4f48-a640-db75eccca3f7 |  | checkpoint | Fire Rated (intumescent) Coatings to Structural Steel: documents reviewed and attached
boolean | 61680b81-6071-551d-a175-73c7ee522d57 |  | tickbox | Producer Statement Construction (PS3 - use AC2334) for Fire Rated (intumescent) Coatings to Structural Steel from an approved applicator.
boolean | 32b4ae0f-85a3-5375-906d-43e7475fcda6 |  | tickbox | Copy of the suppliers material schedule listing products used and thicknesses applied
boolean | 5c607ebe-d508-55fe-8b98-746b97545267 |  | tickbox | Floor plan identifying location of the intumescent coatings
holdpoint | f6fd8224-e15d-41ef-a54d-e6d1b222dd84 |  | signoff | Request for document
checkpoint-status | dc0f9e30-54eb-4e8d-9a71-699c89e4c038 |  | checkpoint | Fire rated and stopping systems: documents reviewed and attached
boolean | 867ef8e5-23d7-5f62-a07e-92b127831ac0 |  | tickbox | Producer Statement Construction (PS3) for fire stopping of penetrations (collars, wraps, sealants): Plumbing, Electrical, Mechanical ventilation & Communication Services
boolean | 497e59ae-1b09-5a79-943b-a4ff2496a102 |  | tickbox | Copy of the fire rated penetration schedule: Plumbing, Electrical, Mechanical ventilation & Communication Services
boolean | 1b9a4d79-c3e3-5b0d-8872-2b1b6f233dfe |  | tickbox | As Built plans showing penetrations
boolean | 79c625ec-b16e-5721-9650-4a3d7651e278 |  | tickbox | Producer Statement Construction (PS3) for installed fire rated constructions (i.e. fire rated walls, partitions, floors, ceilings) - to show Fire Rating
boolean | e66fda0b-0e3d-564f-8106-4ae43e65da1e |  | tickbox | Fire door declaration documentation and register of doorsets by the manufacturer (refer NZS4520: 2010 clause 6.4.3)
holdpoint | 9aa56a8b-8d3b-4263-84d0-81d6640664d3 |  | signoff | Request for document
checkpoint-status | 81eb4d09-8b5f-46a1-a971-50d881b18b96 |  | checkpoint | Surface coatings: (Use AC2333 for surface finishes, i.e. paint, floor coverings etc.): documents reviewed and attached
boolean | 62f8febd-3d20-53a8-9aac-09745dd13f11 |  | tickbox | Producer Statement Construction (PS3) for surface finishes confirming compliance of products used (material categories 1-3 NZBC clause C3.4(a))
boolean | 04baba43-2a77-51a7-9807-becb571a2545 |  | tickbox | Producer Statement Construction (PS3) for floor surface materials used confirming compliance of products used (NZBC clause C3.4(b))
holdpoint | 0881defc-e988-47f2-b462-86f251b43465 |  | signoff | Request for document
checkpoint-status | 76b161aa-7b04-41c1-b2e1-46c93f3d8b5e |  | checkpoint | Acoustic Testing: (10% of apartments, must be a representative sample): documents reviewed and attached
boolean | 4c3a0d7e-9511-5f33-8be0-7d0a360aeebd |  | tickbox | Report / Test Certificates from a council approved acoustic engineer confirming compliance with NZBC G6
holdpoint | 0d34cbcb-ef92-464d-b087-72cee146134a |  | signoff | Request for document
checkpoint-status | 38db4537-08ad-451e-bb14-3fe1079cb7be |  | checkpoint | Fire Safety Construction Review: documents reviewed and attached
boolean | 0a0547f0-c9b0-5b57-bcd0-9b165a33c1eb |  | tickbox | Producer Statement Construction Review (PS4) from a council approved fire engineer for the fire safety systems confirming compliance with the relevant NZBC clauses and the approved fire report
holdpoint | a0f18e06-98a8-4eff-adfa-4d65285738a0 |  | signoff | Request for document
checkpoint-status | 2cf42d2f-5698-4268-b532-3534dbe0c4cb |  | checkpoint | Automatic doors e.g. sliding or revolving doors: documents reviewed and attached
boolean | 7cf4d278-6051-59d5-8bb1-7fcc508de5e4 |  | tickbox | Producer Statement Construction (PS3) for the installation of automatic doors (confirming fail safe override)
boolean | 2f8457df-76fb-5b71-8d7b-7afc6fbfb089 |  | tickbox | As built documentation to include full set of as built plans and operation and maintenance manual)
holdpoint | d3661159-8a07-4f15-8be6-c772caa20ca8 |  | signoff | Request for document
checkpoint-status | 92c05843-1af2-4f68-bc5e-dd0f02e1d354 |  | checkpoint | Access controlled doors: documents reviewed and attached
boolean | 7f06b276-acbf-56ba-a4d2-4c3c2af1ea77 |  | tickbox | Producer Statement Construction (PS3) for the installation of access control to doors (confirming fail safe override)
boolean | 440ded7d-49ca-5f20-8569-56b740643a53 |  | tickbox | As built documentation (including as built plans showing location of all systems, equipment schedules noting make of systems installed and any operation and maintenance manual)
holdpoint | b2d616f5-88b9-4f49-96eb-aa5a72db4936 |  | signoff | Request for document
checkpoint-status | 378340fa-1f19-422e-b8dd-3004f2c875cb |  | checkpoint | Interfaced fire or smoke doors or windows: documents reviewed and attached
boolean | 40f03f26-587a-5fb7-9360-18ae72a2ca2b |  | tickbox | Producer Statement Construction (PS3) for the installation of electromagnetic door holders
boolean | cd997357-915d-5aa8-879a-277ea97a2a8d |  | tickbox | As built documentation (including as built plans showing location of all systems, equipment schedules noting make of systems installed and any operation and maintenance manual)
holdpoint | 5a5d606d-5481-4b4e-9751-ca322d215816 |  | signoff | Request for document
checkpoint-status | 5a5ff029-cc15-40ee-a89a-147f49cceffb |  | checkpoint | Emergency lighting systems: documents reviewed and attached
boolean | 9e6d241f-375b-5a24-ad8e-8339d7378293 |  | tickbox | Producer Statement Construction (PS3) for the Emergency Lighting from the electrical contractor confirming compliance with NZBC F6
boolean | f315286e-ba29-5a2f-b57c-93e06fe02944 |  | tickbox | Producer Statement Construction Review (PS4) for the Emergency Lighting from a Council Approved Electrical Engineer confirming compliance with NZBC F6
boolean | fe5a461b-2038-5425-b097-b3629eb9c99e |  | tickbox | Duration test results for each emergency light fitting from electrical contractor or IQP
boolean | 1423f3f1-e9ac-5ec7-81c1-154df25e8108 |  | tickbox | Lux test results for the emergency lighting system
boolean | 29de16aa-25ce-56ec-967b-a259e95f2db1 |  | tickbox | As Built plan including model of systems installed
boolean | 94f31aa8-a633-5c22-bf7e-7449c59dcfbb |  | tickbox | Electrical work certificate
holdpoint | 8025b436-046d-483e-b9a8-c15789d3dfb3 |  | signoff | Request for document
checkpoint-status | be0069fd-4117-487c-9f80-26e3a9458399 |  | checkpoint | Escape route pressurisation systems: documents reviewed and attached
boolean | 2da45404-a491-5e12-a92f-0470214cda10 |  | tickbox | Producer Statement Construction (PS3) from a council approved mechanical contractor for the installation of the escape route pressurisation system
boolean | d7e4e560-4f04-56f7-a90d-cadaccc5a307 |  | tickbox | Producer Statement Construction Review (PS4) from a council approved mechanical engineer contractor for the installation of the escape route pressurisation system
boolean | 7190397e-d722-53a9-9bd5-8015cce36ceb |  | tickbox | Copies of test/commissioning results verifying measured airflow rates meets design (including interface test with fire alarm system)
boolean | 4a3f3218-3844-5447-ac97-49c46baaa58c |  | tickbox | As built documentation (including all as built plans, equipment schedules noting make of systems installed and any operation and maintenance manual)
boolean | 50e62e57-1488-569a-977c-b5f056295cb5 |  | tickbox | Electrical work certificate
holdpoint | 12e5fcc6-4a1a-4d59-a0fe-14ecd15e4d31 |  | signoff | Request for document
checkpoint-status | 09f967fa-f030-4b56-aeff-9d893c9ee39f |  | checkpoint | Passenger carrying lifts: documents reviewed and attached
boolean | 0d6e04b3-b6d8-5568-b54a-56fc018f1136 |  | tickbox | Producer Statement Construction (PS3) for the lift Installation.
boolean | 9cdaa81f-2c91-5b2e-a4f9-c1b47d834415 |  | tickbox | Producer Statement Construction Review (PS4) from a council approved engineer together with copies of all documentation required by the lift peer reviewer (lift safety certificate, copies of defect reports signed off, maintenance checklist and as built documentation etc)
boolean | 9c34fc3b-8388-5947-83b2-3e574abe2baa |  | tickbox | Codemark construction certification and inspection/maintenance sheets
holdpoint | 5e946a65-b6e9-45e5-8d8a-e3814aa24bb6 |  | signoff | Request for document
checkpoint-status | 5a6af8fa-99d7-4818-9eff-43583dd95924 |  | checkpoint | Signs for all systems: documents reviewed and attached
boolean | bf38bcf8-d421-51a4-ad63-89fb61fc89c7 |  | tickbox | As built plans showing location for any of the following signs through the building:
boolean | 138de35d-9aee-5480-a987-7637c26f7968 |  | tickbox | SS 1/1: Sign showing maximum storage heights
boolean | 2de0ddf8-a5b8-5793-8577-9767a3c2467e |  | tickbox | SS 2/1: Sign showing how to operate a fire alarm call point
boolean | be1981a4-081f-5932-bbdc-5e6648d8e35d |  | tickbox | SS 3/1: Sign showing location of accessible automatic
boolean | 39f50c14-e82f-56a8-9bde-e0bd586de063 |  | tickbox | SS 3/2: Sign showing and automatic closing fire or smoke door
boolean | 58e4b3f2-8ede-59dc-b9c1-0e24bd5d7cb3 |  | tickbox | SS 3/2: Sign showing location of an emergency door release on access control doors
boolean | 182a3aa4-38be-54c4-82e7-7b2961a9f0f7 |  | tickbox | SS 8/1: Sign showing location of accessible lift
boolean | 3817ba1f-5761-5dfb-bd4e-e77f731439e7 |  | tickbox | Sign showing not to use the lift in event of fire
boolean | 879059aa-eb88-588f-bfec-a335f32890be |  | tickbox | Sign showing lift load ratings
boolean | e4c0182c-4a2b-584a-8236-1bf7d7107ee8 |  | tickbox | SS 8/3: Sign showing hazards to escalators and moving walks
holdpoint | 3f12bf42-7f17-4577-a3a9-421180c1e47f |  | signoff | Request for document
checkpoint-status | 36076d11-f82d-4641-bb5d-11ab30b5eda2 |  | checkpoint | Final exits (to be inspected at final inspection): documents reviewed and attached
boolean | e7f657e9-e95e-53a0-9e07-e5675fa5ed4a |  | tickbox | As built plans confirming final location of final exist (to include if exits are interfaced with any automatic or access-controlled doors)
holdpoint | dcfc3a71-4743-4063-b6a7-2f69092b8f4e |  | signoff | Request for document
checkpoint-status | 6f54f8b8-a512-4e7e-b320-50ee7cf60054 |  | checkpoint | Fire separation that forms part of the means of escape from fire: documents reviewed and attached
boolean | e4f91f2e-1618-58ff-b9cf-ad0bc6f499f1 |  | tickbox | As built plans confirming final location of Fire separation that forms part of the means of escape from fire
holdpoint | 2ad6655a-08d4-4c0f-be81-42d6f2925087 |  | signoff | Request for document
checkpoint-status | 36c3e632-f3d1-4604-8a07-f940b7c34721 |  | checkpoint | Smoke separation that forms part of the means of escape from fire: documents reviewed and attached
boolean | 8a0c45f9-3699-5cc4-b10a-7804c0371361 |  | tickbox | As built plans confirming final location of walls forming a protected path in a building, smoke resistant lift lobby, smoke stop door, smoke cell
holdpoint | 9d5b60e5-4410-4d67-930d-1e9483fcfbf0 |  | signoff | Request for document
checkpoint-status | f2050039-ae23-464e-be1d-752bb6d5efb2 |  | checkpoint | Any additional documents required
holdpoint | 71aba0f4-f379-4001-aba4-298d0ed97a24 |  | signoff | Request for document
checkpoint-status | 392ae301-e22e-4bd8-8757-01a3f30c82db |  | checkpoint | CCC lodgement form reviewed and attached
holdpoint | dbe93d9d-de4d-4b04-886e-d5cf001a60d6 |  | signoff | Request for document
checkpoint-status | 280ee814-54fb-476d-a69b-f50e0f3a9f87 |  | checkpoint | Specified Systems form reviewed and attached
holdpoint | 4b229de3-fc0e-416b-9608-e5bb14fc4ed2 |  | signoff | Request for document
checklist-flat |  |  | checklist | Building Consent - |  |  |  |  | Yes | Add Council BC Upload Checklist | 68ae5c5e-3e15-42a0-9dbb-6186382e465b
checkpoint-status |  |  | checkpoint | Latest building consent attached (superseded and attached as required)
checklist-flat | b81f5e5e-b90f-4f3d-8389-c2609a06c322 |  | checklist | Facade consent |  |  |  |  | Yes | Add Facade Consent Checklist | 6c039fa7-8c9d-4798-86b1-8e1eb250f75b
checkpoint-status | 3e6e1791-f4f1-4328-afb4-69674bedd8cf |  | checkpoint | Record of Title
holdpoint | f5d43fc6-3afc-4aef-80c6-d0ce94e494ef |  | signoff | Request for document
checkpoint-status | fc8ad235-bd1d-4566-b2a0-75fe2e116935 |  | checkpoint | Passed final inspection
holdpoint | aeae005c-4da0-41a5-a4d7-f4fb00c0f01e |  | signoff | Request for document
checkpoint-status | 7e6c283e-a145-4141-a268-483274e04160 |  | checkpoint | Summary sheet from consent book site inspection records
holdpoint | ba3240b2-831c-4e3c-bc8e-c441f324e916 |  | signoff | Request for document
checkpoint-status | 0668d1da-012b-4690-b7cf-22f80d352d1e |  | checkpoint | Summary sheet from consent book LBP records
holdpoint | 19b13c7a-4069-437b-807b-2dbb2ee6ea51 |  | signoff | Request for document
checkpoint-status | ce1fb5a0-ad9d-4209-aabd-53a00d3015db |  | checkpoint | Electrical: documents reviewed and attached
boolean | a5d683f0-5bcb-5f0b-ae86-ee5c92ed67b8 |  | tickbox | Electrical Compliance and Safety Certificate
boolean | 3f71fc3b-00dd-5f1c-8c99-a9c9f74d313b |  | tickbox | Record of inspections (For all high-risk works)
holdpoint | 4a551ae0-619a-4441-8626-57a75c8e55bb |  | signoff | Request for document
checkpoint-status | a2e82f03-3ff7-4db8-a3f3-914e7b6d4195 |  | checkpoint | Exterior: documents reviewed and attached
boolean | 4bafc93a-a050-5b90-9c3e-a7a91346fd33 |  | tickbox | Plaster system - Producer Statement Construction (PS3) and Manufacturers Product Warranty
boolean | 85e3cf12-97d0-57b0-b418-34fda955f0b5 |  | tickbox | Brick work - Producer Statement Construction (PS3) and Manufacturers Product Warranty
holdpoint | 7bdbbbd6-3376-421b-b193-618ca260e92e |  | signoff | Request for document
checkpoint-status | 016e8d2d-ab97-4ad4-8426-82c605e496a5 |  | checkpoint | Glazing & External Joinery: documents reviewed and attached
boolean | 3772c5d3-cd69-59c6-a9a8-dc6ff40a423b |  | tickbox | Producer Statement for the aluminium joinery confirming compliance with NZS4211:2008
boolean | 16336518-641f-5a1e-b881-c1a466c2922a |  | tickbox | Producer Statement Construction (PS3) for safety glazing confirming compliance with NZS4223
boolean | d0952686-d5aa-50e3-bde0-21ea9dde638c |  | tickbox | Producer Statement Design (PS1) from joinery manufacturer
boolean | e43476e8-203b-5548-b83d-b3bee98e4e4b |  | tickbox | Producer Statement for the fire rated windows confirming compliance with NZS4232 pt2
holdpoint | 697eed6b-a7ba-4b24-bfc6-197fc64e5186 |  | signoff | Request for document
checkpoint-status | de939a8a-f367-4cb6-8ecc-0ce7d6e3cf23 |  | checkpoint | Waterproofing: documents reviewed and attached
boolean | 3cc94e70-4ce2-5862-9771-0c553a49488d |  | tickbox | Roof Membrane: Producer Statement Construction (PS3) and Manufacturers Product Warranty
boolean | 2f3e1598-c8d3-5b71-b3f8-943fa624ae52 |  | tickbox | Deck Membrane: Producer Statement Construction (PS3) and Manufacturers Product Warranty
boolean | 21cb9738-c4a9-54d7-a0fe-6c9c6ccd2599 |  | tickbox | Tanking Membrane: Producer Statement Construction (PS3) and Manufacturers Product Warranty
holdpoint | 0b91808c-0f5d-4615-9005-732c25c61339 |  | signoff | Request for document
checkpoint-status | 91deba45-f93d-4d54-9301-8029f40b4184 |  | checkpoint | Roof Abseil and Fall Arrest System: documents reviewed and attached
boolean | 1b59e9df-b4e6-518c-8c35-9774e45a2d90 |  | tickbox | Producer Statement Design (PS1) for the installation of the Roof Abseil and/or Fall Arrest System
boolean | a9ab0579-716a-526a-8b52-255a7afba6e8 |  | tickbox | Producer Statement Construction (PS3) for the installation of the Roof Abseil and/or Fall Arrest System
boolean | fc85fe4e-7325-5949-a25a-7a6e5dc665f8 |  | tickbox | Producer Statement Construction Review (PS4) for the installation of the Roof Abseil and / or Fall Arrest System
holdpoint | 7376ab08-73db-4a85-8bf6-d0bc3cb8c58c |  | signoff | Request for document
checkpoint-status | e6bcb272-6101-43a4-8498-9136ec0b57d1 |  | checkpoint | Balustrades: (PS3 must state type of balustrade/balustrade system installed, use AC2322): documents reviewed and attached
boolean | e1383aef-c0de-558f-b7dc-88a61440aa70 |  | tickbox | Producer Statement Construction (PS3) for the glass balustrade installation.
holdpoint | 5222d316-10c0-4b23-a52e-ae73e8ef2266 |  | signoff | Request for document
checkpoint-status | 3172f65e-0143-4f0b-926e-dc6066cce19e |  | checkpoint | Facade Systems: documents reviewed and attached
boolean | 19d9d156-af6a-5d5f-a566-648a6a91f1c7 |  | tickbox | Producer Statement Construction Review (PS4) from a council approved faÁade engineer for the faÁade system
boolean | 1e55fde6-c3b9-5f1a-8519-c012de09517d |  | tickbox | Written Report from a council approved faÁade engineer for the faÁade system to support the PS4
boolean | 4e703245-1e2c-505c-baac-2b435556a644 |  | tickbox | Producer Statement Construction (PS3) for the installation of the faÁade system
boolean | e18eb82b-9dcd-55cd-8028-c01c2f5d9ace |  | tickbox | Construction issue shop drawings
boolean | 31738d68-0194-5389-a92e-ed6ef552200a |  | tickbox | FaÁade system maintenance manual
boolean | ffa4b843-7205-54ef-9509-cc9a59ab8f7a |  | tickbox | Quality assurance, construction monitoring and audit records
boolean | 8badec27-2a20-577e-9409-873b1083fafc |  | tickbox | Warranties/Guaranties (from main and sub-contractors)
holdpoint | dcb15362-a8c2-448e-8881-3c022b37153a |  | signoff | Request for document
checkpoint-status | 49a43fb0-ead7-41ce-8366-8075ec0af24b |  | checkpoint | Automatic doors e.g. sliding or revolving doors: documents reviewed and attached
boolean | a2fd1d18-3199-53db-aef7-3ab334455174 |  | tickbox | Producer Statement Construction (PS3) for the installation of automatic doors (confirming fail safe override)
boolean | 89dadcc7-0834-566e-8441-4bb4afe63a0c |  | tickbox | As built documentation to include full set of as built plans and operation and maintenance manual)
holdpoint | eb434d83-77d5-4a88-aa7a-48b93d1244f5 |  | signoff | Request for document
checkpoint-status | 7bc10f1b-cf48-4d1a-8ed1-07395df3ddc6 |  | checkpoint | Access controlled doors: documents reviewed and attached
boolean | 5b3cc8cf-10d7-5f19-aae6-2b44cc098d7a |  | tickbox | Producer Statement Construction (PS3) for the installation of access control to doors (confirming fail safe override)
boolean | aa028d73-afdf-5852-8e01-a969797cfb66 |  | tickbox | As built documentation (including as built plans showing location of all systems, equipment schedules noting make of systems installed and any operation and maintenance manual)
holdpoint | 85e0e3c2-de8f-47c7-9bc1-ec9432d88cbd |  | signoff | Request for document
checkpoint-status | 39320e69-9d07-4773-b7f7-e76ddc0fc180 |  | checkpoint | Any additional documents required
holdpoint | b56f04cc-5182-4ca8-a159-2c4a6a847973 |  | signoff | Request for document
checkpoint-status | 23f97821-d892-4c9c-a5f7-cb0053df7c92 |  | checkpoint | CCC lodgement form reviewed and attached
holdpoint | 86fcaf3b-25bf-4f8b-8e2e-b16315b1c21b |  | signoff | Request for document
checkpoint-status | e101546e-7ade-475e-a5e3-81ca7de7e937 |  | checkpoint | Specified Systems form reviewed and attached
holdpoint | 1a05decb-7b04-4b68-b5fc-d198f0a941cf |  | signoff | Request for document
checklist-flat |  |  | checklist | FC - R - External Plaster - Nibs & Beams |  |  |  |  | Yes | FC - R - External Plaster - Nibs & Beams | 6eef0248-0acd-4298-91ef-d72d52f78b9f
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | External Plaster works for Nibs & Beams completed and acceptable
checklist-flat |  |  | checklist | C - R - Bulk Excavation |  |  |  |  | Yes | C - R - Bulk Excavation | 719522cc-66c9-4626-966c-d26039109128
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Excavation completed - Correct locations and RL's achieved
checklist-flat |  |  | checklist | F - R - Underground services |  |  |  |  | Yes | F - R - Underground services | 74a725fc-e5f1-428d-a69b-27f0b4f19c93
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All underground services installation completed as per the specifications
checklist-flat |  |  | checklist | ST - R - Insitu Stitch Joints |  |  |  |  | Yes | ST - R - Insitu Stitch Joints | 7526573a-ff73-4c9f-9c37-75923a7aafed
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Insitu Stitch Joints concrete pour completed and acceptable
checklist-flat |  |  | checklist | C - R - Service Trenches - Common Service Trenches |  |  |  |  | Yes | C - R - Service Trenches - Common Service Trenches | 77ac0904-662d-4919-ad48-ee2fdd754281
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Common service trench works completed as per the specifications
checklist-flat | 77319382-62c4-4119-b706-52114dcecc84 |  | checklist | Fire Consent - |  |  |  |  | Yes | Add Fire Consent Checklist | 7ad1cb9c-964a-4b56-890f-696931406774
checkpoint-status | 5a679acc-e9e6-43bd-8ebc-225e7a00a063 |  | checkpoint | Producer Statement construction (PS3) Fire Protection – Intumescent Coatings to structural Steel
holdpoint | 8e987bf0-ba45-45b0-94f0-26b4f131b8c9 |  | signoff | Request Signoff
checkpoint-status | b2f8b92d-3229-44b4-8b38-9904c3a27ec3 |  | checkpoint | Producer Statement construction (PS3) Fire Stopping of Fire rated walls, floors & ceilings
holdpoint | 70b711ce-861f-4ea4-976b-cd81d64e1c15 |  | signoff | Request Signoff
checkpoint-status | f98c8ab1-b5a4-4c73-8849-891c75e6de1f |  | checkpoint | Installation, testing & commissioning certificates for fire safety systems
holdpoint | 61eed30f-b724-48e9-915a-df51674f784d |  | signoff | Request Signoff
checkpoint-status | cf55ab1b-44f6-412b-a4a7-cdb65f3464c7 |  | checkpoint | Fire alarm certification
holdpoint | 4af88f36-2224-4fc7-8c97-c31f92afea65 |  | signoff | Request Signoff
checkpoint-status | ac8d919d-d602-4d93-a8ff-dea4b1a9a19c |  | checkpoint | Fire sprinkler system certification
holdpoint | 81d517f4-580e-4304-8e24-af0a13eb7adc |  | signoff | Request Signoff
checkpoint-status | bec82300-a544-4c5b-8093-e0ddc801642b |  | checkpoint | Producer statement construction (PS3) – Interior surfaces finishes, floor coverings & suspended flexible fabrics
holdpoint | f1e4c959-3276-4654-8f9d-a35c649fff83 |  | signoff | Request Signoff
checkpoint-status | cb25f933-8fbb-482d-95b0-97cf0fbc4b42 |  | checkpoint | Producer Statement construction (PS3) – fire doors
holdpoint | fbf03824-cfb1-425f-a0d4-394d43413869 |  | signoff | Request Signoff
checkpoint-status | f2d8b1e9-617c-4a58-b33d-370fe1147553 |  | checkpoint | Producer Statement construction (PS3) – Proprietary product installation
holdpoint | 4b8d7077-8fcf-4d71-a25a-5619e7b0f984 |  | signoff | Request Signoff
checkpoint-status | 34969226-3d35-452d-9182-53161ff6eb64 |  | checkpoint | Energy works certificate – electrical
holdpoint | 7b58d542-aeda-48c1-af33-e0fc10479f10 |  | signoff | Request Signoff
checkpoint-status | b87b537a-f04d-4a90-9502-feb2640f6e57 |  | checkpoint | All documents received, reviewed, attached and approved
checkpoint-status | d2cf6203-0a46-4eb6-beed-e647ab367eae |  | checkpoint | Code Compliance Certificate issued, approved and attached
checklist-flat |  |  | checklist | CST - R - Hydraulic Consent |  |  |  |  | Yes | CST - R - Hydraulic Consent | 7d26aabb-246f-46de-bb3b-ce879efcae53
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Plumbing
boolean | 65bad875-3836-5e02-9095-1c31abc27d26 |  | tickbox | Producer Statement Construction (PS3): Plumbing
boolean | e31cf3ef-5ce7-5f6d-a942-6c3acb54b3cf |  | tickbox | Confirmation of water saving devices
boolean | c7bdc965-0613-5482-9083-41bc280a4b4a |  | tickbox | Plumbing under slab as built plan
boolean | c56d9d36-0116-5ddc-94bd-a013edf76c8c |  | tickbox | Producer Statement Review(PS4): hydraulic systems of the building from a council approved engineer
checkpoint-status |  |  | checkpoint | Gas-fitting Work Certificate
checkpoint-status |  |  | checkpoint | Automatic Backflow Preventers Connected to Potable Water supply
boolean | ac1b303c-5748-5a9d-a333-c3be56f64d4b |  | tickbox | Backflow prevention - PS3 and test certificates showing location and type of devices
checkpoint-status |  |  | checkpoint | Application for compliance schedule (AC2102)
checkpoint-status |  |  | checkpoint | Confirmation of performance standards for specified systems (AC2150)
checklist-flat |  |  | checklist | FC - R - Exterior Tiling |  |  |  |  | Yes | FC - R - Exterior Tiling | 81093153-663b-435f-8fce-36f3384a8f80
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Exterior Tiling works completed and acceptable
checklist-flat |  |  | checklist | CST - R - Piling Consent |  |  |  |  | Yes | CST - R - Piling Consent | 822b9031-9c7a-411b-983f-b31eb6141453
checkpoint-status |  |  | checkpoint | Record of Title
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Construction Review
boolean | 2e28034f-ef02-586f-b4f3-7853d496b765 |  | tickbox | Producer Statement Review(PS4): Geotechnical
boolean | 4fef542b-b488-5e25-88a6-d540a297808d |  | tickbox | Producer Statement Review(PS4): Compaction of hardfill
boolean | 3e66a54e-b06f-5d59-9b78-d0640e22cdf8 |  | tickbox | Producer Statement Review(PS4): Drain Bridging
boolean | ae98a39a-358a-5696-9fd6-bf7e2b4fa79a |  | tickbox | Producer Statement Review(PS4): Engineer's observation
checkpoint-status |  |  | checkpoint | Producer Statement Construction(PS3): Piling
checkpoint-status |  |  | checkpoint | Pile records and cards
checkpoint-status |  |  | checkpoint | Surveyor certificate for siting
checkpoint-status |  |  | checkpoint | Mill certificates
checkpoint-status |  |  | checkpoint | Concrete dockets
checklist-flat |  |  | checklist | C - R - Manhole Installation |  |  |  |  | Yes | C - R - Manhole Installation | 84a12b15-ca8d-46ea-9423-6305f7ff1046
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Manhole Installation completed as per the specifications
checklist-flat |  |  | checklist | F - R - Shell Beam Installation |  |  |  |  | Yes | F - R - Shell Beam Installation | 88b05bbb-91a9-4f32-a06a-87ff58aa71b9
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Shell Beam installation completed as per the specifications
checklist-flat |  |  | checklist | F - R - Underslab plumbing |  |  |  |  | Yes | F - R - Underslab plumbing | 8c16075f-8950-4672-8fd8-252bf56b4885
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All underslab plumbing installation completed as per the specifications
checklist-sectioned |  |  | checklist | Pour: |  |  |  |  | Yes | ST - R - Concrete Pour - Ryman Owned | 8c2819d8-974a-4b54-bc0d-51ee8eed94a0
checkpoint-group |  |  | section | Pour Details
checkpoint-status |  |  | checkpoint | Pour details entered
text | 62d7043d-db5f-58ee-a999-0e0cb0f6adb9 |  | textbox | Area to be poured:
text | 8241b050-5bd3-551d-840b-583641db7005 |  | textbox | Date of pour:
checkpoint-status |  |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-group |  |  | section | Formwork and Embedded Items
checkpoint-status |  |  | checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint-status |  |  | checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint-status |  |  | checkpoint | All surfaces correctly prepared (e.g joints to existing concrete, release agent to formwork etc)
checkpoint-status |  |  | checkpoint | Any control joints/ stop ends installed accurately and correctly braced
checkpoint-group |  |  | section | Reinforcing
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/correct
checkpoint-status |  |  | checkpoint | Splice laps checked/correct
checkpoint-status |  |  | checkpoint | All couplers installed correctly (if reid bar couplers have been used, has epconC8 epoxy been used as specified)
boolean | b878c815-8f9a-554f-a407-657f8cc135ab |  | tickbox | Appointment with the engineers confirmed (Enter date & time of the appointment)
boolean | 4fa14a86-1041-5ebf-bb56-6e89d5075c3b |  | tickbox | Reidbar – coupler and flange nut installations are inspected by the MV Engineer
checkpoint-status |  |  | checkpoint | IMBMS couplers testing carried out for Village Podiums in the form of tensile testing in accordance with NZS3101.1.2006 and results acceptable
checkpoint-status |  |  | checkpoint | All starter bars are installed correctly (location, size and spacing )
checkpoint-status |  |  | checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Welding certificates sited and attached
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
checkpoint-group |  |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status |  |  | checkpoint | Waterproofing elements have been correctly installed and checked
checkpoint-status |  |  | checkpoint | Relevant service requirements completed (locations checked and accurate)
checkpoint-status |  |  | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint-status |  |  | checkpoint | Ryman inspection completed - Approval given to pour concrete
checkpoint-group |  |  | section | Concrete Supplier Specifics
checkpoint-status |  |  | checkpoint | Concrete Supplier details entered
text | 1b3fc9bf-8ae8-5031-805d-aa24dc4caa1f |  | textbox | Supplier Name:
text | c2ca0f1f-b70c-5ab0-ae49-844b6d8874fc |  | textbox | Specified concrete strength: |  |  | mPA
text | f8fc6087-cb35-5307-992d-d3266b4ea045 |  | textbox | Concrete strength ordered: |  |  | mPA
text | 3379f871-c5f7-54de-8718-b4cce56ec7d2 |  | textbox | Concrete quantity ordered: |  |  | m3
button | 61de42ab-8da6-53e8-82a8-95efbadb1ce5 |  | button | Test blocks booked | Yes, No, N/A
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-group |  |  | section | Placement Method
checkpoint-status |  |  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
checkpoint-status |  |  | checkpoint | Heights and falls checked/confirmed before placement
button | e243d9a9-d728-53e9-8474-a303135fc270 |  | button | Is the cover correct to specification | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Heights and falls checked/ confirmed after placement
checkpoint-status |  |  | checkpoint | Any curing compound applied correctly
checkpoint-status |  |  | checkpoint | Concrete placement completed - specified level of finish achieved
checkpoint-group |  |  | section | Post Pour Checks/Sign Off
checkpoint-status |  |  | checkpoint | Any remedial work completed
holdpoint |  |  | signoff | Raise remedial/ Request Signoff
checkpoint-status |  |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checklist-flat |  |  | checklist | ST - R - Intumescent Painting |  |  |  |  | Yes | ST - R - Intumescent Painting | 8d72f23e-4445-4e1f-901e-4f344b6ee93c
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Intumescent Painting completed and acceptable
checklist-flat |  |  | checklist | FC - R - Flashing installation |  |  |  |  | Yes | FC - R - Flashing installation | 90e96df6-3c97-4430-a014-98b10747198e
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Flashing installation completed and acceptable
checklist-flat |  |  | checklist | FC - R - Passive fire |  |  |  |  | Yes | FC - R - Passive fire | 944f6f48-f202-4ab7-aee6-160161ccfac8
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Passive Fire works completed and acceptable
checklist-flat |  |  | checklist | H - R - Handover |  |  |  |  | Yes | H - R - Handover | 94688674-aa57-48b3-9b85-e653d8fe9a55
checkpoint-status |  |  | checkpoint | Hardware/Fittings
checkpoint-status |  |  | checkpoint | Plumbing
checkpoint-status |  |  | checkpoint | Electrical
checkpoint-status |  |  | checkpoint | Joinery/Doors
checkpoint-status |  |  | checkpoint | Decorating
checkpoint-status |  |  | checkpoint | Flooring
checkpoint-status |  |  | checkpoint | Other
checkpoint-status |  |  | checkpoint | Upload Related Ryman Fitout quality inspection record (QT-012)
checklist-flat |  |  | checklist | ST - R - Concrete Pour |  |  |  |  | Yes | ST - R - Concrete Pour | 96a7e498-a587-48b4-8555-4e731b8d76b1
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Concrete pour completed and acceptable
checklist-flat |  |  | checklist | ST - R - Rib & Infill Installation |  |  |  |  | Yes | ST - R - Rib & Infill Installation | 9cac0aed-c5d5-4066-ae3f-6f5c26cb00eb
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Rib & Infill Installation completed and acceptable
checklist-flat |  |  | checklist | FC - R - Eyebrow - Canopy |  |  |  |  | Yes | FC - R - Eyebrow - Canopy | 9d146caa-5f40-4124-ac83-2cbd3ef3665d
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Exterior Tiling works completed and acceptable
checklist-flat |  |  | checklist | F - R - Survey Certificates |  |  |  |  | Yes | F - R - Survey Certificates | 9e436654-89ea-44d7-86d9-ed0d92ab6535
checkpoint-status |  |  | checkpoint | survey certificates for correct building height/location/setout attached
checklist-flat |  |  | checklist | ST - R - Precast Wall Bracket Installation |  |  |  |  | Yes | ST - R - Precast Wall Bracket Installation | a25aee36-6d2e-43e3-a654-c4042117c86a
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Wall Bracket Installation completed and acceptable
checklist-flat |  |  | checklist | ST - R - Precast Flat Slab Installation |  |  |  |  | Yes | ST - R - Precast Flat Slab Installation | a507f6c1-1b87-4308-9e83-d535eba3a965
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Flat Slab Installation completed and acceptable
checklist-flat | 40a5d9fc-c081-4449-97c8-dbed06017684 |  | checklist | Daily Site Report: |  |  |  |  | Yes | Add Daily Site Report | aa425113-a422-4228-ac67-1a4d096b6ce5
checkpoint-no-status | 1e8f51d2-2b41-4f51-99f5-e65792945414 |  | checkpoint | Daily Site Report:
text | 833e177a-2ddc-4d3d-8956-9d89d24fc7dc |  | textbox | Weather in AM:
text | 2343dc33-009c-40a0-b4e0-09f6324f3a13 |  | textbox | Weather in PM:
checkpoint-status | e9905018-636e-4b48-9769-01bf71fee0cf |  | checkpoint | Audits, Inspections, Inductions, Dangerous Goods, etc
checkpoint-status | d4dc3c8f-5ce2-4d37-9f7c-20d2e678e1e2 |  | checkpoint | Hazards or Accidents noted or reported and action taken including first aid
checkpoint-status | 39c46ce3-2d93-44cc-896e-cf9162f04434 |  | checkpoint | Toolbox or other safety meetings / committees
checkpoint-status | e158b2fc-780a-4a69-aebb-73dea85783a8 |  | checkpoint | Visitors to Site (includes TA, Consultants, Client)
checkpoint-status | d958af24-af9f-474e-b31f-c78e5aac099e |  | checkpoint | Task Analysis
checkpoint-status | ce86a4fa-5094-4803-b56b-04306edbbe49 |  | checkpoint | Coaching / Training
checkpoint-status | 9c0351f5-da9b-4386-ae9a-268ef5f4665b |  | checkpoint | Employee suggestions and input
checkpoint-status | b686f747-2ff7-4499-b489-e336109cb56d |  | checkpoint | General comments
checklist-flat |  |  | checklist | CST - R - Mechanical Constant |  |  |  |  | Yes | CST - R - Mechanical Constant | acafc656-48ba-400f-9658-c9ee473c3580
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Electrical
boolean | 1543c233-7ab8-5a1c-b0e9-c5264b33131e |  | tickbox | Electrical compliance and safety certificate
boolean | 0626fdb6-fcda-518a-8f04-ac09f8e8fcb3 |  | tickbox | record of inspections for high risk works
checkpoint-status |  |  | checkpoint | Automatic doors
boolean | 4c532e82-c112-5d87-a7dd-1c95f399f19e |  | tickbox | Producer Statement Construction(PS3): automatic door installation and failsafe override
boolean | 6ab57021-7572-5daf-9cea-671134d6aa11 |  | tickbox | As built documentation; plans, operation and maintenance manual
checkpoint-status |  |  | checkpoint | Access controlled doors
boolean | fcf9c56a-13bf-54f1-8b87-cad222c94397 |  | tickbox | Producer Statement Construction(PS3): installation of access control to doors and failsafe override
boolean | 01166177-0485-5261-a1f2-696c6d2c2790 |  | tickbox | As built documentation; location of systems, the make of the systems and operation manuals
checkpoint-status |  |  | checkpoint | Escape route pressurization systems
boolean | e6913633-1f72-57f0-9a91-5bce9711eade |  | tickbox | Producer Statement Construction(PS3): Installation of escape route pressurization systems from approved mechanical contractor
boolean | ec06baee-62dc-5438-8b26-4fbb18706405 |  | tickbox | Producer Statement Review(PS4): Installation of escape route pressurization systems from approved mechanical contractor
boolean | ee53ed80-c962-58a8-94ee-47cc7dac1add |  | tickbox | test/commissioning results verifying measured airflow rates meet design and interface with alarm system
boolean | 90022f9c-3ba6-596e-bc50-c1dc73674944 |  | tickbox | As built documentation; equipment schedules and make of systems, operation and maintenance manuals
boolean | 96186075-230e-51df-b4cc-ca0c5da5264b |  | tickbox | Electrical work certificate
checkpoint-status |  |  | checkpoint | Passenger Carrying Lifts
boolean | 6f6a25f6-7144-5316-8e8a-6db392eff2f5 |  | tickbox | Codemark construction certification and inspection/maintenance sheets
checkpoint-status |  |  | checkpoint | Mechanical ventilation or air conditioning system
boolean | 0377e1cc-b708-5030-a9c5-17ca0b95ef01 |  | tickbox | Producer Statement Construction(PS3): Kitchen extract system (compliance with NZBC G4)
boolean | 657af15f-fc62-5bfe-85a6-b0534b89d58a |  | tickbox | Producer Statement Construction(PS3): Confirmation from mechanical contractor the systems comply with NZBC G4
boolean | 04ef7f3f-e7fb-5d24-b2f6-6497d24cc1b5 |  | tickbox | Producer Statement Review(PS4): Confirmation from council approved mechanical engineer that the systems comply with NZBC G4
boolean | f669cb83-421f-58d4-9be6-b07fca0d579a |  | tickbox | Producer Statement Review(PS4): Installation of seismic restraints in accordance with NZS 4219:2009:"Seismic Performance of Engineering Systems in Buildings"
boolean | 80a1bb9d-fc81-5683-aab0-5ae05aadc8bb |  | tickbox | test/commissioning results verifying measured airflow rates meet design and interface with alarm system
boolean | 962579f7-9951-57da-b6e9-7c8e28903a31 |  | tickbox | As built documentation; equipment schedules and make of systems, operation and maintenance manuals
checkpoint-status |  |  | checkpoint | Application for compliance schedule (AC2102)
checkpoint-status |  |  | checkpoint | Confirmation of performance standards for specified systems (AC2150)
checklist-flat |  |  | checklist | FC - R - Lintels |  |  |  |  | Yes | FC - R - Lintels | af34d68d-c570-4220-887f-6f07cbf86c56
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Lintels completed and acceptable
checklist-flat |  |  | checklist | FC - R - Balustrades Installation |  |  |  |  | Yes | FC - R - Balustrades Installation | b1045026-585d-45c6-9428-e046b4cadf6a
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Balustrades installation completed and acceptable
checklist-flat |  |  | checklist | CST - R - Site Inspection Details |  |  |  |  | Yes | CST - R - Site Inspection Details | b205d085-d891-462e-bf16-4307c62da668
checkpoint-status |  |  | checkpoint | Specific site works location
checkpoint-status |  |  | checkpoint | Contractor QA reviewed and approved
checkpoint-status |  |  | checkpoint | Have the consented drawings been followed?
checkpoint-status |  |  | checkpoint | General comments, photos, and observations during inspection
checkpoint-status |  |  | checkpoint | Works completed to required specifications - Engineer signoff
checklist-flat | b7baccfa-1cbb-4958-80d4-8c5694fc8f23 |  | checklist | Foundation Consent - |  |  |  |  | Yes | Add Foundation Consent Checklist | b2d9f7dc-7dec-48d2-bd07-d745a46700ee
checkpoint-status | 7fb9efa7-0f6e-423c-9a0f-fc2765426d9c |  | checkpoint | Producer statement construction review (PS4) Geotechnical
holdpoint | d75e6987-e338-42b6-be95-3958831f4076 |  | signoff | Request Signoff
checkpoint-status | 92e6e207-2975-4be6-a981-785a123667a8 |  | checkpoint | Producer statement construction review (PS4) compaction of Hard-fill
holdpoint | 3c559780-a86b-4473-986c-d884001a6f32 |  | signoff | Request Signoff
checkpoint-status | b8c5feee-eb69-409f-8356-aa365a6d5d14 |  | checkpoint | Producer Statement Construction review (PS4) engineers’ observation
holdpoint | 308981b0-4bac-47cc-a0b3-46abb2e9ba74 |  | signoff | Request Signoff
checkpoint-status | f712fc90-8c4c-46de-b030-53dc0a134be5 |  | checkpoint | Producer statement construction (PS3) sub-soli drains
holdpoint | 8a2a7aec-a63a-47a4-b192-9f49348d1390 |  | signoff | Request Signoff
checkpoint-status | 8a16c019-21f0-4e4f-a8f4-2763ce602360 |  | checkpoint | Producer statement construction (PS3) ‘Rib & In-fill’ floor slab
holdpoint | 4ba0dd12-94b4-4d45-840c-b455bfe71115 |  | signoff | Request Signoff
checkpoint-status | e88b3c72-b864-4c51-94d1-7370fd50a511 |  | checkpoint | Producer Statement Construction Review (PS4) Type A or B Masonry
holdpoint | f2c8ffb5-2481-45d9-a9fa-d0afe2c4cb06 |  | signoff | Request Signoff
checkpoint-status | 4e50c39b-9e65-475f-9b01-cb7021e3d9a1 |  | checkpoint | Producer Statement Design (PS1) Precast and Pre-Stressed Concrete
holdpoint | c8f9df65-1a6a-4d39-bb85-9c60cf5f4cd8 |  | signoff | Request Signoff
checkpoint-status | d51bdc45-cd98-4356-9662-1ee3e91bb1d1 |  | checkpoint | Producer Statement Construction (PS3) Precast and Pre-Stressed Concrete
holdpoint | 0ebd13e4-68d3-4467-9310-9d70086dbae8 |  | signoff | Request Signoff
checkpoint-status | 60437e35-0eea-42c4-8b95-196ffdda0550 |  | checkpoint | Producer Statement Construction Review (PS4) Precast and Pre-Stressed Concrete
holdpoint | adf65b6b-3160-454c-a8b4-28531bfd7c71 |  | signoff | Request Signoff
checkpoint-status | e0959697-7c65-4f0d-9a8c-beb84458b9ad |  | checkpoint | Producer Statement Construction (PS3) Site Welding
holdpoint | a8ba07b7-82b8-408e-9bb8-bccb0bcd501e |  | signoff | Request Signoff
checkpoint-status | e95227c6-20dc-46af-8f22-9ac2ac8d5aaf |  | checkpoint | Inspection and Test Plan (ITP) structural steel welding
holdpoint | 6dd19834-da8b-452a-887f-b4354818812e |  | signoff | Request Signoff
checkpoint-status | 1dd0a660-92da-459c-a02f-8b95d1a772f8 |  | checkpoint | Producer Statement Construction (PS3) Corrosion Protection
holdpoint | 683aaab1-893d-4769-8179-de3e990a98db |  | signoff | Request Signoff
checkpoint-status | 0f8de714-29c0-49c5-9341-909677f7ab6d |  | checkpoint | Producer Statement Construction (PS3) Fire Protection – Intumescent Coatings to Structural Steel
holdpoint | b0f4b95e-f319-4014-9f1b-8a0a51378724 |  | signoff | Request Signoff
checkpoint-status | ee011610-03c8-49c5-b7c4-b150f4170561 |  | checkpoint | Producer Statement Construction (PS3) Waterproofing Membrane
holdpoint | 80034cee-3fa7-40ed-80c0-c84d9bd98ac2 |  | signoff | Request Signoff
checkpoint-status | bbd750ca-e9c7-44a7-8658-f40e58137380 |  | checkpoint | Product Warranty – Waterproof Membrane
holdpoint | a0c48dca-7756-49e9-9a9e-e7b519629852 |  | signoff | Request Signoff
checkpoint-status | e519a3b4-6044-41a2-a477-0a8b4801541d |  | checkpoint | Producer Statement Construction (PS3) – Proprietary Product Installation
holdpoint | 319459ea-8755-4b7d-8143-7c889d93225b |  | signoff | Request Signoff
checkpoint-status | afa27df7-ade5-4216-9a5d-6b5fe90fe8f4 |  | checkpoint | Surveyor’s Certificate – Siting
holdpoint | 3b57a051-dc18-4ba9-b594-aeb0eeb28ac6 |  | signoff | Request Signoff
checkpoint-status | bd53d2b4-267a-4a58-a279-aae430be83ab |  | checkpoint | Surveyor’s Certificate – Floor Level
holdpoint | 7918242f-fd60-4b3d-80cb-83e07fc9e85e |  | signoff | Request Signoff
checkpoint-status | c1b7054d-4fd3-4089-8d2d-9b27ffc0c060 |  | checkpoint | All documents received, reviewed, attached and approved
checkpoint-status | a2a4c4ad-2572-40a3-b4c6-f2f3c2f84c0a |  | checkpoint | Code Compliance Certificate issued, approved and attached
checklist-flat |  |  | checklist | FC - R - Balconies |  |  |  |  | Yes | FC - R - Balconies | b6ebf60d-2e00-48da-9351-228812f66e59
checkpoint-status |  |  | checkpoint | Waterproofing and flashing checked and acceptable
checkpoint-status |  |  | checkpoint | All screed to nib and deck falls checked and accurate
checkpoint-status |  |  | checkpoint | Soffit Checked and accurate
checkpoint-status |  |  | checkpoint | Flood test completed and acceptable
checkpoint-status |  |  | checkpoint | Installation of deck tiles completed and acceptable
checkpoint-status |  |  | checkpoint | All works on balcony are completed to required specification.
checklist-flat |  |  | checklist | FC - R - Roofing |  |  |  |  | Yes | FC - R - Roofing | b7ebfe54-f7f7-40da-9a37-7a66a880a7ae
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Roofing installation completed and acceptable
checklist-flat |  |  | checklist | CST - R - Foundation Consent |  |  |  |  | Yes | CST - R - Foundation Consent | b822a49a-2454-4e3f-a8ff-064c194dd6b3
checkpoint-status |  |  | checkpoint | Record of title
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Pre-cast concrete
boolean | 4b7bf450-a9a7-5076-8da0-9082104e1003 |  | tickbox | Producer Statement Design(PS1): Prestressed concrete beams and floor units
boolean | 605a890a-3f62-53c4-bbbe-de1e95c0904a |  | tickbox | Producer Statement Construction(PS3): Prestressed concrete beams and floor units
boolean | a33fdc34-1eaa-534f-9d5d-c6de8b789c16 |  | tickbox | Producer Statement Review(PS4): Prestressed concrete beams and floor units
boolean | 3114b428-d0c2-569a-849c-6edf32a0a57b |  | tickbox | Shop drawings for concrete beams and floor units
checkpoint-status |  |  | checkpoint | Producer Statement Construction(PS3): sub-soil drainage
checkpoint-status |  |  | checkpoint | Waterproofing
boolean | e2aaa27e-c8b8-56ef-b348-be17dae27292 |  | tickbox | Producer Statement Construction(PS3): Waterproofing Membrane
boolean | 4fef7d51-1905-5ee3-b715-03389ab6397a |  | tickbox | Manufacturer's warranty for waterproofing membrane
checkpoint-status |  |  | checkpoint | Mill certificates
checkpoint-status |  |  | checkpoint | Concrete dockets
checkpoint-status |  |  | checkpoint | Producer Statement Review(PS4): Engineer's observation
checkpoint-status |  |  | checkpoint | Surveyor certificate for siting
checklist-flat |  |  | checklist | Minor Variation - |  |  |  |  | Yes | Add Council Minor Variation Checklist | c2b43176-dfcb-41a7-8350-13c8f578bedb
checkpoint-status |  |  | checkpoint | Minor variation status (Pass once approved & all information is attached including observations, correspondence & close out evidence)
label | d83c76ad-c2c4-422a-b3d0-5e46ac4be24f |  | note | PASS above checkpoint when variation is approved
label | ab21c4bc-c773-43ee-88d7-f338c674ee92 |  | note | If minor variation is a FAIL - document why below and follow appropriate corrective actions
text | e716f58a-4420-4e11-91ae-f4fef0f7ba87 |  | textbox | Date of application
text | 6931f74e-964b-42b5-905c-440c2ce0001a |  | textbox | Reason for application
text | 4ce69a81-cba4-4eac-b963-ff28392bbaf5 |  | textbox | Date of approval / acceptance
text | 78d9159e-0896-4188-a542-fa6b1bf43aaa |  | textbox | Inspection Type Code (If applicable e.g. Site meeting IME)
boolean | d24858c1-85f5-44b8-99c0-818a707a7f19 |  | tickbox | Council approval of minor variation attached
checklist-flat |  |  | checklist | FC - R - Anchor Points - Static line installation |  |  |  |  | Yes | FC - R - Anchor Points - Static line installation | c327c52e-940f-47c4-84eb-4c18871aa68f
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Static line installation completed and acceptable
checklist-flat |  |  | checklist | CST - R - Façade Consent |  |  |  |  | Yes | CST - R - Façade Consent | c701ed16-27cc-464a-878f-609c936c0222
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Exterior
boolean | ed0032cb-2141-50fd-aca6-99162bf41592 |  | tickbox | Producer Statement Construction(PS3): Plaster system and manufacturer's product warranty
boolean | d50273e3-5478-5110-a19f-851595f2139e |  | tickbox | Producer Statement Construction(PS3): Brick work and manufacturer's product warranty
checkpoint-status |  |  | checkpoint | Glazing and external joinery
boolean | bc876715-f6a9-564c-9561-1d7c89d80e5f |  | tickbox | Producer statement for aluminium joinery complying with NZS4211:2008
boolean | fadeb334-2f20-5ae2-9352-9adc092ebe47 |  | tickbox | Producer Statement Construction(PS3): safety glazing in compliance with NZS4211:2008
boolean | 3808f7c7-0067-5a73-9061-86a9ab05b085 |  | tickbox | Producer Statement Design(PS1) from joinery manufacturer
boolean | 68997f0b-f736-56a0-8e25-781c6532cb79 |  | tickbox | Producer statement for fire rated windows confirming compliance with NZS4232
checkpoint-status |  |  | checkpoint | Waterproofing
boolean | da89c4b3-9bdf-5395-b135-60aba1d10c84 |  | tickbox | Producer Statement Construction(PS3): Roof membrane and Manufacturer's product warranty
boolean | 0809f62e-8e8b-5a51-a149-5e7ecf202a28 |  | tickbox | Producer Statement Construction(PS3): Deck Membrane and manufacturer's product warranty
boolean | 3413db5f-b4b2-5db9-990b-869bff985171 |  | tickbox | Producer Statement Construction(PS3): Tanking membrane and manufacturer's product warranty
checkpoint-status |  |  | checkpoint | Roof abseil and fall arrest system
boolean | 2acf23f7-44d0-514a-8a64-c1837c812ffe |  | tickbox | Producer Statement Design(PS1): installation of roof abseil and/or fall arrest system
boolean | f07b5307-fcaa-5155-b8a0-797c011743cb |  | tickbox | Producer Statement Construction(PS3): installation of roof abseil and/or fall arrest system
boolean | 79e42827-6bde-5973-9ff8-a8cea12c95a1 |  | tickbox | Producer Statement Review(PS4): installation of roof abseil and/or fall arrest system
checkpoint-status |  |  | checkpoint | Balustrades
boolean | d607a1d1-3bce-5ee7-9db9-77d4a00acffe |  | tickbox | Producer Statement Construction (PS3) for the balustrade installation
checkpoint-status |  |  | checkpoint | Façade systems
boolean | 7291c91f-21cc-56b2-87db-a3b4df27f561 |  | tickbox | Producer Statement Review(PS4): from council approved façade engineer for façade system
boolean | 1870a01c-d31e-5bdb-82cb-c478fbe1f6cd |  | tickbox | Written report from council approved façade engineer for façade system (supporting the PS4)
boolean | 705dd146-382c-58f7-ad6e-1c7000158bd8 |  | tickbox | Producer Statement Construction(PS3): installation of the façade system
boolean | 30a4cac5-a481-5c2e-9f5d-19862de25f2b |  | tickbox | Façade System Maintenance Manual
boolean | a359c9e7-b152-5a33-8c0d-8a363bf7ce58 |  | tickbox | Warranties/Guarantees from main and sub-contractors
checklist-flat |  |  | checklist | FC - R - Anchor Points - Anchor Point Installation |  |  |  |  | Yes | FC - R - Anchor Points - Anchor Point Installation | c74af52b-a083-4746-b771-0aaf4d8ab4b7
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Anchor point installation completed and acceptable
checklist-flat |  |  | checklist | ST - R - Precast Shell Beam Lintel Installation |  |  |  |  | Yes | ST - R - Precast Shell Beam Lintel Installation | c9748fc9-ca6a-40c8-8a43-d5c66fda77fe
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Shell Beam Lintel Installation completed and acceptable
checklist-flat |  |  | checklist | CST - R - Demolition Consent |  |  |  |  | Yes | CST - R - Demolition Consent | cec2a4b7-1955-4f20-bdf3-5776dc5b7068
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection passed
checkpoint-status |  |  | checkpoint | Summary Sheet - Site inspection records
checkpoint-status |  |  | checkpoint | Summary Sheet - LBP Records
checkpoint-status |  |  | checkpoint | Asbestos - Asbestos Clearance Certificates & PS3
checkpoint-status |  |  | checkpoint | Demolition - PS3
checklist-flat |  |  | checklist | FC - R - RAB Board |  |  |  |  | Yes | FC - R - RAB Board | cf8d5409-7fb0-4d4a-b39a-bff9b3ef487e
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | RAB Board works completed and acceptable
checklist-flat |  |  | checklist | F - R - Crane Piling |  |  |  |  | Yes | F - R - Crane Piling | cfe5e266-4c1a-49e6-8905-d9be4e21b84a
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Crane Piling completed and acceptable
checklist-flat |  |  | checklist | ST - R - Timber Framing |  |  |  |  | Yes | ST - R - Timber Framing | d0dfaf65-0cce-42cc-9a16-bcc436bec1ea
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Timber frame installation completed and acceptable
checklist-flat |  |  | checklist | ST - R - Precast Balcony Installation |  |  |  |  | Yes | ST - R - Precast Balcony Installation | d1bfd838-9fbd-45ab-99be-21f1f07ff3fa
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Joints grouted with Sika 212 and PEF rod.
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Balcony Installation completed and acceptable
checklist-flat |  |  | checklist | RFI |  |  |  |  | Yes | Add RFI Checklist | d36369af-2020-4443-bf69-c01e3739a0ca
checkpoint-status |  |  | checkpoint | RFI status (Pass once responded & all information is attached including RFI & responses)
text | bbd3e477-d66e-4985-917d-66e77fdab337 |  | textbox | Date RFI was issued
text | 30199c1d-fc6f-48df-a70b-de4ce497b888 |  | textbox | Date RFI to be responded by
text | 9169d1b8-2606-4da1-b66e-416cbcd60c33 |  | textbox | Date RFI was responded
boolean | 4d778de3-a159-40fc-bdb6-a3cd2e81b9b7 |  | tickbox | RFI attached
boolean | f1f377fc-930e-4fdd-a553-f5b63fbf788d |  | tickbox | RFI responses attached
checklist-sectioned | 0b275239-7a27-4a76-9a0b-5ec27e0f8e1c |  | checklist | Constructor Audit - Structural Foundations - |  |  |  |  | Yes | Add 01 Constructor Audit (Auckland Council Assessment) - Structural Foundations Checklist (V2) | d6d9a0e5-cc81-4390-9d0c-a3f0eaf128e1
checkpoint-group | 218d3d4f-acaf-4844-8ac5-df77fc7836ec |  | section | Foundations Assessment - Details / Drawings / Documentation
checkpoint-status | 173c7155-87ea-4095-981f-f2981404223e |  | checkpoint | Clearly identify area/element covered in this assessment (Pass once detailed below)
text | 16bc1ae2-6d21-44be-9ceb-88b5cdc52f81 |  | textbox | Date of assessment (format - dd/mm/yyyy)
text | 43ce7fb3-5029-4481-9d01-a0e1394d79ac |  | textbox | Detailed breakdown of element(s) including location and grid references relating to this audit
label | 688abc83-17e1-4ac3-b6ee-aa6fd7c4b947 |  | note | Add description for what work was carried out on the element. Inspector cannot tell if the beam was erected, coated, welded etc
boolean | 47ce8365-010c-40ad-a621-de65eaf47501 |  | tickbox | Attach marked up plan detailing element(s), location and grid references relating to this assessment
checkpoint-status | 69a1ed7f-3899-4fea-b1c1-cdd58931c457 |  | checkpoint | Description of work being undertaken (PASS once all below details are entered)
button | 59717df6-8d3c-4ed3-b547-afffcc04c741 |  | button | Does the work being undertaken comply with the issued building consent or approved minor variations or amendments | Yes, No
text | 2bd35dcd-01ac-4e1c-b9b3-d5a87dddd93b |  | textbox | If "NO" what are the discrepancies? clearly detail here
text | a2fbfe4b-28e9-48c5-bf83-939ffe92cebb |  | textbox | Latest building consent number, stage and amendments (if applicable)
text | 9070dfd6-aa49-42bd-996b-7095a977dc93 |  | textbox | Relevant drawings & revision numbers
boolean | c7f88aa1-b67d-436e-8cda-843af4072fb1 |  | tickbox | Attach all relevant drawings with revision numbers clearly detailed
button | a4e8524a-cc22-4656-8235-2fa928236141 |  | button | Construction drawing revisions match consented drawing revisions | Yes, No
text | a42c5d21-373b-4fdc-b766-db4b919c051a |  | textbox | If "NO" what are the discrepancies? (comment here and attach evidence of discrepancies)
button | f1e863b7-ae74-4df8-9492-9175eb0d5e99 |  | button | Does the installation of this building element compromise any previously assessed/inspected building elements? | Yes, No
label | 5b5b7ce9-036b-4a16-bbf3-40969961fa19 |  | note | Select "NO" if this has been considered & does not compromise any previously assessed/inspected building elements (attach any relevant supporting evidence below)
text | dd7f94fb-492c-4360-8e79-3fb79e93205c |  | textbox | If "YES" explain here (what is compromised, how it it is compromised & how this will be mitigated/managed)
checkpoint-status | 63f11506-d0f7-4089-8aa4-0c552209b4e6 |  | checkpoint | Select "PASS" and progress if all above items have been considered and sufficient supporting documentation attached
checkpoint-group | 42eab481-dd32-407e-911d-dcaff1868884 |  | section | Structural Foundations Assessment - Council / Consultant Summary
checkpoint-status | 574f7d81-b1ab-4577-9c2a-7d4eb7822245 |  | checkpoint | Structural foundations assessment details (Pass once inputted below)
text | 8d5f5e25-fd9b-4efd-90c7-7b8c97e4ce4f |  | textbox | Describe progress of construction since last audit
button | 05616b1e-837e-404f-810d-9f277450dbac |  | button | NEW BC AMENDMENTS - has there been any requirement for a new amendment since the last council audit/inspection | Yes, No
text | e5ccfac7-e9f6-4f36-a0ce-394076867275 |  | textbox | If yes - detail amendment here including status
button | 947db561-2dca-4eb6-949b-d07448e6b5fd |  | button | APPROVED BC AMENDMENTS - have any previously open AMENDMENTS been responded to by Auckland Council since the last audit/inspection | Yes, No, N/A
text | 51eec31d-b808-45ba-9748-defa6ed9d82a |  | textbox | If yes - detail here and ensure latest Building Consent (including amendment) is uploaded into Conqa
button | a4fdaa28-e534-4f77-9318-3003a9066782 |  | button | WIP AMENDMENTS - are there any AMENDMENTS which will maintain a "Work in Progress" status for this audit | Yes, No, N/A
text | e0aad338-b290-4688-9d8e-e034cab77295 |  | textbox | If yes - detail amendment here and provide an update on the status
button | 6d6d4d71-2ec8-4025-9287-b5c82babd0db |  | button | NEW MINOR VARIATIONS - has there been any requirement for a new minor variation since the last council audit/inspection | Yes, No
text | 1ae3d881-14cb-4929-b47f-cb07a23b89a9 |  | textbox | If yes - detail here including status
button | a966e8df-3096-4b45-a85e-7b69f5c61298 |  | button | APPROVED MINOR VARIATIONS - have any previously open minor variations been responded to by Auckland Council since the last audit/inspection | Yes, No, N/A
text | 16b57858-8e01-4645-8941-5fcf3f70fe7c |  | textbox | If yes - detail here and ensure latest status (including approval) is uploaded into Conqa
button | 3943822b-aa3a-4b98-9dfa-41f32a431e08 |  | button | WIP MINOR VARIATIONS - are there any minor variations which will maintain a "Work in Progress" status for this audit | Yes, No, N/A
text | 7608b8e7-8a3e-4e38-9f23-3e50f84da682 |  | textbox | If yes - detail variation here and provide an update on the status
checkpoint-status | 8a938971-1a5f-4b37-8c7b-aec30a9e141d |  | checkpoint | PREVIOUS COUNCIL AUDITS/ INSPECTIONS - Any previous council audit / inspection issues (fails / anomalies) relating to this BC have been addressed & closed out
label | 0dc4de0f-153f-4322-b106-b379f6071242 |  | note | "Pass" if there are no outstanding issues (fails / anomalies) from previous council audits/inspections relating to this Building Consent
label | 00d18b98-50d8-4147-882f-a5a106fea336 |  | note | "Fail" if outstanding issues (fails / anomalies) remain un actioned/closed from previous inspections / audits and provide context
label | 4811cf76-59a5-41f2-af52-6f843b1082f2 |  | note | Prior to selecting "Pass" and confirming there are no outstanding fails / anomalies, ensure these have been appropriately closed out and the appropriate evidence attached HERE & in the appropriate audit/inspection
checkpoint-status | eda74b51-24d0-4550-a2ca-e02a3f945321 |  | checkpoint | Engineer / Consultant Inspection Summary & Observation Closeout
button | d8a1fe6b-31e8-4cdf-bd7d-697dd648ca23 |  | button | Are the relevant engineers / consultants attending site & achieving the correct level of monitoring | Yes, No, N/A
text | 3f0089c3-3659-40c1-b903-d378ae54562d |  | textbox | List all engineers / consultants who have been to site since the last Council audit/inspection & describe all elements/work checked by the engineer
button | 0882353a-49a1-4f47-b603-41ecc54e8ec9 |  | button | Viewed all engineers reports since last audit undertaken & have identified what elements and areas have been checked by the engineer | Yes, No
label | 04909e22-12ac-4d91-b515-2ecf1b85b887 |  | note | "Pass" ABOVE checkpoint if there are no outstanding engineers remedials/observations
label | 081e3c92-6a31-40fe-b2d0-6460e656d3d2 |  | note | "Fail" ABOVE checkpoint if outstanding engineers remedials/observations remain unresolved and provide context
button | 0b9c188e-9144-4b41-8ed2-d233d77a271d |  | button | NEW OBSERVATIONS/REMEDIALS - has there been any new engineer / consultant remedials/observations since the last council audit/inspection | Yes, No
text | 794610ae-9b6e-48d8-b4dd-6630cf2aa04d |  | textbox | If yes - detail here including status
button | 2a886bd5-6ead-4eba-b0fa-d0c9c59990b7 |  | button | APPROVED OBSERVATIONS/REMEDIALS - have any previously open remedial/observations been approved by the appropriate engineer / consultant since the last audit/inspection | Yes, No, N/A
text | fd2ad9b9-4e66-4f55-aa18-b59dc9d8c8eb |  | textbox | If yes - detail here and ensure latest status (including approval) is uploaded into Conqa
button | bf5c2c48-5b8c-424a-925e-0ac0a132b2bc |  | button | WIP OBSERVATIONS/REMEDIALS - are there any remedials/observations which will maintain a "Work in Progress" status for this audit | Yes, No, N/A
text | cf2004b1-3705-4e76-ab6b-c9bef0283569 |  | textbox | If yes - detail here and provide an update on the status
boolean | b756337d-37eb-4ddd-9e1f-7d623729c682 |  | tickbox | All relevant consultant inspections completed since the last Auckland Council audit/inspection attached HERE including any corrective action undertaken with sufficient evidence of close out.
checkpoint-status | da343162-5e24-45ad-bb07-e0e0e8b280d7 |  | checkpoint | ANY OTHER THIRD PARTY CONSULTANTS - Described work / elements checked by others (third party)
text | dad29600-6840-4c76-8aa7-ef7bc79a536d |  | textbox | If applicable, describe any action/remedial items still to be signed off by others
boolean | 5a837a8f-d1f8-4381-802c-27874659e44b |  | tickbox | Any relevant third party consultant inspections completed since the last Auckland Council audit/inspection attached HERE including any corrective action undertaken with sufficient evidence of close out.
label | 3268cafd-9722-46a1-9109-0396b962f0f8 |  | note | If required use this checkpoint to detail and other action/remedial items have been signed off or select "N/A" if there has been no requirement for a third party
checkpoint-group | a7c6e5fa-2292-4a28-bd5b-bc50d461ecf5 |  | section | Main Contractors & Trades QC/QA and supporting documentation
checkpoint-status | f1a04c6a-d7d5-4437-ac51-f7fb01d34c0f |  | checkpoint | General Site Photos / As Builts
label | 58808f5d-3896-4f11-8534-cb4756660a66 |  | note | Attach a minimum of 10 site photos giving an overview of the on site progress relating to this Building Consent since the last audit / inspection
label | ec2941ff-3506-4c89-bc80-89e6a1fe1b5c |  | note | Attach any relevant progressive as builts / mark ups
checkpoint-status | 5f6ba618-6593-49ff-a9c7-23e2537f3ff5 |  | checkpoint | PILING - trade / element applicable to this audit
label | 3632ee01-1688-49b8-9f4b-709cbf6ee106 |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | c144eca8-76cb-442e-9b95-70649250cd41 |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | f5870b1c-56b1-442a-90ad-a34aba029e74 |  | textbox | Overview of progress relating to this trade/element (Piling) since last audit
label | 582bdaf3-0f1d-49b1-a95d-91b8ba38fd3d |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, Pile/post type recorded, Piles/post footing sizes and general layout, concrete batch certs confirming mPa and any additives, reinforcing detail sheets
label | be3a2090-19a1-4a12-b979-abdca2f52d7d |  | note | COMPLIANCE CONSIDERATIONS - PS3, PS4, all reinforcing steel bars/ mesh mill certs or steel grade confirmation from supplier, all reinforcing steel fabricator detail sheets for cages/ bent rebar- must verify rebar sourced from approved supplier, concrete cylinder tests for previous month deliveries
boolean | 21ed294e-0766-4eeb-974b-87074383f43d |  | tickbox | Piling - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status | 3c80b842-2628-4ff1-b5c2-76cb5969b7a8 |  | checkpoint | EXCAVATION (Bulk/Detailed) - trade / element applicable to this audit
label | ff18f01b-e87a-4e3b-b4e2-722ceacf9d10 |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | cee67b87-92e4-4fa6-a130-9b164b3f1593 |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | 4faebaeb-6b9c-4878-a114-7d273891c376 |  | textbox | Overview of progress relating to this trade/element (Excavation) since last audit
label | f06cf420-8cd8-404f-80c7-2cecc2a557bc |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, resource consent considerations, environmental considerations, footing size, batters, soft spots, compaction methodology, heights
label | 4f8967c5-5243-4dfb-bd58-1eb13eef8054 |  | note | COMPLIANCE CONSIDERATIONS - Compaction methodology & results, geotechnical overview, PS4
boolean | 1058a14c-7643-4fbe-9d24-e4b56c731e87 |  | tickbox | Excavation - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status | 58265d0b-d379-4b0a-83cc-de8f5587c2ac |  | checkpoint | PLUMBING/DRAINAGE - trade / element applicable to this audit
label | 065b879a-e1a0-4022-a523-682ca030c047 |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | 75dbfbc3-f535-4f9f-a125-44cbd738206e |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | b0a34c59-bbd1-49a2-9f18-0f925bec6cb9 |  | textbox | Overview of progress relating to this trade/element (Plumbing/Drainage) since last audit
label | 62a6eded-51e5-42f2-8c69-813ea58bd474 |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, Trade details & license, materials, heights / gradients, protection for services (bedding, sleeves, other), tests (water, air or other), consideration for specifics (floor waste gully, HWC overflow etc), backfill methodology
label | a7183597-9690-4fe2-b869-f920f552d7a6 |  | note | COMPLIANCE CONSIDERATIONS - As builts, product conformity, test reports, CCTV, PS3, PS4
boolean | 80a89d5e-58d1-43e1-a8ed-e1cc54b3ce30 |  | tickbox | Plumbing/Drainage - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status | 7db3cc37-b8d6-47cf-824f-ef0d34780cfc |  | checkpoint | UNDERSLAB SERVICES - trade / element applicable to this audit
label | 748fe0d3-632c-429d-bb17-ad5748f5badd |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | 52ad57b6-db07-488b-810d-619359a10da9 |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | e6b68ac0-4a5e-4741-9f38-ee9c0fe474d5 |  | textbox | Overview of progress relating to this trade/element (Underslab Services) since last audit
label | dac9a1bd-be94-4384-b875-3bd28166c789 |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, Trade details & license, materials, heights / gradients, protection for services (bedding, sleeves, other), tests (water, air or other), consideration for specifics, backfill methodology
label | 4d52b766-d446-4c39-ac46-a53e303f8471 |  | note | COMPLIANCE CONSIDERATIONS - As builts, product conformity, test reports, CCTV, PS3, PS4
boolean | f5cfc77c-ce1b-49f4-b570-e644912baa9a |  | tickbox | Underslab Services - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status | ed0606fb-1129-454d-ad46-6837c68be634 |  | checkpoint | TANKING/WATERPROOFING - trade / element applicable to this audit
label | 51c1ef90-34ef-4912-9b0f-6d53c9d4c8bd |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | e408a7de-070f-4bc7-9cab-58245b747162 |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | 157b6e30-8e89-48aa-801f-d3e6f56927a4 |  | textbox | Overview of progress relating to this trade/element (Tanking/waterproofing) since last audit
label | fea58956-c42c-455e-884f-69da0043e271 |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, Trade details & license, materials/system, manufacturer's specifications, substrate, drainage, installation, joints / controll joints, terminations, protection, backfill methodology
label | 55ee828a-d779-4669-a3b3-5c33820fe71b |  | note | COMPLIANCE CONSIDERATIONS - manufacturer's warranty, workmanship warranty, PS3, PS4
boolean | a1192a27-0378-4fff-8261-7242c92c906c |  | tickbox | Tanking/waterproofing - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status | 72532446-79ee-4792-8968-ba065ae3f717 |  | checkpoint | FORMWORK - trade / element applicable to this audit
label | 5139fa67-1b55-46f6-93c7-658f3b6c432b |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | 44cc05f8-0044-4409-b7e2-c4d5160a9f84 |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | 52f9a79d-c1a9-43b8-b6c4-e3ac58486094 |  | textbox | Overview of progress relating to this trade/element (Formwork) since last audit
label | b5eedf6c-42e2-48dd-8e21-0fa2f2083fb0 |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, setout, heights, stability/bracing, DPM / terminations
boolean | 6231a682-7779-4a55-956e-748f9e79bdda |  | tickbox | Formwork - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status | 39390c4f-1745-440c-8d97-29fca01cf584 |  | checkpoint | REINFORCING - trade / element applicable to this audit
label | b0f99f5a-65ae-4ea8-8672-ad5f219bf5ff |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | 0cb69b85-a785-4954-a575-7096ab34ae55 |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | e3979441-64b1-4df4-9821-24adc90a470a |  | textbox | Overview of progress relating to this trade/element (Reinforcing) since last audit
label | e36913e5-6787-425f-b2c4-7f2ecee2164f |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, detail sheets, reo mill certs, size, grade, laps, bends, cover, starters (size & location), cast in items
label | e0be6c8c-d28d-4a98-85d6-95df14929328 |  | note | COMPLIANCE CONSIDERATIONS - PS3, PS4, all reinforcing steel bars/ mesh mill certs or steel grade confirmation from supplier, all reinforcing steel fabricator detail sheets for cages/ bent rebar- must verify rebar sourced from accredited supplier
boolean | 58dc22df-0ca1-4df9-9ad0-a627dd9409f7 |  | tickbox | Reinforcing - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status | 30d468a1-8713-4e86-975d-814081259e51 |  | checkpoint | CONCRETE PLACEMENT - trade / element applicable to this audit
label | 1c0a11ea-7eef-4190-9585-c6e123ccf93f |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | 67de6868-5a9e-4c4b-a345-81c493fe318a |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | 0f533a9f-1c39-4139-afb8-242474b4b763 |  | textbox | Overview of progress relating to this trade/element (Concrete Placement) since last audit
label | 9c058e1f-e58d-44c8-b206-5a90dad9b642 |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, approval, mPa, slump tests, vibration, finish, curing, concrete batch certs confirming mPa and any additive
label | aa098653-bd18-4f5f-a722-befba1852cbc |  | note | COMPLIANCE CONSIDERATIONS - PS3, PS4, concrete cylinder tests for previous month deliveries (7, 14 and/or 28 days as required)
boolean | 11082fd9-9038-4cff-b3c0-dedce5c79164 |  | tickbox | Concrete Placement - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status | 8285ea99-6fd9-427d-aeec-f13035c2f726 |  | checkpoint | BLOCKWORK INC REINFORCING - trade / element applicable to this audit
label | bea44542-5e95-4b71-b2b3-9830cec3435a |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | 7a20cba0-22c2-4c82-afd5-0427421c4c2f |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | d6fd772d-7668-4bb1-a41f-d7c6c5800973 |  | textbox | Overview of progress relating to this trade/element (Blockwork Inc Reinforcing) since last audit
label | 37d01b08-1758-4c36-ab0a-b503636608c0 |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, compliance method, masonry grade, size, setout, level and plumb, heights, wash outs, stretcher or stack bond, Mortar joint sizes (7-13mm), tooled to match proposed finish, bond beams, control joints, Approval, mPa, slump tests, vibration, finish, sealer, concrete batch certs confirming mPa and any additive
label | 96ed8f23-e064-42db-8954-42fc5d1fdae6 |  | note | COMPLIANCE CONSIDERATIONS - PS3, PS4, all reinforcing steel bars/ mesh mill certs or steel grade confirmation from supplier, all reinforcing steel fabricator detail sheets for cages/ bent rebar- must verify rebar sourced from approved supplier, concrete cylinder tests for previous month deliveries (7, 14 and/or 28 days as required)
boolean | 1ae7de1b-00e9-477d-87f1-d49d4f1b6327 |  | tickbox | Blockwork Inc Reinforcing - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status | 6ecbcd7f-de3d-4456-a7a9-c871446bd324 |  | checkpoint | PRECAST MANUFACTURE - trade / element applicable to this audit
label | 8586011d-cb9e-4b6c-b2d0-0fb3e04a6a0d |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | 64deb068-a483-46bc-a67c-535a40c3d73a |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | 08fa7b67-37c8-49c3-951b-f1e30068bfa5 |  | textbox | Overview of progress relating to this trade/element (Precast Manufacture) since last audit
label | b91f7865-68c7-49ca-acf6-89d34fc6c59d |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, mPa, slump tests, vibration, finish, curing, concrete batch certs confirming mPa and any additive, detail sheets, reo mill certs, size, grade, laps, bends, cover, inserts / cast in items, starters (size & location)
label | eea7e0c0-26db-4867-b73b-d5db56dc5895 |  | note | COMPLIANCE CONSIDERATIONS - PS1, concrete test results (7, 14 and/or 28 days as required), mill certs & steel grade confirmation from accredited supplier, PS3, PS4
boolean | e0f5ce13-c7a0-47fa-b821-7d83e734ebb4 |  | tickbox | Precast Manufacture - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status | 92ec2c60-c07b-47ae-944e-0cf961f032c6 |  | checkpoint | PRECAST INSTALLATION - trade / element applicable to this audit
label | 39a26094-3ea9-40a5-b5ed-13f5d5dc522a |  | note | "PASS" if this trade/element is applicable to this audit and complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | 9d4a1461-10a5-4390-be21-9f5e3e9869cc |  | note | "N/A" if this trade/element is not applicable to this audit, comment below as to whether the trade/element is N/A, yet to start or completed
text | e2e2a16e-2627-47a1-92f2-43ffffd34a13 |  | textbox | Overview of progress relating to this trade/element (Precast Installation) since last audit
label | cbbfde7f-9738-4bc1-a0f6-6658ac67e6fc |  | note | ON SITE KEY CONSIDERATIONS - Design & specifications, setout, precast starters (size & length), seating, bracing/propping, alignment/plumb/level, joints/connections
boolean | de6fae1d-de48-4945-9656-4f502bf8c717 |  | tickbox | Precast Installation - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status | b5706d9d-4c39-4ebd-b32f-4bcae199e83d |  | checkpoint | Any other trade / element - trade / element applicable to this audit
label | 0ffa3d08-7ec3-497d-a4d0-52adc829463c |  | note | "PASS" and detail below if any other trade/element is applicable to this audit. Complete the below progress overview along with attaching supporting QC/QA documentation and consideration for compliance requirements.
label | 16bffadb-8e27-4cfa-85e2-a90b51b52a41 |  | note | "N/A" if no other trade/element is applicable to this audit, comment below if required
text | 82d6aa26-2790-46e7-a81e-bdd8aab10e8d |  | textbox | Overview of progress relating to this trade/element since last audit
boolean | fe057607-efce-467c-a00d-7f1c1ed6a166 |  | tickbox | Any other trade / element - main contractor / trade supporting QC/QA documentation attached below with consideration for any compliance requirements
checkpoint-status | 176e1249-eb8b-4f1b-871b-b787c4f166b9 |  | checkpoint | Select "PASS" and notify Auckland Council if all above items have been considered and sufficient supporting documentation attached
text | d56edffd-799a-470c-bd63-1684cfbc1c05 |  | textbox | Date this Audit report was sent to Auckland Council
text | d0feac1e-23b9-4d05-be41-03999f2a5053 |  | textbox | Inspector(s) from Auckland Council who this was sent to (including email address)
checkpoint-group | 7b26cac6-abab-4005-b8d3-2fdc3f9ebf17 |  | section | Close out of Audit
checkpoint-status | 99c2a057-f5dd-4ff8-bc96-4ba40fb375b8 |  | checkpoint | Close out of Audit - Pass once Council Audit is completed and attached with any corrective actions detailed and closed out below
text | 3fe460f9-75bb-43e7-803b-4b62448a5ca6 |  | textbox | Date Auckland Council Inspector sent receipt / audit response
boolean | f3681205-aec3-40fe-bf12-4ebabee3d18e |  | tickbox | Council Audit completed and attached
text | d568c5a7-2746-45b1-a80b-a44eb5e0f04f |  | textbox | As detailed in this Council Audit or discussed - next Audit will occur on
checkpoint-status | 48d8294e-6aed-4fcb-827c-3e29310e93df |  | checkpoint | Any Relevant Observation Closeout evidence attached here if applicable (Pass once completed)
text | 39255968-2939-4146-9a76-423e07e03822 |  | textbox | Corrective actions required before next audit
label | 7599ddd3-e408-4a53-8f93-fafa888e15a4 |  | note | These should include a summary list of close outs still to be addressed from any of the above line items and comments made in the council audit or any outstanding from previous audits/inspections relating to this building consent
checklist-flat |  |  | checklist | FC - R - Windows and Sliders |  |  |  |  | Yes | FC - R - Windows and Sliders | d81e2a60-9ef9-4101-88eb-2b76f6de5058
checkpoint-status |  |  | checkpoint | Check clearance around opening min 6mm/ max 18mm
checkpoint-status |  |  | checkpoint | Packers to be correctly used and set back to allow continuous air seal
checkpoint-status |  |  | checkpoint | Check air seal is provided at the rear of the window reveal
holdpoint |  |  | signoff | Raise remedial/ request signoff
checkpoint-status |  |  | checkpoint | Window and slider installation completed and acceptable
checklist-flat | e0acbb7f-6d8d-41c7-9baf-09c6fec35a66 |  | checklist | Mechanical & Hydraulic Consent - |  |  |  |  | Yes | Add Mechanical & Hydraulic Consent Checklist | d95b2d45-cd10-4ce5-bc9a-d94f40526957
checkpoint-status | 45f40e63-cf5d-45b4-a0b3-64e9aad889c6 |  | checkpoint | Energy works certificate – Gas
holdpoint | fa5622f5-b110-4387-9a5c-709e4a4a2f80 |  | signoff | Request Signoff
checkpoint-status | 7d70cbe0-0400-4c18-81a7-2d5b9adb237b |  | checkpoint | Energy works certificate – Electrical
holdpoint | a180673e-69b8-4c02-b915-f2abcda29676 |  | signoff | Request Signoff
checkpoint-status | 054c959c-81df-41be-ac00-b580068ac6f8 |  | checkpoint | Producer Statement construction (PS3) fire stopping of fire rated walls, floors & ceilings
holdpoint | 73371a0d-d450-47c7-81e8-18fb393dffcd |  | signoff | Request Signoff
checkpoint-status | 89ea9e49-40b1-46f2-bfd4-a8c9fdaec452 |  | checkpoint | Producer Statement construction (PS3) heating ventilation & air conditioning (HVAC)
holdpoint | d716535e-e18b-4d65-933d-ddb79ff117b5 |  | signoff | Request Signoff
checkpoint-status | 27c6f103-898d-4951-bf6f-99f17854274c |  | checkpoint | Producer Statement construction (PS3) – Proprietary product installation
holdpoint | 6a868e47-584c-48ad-9c27-fec42b55e18e |  | signoff | Request Signoff
checkpoint-status | a2104329-9cb1-419a-bebf-7282ed604b32 |  | checkpoint | Producer Statement construction (PS3) waste water sump pumps
holdpoint | 5bb25590-ca62-4155-9959-94971442ef3a |  | signoff | Request Signoff
checkpoint-status | 5a459cca-4aad-4adf-946d-0aa49eb616cd |  | checkpoint | All documents received, reviewed, attached and approved
checkpoint-status | 1f0af62f-ed95-4888-8b30-34fcce15a0a6 |  | checkpoint | Code Compliance Certificate issued, approved and attached
checklist-flat |  |  | checklist | FC - R - Cladding Sealant |  |  |  |  | Yes | FC - R - Cladding Sealant | ddfe41cb-0178-47d6-b417-7b6f81808a7b
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Cladding sealant completed and acceptable
checklist-flat |  |  | checklist | FC - R - Ecoply Board |  |  |  |  | Yes | FC - R - Ecoply Board | de09eece-7a97-4802-b257-17298195c49d
checkpoint-status |  |  | checkpoint | Fixing and spacings checked in accordance with manufacturers specs.
checkpoint-status |  |  | checkpoint | Bracing checked and accurate
checkpoint-status |  |  | checkpoint | Penetrations and punctures sealed with flashing tape
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Ecoply board installation completed and acceptable
checklist-flat | 19fd1ebe-5bbd-42d3-8ee9-3ee29c89f922 |  | checklist | Structural Consent - |  |  |  |  | Yes | Add Structural Consent Checklist | e63a81a2-d311-4522-9218-fbc8fd357b69
checkpoint-status | bfe193a0-5d9d-4ec1-9bdc-41cd5b4c8d2f |  | checkpoint | Producer Statement Construction Review (PS4) Geotechnical
holdpoint | ff99e6da-3ae4-40b4-b429-d6221639fa31 |  | signoff | Request Signoff
checkpoint-status | 5efb67f3-b6cf-4bed-bffc-f1817ffe57ff |  | checkpoint | Producer Statement Construction Review (PS4) Compaction of Hard-fill
holdpoint | 6ce99294-88be-41fc-9610-9682287c4599 |  | signoff | Request Signoff
checkpoint-status | b070927d-7d46-49ac-bb08-273e645f10d1 |  | checkpoint | Producer Statement Construction Review (PS4) Drain Bridging
holdpoint | e1f47f41-f52c-44c5-ae5a-57c5264a8722 |  | signoff | Request Signoff
checkpoint-status | 03e50b07-1b3e-4a18-9899-405603a3670e |  | checkpoint | Producer Statement Construction Review (PS4) Engineers Observation
holdpoint | 06b8a07c-8be9-4fbe-9fe1-9df6f0bea179 |  | signoff | Request Signoff
checkpoint-status | ecb9d7d2-1302-40f6-844e-8bb360ca5617 |  | checkpoint | Producer Statement Construction (PS3) Sub-Soil Drains
holdpoint | dbaaa481-f154-4a2d-b1ed-d20c8a1d027a |  | signoff | Request Signoff
checkpoint-status | c4853615-7841-46b6-bdf1-8824dcf70d94 |  | checkpoint | Producer Statement Construction Review (PS4) Ground Anchors
holdpoint | e02179b6-0239-4878-be12-d2a3d6370e1f |  | signoff | Request Signoff
checkpoint-status | 4f032279-4dde-4583-b7f5-e76ebb400f19 |  | checkpoint | Producer Statement Construction (PS3) ‘Rib & In-fill’ Floor Slab
holdpoint | 64a611ed-131f-417a-a7ce-3977bb4426cf |  | signoff | Request Signoff
checkpoint-status | e3211772-328b-4313-bf35-6bba212b4680 |  | checkpoint | Producer Statement Construction (PS3) ‘AFS Logicwall’
holdpoint | acd04e56-5dff-4b74-bd07-f96b0922fa87 |  | signoff | Request Signoff
checkpoint-status | d8a5a48d-4073-49c9-832c-84e7cf9082af |  | checkpoint | Producer Statement Construction Review (PS4) ‘AFS Logicwall’
holdpoint | 745d2956-d0f8-41d8-b7b0-9f16144a2b54 |  | signoff | Request Signoff
checkpoint-status | 0d5c956c-eb3f-46df-a75b-4d2d22418505 |  | checkpoint | Producer Statement Construction Review (PS4) Type A or B Masonry
holdpoint | 1f161a53-3624-46b5-8be1-dbfcd6bbdb9e |  | signoff | Request Signoff
checkpoint-status | ba97cea3-ac50-4c42-a657-2bd30f13e8b6 |  | checkpoint | Producer Statement Design (PS1) Precast and Pre-Stressed Concrete
holdpoint | 6eba2c72-53fc-433d-9530-059f1455bbef |  | signoff | Request Signoff
checkpoint-status | 02517a0d-240a-40e4-9dee-dc06e8593f60 |  | checkpoint | Producer Statement Construction (PS3) Precast and Pre-Stressed Concrete
holdpoint | aedf4278-43bb-46e4-864d-8da39346ad15 |  | signoff | Request Signoff
checkpoint-status | 15c49389-4808-40b4-95ac-99a2752cb1bf |  | checkpoint | Producer Statement Construction Review (PS4) Precast and Pre-Stressed Concrete
holdpoint | e50e2123-19cb-4dba-86d4-c0bc78d0e2c5 |  | signoff | Request Signoff
checkpoint-status | 5ac370df-2981-42ae-bd32-57c75cd1c261 |  | checkpoint | Producer Statement Construction (PS3) Site Welding
holdpoint | 0d0749bf-631f-49e9-a68c-1f049622a5cd |  | signoff | Request Signoff
checkpoint-status | d0dd9381-5530-4de6-a35a-44b0d911ad48 |  | checkpoint | Inspection and Test Plan (ITP) structural steel welding
holdpoint | d787a328-27d0-41a2-af59-ed7bb02c7dd0 |  | signoff | Request Signoff
checkpoint-status | 6f00bf8e-833c-430b-8821-351329187b02 |  | checkpoint | Producer Statement Construction (PS3) Corrosion Protection
holdpoint | 92cbd0bd-ea5b-41d6-b8fa-ea94a7f71df1 |  | signoff | Request Signoff
checkpoint-status | 7c26fec9-fa49-41cb-a016-98d2ce1767da |  | checkpoint | Producer Statement Construction (PS3) Fire Protection – Intumescent Coatings to Structural Steel
holdpoint | a5d48877-af98-45c1-ab2b-c80853500bce |  | signoff | Request Signoff
checkpoint-status | 3fd6ac64-fabe-4cdc-851d-0f098c77f979 |  | checkpoint | Producer Statement Construction (PS3) Fire Stopping of Fire Rated Walls, Floors & Ceilings
holdpoint | cd69367e-fad2-4e1a-a9cb-b004cffbcdec |  | signoff | Request Signoff
checkpoint-status | aeeddbc7-d227-4e2f-9b44-cd6054267dc2 |  | checkpoint | Producer Statement Construction (PS3) Waterproofing Membrane
holdpoint | 393a796b-6d49-48c4-8c84-0c4eb46401ac |  | signoff | Request Signoff
checkpoint-status | d2335c96-c969-41a4-9fb5-86cf7687990e |  | checkpoint | Product Warranty – Waterproof Membrane
holdpoint | 4637180a-94aa-4b94-a0fe-3f9a1ff5944e |  | signoff | Request Signoff
checkpoint-status | 9aaa8dc1-9082-4c29-8186-a428080b1a7e |  | checkpoint | Producer Statement Construction (PS3) – Proprietary Product Installation
holdpoint | d903c426-e394-47d9-bf23-2589f2b6bc20 |  | signoff | Request Signoff
checkpoint-status | e707dacb-eb35-4a0e-bbcc-7d8e7735c416 |  | checkpoint | Surveyor’s Certificate – Siting
holdpoint | 7a3f8cca-dacd-454a-bc4c-9164b1962c12 |  | signoff | Request Signoff
checkpoint-status | d9ced028-7b0a-4cef-9cf9-87981bb30de7 |  | checkpoint | Surveyor’s Certificate – Floor Level
holdpoint | bad334a4-a008-4ef7-a151-ba387002feaf |  | signoff | Request Signoff
checkpoint-status | e8cb2961-2f91-4600-9090-6ed06d8a648c |  | checkpoint | All documents received, reviewed, attached and approved
checkpoint-status | 1a3a04aa-b4af-45aa-a302-b06d3486552f |  | checkpoint | Code Compliance Certificate issued, approved and attached
checklist-flat | 7ba945b0-3768-4f3a-b697-f291e5567fe3 |  | checklist | Council Inspection - |  |  |  |  | Yes | Add Council Inspection Checklist | ecdd35c4-1ac8-4826-9a38-360e4c30a450
checkpoint-status | f79e79a1-ac68-492e-a42f-46b64162e53b |  | checkpoint | Inspection completed, attached and any relevant observations closed out (Pass once all information is attached including observations with evidence of closeout)
text | e716f58a-4420-4e11-91ae-f4fef0f7ba87 |  | textbox | Date of inspection:
text | 78d9159e-0896-4188-a542-fa6b1bf43aaa |  | textbox | Inspection Type Code:
text | 6931f74e-964b-42b5-905c-440c2ce0001a |  | textbox | Area inspection relates to
select | ca58c4ad-f5b3-41c0-ae49-ce6c1c3289f9 |  | dropdown | Inspection Outcome | Pass,Fail,Partial Pass,N/A
boolean | d24858c1-85f5-44b8-99c0-818a707a7f19 |  | tickbox | Council inspection attached
holdpoint | ba0deaef-ffd8-404a-8770-0053f4c71b07 |  | signoff | Raise Remedial / Request Signoff
checkpoint-status | 1d0db66b-778c-4d25-a10e-22d444c7d7dd |  | checkpoint | All Relevant Observation Closeout evidence attached here if applicable (Pass once completed)
text | 659f0de8-c7a9-45fe-9851-606ecd798dd2 |  | textbox | Outstanding Information Required
checklist-flat |  |  | checklist | ST - R - Blockwork |  |  |  |  | Yes | ST - R - Blockwork | efb3952b-ac29-477f-827b-fa9171e68220
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Blockwork walls completed and acceptable
checklist-flat |  |  | checklist | FC - R - Exterior Timber Framing |  |  |  |  | Yes | FC - R - Exterior Timber Framing | f27b0d7b-792d-4e68-a113-974ded57198f
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / RequeFC Signoff
checkpoint-status |  |  | checkpoint | Exterior Timber Framing works completed and acceptable
checklist-flat |  |  | checklist | CST - R - Restricted Building Works Consent |  |  |  |  | Yes | CST - R - Restricted Building Works Consent | f8a3d916-aa25-4374-8dec-7475fddbdd40
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Record of works
boolean | 57366799-6a74-5176-be03-591c3c69452e |  | tickbox | Foundations
boolean | 3e730d6e-2a17-5beb-beb1-27df771161f6 |  | tickbox | Slab or subfloor framing
boolean | a70bc945-0728-576d-a298-6ae1aad561cf |  | tickbox | Blockwork
boolean | d1c4f3e2-2a7c-544f-98be-9fd00d917819 |  | tickbox | Walls
boolean | d94f357f-e048-5152-9949-83694fefc2db |  | tickbox | Roof
boolean | 3ca0f28b-8705-506f-88b3-4ff61667a6a0 |  | tickbox | Columns and Beams
boolean | 5dc1a8e9-c9fc-55c6-92df-ef05421c4b2d |  | tickbox | Bracing
boolean | b2b6e619-f334-5ac0-ac97-3d3c26a04648 |  | tickbox | Damp proofing
boolean | d190e9ff-428a-5ba5-b6d8-67dfbbfb9812 |  | tickbox | Roof cladding or roof cladding system
boolean | cacac8e9-1086-537f-a3aa-7d47777881e1 |  | tickbox | Ventilation system
boolean | f37c071c-c09a-5932-8292-ad92b3fab619 |  | tickbox | Wall cladding or wall cladding system
boolean | 14121af4-825f-5ef5-aad6-4f2ae8d14f18 |  | tickbox | Waterproofing
checkpoint-status |  |  | checkpoint | Record of warranties
checklist-flat |  |  | checklist | CST - R - Council Inspection |  |  |  |  | Yes | CST - R - Council Inspection | f9974d6e-a26b-40e6-89d1-83d632bcf129
checkpoint-no-status |  |  | checkpoint | Inspection Details:
text | 1149179f-81ad-5cba-8de8-324a456b5a88 |  | textbox | Date of Inspection
text | 28848b5d-040a-5ec2-a591-ee20ee95eb11 |  | textbox | Type of Inspection
text | 55cc5059-368c-5e51-8aff-6dfc02f18621 |  | textbox | Area Inspection relates to
select | 5d7bc071-d3c2-51e1-ad6f-30eff85b88e6 |  | dropdown | Inspection outcome | Pass, Partial Pass, Fail
boolean | 19d7b003-8b88-52ba-9610-c844c23ca6d3 |  | tickbox | Council inspection attached
checkpoint-status |  |  | checkpoint | Relevant Observation Closeout evidence attached below if applicable (pass once completed)
text | dd733476-53e8-5f59-91a2-ae466c28a332 |  | textbox | Failed comments and Required Action