## Breakdown
Miriam Corban(Marin) | Tire 1 | Tire 2 | Tire 3
Building 01
Entrance Ramp
|  |  | Concrete Pour | Prepopulate | Concrete Pour
|  |  | Compliance documents | Prepopulate | Compliance documentation

## Checklist
Order | Type | Name
201000 | checklist-flat | CST - S - Completion Documents
201001 | checkpoint | All relevant Compliance Documentation completed and attached above
201002 | bool | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
201003 | label | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
201004 | holdpoint | Request Signoff
34000 | checklist | ST - S - Concrete Pour
34001 | section | Pour Details
34002 | checkpoint | Pour details entered
34003 | text | Area to be poured:
34004 | text | Date of pour:
34005 | checkpoint | Latest drawings available, checked and referenced
34006 | section | Formwork and Embedded Items
34007 | checkpoint | Formwork - location, height, falls and dimensions checked and accurate
34008 | checkpoint | Service penetrations formed correctly and locations checked/correct
34009 | checkpoint | All surfaces correctly prepared (e.g joints to existing concrete, release agent to formwork etc)
34010 | checkpoint | Any control joints/ stop ends installed accurately and correctly braced
34011 | section | Reinforcing
34012 | checkpoint | Size and type correct to specification
34013 | checkpoint | Reinforcing spacing and location correct
34014 | checkpoint | Specified covers checked/correct
34015 | checkpoint | Splice laps checked/correct
34016 | checkpoint | All couplers installed correctly (if reid bar couplers have been used, has epconC8 epoxy been used as specified)
34017 | bool | Appointment with the engineers confirmed (Enter date & time of the appointment)
34018 | bool | Reidbar – coupler and flange nut installations are inspected by the MV Engineer
34019 | checkpoint | IMBMS couplers testing carried out for Village Podiums in the form of tensile testing in accordance with NZS3101.1.2006 and results acceptable
34020 | checkpoint | All starter bars are installed correctly (location, size and spacing )
34021 | checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
34022 | checkpoint | Welding certificates sited and attached
34023 | checkpoint | Mill certificate reviewed, attached and approved
34024 | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
34025 | section | Pre-Pour Completion (Approval to pour)
34026 | checkpoint | Waterproofing elements have been correctly installed and checked
34027 | checkpoint | Relevant service requirements completed (locations checked and accurate)
34028 | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
34029 | checkpoint | Ryman inspection completed - Approval given to pour concrete
34030 | section | Concrete Supplier Specifics
34031 | checkpoint | Concrete Supplier details entered
34032 | text | Supplier Name:
34033 | text | Specified concrete strength: | mPA
34034 | text | Concrete strength ordered: | mPA
34035 | text | Concrete quantity ordered: | m3
34036 | button | Test blocks booked | Yes, No, N/A
34037 | checkpoint | All concrete dockets photographed/ attached
34038 | checkpoint | Concrete strength test reports attached and required concrete strength achieved
34039 | section | Placement Method
34040 | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
34041 | checkpoint | Heights and falls checked/confirmed before placement
34042 | button | Is the cover correct to specification | Yes, No, N/A
34043 | checkpoint | Heights and falls checked/ confirmed after placement
34044 | checkpoint | Any curing compound applied correctly
34045 | checkpoint | Concrete placement completed - specified level of finish achieved
34046 | section | Post Pour Checks/Sign Off
34047 | checkpoint | Any remedial work completed
34048 | holdpoint | Raise remedial/ Request Signoff
34049 | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached