## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Precast Wall Bracket Installation |  |  |  |  | Yes | Precast Wall Bracket Installation | 2f05486f-fc33-455d-9710-439208d994f7
checkpoint-status |  |  | checkpoint | Bracket correct size as per drawing
checkpoint-status |  |  | checkpoint | Cast in weld plate in correct position
checkpoint-status |  |  | checkpoint | Adequately braced and braces to be tagged
checkpoint-status |  |  | checkpoint | Bracket installed in correct position, plumb and level
checkpoint-status |  |  | checkpoint | Welding inspected and correct as per drawing
checkpoint-status |  |  | checkpoint | Paint repair completed
checkpoint-status |  |  | checkpoint | Bracket installation completed correctly (checked location & level)
checklist-sectioned |  |  | checklist | Concrete Pour - Without Reo |  |  |  |  | Yes | Concrete Pour - Without Reo | 3797f589-4a6b-49fe-9f62-d20c60820cc5
checkpoint-group |  |  | section | Pour Details
checkpoint-status |  |  | checkpoint | Pour details entered
text | 8fef1edd-f45e-56e1-b67f-00b25e88950f |  | textbox | Area to be poured:
text | dda5fb25-85d2-5192-887c-0c4ad6b095a4 |  | textbox | Date of pour:
checkpoint-status |  |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-group |  |  | section | Formwork and Embedded Items
checkpoint-status |  |  | checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint-status |  |  | checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint-status |  |  | checkpoint | All surfaces correctly prepared (e.g joints to existing concrete, release agent to formwork etc)
checkpoint-status |  |  | checkpoint | Any control joints/ stop ends installed accurately and correctly braced
checkpoint-group |  |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status |  |  | checkpoint | Waterproofing elements have been correctly installed and checked
checkpoint-status |  |  | checkpoint | Relevant service requirements completed (locations checked and accurate)
checkpoint-status |  |  | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint-status |  |  | checkpoint | Ryman inspection completed - Approval given to pour concrete
checkpoint-group |  |  | section | Concrete Supplier Specifics
checkpoint-status |  |  | checkpoint | Concrete Supplier details entered
text | def97268-c8e1-5ecd-8e9a-54903752cff3 |  | textbox | Supplier Name:
text | 357daae6-e2b0-57bf-bf1d-8ed2e3e0fd08 |  | textbox | Specified concrete strength:
text | 207d7ec9-de6c-5098-b33f-54e6ed439c58 |  | textbox | Concrete strength ordered:
text | e3afd4a5-972b-514b-9c4a-258ac058c62f |  | textbox | Concrete quantity ordered:
button | 4898ce65-3feb-5adf-98fc-74e65a689699 | DataPoint is missing 'button' values | button | Test blocks booked
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-group |  |  | section | Placement Method
checkpoint-status |  |  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
checkpoint-status |  |  | checkpoint | Heights and falls checked/confirmed before placement
button | 60f2e4b6-36ce-5af1-a0cc-da6d22a31314 | DataPoint is missing 'button' values | button | Is the cover correct to specification
checkpoint-status |  |  | checkpoint | Heights and falls checked/ confirmed after placement
checkpoint-status |  |  | checkpoint | Any curing compound applied correctly
checkpoint-status |  |  | checkpoint | Concrete placement completed - specified level of finish achieved
checkpoint-group |  |  | section | Post Pour Checks/Sign Off
checkpoint-status |  |  | checkpoint | Any remedial work completed
holdpoint |  |  | signoff | Raise remedial/ Request Signoff
checkpoint-status |  |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checklist-flat |  |  | checklist | Service Nogs Toilet |  |  |  |  | Yes | Service Nogs Toilet | 39871357-b4e3-404a-af86-5f232a7d4b94
checkpoint-status |  |  | checkpoint | Wall Vanity nogs installed
checkpoint-status |  |  | checkpoint | Handrail and Toilet roll holder Nogs installed
checklist-sectioned |  |  | checklist | Service Nogs Bathroom |  |  |  |  | Yes | Service Nogs Bathroom | 3df2b542-3475-4d9e-b771-3702d09f7f89
checkpoint-group |  |  | section | Bathroom
checkpoint-status |  |  | checkpoint | Mirror cabinet nogs installed
checkpoint-status |  |  | checkpoint | Wall Vanity nogs installed
checkpoint-status |  |  | checkpoint | Toilet: Handrail nogs Installed
checkpoint-status |  |  | checkpoint | Shower: Handrails nogs (3 areas) installed
checkpoint-status |  |  | checkpoint | Wall Mounted Heater nog installed
checkpoint-status |  |  | checkpoint | Towel rail nogs installed
checkpoint-status |  |  | checkpoint | Shower head nog installed
checkpoint-status |  |  | checkpoint | Shower mixer nog installed
checkpoint-group |  |  | section | Laundry
checkpoint-status |  |  | checkpoint | Dryer nogs installed
checkpoint-status |  |  | checkpoint | Cupboard nogs installed
checklist-sectioned |  |  | checklist | Formwork Slab - |  |  |  |  | Yes | QA - Formwork Slab Checklist (V2) | 6024662a-34e2-42c9-bff1-9b79fd9bf742
checkpoint-group |  |  | section | Prestart Checks
checkpoint-status |  |  | checkpoint | Site conditions acceptable
text | bd093d8c-30b1-4606-a01c-87bf0611056e |  | textbox | Start Date
checkpoint-group |  |  | section | Pre Pour
checkpoint-status |  |  | checkpoint | Pour Details
text | c56b76ce-8218-4659-81a6-5ef397ab5d15 |  | textbox | Date of Pour
text | c838605c-aa66-403c-9ae7-913ad147ab6e |  | textbox | MPA
text | ac4d2fb7-6b5d-4239-b3a8-9f727d74a871 |  | textbox | Description
text | be7c45f2-1f28-4ff3-aaeb-ac60f4c1effb |  | textbox | Concrete Ordered
text | c9f6488b-aba9-489f-8fae-c4936bb97a32 |  | textbox | Area
text | f5f30a35-e9d9-4b53-be2f-a9775eafc9ac |  | textbox | Concrete Volume
checkpoint-status |  |  | checkpoint | Working off correct drawing?
text | d0bd036f-6dd2-4552-86a7-db3749478400 |  | textbox | Drawing revision Number
boolean | 693af552-8482-4cb6-850c-26fb9bbd896e |  | tickbox | Marked up drawings
checkpoint-status |  |  | checkpoint | Dimension, Gridlines & R.Ls
text | 79f7c9a4-128a-42f5-883e-3fc2c007df00 |  | textbox | R.L
checkpoint-status |  |  | checkpoint | Correct dimensions
checkpoint-status |  |  | checkpoint | Formwork cleaned, oiled and braced sufficiently
checkpoint-status |  |  | checkpoint | Penetrations located and checked
checkpoint-status |  |  | checkpoint | Cast in items located and checked
checkpoint-status |  |  | checkpoint | Correct for specified finish
checkpoint-status |  |  | checkpoint | Propping as per design
checkpoint-status |  |  | checkpoint | Access for pouring
checkpoint-status |  |  | checkpoint | 2 vibrators in working order
checkpoint-status |  |  | checkpoint | Reinforcement - any cover issues?
checkpoint-status |  |  | checkpoint | Site instructions captured
checkpoint-status |  |  | checkpoint | Engineer informed of pour
checkpoint-status |  |  | checkpoint | Council inspector notified
checkpoint-status |  |  | checkpoint | Waterproofing
checkpoint-group |  |  | section | Pour
checkpoint-status |  |  | checkpoint | MPA correct
text | 264991d9-759c-46f6-b26e-103faee87d2b |  | textbox | MPA
text | 77c7f148-9d8a-454d-add1-47088ffa8dfc |  | textbox | Start time:
text | 3d1d8ba8-3cc0-4ca8-b471-327ac9d86535 |  | textbox | Concrete Used
text | d9fd804d-e1a1-4534-bc56-d9e26888f874 |  | textbox | Placed by:
text | ae4dc26e-ea93-417b-a8cf-05aa84209950 |  | textbox | Weather (Please specify conditions
checkpoint-status |  |  | checkpoint | Docket attached
text | 38fe3a21-5b9f-476c-be8d-03abba69d4c6 |  | textbox | Docket Number - Docket attached
checkpoint-status |  |  | checkpoint | Vibration
checkpoint-status |  |  | checkpoint | As per specified finish
checkpoint-status |  |  | checkpoint | Area cleaned up
text | 7cf66c60-1a4f-4f51-8016-dc27cb4027ca |  | textbox | Finish time
text | 72ebc844-0958-4aee-92e8-6d099ba172aa |  | textbox | Weather
checkpoint-group |  |  | section | Post Pour
checkpoint-status |  |  | checkpoint | Is the surface cured?
checkpoint-status |  |  | checkpoint | Saw cuts
checkpoint-status |  |  | checkpoint | As built floor levels - acst in's, set downs, penetrations
checkpoint-status |  |  | checkpoint | Concrete surface to specifications
checkpoint-status |  |  | checkpoint | Construction joints roughened
checkpoint-status |  |  | checkpoint | Compression strength test
checkpoint-status |  |  | checkpoint | Pour complete
text | f13b7b37-003b-490d-8fa9-ec394430ef8f |  | textbox | Completion date:
checklist-flat |  |  | checklist | Precast Balcony Installation |  |  |  |  | Yes | Precast Balcony Installation | 60679406-b200-467f-b577-6cff76162ebe
checkpoint-status |  |  | checkpoint | Joints Scabbled
checkpoint-status |  |  | checkpoint | Temporary supports correctly placed
checkpoint-status |  |  | checkpoint | Precast balcony Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status |  |  | checkpoint | Pracast Balcony install complete (checked location & level)
checklist-flat |  |  | checklist | Panel Starter bars Installation |  |  |  |  | Yes | Panel Starter bars Installation | 6349a3d0-66e1-4daf-8632-89a765947260
checkpoint-status |  |  | checkpoint | Correct drawings referenced and attached
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/ correct
checkpoint-status |  |  | checkpoint | Any additional items installed/completed (trimmer bars etc.) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Panel starter bars installed correctly to specifications (location, size, length and spacing) and ready to place the precast panels
checklist-flat |  |  | checklist | Precast Edge Beams Installation |  |  |  |  | Yes | Precast Edge Beams Installation | 6c8cb3b9-a12b-49e3-a994-5824038423ea
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status |  |  | checkpoint | Edge Beams installation completed (checked location & level) and no damages
checklist-sectioned |  |  | checklist | Columns - |  |  |  |  | Yes | QA - Columns Checklist (V1) | 72efef81-d7a4-4355-9ceb-e7175e703f45
checkpoint-group |  |  | section | Prestart Checks
checkpoint-status |  |  | checkpoint | Site conditions acceptable
text | 50d470bb-907c-41f5-a466-c2ccdcf99055 |  | textbox | Area/Columns to be poured
checkpoint-status |  |  | checkpoint | Working off correct set of drawings
text | 6514cd54-9bd5-421a-a24e-119688a8a400 |  | textbox | Drawing & Revision Number
checkpoint-status |  |  | checkpoint | Cast in items have been identified
checkpoint-group |  |  | section | Pre Pour
checkpoint-status |  |  | checkpoint | Pour Details
text | a72044be-31e6-4d63-b721-9bbc345a3962 |  | textbox | Date of Pour
text | 29d836ce-55ca-4e88-8ea8-a6424d53d888 |  | textbox | Concrete Mix Design Ordered
checkpoint-status |  |  | checkpoint | Appropriate RL's & Grids setout and clearly marked
checkpoint-status |  |  | checkpoint | Correct Dimensions
checkpoint-status |  |  | checkpoint | Formwork cleaned, oiled, straight and braced sufficiently
checkpoint-status |  |  | checkpoint | Cast in items located and checked
checkpoint-status |  |  | checkpoint | Propping as per design
checkpoint-status |  |  | checkpoint | Access for pouring
checkpoint-status |  |  | checkpoint | 2 vibrators in working order
checkpoint-status |  |  | checkpoint | Reinforcing completed, checked and approved by engineer
boolean | 28e75e1b-4e2a-4a1e-b78a-596e9f0f2772 |  | tickbox | Specified covers checked/correct
boolean | be62772f-02a1-4212-8958-f3ceebc5324e |  | tickbox | Approved by engineer
checkpoint-status |  |  | checkpoint | Bottom of column is clean and free of debris/roughened
checkpoint-status |  |  | checkpoint | Column Pre Pour Completed & Approval to Pour
boolean | 7dff14bb-1d31-4dd2-9371-15602a4fa7b7 |  | tickbox | Pre Pour Report sent to Main Contractor
holdpoint |  |  | signoff | Request Signoff
checkpoint-group |  |  | section | Pour
checkpoint-status |  |  | checkpoint | Concrete checked on arrival & correct (slump, MPa etc)
text | ec29091f-6cce-4282-88de-76cc0faf4cc0 |  | textbox | Concrete Strength Delivered (MPa)
text | 465ae094-4961-411d-a6a9-75fc2af92bbd |  | textbox | Concrete Strength Delivered (Slump)
text | f779e76a-761a-481e-bae6-dadc50fa919c |  | textbox | Start Time
text | bedc2dc4-fa73-408b-b149-14f31869f228 |  | textbox | Weather (please specify conditions)
text | 3a224801-e213-43f7-9398-6b0e1485695e |  | textbox | Docket Number or photo of docket uploaded
boolean | 2bcbad4a-d6a4-4974-9103-796b9e03ce3f |  | tickbox | Photo of docket uploaded
checkpoint-status |  |  | checkpoint | Check cast ins, & starters
checkpoint-status |  |  | checkpoint | Vibration
checkpoint-status |  |  | checkpoint | As per specification finish - heights checked and correct
boolean | a4c048aa-b99d-4bd2-ab2c-ed6fb321de8b |  | tickbox | Retardar / Waterblast
checkpoint-status |  |  | checkpoint | Area Cleaned up - no concrete splatter
checkpoint-group |  |  | section | Post Pour
checkpoint-status |  |  | checkpoint | Is the surface cured?
checkpoint-status |  |  | checkpoint | As builts cast ins/setdowns/penetrations
checkpoint-status |  |  | checkpoint | Concrete surface to specifications
checkpoint-status |  |  | checkpoint | Construction joints correct location, roughened and clean
checkpoint-status |  |  | checkpoint | Compression strength test
checkpoint-status |  |  | checkpoint | Concrete Pour & Post Pour checks completed
checklist-flat |  |  | checklist | Precast Wall Panel Installation |  |  |  |  | Yes | Precast Wall Panel Installation | 7c833a7d-dfb4-44ba-8fbc-ea536a12d921
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Appointment with the engineers confirmed (Enter date & time of the appointment)
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and Braces to be tagged
checkpoint-status |  |  | checkpoint | Grout sleeves correctly grouted
checkpoint-status |  |  | checkpoint | Precast Wall Panel Installation completed correctly (checked location & level) and damage free
checklist-flat |  |  | checklist | ST - S - Steel-Deck Concrete Topping |  |  |  |  | Yes | ST - S - Steel-Deck Concrete Topping | 7d9631a5-551b-4f9b-9d06-b744b3045976
checkpoint-status |  |  | checkpoint | Area clean and accessible
checkpoint-status |  |  | checkpoint | Material and size are correct
checkpoint-status |  |  | checkpoint | Installed in the correct location and orientation
checkpoint-status |  |  | checkpoint | Firmly secured in the correct method
checkpoint-status |  |  | checkpoint | Area left tidy and accessible, and work signed off
checklist-flat |  |  | checklist | Precast Flat Slab Installation |  |  |  |  | Yes | Precast Flat Slab Installation | a9d5f639-8397-484a-9828-8225ba5ad340
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status |  |  | checkpoint | Precast Flat Slab Installation completed (checked location & level) and no damages
checklist-flat |  |  | checklist | Precast Beam Installation |  |  |  |  | Yes | Precast Beam Installation | ba9d5616-2c05-4962-9797-0f9deb553393
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status |  |  | checkpoint | Precast Beam Installation completed (checked location & level) and no damages
checklist-flat |  |  | checklist | Stair Installation |  |  |  |  | Yes | Stair Installation | bb959a2d-72bb-4680-aa4e-bf3b166d2cf9
checkpoint-status |  |  | checkpoint | Items inspected on arrival and correct (length, width, size/shape) as per design/shop drawings and damage free
checkpoint-status |  |  | checkpoint | Grid Set-out offset and level correct
checkpoint-status |  |  | checkpoint | Joints scabbled and acceptable
checkpoint-status |  |  | checkpoint | All setout completed correctly and approved
checkpoint-status |  |  | checkpoint | Temporary support installed and approved
checkpoint-status |  |  | checkpoint | Stairs placed, locations, heights and orientation approved. No damage during installation
checklist-sectioned |  |  | checklist | Precast Placement - |  |  |  |  | Yes | QA - Precast Placement Checklist (V2) | be547957-95ee-4d61-8a0f-ef87a4c0ce74
checkpoint-group |  |  | section | Pre Erection
checkpoint-status |  |  | checkpoint | Pre Erection details captured
text | 854ef17f-960a-4095-a5a5-ef2594020a66 |  | textbox | Description
text | 0434f88b-a094-4efc-917c-0f3651cc1e4b |  | textbox | P.C Supply Comments
text | a4b3984a-a45b-48af-8b90-0ce7de2a3b1a |  | textbox | Start date
checkpoint-status |  |  | checkpoint | R.L's & Dimensions Correct
text | 6c355cad-cac7-44ef-9454-dc8c7a07881b |  | textbox | R.L's
text | df8441f6-6f47-4880-a592-717aea833a64 |  | textbox | Drawing revision
checkpoint-status |  |  | checkpoint | Access Suitable?
checkpoint-group |  |  | section | Erection
checkpoint-status |  |  | checkpoint | Level, Plumb and in the right location
text | e6b65f08-14f8-4903-b888-e0fb8576da53 |  | textbox | Placed by:
checkpoint-status |  |  | checkpoint | Propping
checkpoint-status |  |  | checkpoint | Fixings Secure
checkpoint-group |  |  | section | Post Erection & Grouting
checkpoint-status |  |  | checkpoint | Grouting Completed
button | eb7854ab-5a4d-44b1-a9c7-4bf8b25c5e7d |  | button | Grout compatibility checked and acceptable | Yes, No, N/A
text | 939471da-7514-4fd0-a114-2d9292669b4c |  | textbox | Area to be grouted
boolean | d1861c23-ff3c-4667-9db1-a54536e3b227 |  | tickbox | Grout placed and cleaned up
checkpoint-status |  |  | checkpoint | Placement complete
text | 2f98025e-44a5-4b04-a137-4119392e07e0 |  | textbox | Date completed
checklist-sectioned |  |  | checklist | Rib & Infill Installation |  |  |  |  | Yes | Rib & Infill Installation | c8b7fa47-86b5-48e5-ae43-cb9ce38fd7a7
checkpoint-group |  |  | section | Pre-commencement
checkpoint-status |  |  | checkpoint | Items inspected on arrival and correct (length, width, size/shape) as per design/shop drawings and damage free
checkpoint-status |  |  | checkpoint | Grid set-out offset and level correct
checkpoint-status |  |  | checkpoint | Props tagged and fixings as per approved temp works design and temp work approval report attached
checkpoint-status |  |  | checkpoint | All back propping completed, checked and approved as per design
checkpoint-status |  |  | checkpoint | Structural Steel Brackets fitted and fixed (correct height and as per design)
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | All grids ready for rib installation
checkpoint-status |  |  | checkpoint | All Ribs placed, locations, heights and orientation approved. No damage during install and approval given to install planks
checkpoint-status |  |  | checkpoint | All planks installed correctly (adequate seating etc)
checkpoint-status |  |  | checkpoint | All gaps filled, infills installed, PF rod/expanding foam installed (NO GAPS)
checkpoint-status |  |  | checkpoint | Rib & Infill Installation completed correctly (checked location & level) and damage free
checklist-flat |  |  | checklist | Compromised RL/Grid - Area/Date: |  |  |  |  | Yes | Compromised RL Checklist (V2) | c8fa1406-8d16-4fba-bbd8-cca0d9d652ba
checkpoint-status |  |  | checkpoint | Compromised RL's Recorded & Signed Off
text | 18759373-a43f-4b74-9ee3-7d0020057e81 |  | textbox | Date Identified
text | a233404a-5b66-4597-a850-295e6e2346f7 |  | textbox | Description of change / remedial required
text | 1d58266c-0e5f-4ea7-b64a-de8e9bb06fb0 |  | textbox | Location
text | 26203559-48ca-4e68-81f8-e4a8f0b03682 |  | textbox | Signed off - By who?
boolean | 24d2c795-ca4f-4c07-80a2-274e58a66e07 |  | tickbox | Photos taken
checklist-flat |  |  | checklist | Precast Shell Beam Lintel Installation |  |  |  |  | Yes | Precast Shell Beam Lintel Installation | e45a2750-2bfd-488b-86d6-99863e9eba6d
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status |  |  | checkpoint | Precast Shell Beam Lintel Installation completed (checked location & level) and no damages
checklist-sectioned |  |  | checklist | Concrete Pour |  |  |  |  | Yes | Concrete Pour | e8c7fbf3-6a26-45c4-9f63-f699c8ff06e9
checkpoint-group |  |  | section | Pour Details
checkpoint-status |  |  | checkpoint | Pour details entered
text | 5e940164-88a3-553f-9caf-11f12337c72b |  | textbox | Area to be poured:
text | 5620a744-783e-58ab-ae7f-aedc85043a0b |  | textbox | Date of pour:
checkpoint-status |  |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-group |  |  | section | Formwork and Embedded Items
checkpoint-status |  |  | checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint-status |  |  | checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint-status |  |  | checkpoint | All surfaces correctly prepared (e.g joints to existing concrete, release agent to formwork etc)
checkpoint-status |  |  | checkpoint | Any control joints/ stop ends installed accurately and correctly braced
checkpoint-group |  |  | section | Reinforcing
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/correct
checkpoint-status |  |  | checkpoint | Splice laps checked/correct
checkpoint-status |  |  | checkpoint | All couplers installed correctly (if reid bar couplers have been used, has epconC8 epoxy been used as specified)
boolean | 526ae3bf-5e90-5779-be43-346a9b774907 |  | tickbox | Appointment with the engineers confirmed (Enter date & time of the appointment)
boolean | 3d62cf69-ee70-5f64-b46f-94d4ce31e3f3 |  | tickbox | Reidbar – coupler and flange nut installations are inspected by the MV Engineer
checkpoint-status |  |  | checkpoint | IMBMS couplers testing carried out for Village Podiums in the form of tensile testing in accordance with NZS3101.1.2006 and results acceptable
checkpoint-status |  |  | checkpoint | All starter bars are installed correctly (location, size and spacing )
checkpoint-status |  |  | checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Welding certificates sited and attached
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
checkpoint-group |  |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status |  |  | checkpoint | Waterproofing elements have been correctly installed and checked
checkpoint-status |  |  | checkpoint | Relevant service requirements completed (locations checked and accurate)
checkpoint-status |  |  | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint-status |  |  | checkpoint | Ryman inspection completed - Approval given to pour concrete
checkpoint-group |  |  | section | Concrete Supplier Specifics
checkpoint-status |  |  | checkpoint | Concrete Supplier details entered
text | 1d5b527e-daa6-52d8-a7b5-b616677e6109 |  | textbox | Supplier Name:
text | 88916d7a-88f4-50c2-b78b-3f606bd34fb6 |  | textbox | Specified concrete strength: | mPA
text | fe14aa11-f63b-5153-9f0e-9327a1b61648 |  | textbox | Concrete strength ordered: | mPA
text | e31d166e-2a31-5b2e-a3c5-dddfc61b1d79 |  | textbox | Concrete quantity ordered: | m3
button | aa269f05-d5b7-5a8c-839a-49465838545e |  | button | Test blocks booked | Yes, No, N/A
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-group |  |  | section | Placement Method
checkpoint-status |  |  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
checkpoint-status |  |  | checkpoint | Heights and falls checked/confirmed before placement
button | 1932d7c0-e88f-5415-838a-d9f26b9d047c |  | button | Is the cover correct to specification | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Heights and falls checked/ confirmed after placement
checkpoint-status |  |  | checkpoint | Any curing compound applied correctly
checkpoint-status |  |  | checkpoint | Concrete placement completed - specified level of finish achieved
checkpoint-group |  |  | section | Post Pour Checks/Sign Off
checkpoint-status |  |  | checkpoint | Any remedial work completed
holdpoint |  |  | signoff | Raise remedial/ Request Signoff
checkpoint-status |  |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | Insitu Stitch Joints |  |  |  |  | Yes | Insitu Stitch Joints | ee5fefcd-643c-4b40-a1e6-260ef23b7ef2
checkpoint-group |  |  | section | Pour Details
checkpoint-status |  |  | checkpoint | Pour Details:
text | 7a4fca31-ea7e-5d0d-be32-c3b9891ded97 |  | textbox | Area to be poured:
text | 6798d671-28c5-5cb8-98e2-dde78818fda2 |  | textbox | Date of pour:
checkpoint-status |  |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-group |  |  | section | Formwork
checkpoint-status |  |  | checkpoint | Formwork braced & fixed correctly
checkpoint-status |  |  | checkpoint | All surfaces correctly prepared (e.g joints to existing concrete, release agent to formwork etc)
checkpoint-group |  |  | section | Reinforcing
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-group |  |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status |  |  | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All relevant inspections completed and attached
checkpoint-status |  |  | checkpoint | Ryman inspection completed - Approval given to pour concrete
checkpoint-group |  |  | section | Concrete Supplier Specifics
checkpoint-status |  |  | checkpoint | Test blocks booked
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-group |  |  | section | Post Pour Checks/Sign Off
checkpoint-status |  |  | checkpoint | Any remedial work completed
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checklist-flat |  |  | checklist | Precast Spandrel Panel Installation |  |  |  |  | Yes | Precast Spandrel Panel Installation | f83fcda1-8eb3-4e29-bf9a-e2503fd083de
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status |  |  | checkpoint | Precast Spandrel Panel Installation completed (checked location & level) and no damages