## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Concrete Reinforcing |  |  |  |  | Yes | Concrete Reinforcing | 2abc69e5-8a2a-4621-93b0-53b10ac50a0c
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/correct
checkpoint-status |  |  | checkpoint | Splice laps checked/correct
checkpoint-status |  |  | checkpoint | All couplers installed correctly (if reid bar couplers have been used, has epconC8 epoxy been used as specified)
boolean | 2f2d149d-155d-5525-81f7-134cd8800bc5 |  | tickbox | Appointment with the engineers confirmed (Enter date & time of the appointment)
boolean | 60c3fba2-7c3a-5564-ba71-5efd18e5bb94 |  | tickbox | Reidbar – coupler and flange nut installations are inspected by the MV Engineer
checkpoint-status |  |  | checkpoint | IMBMS couplers testing carried out for Village Podiums in the form of tensile testing in accordance with NZS3101.1.2006 and results acceptable
checkpoint-status |  |  | checkpoint | All starter bars are installed correctly (location, size and spacing )
checkpoint-status |  |  | checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Welding certificates sited and attached
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
checklist-flat |  |  | checklist | Slab Reinforcement |  |  |  |  | Yes | Slab Reinforcement | 4d44bc1c-12bd-4ca5-8f63-4446d38f742b
checkpoint-status |  |  | checkpoint | Size and type to correct specification
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/correct
checkpoint-status |  |  | checkpoint | Splice laps checked/correct
checkpoint-status |  |  | checkpoint | Any starter bars are installed correctly (location, size, length, spacing)
checkpoint-status |  |  | checkpoint | Any additional items installed/completed (trimmer bars etc) and excess reinforcing
checkpoint-status |  |  | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
checkpoint-status |  |  | checkpoint | Raise remedial/Request Sign Off
checklist-flat |  |  | checklist | Compliance documentation |  |  |  |  | Yes | Compliance documentation | a9c877ed-3e20-4259-bcb8-f2ca0843079e
checkpoint-status |  |  | checkpoint | Mill Certificates attached
checkpoint-status |  |  | checkpoint | Other documentation attached
checkpoint-status |  |  | checkpoint | Producer Statements attached (PS3)
checkpoint-status |  |  | checkpoint | As-builts attached
checklist-flat |  |  | checklist | Lift Footing Reinforcement |  |  |  |  | Yes | Lift Footing Reinforcement | b9a801e7-80a5-49bc-8be4-4062c8904c0c
checkpoint-status |  |  | checkpoint | Size and type to correct specification
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/correct
checkpoint-status |  |  | checkpoint | Splice laps checked/correct
checkpoint-status |  |  | checkpoint | Any starter bars are installed correctly (location, size, length, spacing)
checkpoint-status |  |  | checkpoint | Any additional items installed/completed (trimmer bars etc) and excess reinforcing
checkpoint-status |  |  | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
checkpoint-status |  |  | checkpoint | Raise remedial/Request Sign Off
checklist-flat |  |  | checklist | Insitu stitch joints |  |  |  |  | Yes | Insitu stitch joints | dc357c5f-b25d-4d7c-a4ef-44c1384aced8
checkpoint-status |  |  | checkpoint | Size and type to correct specification
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/correct
checkpoint-status |  |  | checkpoint | Splice laps checked/correct
checkpoint-status |  |  | checkpoint | All couplers installed correctly (if reidbar couplers have been used, has epconC8 epoxy been used as specified)
checkpoint-status |  |  | checkpoint | Any starter bars are installed correctly (location, size, length, spacing)
checkpoint-status |  |  | checkpoint | Any additional items installed/completed (trimmer bars etc) and excess reinforcing
checkpoint-status |  |  | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
checkpoint-status |  |  | checkpoint | Raise remedial/Request Sign Off
checklist-flat |  |  | checklist | Strip Footing Reinforcement |  |  |  |  | Yes | Strip Footing Reinforcement | f3c81010-7e3c-4b86-9bc8-cc25b784cf40
checkpoint-status |  |  | checkpoint | Size and type to correct specification
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/correct
checkpoint-status |  |  | checkpoint | Splice laps checked/correct
checkpoint-status |  |  | checkpoint | Any starter bars are installed correctly (location, size, length, spacing)
checkpoint-status |  |  | checkpoint | Any additional items installed/completed (trimmer bars etc) and excess reinforcing
checkpoint-status |  |  | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
checkpoint-status |  |  | checkpoint | Raise remedial/Request Sign Off