## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Date: |  |  |  |  | Yes | H&S - Monthly Safety Audit | 019511b9-356a-4d7a-8774-086e48467a3c
checkpoint-group |  |  | section | ADMINISTRATION - Main Contractor
checkpoint-status |  |  | checkpoint | 1. Is there evidence of Site Specific Safety activity requirements in any tender document?
checkpoint-status |  |  | checkpoint | 2. Is there a Site Safety Management Plan in place?
checkpoint-status |  |  | checkpoint | 3. Is there evidence of a hazard identificiation and control procedure including at least one of these activities: hazard register, up to date hazard ID board, task analysis?
checkpoint-status |  |  | checkpoint | 4. Is there a record of Passport, Workplace Safety or Gold Card numbers for all Workers on Site?
checkpoint-status |  |  | checkpoint | 5. Is there evidence that at least one "Site Subcontractor Safety Meeting" was held in the last 30 days?
checkpoint-status |  |  | checkpoint | 6. Is there evidence that a Toolbox Talk was held in the last 30 days?
checkpoint-status |  |  | checkpoint | 7. Is there evidence that at least one Safety Inspection was conducted in the last 30 days?
checkpoint-status |  |  | checkpoint | 8. Is there a Training/Competency Register for all Main Contractor Employees on site?
checkpoint-status |  |  | checkpoint | 9. Is an Accident Register being maintained?
checkpoint-status |  |  | checkpoint | 10. Is an Accident Register being maintained?
checkpoint-status |  |  | checkpoint | 11. Is Task Analysis being carried out for "Significantly Hazardous Physical Work"?
checkpoint-status |  |  | checkpoint | 12. Is there a Safety Activity Wall-Chart displayed on site?
checkpoint-status |  |  | checkpoint | 13. Has anyone from the Management Team signed the Wall-Chart in the last 30 days?
checkpoint-status |  |  | checkpoint | 14. For current Notifiable Work is there evidence that DoL is notified?
checkpoint-status |  |  | checkpoint | 15. For current Notifiable Work do all Supervisors have a current Gold Card (or apporpriate equivalent)?
checkpoint-status |  |  | checkpoint | 16. Is there an operating Permit to Work system in place?
checkpoint-status |  |  | checkpoint | 17. Is there a site emergency plan?
checkpoint-status |  |  | checkpoint | 18. Are there arrangements to deal with Visitors to site (for e.g. signage, escorts, PPE or inductions)?
checkpoint-status |  |  | checkpoint | 19. Is there a Site Specific Induction Procedure in place?
checkpoint-group |  |  | section | ADMINISTRATION - Subcontractors
checkpoint-status |  |  | checkpoint | 1. Is there evidence of a Pre-Start Meeting held with the selected Subcontractor?
checkpoint-status |  |  | checkpoint | 2. Does the selected Subcontractor have a Site Specific Safety Plan?
checkpoint-status |  |  | checkpoint | 3. Is there evidence of a hazard identification and control procedure including at least one of these activities: hazard register or task analysis?
checkpoint-status |  |  | checkpoint | 4. Is there evidence that a Tool Box Talk was held in the last 30 days?
checkpoint-status |  |  | checkpoint | 5. Is there a Training/Competency Register for all Subcontractor Employees on site?
checkpoint-status |  |  | checkpoint | 6. Is Task Analysis being carried out for “Significantly Hazardous Physical Work”?
checkpoint-status |  |  | checkpoint | 7. Has Emergency Planning been completed for all “Significantly Hazardous Work”?
checkpoint-status |  |  | checkpoint | 8. Is the name and contact number of the Safety Supervisor documented?
checkpoint-status |  |  | checkpoint | 9. For current Notifiable Work, where the Subcontractors employees are involved, is there evidence that DoL is notified?
checkpoint-status |  |  | checkpoint | 10. For current Notifiable Work do all Supervisors have a current Gold Card (or apporpriate equivalent)?
checkpoint-status |  |  | checkpoint | 11. Is an Accident Register being maintained?
checkpoint-status |  |  | checkpoint | 12. Is there evidence of Accident/Incident Investigation?
checkpoint-status |  |  | checkpoint | 13. Are Passport details provided for Subcontractor's Employees?
checkpoint-status |  |  | checkpoint | 14. Is there evidence that the Subcontractor has completed a self inspection in the last 30 days?
checkpoint-status |  |  | checkpoint | 15. Is there a Hazardous Substances Register and Safety Data Sheets for Hazardous substances?
checkpoint-group |  |  | section | FACILITIES
checkpoint-status |  |  | checkpoint | 1. Are site offices clean & tidy?
checkpoint-status |  |  | checkpoint | 2. Are there toilet facilities sufficient for number of sit Workers?
checkpoint-status |  |  | checkpoint | 3. Are separate toilet facilities available for female Workers?
checkpoint-status |  |  | checkpoint | 4. Are toilet areas clean & tidy?
checkpoint-status |  |  | checkpoint | 5. Are toilets supplied with paper and handwash?
checkpoint-status |  |  | checkpoint | 6. Are there amenities or arrangements for Workers to have lunch and smoko?
checkpoint-status |  |  | checkpoint | 7. Are lunch room & food prep area clean and tidy?
checkpoint-status |  |  | checkpoint | 8. Have hand washing facilities been provided?
checkpoint-status |  |  | checkpoint | 9. Are first aid kits in place & well stocked?
checkpoint-status |  |  | checkpoint | 10. Are first aid kit contents within expiry date?
checkpoint-status |  |  | checkpoint | 11. Are appropriate fire extinguishers charged & current (Serviced 12 monthly)
checkpoint-status |  |  | checkpoint | 12. Is there adequate site signage?
checkpoint-status |  |  | checkpoint | 13. Is there adequate site fencing?
checkpoint-group |  |  | section | HOUSEKEEPING
checkpoint-status |  |  | checkpoint | 1. Are work areas clean & tidy?
checkpoint-status |  |  | checkpoint | 2. Are access ways clear? (including stairways)
checkpoint-status |  |  | checkpoint | 3. Are materials stacked safely?
checkpoint-status |  |  | checkpoint | 4. Have adequate rubbish bins or skips been provided?
checkpoint-status |  |  | checkpoint | 5. Have hazardous substances and chemicals been adequately controlled?
checkpoint-status |  |  | checkpoint | 6. Have combustable materials and substances been adequately controlled?
checkpoint-status |  |  | checkpoint | 7. Have all vertical reinforcing steel bars been capped?
checkpoint-status |  |  | checkpoint | 8. Are there enclosed material waste chutes?
checkpoint-status |  |  | checkpoint | 9. Have nails in timber been made safe?
checkpoint-status |  |  | checkpoint | 10. Are slips & trips hazards controlled?
checkpoint-group |  |  | section | PERSONAL PROTECTIVE EQUIPMENT (PPE)
checkpoint-status |  |  | checkpoint | 1. Has mandatory PPE for site been specified and signage posted?
checkpoint-status |  |  | checkpoint | 2. Are hard hats being worn where required?
checkpoint-status |  |  | checkpoint | 3. Are safety glasses/goggles being worn where required?
checkpoint-status |  |  | checkpoint | 4. Are respirators or masks being worn where required?
checkpoint-status |  |  | checkpoint | 5. Is hearing protection being worn where required?
checkpoint-status |  |  | checkpoint | 6. Are appropriate gloves being worn where required?
checkpoint-status |  |  | checkpoint | 7. Is protective clothing being worn where required?
checkpoint-status |  |  | checkpoint | 8. Is high visibility clothing being worn where required?
checkpoint-status |  |  | checkpoint | 9. Is safety footwear being worn where required?
checkpoint-group |  |  | section | EXCAVATIONS AND TRENCHES
checkpoint-status |  |  | checkpoint | 1. Have underground services been located? (plans, service location)
checkpoint-status |  |  | checkpoint | 2. Are excavations battered, benced or supported? (trenches >1.5m deep)
checkpoint-status |  |  | checkpoint | 3. Is there adequate shoring, trenchshields, sheetpiles before entry into excavations?
checkpoint-status |  |  | checkpoint | 4. Is there edge protection to prevent falls?
checkpoint-status |  |  | checkpoint | 5. Is there safe ladder access to excavation?
checkpoint-status |  |  | checkpoint | 6. Does job method avoid work in usupported trenches?
checkpoint-status |  |  | checkpoint | 7. Is materials & spoil stored to prevent edge collapse? (600mm)
checkpoint-status |  |  | checkpoint | 8. Are vehicles & plant at distance to prevent collapse?
checkpoint-status |  |  | checkpoint | 9. Is a "stop block" used for tipping vehicles?
checkpoint-group |  |  | section | FALSEWORK / FORMWORK
checkpoint-status |  |  | checkpoint | 1. Has the propping been designed & inspected by a Competent Person?
checkpoint-status |  |  | checkpoint | 2. Has falsework and formwork been checked by a Competent Person before pour?
checkpoint-status |  |  | checkpoint | 3. Is there adequate bearing on all supports?
checkpoint-status |  |  | checkpoint | 4. Are support frames/props plumb?
checkpoint-status |  |  | checkpoint | 5. Are frames/props appropriately braced and/or tied?
checkpoint-status |  |  | checkpoint | 6. Are the correct pins used in props?
checkpoint-status |  |  | checkpoint | 7. Are forkheads used for bearer support?
checkpoint-status |  |  | checkpoint | 8. Are forkheads wedged centrally?
checkpoint-status |  |  | checkpoint | 9. Are screwjacks within maximum extension allowed?
checkpoint-status |  |  | checkpoint | 10. Have falls from falsework and formwork been controlled?
checkpoint-group |  |  | section | WELDING AND GAS CUTTING
checkpoint-status |  |  | checkpoint | 1.Are gas bottles secured in use and/or stored correctly?
checkpoint-status |  |  | checkpoint | 2. Do gas sets have flash black arrestors?
checkpoint-status |  |  | checkpoint | 3. Is there a Hot Work Procedure/Permit System?
checkpoint-status |  |  | checkpoint | 4. Are there welding screens and/or signs in place?
checkpoint-status |  |  | checkpoint | 5. Is there an appropriate extinguisher at the work area?
checkpoint-group |  |  | section | SUN EXPOSURE
checkpoint-status |  |  | checkpoint | 1. Is shade cover or screens over work areas where practicable?
checkpoint-status |  |  | checkpoint | 2. Are Employees wearing clothing to prevent sun exposure?
checkpoint-status |  |  | checkpoint | 3. Is there a sun screen on site of the broad spectrum range?
checkpoint-status |  |  | checkpoint | 4. Does the sun screen on site provide a sun protection factor of 30 or more?
checkpoint-status |  |  | checkpoint | 5. Are Workers on site applying sun screen to exposed skin areas?
checkpoint-group |  |  | section | NOISE
checkpoint-status |  |  | checkpoint | 1. Is noise level for operations/site being measured?
checkpoint-status |  |  | checkpoint | 2. Is Worker exposure to noise being monitored?
checkpoint-status |  |  | checkpoint | 3. Have work operations been arranged to reduce exposure to noise hazards?
checkpoint-status |  |  | checkpoint | 4. Has plant and equipment been configured to reduce noise?
checkpoint-status |  |  | checkpoint | 5. Are Workers wearing hearing protection on site?
checkpoint-status |  |  | checkpoint | 6. Is hearing loss of Workers being moniitored?
checkpoint-group |  |  | section | CONFINED SPACE
checkpoint-status |  |  | checkpoint | 1. Is there a Confined Space Management (CSM) plan on site?
checkpoint-status |  |  | checkpoint | 2. Is there a competently trained CSM Supervisor on site?
checkpoint-status |  |  | checkpoint | 3. Have all Workers been trained to work in a Confined Space (CS)?
checkpoint-status |  |  | checkpoint | 4. Is an Entry Permit System in use to manage CS work?
checkpoint-status |  |  | checkpoint | 5. Is a monitoring person stationed outside the CS while work in progress?
checkpoint-status |  |  | checkpoint | 6. Have all services associated with CS been disconnected or isolated (lockout tagout)?
checkpoint-status |  |  | checkpoint | 7. Does the CSM Plan describe the Emergency Rescue Procedures?
checkpoint-status |  |  | checkpoint | 8. Is Emergency Rescue Equipment available at or near the entry?
checkpoint-status |  |  | checkpoint | 9. Is emergency breathing apparatus available at or near the entry?
checkpoint-status |  |  | checkpoint | 10. Before entry to CS is atmospheric testing carried out?
checkpoint-status |  |  | checkpoint | 11. During work in CS is atmospheric testing carried out?
checkpoint-group |  |  | section | CEMENT AND CONCRETE
checkpoint-status |  |  | checkpoint | 1. Are Concrete Workers trained and competent?
checkpoint-status |  |  | checkpoint | 2. Are Cement Workers protected from contact with wet cement?
checkpoint-status |  |  | checkpoint | 3. Is concrete pump boom area isolated from Workers being underneath?
checkpoint-status |  |  | checkpoint | 4. Is clean water on site readily available?
checkpoint-group |  |  | section | ASBESTOS
checkpoint-status |  |  | checkpoint | 1. Is Asbestos Removal in accordance with DoL Guidelines?
checkpoint-status |  |  | checkpoint | 2. Is there a Supervisor with a Certificate of Competence for Restricted Work?
checkpoint-status |  |  | checkpoint | 3. Is there an Asbestos Removal Plan on site?
checkpoint-status |  |  | checkpoint | 4. Has access to work area been restricted?
checkpoint-status |  |  | checkpoint | 5. Has adequate signage been posted at work area?
checkpoint-status |  |  | checkpoint | 6. Is there adequate containment of partical drift?
checkpoint-status |  |  | checkpoint | 7. Is there adequate air extraction with HEPA filter?
checkpoint-status |  |  | checkpoint | 8. Is air monitoring for contamination being performed?
checkpoint-group |  |  | section | CHEMICALS
checkpoint-status |  |  | checkpoint | 1. Are Employees provided with Chemical Use Inductions?
checkpoint-status |  |  | checkpoint | 2. Are Chemical Management Responsibilites defined?
checkpoint-status |  |  | checkpoint | 3. Are "Approved Handlers" certified?
checkpoint-status |  |  | checkpoint | 4. Is there a "Location Certificate"?
checkpoint-status |  |  | checkpoint | 5. Is there a "Person in Charge"?
checkpoint-status |  |  | checkpoint | 6. Are Workers protected from chemical exposure?
checkpoint-status |  |  | checkpoint | 7. Are chemicals stored in proper containers?
checkpoint-status |  |  | checkpoint | 8. Are chemicals properly disposed of?
checkpoint-group |  |  | section | DEMOLITION
checkpoint-status |  |  | checkpoint | 1. Is there a Demolition Workplan that complies with AS2061 or local requirements?
checkpoint-status |  |  | checkpoint | 2. Is there an Engineer's Report/advice?
checkpoint-status |  |  | checkpoint | 3. Is there a Demolition Supervisor on site?
checkpoint-status |  |  | checkpoint | 4. Is there site security fencing?
checkpoint-status |  |  | checkpoint | 5. Is there signage for demolition activities?
checkpoint-status |  |  | checkpoint | 6. Is there gantry/overhead protection for the public?
checkpoint-status |  |  | checkpoint | 7. Have all building services been disconnected?
checkpoint-group |  |  | section | FALL PREVENTION
checkpoint-status |  |  | checkpoint | 1. Are there guardrails between 0.9m & 1.1m?
checkpoint-status |  |  | checkpoint | 2. Are fall hazards controlled?
checkpoint-status |  |  | checkpoint | 3. Are fall edges fitted with guardrails/toeboards?
checkpoint-status |  |  | checkpoint | 4. Are holes & floor penetratins covered and marked?
checkpoint-status |  |  | checkpoint | 5. Are stairways fitted with handrails?
checkpoint-status |  |  | checkpoint | 6. Are liftshafts closed off?
checkpoint-group |  |  | section | HARNESS USE
checkpoint-status |  |  | checkpoint | 1. Are restraint systems being used in preference to fall arrest systems?
checkpoint-status |  |  | checkpoint | 2. Are service/maintenance records for harness equipment being kept?
checkpoint-status |  |  | checkpoint | 3. Have Employees undertaken training for harness use?
checkpoint-status |  |  | checkpoint | 4. Are Supervisors of fall arrest systems trained and competent to NZQA US15757?
checkpoint-status |  |  | checkpoint | 5. Is the fall arrest system suitable for the work requirements?
checkpoint-status |  |  | checkpoint | 6. Was all equipment checked prior to use?
checkpoint-status |  |  | checkpoint | 7. Are hazards associated with fall arrest systems controlled?
checkpoint-status |  |  | checkpoint | 8. Is the fall arrest connection correctly set up?
checkpoint-status |  |  | checkpoint | 9. Are harnesses correctly fitted?
checkpoint-status |  |  | checkpoint | 10. Is equipment in serviceable condition?
checkpoint-status |  |  | checkpoint | 11. Is rescue equipment present at job site?
checkpoint-group |  |  | section | LADDERS
checkpoint-group |  |  | section | STANDARD LADDERS
checkpoint-status |  |  | checkpoint | 1. Are ladders of industrial standard?
checkpoint-status |  |  | checkpoint | 2. Are Workers using ladders correctly?
checkpoint-status |  |  | checkpoint | 3. Are ladders set up on firm level ground?
checkpoint-status |  |  | checkpoint | 4. Are ladders secured? (base and/or top)
checkpoint-status |  |  | checkpoint | 5. Is ladder set at correct angle? (4 up to 1 out)
checkpoint-status |  |  | checkpoint | 6. Are ladders in good condition?
checkpoint-status |  |  | checkpoint | 7. Do ladders project 1m above step off point?
checkpoint-group |  |  | section | STEP LADDERS
checkpoint-status |  |  | checkpoint | 1. Is the stepladder suitable for the job?
checkpoint-status |  |  | checkpoint | 2. Are stepladder lock bars in place?
checkpoint-status |  |  | checkpoint | 3. Are stepladders set up on firm level gound?
checkpoint-status |  |  | checkpoint | 4. Are stepladders in good condition?
checkpoint-group |  |  | section | STANDING SCAFFOLD
checkpoint-status |  |  | checkpoint | 1. Is scaffold suitable for the job?
checkpoint-status |  |  | checkpoint | 2. Has scaffold been erected by Certified Scaffolder?
checkpoint-status |  |  | checkpoint | 3. Is scaf-tag/acu-log scaffold register up to date?
checkpoint-status |  |  | checkpoint | 4. Are there adequated baseplates & soleboards?
checkpoint-status |  |  | checkpoint | 5. Are ladders on scaffold secured?
checkpoint-status |  |  | checkpoint | 6. Does ladder extend 1m past step off? (or suitable hand holds)
checkpoint-status |  |  | checkpoint | 7.Is there suitable access to scaffold platforms?
checkpoint-status |  |  | checkpoint | 8. Are work platforms adequate?
checkpoint-status |  |  | checkpoint | 9. Are there guardrails between 0.9m and 1.1m?
checkpoint-status |  |  | checkpoint | 10. Is there an intermediatee rail in place?
checkpoint-status |  |  | checkpoint | 11. Is a toeboard in place?
checkpoint-status |  |  | checkpoint | 12. Is there debris netting in place?
checkpoint-group |  |  | section | MOBILE SCAFFOLD
checkpoint-status |  |  | checkpoint | 1. Is mobile scaffold suitable for the job?
checkpoint-status |  |  | checkpoint | 2. Is mobile scaffold set up on firm level ground?
checkpoint-status |  |  | checkpoint | 3. Is scaf-tag/acu-log in place & up to date?
checkpoint-status |  |  | checkpoint | 4. Are wheels locked?
checkpoint-status |  |  | checkpoint | 5. Are wheels turned out? (increased stability)
checkpoint-status |  |  | checkpoint | 6. Are working levells fully decked & secure?
checkpoint-status |  |  | checkpoint | 7. Is access from within the scaffold frame?
checkpoint-status |  |  | checkpoint | 8. Mobile scaffold at correct base width to height ratio?
checkpoint-status |  |  | checkpoint | 9. Are outriggers fitted where required?
checkpoint-status |  |  | checkpoint | 10. Are there guardrails between 0.9m and 1.1m?
checkpoint-group |  |  | section | SPECIAL SCAFFOLD
checkpoint-status |  |  | checkpoint | 1. Has a Competent Person designed the special scaffold?
checkpoint-status |  |  | checkpoint | 2. Is there a copy of a Registered Engineers Design Certificate?
checkpoint-status |  |  | checkpoint | 3. Does the scaffold structure comply with the Design Certificate?
checkpoint-status |  |  | checkpoint | 4. Has a Certified Scaffolder erected the scaffold?
checkpoint-status |  |  | checkpoint | 5. Is there a current Scaffold Register?
checkpoint-group |  |  | section | SUSPENDED SCAFFOLDS (SWINGING STAGE)
checkpoint-status |  |  | checkpoint | 1. Is there a current Scaffold Register (daily)?
checkpoint-status |  |  | checkpoint | 2. Are roof suspension rigs secured against movement?
checkpoint-status |  |  | checkpoint | 3. Are sufficient counterweights secured in place?
checkpoint-status |  |  | checkpoint | 4. Is the needle overhang and tail lenth ration correct?
checkpoint-status |  |  | checkpoint | 5. Are the suspension ropes secure and in good conditions?
checkpoint-status |  |  | checkpoint | 6. Are all control and emergency buttons operational?
checkpoint-status |  |  | checkpoint | 7. Are operations within the Safe Working Load (SWL) of platform?
checkpoint-status |  |  | checkpoint | 8. Is the path of the suspended scafffold clear of projections?
checkpoint-status |  |  | checkpoint | 9. Is the power cable prevented from becoming dislodged or damaged?
checkpoint-status |  |  | checkpoint | 10. Are Operators all using a safety harness?
checkpoint-status |  |  | checkpoint | 11. Are Workers connected to independent safety line or other engineered anchor system?
checkpoint-status |  |  | checkpoint | 12. Are warning notices and barricades at ground level?
checkpoint-group |  |  | section | ELEVATED WORK PLATFORMS (EWP)
checkpoint-status |  |  | checkpoint | 1. Is EWP set up on firm level ground?
checkpoint-status |  |  | checkpoint | 2. Are outriggers fully extended?
checkpoint-status |  |  | checkpoint | 3. Has area at base of EWP been isolated?
checkpoint-status |  |  | checkpoint | 4. Is EWP at least 4m from power lines?
checkpoint-status |  |  | checkpoint | 5. Are safety harnesses being worn in boom mounted buckets?
checkpoint-status |  |  | checkpoint | 6. Has EWP been inspected & certified within last 6 months?
checkpoint-group |  |  | section | TRANSPORT & MOB MECHANICAL PLANT
checkpoint-status |  |  | checkpoint | 1. Are Drivers/Operators trained?
checkpoint-status |  |  | checkpoint | 2. Are vehicles securely loaded?
checkpoint-status |  |  | checkpoint | 3. Are reversing vehicles controlled?
checkpoint-status |  |  | checkpoint | 4. Are vehicle warning signs displayed?
checkpoint-status |  |  | checkpoint | 5. Does mobile plant have roll over protective structure?
checkpoint-status |  |  | checkpoint | 6. Is protective structure in good repair?
checkpoint-status |  |  | checkpoint | 7. Is seat belt effective and in good repair?
checkpoint-group |  |  | section | EQUIPMENT & MACHINERY & TOOLS
checkpoint-status |  |  | checkpoint | 1. Is machinery in good operation condition?
checkpoint-status |  |  | checkpoint | 2. Are gears, chain drives & shafts, and moving parts guarded?
checkpoint-status |  |  | checkpoint | 3. Are guards secured & in good order?
checkpoint-status |  |  | checkpoint | 4. Do bench saws have a riving knife & hood guard
checkpoint-status |  |  | checkpoint | 5. Does compressed air have matched & secured connections?
checkpoint-group |  |  | section | CRANES & LIFTING APPLIANCES
checkpoint-status |  |  | checkpoint | 1. Are crane outriggers fully extended?
checkpoint-status |  |  | checkpoint | 2. Are loads correctly slung?
checkpoint-status |  |  | checkpoint | 3. Has lift zone been isolated or cleared of people?
checkpoint-status |  |  | checkpoint | 4. Is there a current Test Certificate?
checkpoint-status |  |  | checkpoint | 5. Are Weekly Inspections carried out?
checkpoint-status |  |  | checkpoint | 6. Are the crane slings certified?
checkpoint-status |  |  | checkpoint | 7. Are the Crane Operator & Dogman trained appropriately?
checkpoint-group |  |  | section | POWDER-ACTUATED TOOLS
checkpoint-status |  |  | checkpoint | 1. Is Operator certified?
checkpoint-status |  |  | checkpoint | 2. Does tool have 6 monthly certifcate?
checkpoint-status |  |  | checkpoint | 3. Are tool & cartridges secured when not in use?
checkpoint-status |  |  | checkpoint | 4. Has PAT signage been posted at work area?
checkpoint-status |  |  | checkpoint | 5. Has firing zone been isolated or cleared of people?
checkpoint-status |  |  | checkpoint | 6. Have walls or surfaces been checked for service conduits? (e.g gas or electrical)
checkpoint-status |  |  | checkpoint | 7. Is a 3 second verbal waning given?
checkpoint-status |  |  | checkpoint | 8. Is hearing & eye protection worn?
checkpoint-group |  |  | section | ELECTRICAL
checkpoint-status |  |  | checkpoint | 1. Are electrical tools and leads visually inspected for faults prior to use?
checkpoint-status |  |  | checkpoint | 2. Are electrical leads and tools free from defects and damage?
checkpoint-status |  |  | checkpoint | 3. Are electrical tools and leads tagged quarterly?
checkpoint-status |  |  | checkpoint | 4. Are protected power outlets being used on site (e.g. lifeguards or RCDs)?
checkpoint-status |  |  | checkpoint | 5. Are lifeguard units tagged quarterly?
checkpoint-status |  |  | checkpoint | 6. Are multi-plug boards & double adaptors industrially rated?
checkpoint-status |  |  | checkpoint | 7. Are electrical tools and leads industrial rated?
checkpoint-status |  |  | checkpoint | 8. Does temporary festoon lighting have moulded line sockets?
checkpoint-status |  |  | checkpoint | 9. Are electrical leads clear of pathways and stairs?
checkpoint-status |  |  | checkpoint | 10. Are electrical leads clear of water?
checkpoint-status |  |  | checkpoint | 11. Have electrical leads been protected from traffic?
checkpoint-group |  |  | section | ENVIRONMENTAL ISSUES
checkpoint-status |  |  | checkpoint | 1. Is there an Environmental Protection Plan in place?
checkpoint-status |  |  | checkpoint | 2. Is there a Silt Control Plan in place?
checkpoint-status |  |  | checkpoint | 3. Is there Spill Control in place for refueling operation?
checkpoint-status |  |  | checkpoint | 4. Is Dust controlled?
checkpoint-status |  |  | checkpoint | 5. Is Construction Waste being controlled?
checkpoint-status |  |  | checkpoint | 6. Is Construction Noise being controlled?
checkpoint-group |  |  | section | TRAFFIC MANAGEMENT
checkpoint-status |  |  | checkpoint | 1. Is there a temporary Traffic Management Plan (TMP) on site?
checkpoint-status |  |  | checkpoint | 2. Has the TMP been approved by the Road Controlling Authority?
checkpoint-status |  |  | checkpoint | 3. Are the Traffice Mangagement (TM) measures and signage set up as per the TMP?
checkpoint-status |  |  | checkpoint | 4.Is TM supervised by a qualified (STMS)?
checkpoint-status |  |  | checkpoint | 5. Is there a Traffice Controller (TC ) on site?
checklist-flat |  |  | checklist | Joinery Units - |  |  |  |  | Yes | QA - 31. Joinery Units (RevA) | 037d97e4-e87c-413f-9a97-29412b69c619
checkpoint-status |  |  | checkpoint | Construction drawings sent to door supplier.
checkpoint-status |  |  | checkpoint | Confirm all kitchen sizes, types and handings
checkpoint-status |  |  | checkpoint | Confirm colours, tops, handles, appliances openings
checkpoint-status |  |  | checkpoint | Delivery agreed.
checkpoint-status |  |  | checkpoint | Installation completed.
checkpoint-status |  |  | checkpoint | All inserts installed
checkpoint-status |  |  | checkpoint | Rubbish bins installed
checkpoint-status |  |  | checkpoint | Soft close hardware inatalled
checkpoint-status |  |  | checkpoint | All draws / doors opening closing, correct clearances. No binding
checkpoint-status |  |  | checkpoint | All accessible items installed
checkpoint-status |  |  | checkpoint | All shelves correctly installed
checkpoint-status |  |  | checkpoint | All screw buttons / stickers installed
checkpoint-status |  |  | checkpoint | All stickers removed from units
checkpoint-status |  |  | checkpoint | All units cleaned
checkpoint-status |  |  | checkpoint | Silicone work all complete
checklist-sectioned |  |  | checklist | Date: |  |  |  |  | Yes | H&S - Safari Weekly Safety Audit | 04a0f688-ded4-4999-bf1a-75405778c9f8
checkpoint-group |  |  | section | Documentation Checks
checkpoint-status |  |  | checkpoint | Is there evidence of Site Specific Safety activity requirements in any tender document?
checkpoint-status |  |  | checkpoint | Is there a Site Safety Management Plan in place?
checkpoint-status |  |  | checkpoint | Is there evidence of a hazard identificiation and control procedure including at least one of these activities: hazard register, up to date hazard ID board, task analysis?
checkpoint-status |  |  | checkpoint | Is there a record of Passport, Workplace Safety or Gold Card numbers for all Workers on Site?
checkpoint-status |  |  | checkpoint | Is there evidence that a Toolbox Talk was held in the last week for each subcontractor that has worked in the last week?
checkpoint-status |  |  | checkpoint | Is an Accident Register being maintained?
checkpoint-status |  |  | checkpoint | Is Task Analysis being carried out for "Significantly Hazardous Physical Work"?
checkpoint-status |  |  | checkpoint | Is there a Safety Activity Wall-Chart displayed on site?
checkpoint-status |  |  | checkpoint | Are there arrangements to deal with Visitors to site (for e.g. signage, escorts, PPE or inductions)?
checkpoint-status |  |  | checkpoint | Is there a Site Specific Induction Procedure in place?
checkpoint-group |  |  | section | Site Control
checkpoint-status |  |  | checkpoint | Hazard board and signage up-to-date
checkpoint-status |  |  | checkpoint | Environmental plan – issues
checkpoint-status |  |  | checkpoint | Toolbox Talk last date
text | 545bb1b2-067b-4dc4-a65b-dd1d13113bd7 |  | textbox | Last Date:
checkpoint-status |  |  | checkpoint | Safety inductions for all on site
checkpoint-status |  |  | checkpoint | Safety notice board current
checkpoint-group |  |  | section | Site Facilities
checkpoint-status |  |  | checkpoint | Offices – clean, adequate and good lighting
checkpoint-status |  |  | checkpoint | Smoko sheds – clean, potable water
checkpoint-status |  |  | checkpoint | Toilets – clean, washing water
checkpoint-status |  |  | checkpoint | Tool/equipment sheds adequate
checkpoint-group |  |  | section | General Site Tidiness and Accessways
checkpoint-status |  |  | checkpoint | Clear, safe access to work areas
checkpoint-status |  |  | checkpoint | Stairways and accessways clear
checkpoint-status |  |  | checkpoint | Hoardings/fence and gates secure
checkpoint-status |  |  | checkpoint | Loose materials secure from wind
checkpoint-group |  |  | section | Personal Safety Equipment
checkpoint-status |  |  | checkpoint | Signage displayed and legible
checkpoint-status |  |  | checkpoint | Hardhats being worn
checkpoint-status |  |  | checkpoint | Correct footwear being worn
checkpoint-status |  |  | checkpoint | Glasses/ear muffs/vests/masks used
checkpoint-group |  |  | section | First Aid/Fire Prevention
checkpoint-status |  |  | checkpoint | First Aid box is avalible & Current
checkpoint-status |  |  | checkpoint | Accident register
checkpoint-status |  |  | checkpoint | Fire extinguishers
boolean | a621143a-c5e6-47c9-ac57-5dc346040687 |  | tickbox | Current (12 mth)
boolean | a83760b1-a5f9-4887-82e2-3dccbb85ab7c |  | tickbox | Sufficient number
checkpoint-status |  |  | checkpoint | Evacuation
boolean | 5eec962f-47f0-4a20-8a6d-340a88c9b827 |  | tickbox | Current (12 mth)
boolean | 3cb0b218-99e8-421d-8311-3b29365e1a73 |  | tickbox | All emergencies incl
checkpoint-group |  |  | section | Cranes/Hoist/Lifting Equipment
checkpoint-status |  |  | checkpoint | Proper lift assessment plan done
checkpoint-status |  |  | checkpoint | Crane certification current
checkpoint-status |  |  | checkpoint | Slings/chains certified
checkpoint-status |  |  | checkpoint | Operator procedures in place
checkpoint-status |  |  | checkpoint | Inspections being done
checkpoint-status |  |  | checkpoint | Man cage available
checkpoint-status |  |  | checkpoint | Emergency plan in place
checkpoint-group |  |  | section | Compressed Air Equipment
checkpoint-status |  |  | checkpoint | In good condition
checkpoint-status |  |  | checkpoint | Appropriate guards fitted
checkpoint-status |  |  | checkpoint | Trained user
checkpoint-group |  |  | section | Excavations
checkpoint-status |  |  | checkpoint | Correctly shored
checkpoint-group |  |  | section | Welding/Gas Cutting
checkpoint-status |  |  | checkpoint | Hot work permits being issued
checkpoint-status |  |  | checkpoint | Fire extinguishers on hand
checkpoint-status |  |  | checkpoint | Operators using PPE
checkpoint-group |  |  | section | Electrical Equipment
checkpoint-status |  |  | checkpoint | Main board lockable/weatherproof
checkpoint-status |  |  | checkpoint | Current tagged and damage-free leads
checkpoint-status |  |  | checkpoint | Current tagged plant
checkpoint-status |  |  | checkpoint | Current tagged lifeguards
checkpoint-status |  |  | checkpoint | Leads safely placed
checkpoint-status |  |  | checkpoint | Equipment in good condition
checkpoint-status |  |  | checkpoint | Appropriate guards on equipment
checkpoint-status |  |  | checkpoint | Adequate temporary lighting
checkpoint-group |  |  | section | Chemicals
checkpoint-status |  |  | checkpoint | Correctly stored
checkpoint-status |  |  | checkpoint | Safety Data Sheet (SDS) available
checkpoint-status |  |  | checkpoint | Operators using PPE
checkpoint-group |  |  | section | Tools
checkpoint-status |  |  | checkpoint | PAT tool WoF current and secure
checkpoint-status |  |  | checkpoint | Staff trained in tool use (SWPS)
checkpoint-status |  |  | checkpoint | PAT signage on site
checkpoint-group |  |  | section | Scaffolding
checkpoint-status |  |  | checkpoint | Notifiable weekly Scaftag/current
checkpoint-status |  |  | checkpoint | Handrails/mid-rails
checkpoint-status |  |  | checkpoint | Toe boards
checkpoint-status |  |  | checkpoint | Platforms
checkpoint-status |  |  | checkpoint | Ladders/stairs
checkpoint-status |  |  | checkpoint | Base sound
checkpoint-status |  |  | checkpoint | Work platforms clear
checkpoint-status |  |  | checkpoint | Platforms trip free
checkpoint-status |  |  | checkpoint | Planks tied down
checkpoint-status |  |  | checkpoint | Headroom clear
checkpoint-status |  |  | checkpoint | Ties/bracing adequate
checkpoint-group |  |  | section | Ladders
checkpoint-status |  |  | checkpoint | Good condition
checkpoint-status |  |  | checkpoint | Secured top and bottom
checkpoint-status |  |  | checkpoint | Stays to step ladders
checkpoint-status |  |  | checkpoint | Working 2 steps down
checkpoint-group |  |  | section | Fall Hazards
checkpoint-status |  |  | checkpoint | Floor edges
checkpoint-status |  |  | checkpoint | Floor openings
checkpoint-status |  |  | checkpoint | Lift shafts
checkpoint-status |  |  | checkpoint | Stairs
checkpoint-status |  |  | checkpoint | Excavations
checklist-flat |  |  | checklist | Foundations - |  |  |  |  | Yes | QA - 08. Foundations (RevA) | 05d0f701-c11f-492c-acd4-34c308bfcb03
checkpoint-status |  |  | checkpoint | Construction drawings and specification sent to subcontractor.
checkpoint-status |  |  | checkpoint | Site set out by surveyor.
checkpoint-status |  |  | checkpoint | Site RL installed by surveyor.
checkpoint-status |  |  | checkpoint | Confirm foundation RL's bottom off footing
checkpoint-status |  |  | checkpoint | Geotech engineer inspection or confirmation received to proceed
checkpoint-status |  |  | checkpoint | Confirm foundation RL's top off footing
checkpoint-status |  |  | checkpoint | Foundation dimensions confirmed
checkpoint-status |  |  | checkpoint | Waterproofing DPC / Membrane installed inspected
checkpoint-status |  |  | checkpoint | Reinforcing complete
checkpoint-status |  |  | checkpoint | Starters installed and position confirmed
checkpoint-status |  |  | checkpoint | Drossbach starters install and positioned confirmed
checkpoint-status |  |  | checkpoint | Steps & stopends in place
checkpoint-status |  |  | checkpoint | Correct MPA concrete
checkpoint-status |  |  | checkpoint | Council inspection or confirmation received to proceed
checkpoint-status |  |  | checkpoint | Structural engineer inspection or confirmation received to proceed
checkpoint-status |  |  | checkpoint | Rugersole exposed surfaces ready for keying in for next pours
checklist-flat |  |  | checklist | Inspection - |  |  |  |  | Yes | Add Consultant Inspection Checklist | 09b896c8-fc04-42ee-b392-805b2a98500e
checkpoint-status |  |  | checkpoint | Inspection completed, attached and any relevant observations closed out
text | e716f58a-4420-4e11-91ae-f4fef0f7ba87 |  | textbox | Date of Inspection:
text | 78d9159e-0896-4188-a542-fa6b1bf43aaa |  | textbox | Type of Inspection:
text | 534f8c4f-3a28-4d0b-8e31-2e870fe2cb87 |  | textbox | Area inspection relates to
boolean | d24858c1-85f5-44b8-99c0-818a707a7f19 |  | tickbox | Inspection attached
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All Relevant Observation Closeout evidence attached here if applicable (Pass once completed)
text | b4ff21c8-e458-474a-a19a-1cbce0361c6d |  | textbox | Corrective Actions Required
checklist-flat |  |  | checklist | Council Inspection - |  |  |  |  | Yes | Add Council Inspection Checklist | 0a3791e3-25ed-4322-9d2a-efa7689e595f
checkpoint-status |  |  | checkpoint | Inspection completed, attached and any relevant observations closed out (Pass once all information is attached including observations with evidence of closeout)
text | e716f58a-4420-4e11-91ae-f4fef0f7ba87 |  | textbox | Date of inspection:
text | 78d9159e-0896-4188-a542-fa6b1bf43aaa |  | textbox | Inspection Type Code:
text | 6931f74e-964b-42b5-905c-440c2ce0001a |  | textbox | Area inspection relates to
select | ca58c4ad-f5b3-41c0-ae49-ce6c1c3289f9 |  | dropdown | Inspection Outcome | Pass,Fail,Partial Pass,N/A
boolean | d24858c1-85f5-44b8-99c0-818a707a7f19 |  | tickbox | Council inspection attached
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All Relevant Observation Closeout evidence attached here if applicable (Pass once completed)
text | 659f0de8-c7a9-45fe-9851-606ecd798dd2 |  | textbox | Outstanding Information Required
checklist-flat |  |  | checklist | XLAM - |  |  |  |  | Yes | QA - 18. XLAM (RevA) | 0bba250c-ceff-43f0-bcc1-eb47891c7103
checkpoint-status |  |  | checkpoint | Construction drawings and specification received.
checkpoint-status |  |  | checkpoint | Metal work brackets arranged and fixings (screws)
checkpoint-status |  |  | checkpoint | Delivery / lift / install sequence confirmed
checkpoint-status |  |  | checkpoint | Crane ordered, correct size and reach
checkpoint-status |  |  | checkpoint | Check that LVL Beams are included in package
checkpoint-status |  |  | checkpoint | Setout confirmed / GL's offsets in place
checkpoint-status |  |  | checkpoint | Erection process confirmed including lifting points
checkpoint-status |  |  | checkpoint | Temp propping onsite as required to install
checkpoint-status |  |  | checkpoint | Sign off of lift shaft, internal fixing for rails
checkpoint-status |  |  | checkpoint | Weather protection of panels been erected and waiting to be erected
checklist-flat |  |  | checklist | Electrical - |  |  |  |  | Yes | QA - 27. Electrical (RevA) | 12caaaff-bc45-44c3-992e-1f4094b9e816
checkpoint-status |  |  | checkpoint | Construction drawings and specification sent to contractor.
checkpoint-status |  |  | checkpoint | Main power confirmed to site
checkpoint-status |  |  | checkpoint | Switch board approved
checkpoint-status |  |  | checkpoint | Switch board delivery agreed
checkpoint-status |  |  | checkpoint | Locations agreed for all fittings.
checkpoint-status |  |  | checkpoint | Position in conjunction with joinery or bench units.
checkpoint-status |  |  | checkpoint | Coordination with sub-trades; feeds for fire, plumbing sensors etc.
checkpoint-status |  |  | checkpoint | Fitting schedule approved
checkpoint-status |  |  | checkpoint | Nogs in place.
checkpoint-status |  |  | checkpoint | All wiring completed.
checkpoint-status |  |  | checkpoint | Fire collars installed.
checkpoint-status |  |  | checkpoint | EM fittings installed and tested
checkpoint-status |  |  | checkpoint | Power points installed for other services, Fire, Hubs, Lift, Security, Buti's
checkpoint-status |  |  | checkpoint | All fittings installed as per drawings and specification.
checkpoint-status |  |  | checkpoint | Testing and commissioning.
checklist-flat |  |  | checklist | Interior Doors - |  |  |  |  | Yes | QA - 28. Interior Doors (RevA) | 1940775c-e773-418a-a50d-33c054faff88
checkpoint-status |  |  | checkpoint | Construction drawings sent to door supplier.
checkpoint-status |  |  | checkpoint | Door and hardware specification sent to supplier.
checkpoint-status |  |  | checkpoint | Door schedule generated; no. of hinges, floor clearances, architrave or rebated jambs, opening sizes, leaf sizes, jamb thicknesses, clashings, door seals, grill sizes.
checkpoint-status |  |  | checkpoint | Electronic access wiring coordinated.
checkpoint-status |  |  | checkpoint | Delivery agreed.
checkpoint-status |  |  | checkpoint | Installation completed.
checkpoint-status |  |  | checkpoint | Hardware installed as per specification.
checkpoint-status |  |  | checkpoint | Viewing eyes installed at correct height (lower for accessible)
checkpoint-status |  |  | checkpoint | Fire door tags.
checkpoint-status |  |  | checkpoint | Council inspection.
checklist-flat |  |  | checklist | Retaining Wall - |  |  |  |  | Yes | QA - 04. Retaining Wall (RevA) | 1a794728-17e9-4578-8e3f-0e1e1d126085
checkpoint-status |  |  | checkpoint | Construction drawings and specification received.
checkpoint-status |  |  | checkpoint | Type confirmed anchors and schocrete / timber & product ordered
checkpoint-status |  |  | checkpoint | Position confirmed / RL's to base & top checked
checkpoint-status |  |  | checkpoint | Setout confirmed anchors / poles
checkpoint-status |  |  | checkpoint | Inspection carried out holes / anchors - mesh
checkpoint-status |  |  | checkpoint | Engineers inspection booked for inspection or confirmation received to proceed
checkpoint-status |  |  | checkpoint | Shotcrete areas confirmed and quinties monitored / recorded
checkpoint-status |  |  | checkpoint | Spray to correct line / poles set to correct line
checkpoint-status |  |  | checkpoint | Rails installed to crect design
checkpoint-status |  |  | checkpoint | Drainage installed
checkpoint-status |  |  | checkpoint | Backfilling complete
checklist-flat |  |  | checklist | Roofing Membrane - |  |  |  |  | Yes | QA - 20. Roofing Membrane (RevA) | 1dd1498e-4ade-4492-af04-e3512dca5a5a
checkpoint-status |  |  | checkpoint | Sub structure signed off
checkpoint-status |  |  | checkpoint | IDL system confirmed if required
checkpoint-status |  |  | checkpoint | connection / hold downs installed
checkpoint-status |  |  | checkpoint | Plywood substrate installed
checkpoint-status |  |  | checkpoint | Penetration / plinths / parapets brought through the roof to correct height
checkpoint-status |  |  | checkpoint | Nibs and upstands installed
checkpoint-status |  |  | checkpoint | Angle fillets installed
checkpoint-status |  |  | checkpoint | Gutter / sumps / overflows installed correct falls
checkpoint-status |  |  | checkpoint | Pre start inspection from membrane contractor / manufacture
checkpoint-status |  |  | checkpoint | Membrane inspection undertaken by manufacture
checkpoint-status |  |  | checkpoint | Membrane inspection report completed
checkpoint-status |  |  | checkpoint | Roofing installed
checkpoint-status |  |  | checkpoint | Cap / Parapet flashings installed
checkpoint-status |  |  | checkpoint | Council inspection or confirmation received to proceed
checkpoint-status |  |  | checkpoint | Subs QA supplied
checklist-flat |  |  | checklist | Blockwork - |  |  |  |  | Yes | QA - 10. Blockwork (RevA) | 1fa992d1-a761-4ba6-baad-968d6d2521ab
checkpoint-status |  |  | checkpoint | Construction drawings and specification to subcontractor.
checkpoint-status |  |  | checkpoint | Reinforcing ordered for blockwork.
checkpoint-status |  |  | checkpoint | Set out completed – pins in footings profils installed and plumb
checkpoint-status |  |  | checkpoint | RL check for foundations.
checkpoint-status |  |  | checkpoint | Blockwork sizes correct.
checkpoint-status |  |  | checkpoint | Control joint locations and type agreed.
checkpoint-status |  |  | checkpoint | Openings framed out.
checkpoint-status |  |  | checkpoint | Reinforcing placed as per drawings.
checkpoint-status |  |  | checkpoint | Bond beams installed.
checkpoint-status |  |  | checkpoint | Control joints placed.
checkpoint-status |  |  | checkpoint | Washouts installed and cleaned
checkpoint-status |  |  | checkpoint | Council inspection or confirmation received to proceed
checkpoint-status |  |  | checkpoint | Structural engineer inspection or confirmation received to proceed
checkpoint-status |  |  | checkpoint | Grout MPA & slump confirmed.
checklist-flat |  |  | checklist | Fire Protection - Sprinklers - |  |  |  |  | Yes | QA - 25. Fire Protection - Sprinklers (RevA) | 1fe85581-e962-469d-94b5-c82ed7ba3217
checkpoint-status |  |  | checkpoint | Construction drawings to sub-contractor.
checkpoint-status |  |  | checkpoint | Shop drawings issued.
checkpoint-status |  |  | checkpoint | Shop drawing approval.
checkpoint-status |  |  | checkpoint | Co-ordination of sprinkler heads in ceiling with lights / skylights / vents / ducts / smoke detectors.
checkpoint-status |  |  | checkpoint | Sprinkler main confirmed.
checkpoint-status |  |  | checkpoint | Manual call point locations agreed and to code and installed.
checkpoint-status |  |  | checkpoint | Wiring complete / accseeibele units identified and strobs installed
checkpoint-status |  |  | checkpoint | Telephone line if brigade connected.
checkpoint-status |  |  | checkpoint | Fire panel agreed & co-ordinated windows / precast / fire brigade.
checkpoint-status |  |  | checkpoint | Sprinkler pipe installed.
checkpoint-status |  |  | checkpoint | Service interfaces supplied
checkpoint-status |  |  | checkpoint | Sprinkler heads installed and tested.
checkpoint-status |  |  | checkpoint | Pressure tests received for each floor with photos before and after
checkpoint-status |  |  | checkpoint | System final sign off.
checklist-flat |  |  | checklist | PCP Shop Drawings - |  |  |  |  | Yes | QA - 12. PCP Shop Drawings (RevA) | 3bbb21a4-730b-498c-badf-bad64c7cff4e
checkpoint-status |  |  | checkpoint | Construction drawings and specification sent to sub-contractor.
checkpoint-status |  |  | checkpoint | CI's/SIR's items of note communicated to subcontractor and actioned
checkpoint-status |  |  | checkpoint | Coordornation with services complete on penetrations
checkpoint-status |  |  | checkpoint | Program dates issued / staging - sequencing confirmed
checkpoint-status |  |  | checkpoint | Shop drawings issued to Architect for review / approval
checkpoint-status |  |  | checkpoint | Shop drawings issued to Engineer for review / approval
checkpoint-status |  |  | checkpoint | Safari approval of shop drawings. Check dimensions, lifting eyes, RLs, openings, inserts and step locations.
checkpoint-status |  |  | checkpoint | Propping design approved.
checkpoint-status |  |  | checkpoint | Deadmen design confirmed
checkpoint-status |  |  | checkpoint | Lifting plan agreed
checkpoint-status |  |  | checkpoint | Delivery sheets aquired and correct delivery sequence confirmed
checklist-flat |  |  | checklist | Concrete Slab on Grade - |  |  |  |  | Yes | QA - 09. Concrete Slab on Grade (RevA) | 44931c0a-2388-4c56-bedd-5e5db02390c8
checkpoint-status |  |  | checkpoint | Plans showing RLs / set downs / nibs / rebates / slab thickness.
checkpoint-status |  |  | checkpoint | Slab on grade – top of metal RL.
checkpoint-status |  |  | checkpoint | Formwork in place.
checkpoint-status |  |  | checkpoint | Reinforcing steel – mesh size and lap.
checkpoint-status |  |  | checkpoint | Starter bars in correct position and size.
checkpoint-status |  |  | checkpoint | Holding bolts in place.
checkpoint-status |  |  | checkpoint | Floor thickness in place (random slab check areas).
checkpoint-status |  |  | checkpoint | Cover to reinforcing correct.
checkpoint-status |  |  | checkpoint | Construction joints / control joints installed.
checkpoint-status |  |  | checkpoint | Correct MPA / slump.
checkpoint-status |  |  | checkpoint | Council inspection or confirmation received to proceed
checkpoint-status |  |  | checkpoint | Structural engineer inspection or confirmation received to proceed
checkpoint-status |  |  | checkpoint | Levels of finish confirmed.
checkpoint-status |  |  | checkpoint | Curing – water spray / membrane ordered.
checkpoint-status |  |  | checkpoint | Check overspray / clean.
checkpoint-status |  |  | checkpoint | Control joints / saw-cuts and depth.
checklist-flat |  |  | checklist | Insitu slab infill - |  |  |  |  | Yes | QA - 34. Insitu slab infill (RevA) | 4faed5f0-4e45-4dd8-b2a5-6faf38803ff0
checkpoint-status |  |  | checkpoint | Plans showing RLs / set downs / nibs / rebates / slab thickness.
checkpoint-status |  |  | checkpoint | Formwork in place.
checkpoint-status |  |  | checkpoint | Reinforcing steel – mesh size and lap.
checkpoint-status |  |  | checkpoint | Starter bars in correct position and size.
checkpoint-status |  |  | checkpoint | Floor thickness in place (random slab check areas).
checkpoint-status |  |  | checkpoint | Cover to reinforcing correct.
checkpoint-status |  |  | checkpoint | Construction joints / control joints installed.
checkpoint-status |  |  | checkpoint | Correct MPA / slump.
checkpoint-status |  |  | checkpoint | Council inspection or confirmation received to proceed
checkpoint-status |  |  | checkpoint | Structural engineer inspection or confirmation received to proceed
checkpoint-status |  |  | checkpoint | Levels of finish confirmed.
checklist-flat |  |  | checklist | Demolition - |  |  |  |  | Yes | QA - 01. Demolition (RevA) | 50ab8828-0f7a-45f9-911d-34b7cd8d4a23
checkpoint-status |  |  | checkpoint | Pre-start meeting with council.
checkpoint-status |  |  | checkpoint | Asbestos invertergation completed and results confirmed
checkpoint-status |  |  | checkpoint | Method statement from demolition contractor.
checkpoint-status |  |  | checkpoint | Asbestos removal control plan been approved by third party and in place
checkpoint-status |  |  | checkpoint | SSSP from sub-contractor. All other relevant safety documentation received
checkpoint-status |  |  | checkpoint | Traffic management responsibilities identified and in place
checkpoint-status |  |  | checkpoint | Any hold points required?
checkpoint-status |  |  | checkpoint | Existing services disconnection; power, water, gas telephone etc.
checkpoint-status |  |  | checkpoint | Temporary works design completed by the engineer
checkpoint-status |  |  | checkpoint | Dust suppression methods in place and working
checkpoint-status |  |  | checkpoint | Propping supports in place and approved
checkpoint-status |  |  | checkpoint | Protection to adjacent buildings or existing buildings.
checkpoint-status |  |  | checkpoint | Any salvage items required.
checkpoint-status |  |  | checkpoint | SS lines capped
checkpoint-status |  |  | checkpoint | SW lines capped
checkpoint-status |  |  | checkpoint | Council inspection & sign off
checkpoint-status |  |  | checkpoint | Documentation to close out consent all received and filed
checklist-flat |  |  | checklist | Preline - |  |  |  |  | Yes | QA - 22. Preline (RevA) | 51a841df-4fd7-4b8b-9339-c9e454792407
checkpoint-status |  |  | checkpoint | Walls straight and plumb and Nogs and studs in place to take linings.
checkpoint-status |  |  | checkpoint | door timber studs installed with bracing/bolts in correct postion
checkpoint-status |  |  | checkpoint | Lintels complete.
checkpoint-status |  |  | checkpoint | HVAC nogs inplace
checkpoint-status |  |  | checkpoint | Shower rail nogs
checkpoint-status |  |  | checkpoint | Dryer nog
checkpoint-status |  |  | checkpoint | Towel rail nogs
checkpoint-status |  |  | checkpoint | wall hung vanity nogs
checkpoint-status |  |  | checkpoint | Light fitting nogs
checkpoint-status |  |  | checkpoint | Shower and return nogs
checkpoint-status |  |  | checkpoint | Door stop nogs
checkpoint-status |  |  | checkpoint | Kitchen nogs for over head cabinets
checkpoint-status |  |  | checkpoint | Accessible plywood full face nogs in place if applicable
checkpoint-status |  |  | checkpoint | Fire / Accoustic service metal boxes installed
checkpoint-status |  |  | checkpoint | Ceiling battens straight and nogs in place.
checkpoint-status |  |  | checkpoint | Control joins set out and installed
checkpoint-status |  |  | checkpoint | Insulation installed and strapped if required
checkpoint-status |  |  | checkpoint | Services final check; fire wiring, data wiring, mechanical ducting and wiring, plumbing, condensate A/C pipe, electrical, sprinklers
checkpoint-status |  |  | checkpoint | Plumbing water tests / pressure test / pipe isolation checked
checkpoint-status |  |  | checkpoint | plumbing service penetration sealed thru floor inc service risers
checkpoint-status |  |  | checkpoint | Electrical unit DB installed / mains installed / lighting & PP all checked
checkpoint-status |  |  | checkpoint | LV & Data, hib board installed / security / phone / TV wiring checked
checkpoint-status |  |  | checkpoint | Air/fire seal around windows and doors.
checkpoint-status |  |  | checkpoint | Intubat installed where required
checkpoint-status |  |  | checkpoint | Bracing elements marked.
checkpoint-status |  |  | checkpoint | Council inspection attached and remedials (If any) closed out
checklist-flat |  |  | checklist | HVAC - |  |  |  |  | Yes | QA - 23. HVAC (RevA) | 69a5a136-899d-4fbc-b668-1fbcb6093b31
checkpoint-status |  |  | checkpoint | Construction drawings and specification sent to contractor.
checkpoint-status |  |  | checkpoint | Power requirements confirmed
checkpoint-status |  |  | checkpoint | Switch board approved
checkpoint-status |  |  | checkpoint | Switch board delivery agreed
checkpoint-status |  |  | checkpoint | Locations agreed for all fittings / location of isolation key confirmed
checkpoint-status |  |  | checkpoint | Shop drawing presented and approved
checkpoint-status |  |  | checkpoint | Coordination with sub-trades; feeds for fire, plumbing sensors etc.
checkpoint-status |  |  | checkpoint | Garage ventilation installed / intake / extract
checkpoint-status |  |  | checkpoint | Condensate pipe work all connected
checkpoint-status |  |  | checkpoint | All wiring completed.
checkpoint-status |  |  | checkpoint | Fire collars / dampers insalled installed.
checkpoint-status |  |  | checkpoint | Testing and commissioning.
checkpoint-status |  |  | checkpoint | Drop test to final system complete
checklist-flat |  |  | checklist | Piling - |  |  |  |  | Yes | QA - 02. Piling (RevA) | 73150770-5787-4525-b0d9-673ffbac2b9f
checkpoint-status |  |  | checkpoint | Construction drawings and specification to piling contractor and surveyor.
checkpoint-status |  |  | checkpoint | Piling schedule complete with pile reference. Including Controstors piling log accurate to record, pile type, pile level, reinforcing RL, depth of piles / top of piles.
checkpoint-status |  |  | checkpoint | Surveyor to peg all piles.
checkpoint-status |  |  | checkpoint | Reinforcing checked and confirmed accurate before placement
checkpoint-status |  |  | checkpoint | Geotech booked for inspection or confirmation received to proceed
checkpoint-status |  |  | checkpoint | Structural engineer booked for inspection or confirmation received to proceed
checkpoint-status |  |  | checkpoint | Concrete booked – correct slump and MPA confirmed.
checkpoint-status |  |  | checkpoint | Top RL confirmed
checkpoint-status |  |  | checkpoint | Concrete booked – correct slump and MPA confirmed.
checkpoint-status |  |  | checkpoint | Final survey to confrm actual pile location requiring Engineer sign off
checklist-flat |  |  | checklist | Plasterboard Linings - |  |  |  |  | Yes | QA - 30. Plasterboard Linings (RevA) | 74d68f24-553b-4626-bd7e-03afef71a39e
checkpoint-status |  |  | checkpoint | Highlighted plan with types of GIB/EPB sent to fixer.
checkpoint-status |  |  | checkpoint | Pre-line completed and any remedials closed out
checkpoint-status |  |  | checkpoint | Check type of plasterboard is correct.
checkpoint-status |  |  | checkpoint | Check thickness of plasterboard is correct.
checkpoint-status |  |  | checkpoint | Check fixings as per manufacturer’s manuals.
checkpoint-status |  |  | checkpoint | Check service shafts / risers consttructed correctly as per manuals
checkpoint-status |  |  | checkpoint | Correct jointing tape used.
checkpoint-status |  |  | checkpoint | Penetrations where required for services etc. extra layer if required to accomadate passive fire requirement
checkpoint-status |  |  | checkpoint | Deflection head detail and fixings correct
checkpoint-status |  |  | checkpoint | Fire stopping complete.
checkpoint-status |  |  | checkpoint | Fire sealant / sound sealant installed.
checkpoint-status |  |  | checkpoint | Council inspection recevied and remedials (if any) closed out
checkpoint-status |  |  | checkpoint | Fire stopping completed to specified level of finish
checkpoint-status |  |  | checkpoint | Sign off by stopping contractor prior to seal coat.
checklist-flat |  |  | checklist | Postline (Services) - |  |  |  |  | Yes | QA - 29. Postline– services check (RevA) | 7d63e8e8-94e8-4f69-851c-0bfeb627d0f0
checkpoint-status |  |  | checkpoint | AC duct brought through, kitchen, bathroom & laundry
checkpoint-status |  |  | checkpoint | Fire sprinklers brought thru
checkpoint-status |  |  | checkpoint | PP, light & data outlets brought thru
checkpoint-status |  |  | checkpoint | Accoustic / Fire seals installed and lablled corectly
checkpoint-status |  |  | checkpoint | Laundry drain inatalled / HVAC condensate installed
checkpoint-status |  |  | checkpoint | Lagging of pipe work
checkpoint-status |  |  | checkpoint | Service hatches installed
checkpoint-status |  |  | checkpoint | Switch board & data cabinetry recessed correctly
checkpoint-status |  |  | checkpoint | Check size of PP & light cut outs
checklist-flat |  |  | checklist | Postline (Passive Fire) - |  |  |  |  | Yes | QA - 33. Postline – passive fire (RevA) | 806b9c36-eb45-427d-8049-64804e06eae0
checkpoint-status |  |  | checkpoint | All services brought through in correct locations
checkpoint-status |  |  | checkpoint | Penetrations match as-built passive fire mark-up - through floor and walls
checkpoint-status |  |  | checkpoint | All fire rated collers / penetrations installed correctly with compliant stickers
checkpoint-status |  |  | checkpoint | Photos taken of each individual penetration through floor and wall to match as-built
checkpoint-status |  |  | checkpoint | Accoustic and fire seals completed around edges and façade junction
checkpoint-status |  |  | checkpoint | Check fixings as per manufacturer’s manuals (bracing & fire line)
checkpoint-status |  |  | checkpoint | Council / Fire inspection received and remedials (if any) closed out
checklist-flat |  |  | checklist | Plumbing - |  |  |  |  | Yes | QA - 24. Plumbing (RevA) | 84342fb2-9998-4294-899c-60860c1de14c
checkpoint-status |  |  | checkpoint | Construction drawings and specification sent to plumbing contractor.
checkpoint-status |  |  | checkpoint | Positions coordinated with units / kitchens / bathrooms / sinks.
checkpoint-status |  |  | checkpoint | Gas supply confirmed
checkpoint-status |  |  | checkpoint | Lift pumps approved
checkpoint-status |  |  | checkpoint | Nogs installed.
checkpoint-status |  |  | checkpoint | Piping complete and complete and capped off.
checkpoint-status |  |  | checkpoint | Insulation / lagging installed.
checkpoint-status |  |  | checkpoint | Approved water meters installed
checkpoint-status |  |  | checkpoint | Fire collars.
checkpoint-status |  |  | checkpoint | Coordination for sensors etc.
checkpoint-status |  |  | checkpoint | Pressure test / council inspection.
checklist-flat |  |  | checklist | Drainage - |  |  |  |  | Yes | QA - 05. Drainage (RevA) | 8462ee4e-3ace-4d36-a568-a982728d2268
checkpoint-status |  |  | checkpoint | Construction drawings and specification sent to subcontractor.
checkpoint-status |  |  | checkpoint | Site set out by surveyor.
checkpoint-status |  |  | checkpoint | Site RL installed by surveyor.
checkpoint-status |  |  | checkpoint | Confirm backfill requirements (hardfill / compaction)
checkpoint-status |  |  | checkpoint | TMP requirements
checkpoint-status |  |  | checkpoint | Haunching / Benching completed
checkpoint-status |  |  | checkpoint | Lines cleaned out CCTV if required
checkpoint-status |  |  | checkpoint | Puclic connection complete inspected and signed off
checkpoint-status |  |  | checkpoint | Council inspection.
checklist-flat |  |  | checklist | Minor Variation - |  |  |  |  | Yes | Add Council Minor Variation Checklist | 8e1aba6c-c311-43f5-b50f-8b6aac4ee780
checkpoint-status |  |  | checkpoint | Minor variation status (Pass once approved & all information is attached including observations, correspondence & close out evidence)
label | d83c76ad-c2c4-422a-b3d0-5e46ac4be24f |  | note | PASS above checkpoint when variation is approved
label | ab21c4bc-c773-43ee-88d7-f338c674ee92 |  | note | If minor variation is a FAIL - document why below and follow appropriate corrective actions
text | e716f58a-4420-4e11-91ae-f4fef0f7ba87 |  | textbox | Date of application
text | 6931f74e-964b-42b5-905c-440c2ce0001a |  | textbox | Reason for application
text | 4ce69a81-cba4-4eac-b963-ff28392bbaf5 |  | textbox | Date of approval / acceptance
text | 78d9159e-0896-4188-a542-fa6b1bf43aaa |  | textbox | Inspection Type Code (If applicable e.g. Site meeting IME)
boolean | d24858c1-85f5-44b8-99c0-818a707a7f19 |  | tickbox | Council approval of minor variation attached
checklist-flat |  |  | checklist | Lift - |  |  |  |  | Yes | QA - 21. Lift (RevA) | 937e66fe-813d-48a3-b3af-a951c84edf36
checkpoint-status |  |  | checkpoint | Construction drawings and specification to subcontractor.
checkpoint-status |  |  | checkpoint | Lift design complete
checkpoint-status |  |  | checkpoint | Access control / security requirements confirmed
checkpoint-status |  |  | checkpoint | Lift pit & shaft size confirmed
checkpoint-status |  |  | checkpoint | Lift sump installed
checkpoint-status |  |  | checkpoint | Lift finishes confirmed
checkpoint-status |  |  | checkpoint | Lift services confirmed (power, sump pump, ventilation, lighting , security requirements)
checkpoint-status |  |  | checkpoint | Confirmation of service lift required
checkpoint-status |  |  | checkpoint | lift shaft watertight
checkpoint-status |  |  | checkpoint | Trim beams installed / Seperation panels installed as per specification
checkpoint-status |  |  | checkpoint | Lift door openings checked
checkpoint-status |  |  | checkpoint | Top door opening confirmed including service panel
checkpoint-status |  |  | checkpoint | FFL and threshold details complete
checkpoint-status |  |  | checkpoint | Fire rating to inside of opening completed
checkpoint-status |  |  | checkpoint | lifting beam installed and marked correctly
checkpoint-status |  |  | checkpoint | Lift commissioned and signed off in full by Lift contractor
checklist-flat |  |  | checklist | PCP Erection - |  |  |  |  | Yes | QA - 13. PCP Erection (RevA) | 939eafb8-a4e9-4f5c-8629-29bdf4a00bb1
checkpoint-status |  |  | checkpoint | Construction drawings and specification sent to sub-contractor.
checkpoint-status |  |  | checkpoint | For Construction drawings onsite
checkpoint-status |  |  | checkpoint | Deadmen installed
checkpoint-status |  |  | checkpoint | RL's confirmed
checkpoint-status |  |  | checkpoint | Panel set-out check / panel location marked
checkpoint-status |  |  | checkpoint | Drossbach set out confirmed / reo height checked
checkpoint-status |  |  | checkpoint | Panel props onsite with propping plan
checkpoint-status |  |  | checkpoint | Lifting plan approved into TA and signed on by all involved
checkpoint-status |  |  | checkpoint | Packing confirmed / Pef rod installed
checkpoint-status |  |  | checkpoint | Panels plumb and level.
checkpoint-status |  |  | checkpoint | Drossbach packing and grouting confirmed
checkpoint-status |  |  | checkpoint | Defects notified to precast supplier.
checkpoint-status |  |  | checkpoint | Drypacking of base of panels & grounting complee of drossbachs
checklist-flat |  |  | checklist | Suspended Floor (Rib & Tile) - |  |  |  |  | Yes | QA - 16. Suspended Floor (Rib & Tile) (RevA) | 94bc60bb-984a-443c-b04c-65af50759a5d
checkpoint-status |  |  | checkpoint | Construction drawings and specification to subcontractor.
checkpoint-status |  |  | checkpoint | Site dimensions checked
checkpoint-status |  |  | checkpoint | Install/lifting plan agreed into TA and signed onto by all involved
checkpoint-status |  |  | checkpoint | Brackets correctly bolted to required specification
checkpoint-status |  |  | checkpoint | Correct seating allowed
checkpoint-status |  |  | checkpoint | Shoring system designed / required
checkpoint-status |  |  | checkpoint | Shoring installed
checkpoint-status |  |  | checkpoint | Timber infill's correct
checkpoint-status |  |  | checkpoint | Crane ordered, correct size and reach
checkpoint-status |  |  | checkpoint | Reinforcing in place, correct steel and clearances
checkpoint-status |  |  | checkpoint | Perimeter boxing installed
checkpoint-status |  |  | checkpoint | Construction joints / control joints installed.
checkpoint-status |  |  | checkpoint | Correct MPA / slump.
checkpoint-status |  |  | checkpoint | Council inspection or confirmation received to proceed
checkpoint-status |  |  | checkpoint | Structural engineer inspection or confirmation received to proceed
checkpoint-status |  |  | checkpoint | Curing – water spray / membrane ordered.
checkpoint-status |  |  | checkpoint | Check overspray / clean.
checklist-flat |  |  | checklist | Precast Balconies - |  |  |  |  | Yes | QA - 17. Precast Balconies (RevA) | 96941786-1eca-497f-9ec3-9cb7134d3763
checkpoint-status |  |  | checkpoint | Construction drawings and specification to subcontractor.
checkpoint-status |  |  | checkpoint | Install/lifting plan agreed into TA and signed onto by all involved
checkpoint-status |  |  | checkpoint | Site dimensions checked and marked out
checkpoint-status |  |  | checkpoint | Correct seating allowed
checkpoint-status |  |  | checkpoint | Shoring system designed / required
checkpoint-status |  |  | checkpoint | Shoring installed
checkpoint-status |  |  | checkpoint | Structural Steel permanent post beams installed
checkpoint-status |  |  | checkpoint | Crane ordered, correct size and reach
checkpoint-status |  |  | checkpoint | Permanent connection installed (bolted / site welding)
checkpoint-status |  |  | checkpoint | Structural engineer inspection had or photos supplied
checklist-sectioned |  |  | checklist | Date: |  |  |  |  | Yes | H&S - Safari Safety Audit | a2ac8423-1d9a-457d-b3c6-8165e1875f52
checkpoint-group |  |  | section | ADMINISTRATION - Main Contractor
checkpoint-status |  |  | checkpoint | 1. Is there evidence of Site Specific Safety activity requirements in any tender document?
checkpoint-status |  |  | checkpoint | 2. Is there a Site Safety Management Plan in place?
checkpoint-status |  |  | checkpoint | 3. Is there evidence of a hazard identificiation and control procedure including at least one of these activities: hazard register, up to date hazard ID board, task analysis?
checkpoint-status |  |  | checkpoint | 4. Is there a record of Passport, Workplace Safety or Gold Card numbers for all Workers on Site?
checkpoint-status |  |  | checkpoint | 5. Is there evidence that at least one "Site Subcontractor Safety Meeting" was held in the last 30 days?
checkpoint-status |  |  | checkpoint | 6. Is there evidence that a Toolbox Talk was held in the last 30 days?
checkpoint-status |  |  | checkpoint | 7. Is there evidence that at least one Safety Inspection was conducted in the last 30 days?
checkpoint-status |  |  | checkpoint | 8. Is there a Training/Competency Register for all Main Contractor Employees on site?
checkpoint-status |  |  | checkpoint | 9. Is an Accident Register being maintained?
checkpoint-status |  |  | checkpoint | 10. Is an Accident Register being maintained?
checkpoint-status |  |  | checkpoint | 11. Is Task Analysis being carried out for "Significantly Hazardous Physical Work"?
checkpoint-status |  |  | checkpoint | 12. Is there a Safety Activity Wall-Chart displayed on site?
checkpoint-status |  |  | checkpoint | 13. Has anyone from the Management Team signed the Wall-Chart in the last 30 days?
checkpoint-status |  |  | checkpoint | 14. For current Notifiable Work is there evidence that DoL is notified?
checkpoint-status |  |  | checkpoint | 15. For current Notifiable Work do all Supervisors have a current Gold Card (or apporpriate equivalent)?
checkpoint-status |  |  | checkpoint | 16. Is there an operating Permit to Work system in place?
checkpoint-status |  |  | checkpoint | 17. Is there a site emergency plan?
checkpoint-status |  |  | checkpoint | 18. Are there arrangements to deal with Visitors to site (for e.g. signage, escorts, PPE or inductions)?
checkpoint-status |  |  | checkpoint | 19. Is there a Site Specific Induction Procedure in place?
checkpoint-group |  |  | section | ADMINISTRATION - Subcontractors
checkpoint-status |  |  | checkpoint | 1. Is there evidence of a Pre-Start Meeting held with the selected Subcontractor?
checkpoint-status |  |  | checkpoint | 2. Does the selected Subcontractor have a Site Specific Safety Plan?
checkpoint-status |  |  | checkpoint | 3. Is there evidence of a hazard identification and control procedure including at least one of these activities: hazard register or task analysis?
checkpoint-status |  |  | checkpoint | 4. Is there evidence that a Tool Box Talk was held in the last 30 days?
checkpoint-status |  |  | checkpoint | 5. Is there a Training/Competency Register for all Subcontractor Employees on site?
checkpoint-status |  |  | checkpoint | 6. Is Task Analysis being carried out for “Significantly Hazardous Physical Work”?
checkpoint-status |  |  | checkpoint | 7. Has Emergency Planning been completed for all “Significantly Hazardous Work”?
checkpoint-status |  |  | checkpoint | 8. Is the name and contact number of the Safety Supervisor documented?
checkpoint-status |  |  | checkpoint | 9. For current Notifiable Work, where the Subcontractors employees are involved, is there evidence that DoL is notified?
checkpoint-status |  |  | checkpoint | 10. For current Notifiable Work do all Supervisors have a current Gold Card (or apporpriate equivalent)?
checkpoint-status |  |  | checkpoint | 11. Is an Accident Register being maintained?
checkpoint-status |  |  | checkpoint | 12. Is there evidence of Accident/Incident Investigation?
checkpoint-status |  |  | checkpoint | 13. Are Passport details provided for Subcontractor's Employees?
checkpoint-status |  |  | checkpoint | 14. Is there evidence that the Subcontractor has completed a self inspection in the last 30 days?
checkpoint-status |  |  | checkpoint | 15. Is there a Hazardous Substances Register and Safety Data Sheets for Hazardous substances?
checkpoint-group |  |  | section | FACILITIES
checkpoint-status |  |  | checkpoint | 1. Are site offices clean & tidy?
checkpoint-status |  |  | checkpoint | 2. Are there toilet facilities sufficient for number of sit Workers?
checkpoint-status |  |  | checkpoint | 3. Are separate toilet facilities available for female Workers?
checkpoint-status |  |  | checkpoint | 4. Are toilet areas clean & tidy?
checkpoint-status |  |  | checkpoint | 5. Are toilets supplied with paper and handwash?
checkpoint-status |  |  | checkpoint | 6. Are there amenities or arrangements for Workers to have lunch and smoko?
checkpoint-status |  |  | checkpoint | 7. Are lunch room & food prep area clean and tidy?
checkpoint-status |  |  | checkpoint | 8. Have hand washing facilities been provided?
checkpoint-status |  |  | checkpoint | 9. Are first aid kits in place & well stocked?
checkpoint-status |  |  | checkpoint | 10. Are first aid kit contents within expiry date?
checkpoint-status |  |  | checkpoint | 11. Are appropriate fire extinguishers charged & current (Serviced 12 monthly)
checkpoint-status |  |  | checkpoint | 12. Is there adequate site signage?
checkpoint-status |  |  | checkpoint | 13. Is there adequate site fencing?
checkpoint-group |  |  | section | HOUSEKEEPING
checkpoint-status |  |  | checkpoint | 1. Are work areas clean & tidy?
checkpoint-status |  |  | checkpoint | 2. Are access ways clear? (including stairways)
checkpoint-status |  |  | checkpoint | 3. Are materials stacked safely?
checkpoint-status |  |  | checkpoint | 4. Have adequate rubbish bins or skips been provided?
checkpoint-status |  |  | checkpoint | 5. Have hazardous substances and chemicals been adequately controlled?
checkpoint-status |  |  | checkpoint | 6. Have combustable materials and substances been adequately controlled?
checkpoint-status |  |  | checkpoint | 7. Have all vertical reinforcing steel bars been capped?
checkpoint-status |  |  | checkpoint | 8. Are there enclosed material waste chutes?
checkpoint-status |  |  | checkpoint | 9. Have nails in timber been made safe?
checkpoint-status |  |  | checkpoint | 10. Are slips & trips hazards controlled?
checkpoint-group |  |  | section | PERSONAL PROTECTIVE EQUIPMENT (PPE)
checkpoint-status |  |  | checkpoint | 1. Has mandatory PPE for site been specified and signage posted?
checkpoint-status |  |  | checkpoint | 2. Are hard hats being worn where required?
checkpoint-status |  |  | checkpoint | 3. Are safety glasses/goggles being worn where required?
checkpoint-status |  |  | checkpoint | 4. Are respirators or masks being worn where required?
checkpoint-status |  |  | checkpoint | 5. Is hearing protection being worn where required?
checkpoint-status |  |  | checkpoint | 6. Are appropriate gloves being worn where required?
checkpoint-status |  |  | checkpoint | 7. Is protective clothing being worn where required?
checkpoint-status |  |  | checkpoint | 8. Is high visibility clothing being worn where required?
checkpoint-status |  |  | checkpoint | 9. Is safety footwear being worn where required?
checkpoint-group |  |  | section | EXCAVATIONS AND TRENCHES
checkpoint-status |  |  | checkpoint | 1. Have underground services been located? (plans, service location)
checkpoint-status |  |  | checkpoint | 2. Are excavations battered, benced or supported? (trenches >1.5m deep)
checkpoint-status |  |  | checkpoint | 3. Is there adequate shoring, trenchshields, sheetpiles before entry into excavations?
checkpoint-status |  |  | checkpoint | 4. Is there edge protection to prevent falls?
checkpoint-status |  |  | checkpoint | 5. Is there safe ladder access to excavation?
checkpoint-status |  |  | checkpoint | 6. Does job method avoid work in usupported trenches?
checkpoint-status |  |  | checkpoint | 7. Is materials & spoil stored to prevent edge collapse? (600mm)
checkpoint-status |  |  | checkpoint | 8. Are vehicles & plant at distance to prevent collapse?
checkpoint-status |  |  | checkpoint | 9. Is a "stop block" used for tipping vehicles?
checkpoint-group |  |  | section | FALSEWORK / FORMWORK
checkpoint-status |  |  | checkpoint | 1. Has the propping been designed & inspected by a Competent Person?
checkpoint-status |  |  | checkpoint | 2. Has falsework and formwork been checked by a Competent Person before pour?
checkpoint-status |  |  | checkpoint | 3. Is there adequate bearing on all supports?
checkpoint-status |  |  | checkpoint | 4. Are support frames/props plumb?
checkpoint-status |  |  | checkpoint | 5. Are frames/props appropriately braced and/or tied?
checkpoint-status |  |  | checkpoint | 6. Are the correct pins used in props?
checkpoint-status |  |  | checkpoint | 7. Are forkheads used for bearer support?
checkpoint-status |  |  | checkpoint | 8. Are forkheads wedged centrally?
checkpoint-status |  |  | checkpoint | 9. Are screwjacks within maximum extension allowed?
checkpoint-status |  |  | checkpoint | 10. Have falls from falsework and formwork been controlled?
checkpoint-group |  |  | section | WELDING AND GAS CUTTING
checkpoint-status |  |  | checkpoint | 1.Are gas bottles secured in use and/or stored correctly?
checkpoint-status |  |  | checkpoint | 2. Do gas sets have flash black arrestors?
checkpoint-status |  |  | checkpoint | 3. Is there a Hot Work Procedure/Permit System?
checkpoint-status |  |  | checkpoint | 4. Are there welding screens and/or signs in place?
checkpoint-status |  |  | checkpoint | 5. Is there an appropriate extinguisher at the work area?
checkpoint-group |  |  | section | SUN EXPOSURE
checkpoint-status |  |  | checkpoint | 1. Is shade cover or screens over work areas where practicable?
checkpoint-status |  |  | checkpoint | 2. Are Employees wearing clothing to prevent sun exposure?
checkpoint-status |  |  | checkpoint | 3. Is there a sun screen on site of the broad spectrum range?
checkpoint-status |  |  | checkpoint | 4. Does the sun screen on site provide a sun protection factor of 30 or more?
checkpoint-status |  |  | checkpoint | 5. Are Workers on site applying sun screen to exposed skin areas?
checkpoint-group |  |  | section | NOISE
checkpoint-status |  |  | checkpoint | 1. Is noise level for operations/site being measured?
checkpoint-status |  |  | checkpoint | 2. Is Worker exposure to noise being monitored?
checkpoint-status |  |  | checkpoint | 3. Have work operations been arranged to reduce exposure to noise hazards?
checkpoint-status |  |  | checkpoint | 4. Has plant and equipment been configured to reduce noise?
checkpoint-status |  |  | checkpoint | 5. Are Workers wearing hearing protection on site?
checkpoint-status |  |  | checkpoint | 6. Is hearing loss of Workers being moniitored?
checkpoint-group |  |  | section | CONFINED SPACE
checkpoint-status |  |  | checkpoint | 1. Is there a Confined Space Management (CSM) plan on site?
checkpoint-status |  |  | checkpoint | 2. Is there a competently trained CSM Supervisor on site?
checkpoint-status |  |  | checkpoint | 3. Have all Workers been trained to work in a Confined Space (CS)?
checkpoint-status |  |  | checkpoint | 4. Is an Entry Permit System in use to manage CS work?
checkpoint-status |  |  | checkpoint | 5. Is a monitoring person stationed outside the CS while work in progress?
checkpoint-status |  |  | checkpoint | 6. Have all services associated with CS been disconnected or isolated (lockout tagout)?
checkpoint-status |  |  | checkpoint | 7. Does the CSM Plan describe the Emergency Rescue Procedures?
checkpoint-status |  |  | checkpoint | 8. Is Emergency Rescue Equipment available at or near the entry?
checkpoint-status |  |  | checkpoint | 9. Is emergency breathing apparatus available at or near the entry?
checkpoint-status |  |  | checkpoint | 10. Before entry to CS is atmospheric testing carried out?
checkpoint-status |  |  | checkpoint | 11. During work in CS is atmospheric testing carried out?
checkpoint-group |  |  | section | CEMENT AND CONCRETE
checkpoint-status |  |  | checkpoint | 1. Are Concrete Workers trained and competent?
checkpoint-status |  |  | checkpoint | 2. Are Cement Workers protected from contact with wet cement?
checkpoint-status |  |  | checkpoint | 3. Is concrete pump boom area isolated from Workers being underneath?
checkpoint-status |  |  | checkpoint | 4. Is clean water on site readily available?
checkpoint-group |  |  | section | ASBESTOS
checkpoint-status |  |  | checkpoint | 1. Is Asbestos Removal in accordance with DoL Guidelines?
checkpoint-status |  |  | checkpoint | 2. Is there a Supervisor with a Certificate of Competence for Restricted Work?
checkpoint-status |  |  | checkpoint | 3. Is there an Asbestos Removal Plan on site?
checkpoint-status |  |  | checkpoint | 4. Has access to work area been restricted?
checkpoint-status |  |  | checkpoint | 5. Has adequate signage been posted at work area?
checkpoint-status |  |  | checkpoint | 6. Is there adequate containment of partical drift?
checkpoint-status |  |  | checkpoint | 7. Is there adequate air extraction with HEPA filter?
checkpoint-status |  |  | checkpoint | 8. Is air monitoring for contamination being performed?
checkpoint-group |  |  | section | CHEMICALS
checkpoint-status |  |  | checkpoint | 1. Are Employees provided with Chemical Use Inductions?
checkpoint-status |  |  | checkpoint | 2. Are Chemical Management Responsibilites defined?
checkpoint-status |  |  | checkpoint | 3. Are "Approved Handlers" certified?
checkpoint-status |  |  | checkpoint | 4. Is there a "Location Certificate"?
checkpoint-status |  |  | checkpoint | 5. Is there a "Person in Charge"?
checkpoint-status |  |  | checkpoint | 6. Are Workers protected from chemical exposure?
checkpoint-status |  |  | checkpoint | 7. Are chemicals stored in proper containers?
checkpoint-status |  |  | checkpoint | 8. Are chemicals properly disposed of?
checkpoint-group |  |  | section | DEMOLITION
checkpoint-status |  |  | checkpoint | 1. Is there a Demolition Workplan that complies with AS2061 or local requirements?
checkpoint-status |  |  | checkpoint | 2. Is there an Engineer's Report/advice?
checkpoint-status |  |  | checkpoint | 3. Is there a Demolition Supervisor on site?
checkpoint-status |  |  | checkpoint | 4. Is there site security fencing?
checkpoint-status |  |  | checkpoint | 5. Is there signage for demolition activities?
checkpoint-status |  |  | checkpoint | 6. Is there gantry/overhead protection for the public?
checkpoint-status |  |  | checkpoint | 7. Have all building services been disconnected?
checkpoint-group |  |  | section | FALL PREVENTION
checkpoint-status |  |  | checkpoint | 1. Are there guardrails between 0.9m & 1.1m?
checkpoint-status |  |  | checkpoint | 2. Are fall hazards controlled?
checkpoint-status |  |  | checkpoint | 3. Are fall edges fitted with guardrails/toeboards?
checkpoint-status |  |  | checkpoint | 4. Are holes & floor penetratins covered and marked?
checkpoint-status |  |  | checkpoint | 5. Are stairways fitted with handrails?
checkpoint-status |  |  | checkpoint | 6. Are liftshafts closed off?
checkpoint-group |  |  | section | HARNESS USE
checkpoint-status |  |  | checkpoint | 1. Are restraint systems being used in preference to fall arrest systems?
checkpoint-status |  |  | checkpoint | 2. Are service/maintenance records for harness equipment being kept?
checkpoint-status |  |  | checkpoint | 3. Have Employees undertaken training for harness use?
checkpoint-status |  |  | checkpoint | 4. Are Supervisors of fall arrest systems trained and competent to NZQA US15757?
checkpoint-status |  |  | checkpoint | 5. Is the fall arrest system suitable for the work requirements?
checkpoint-status |  |  | checkpoint | 6. Was all equipment checked prior to use?
checkpoint-status |  |  | checkpoint | 7. Are hazards associated with fall arrest systems controlled?
checkpoint-status |  |  | checkpoint | 8. Is the fall arrest connection correctly set up?
checkpoint-status |  |  | checkpoint | 9. Are harnesses correctly fitted?
checkpoint-status |  |  | checkpoint | 10. Is equipment in serviceable condition?
checkpoint-status |  |  | checkpoint | 11. Is rescue equipment present at job site?
checkpoint-group |  |  | section | LADDERS
checkpoint-group |  |  | section | STANDARD LADDERS
checkpoint-status |  |  | checkpoint | 1. Are ladders of industrial standard?
checkpoint-status |  |  | checkpoint | 2. Are Workers using ladders correctly?
checkpoint-status |  |  | checkpoint | 3. Are ladders set up on firm level ground?
checkpoint-status |  |  | checkpoint | 4. Are ladders secured? (base and/or top)
checkpoint-status |  |  | checkpoint | 5. Is ladder set at correct angle? (4 up to 1 out)
checkpoint-status |  |  | checkpoint | 6. Are ladders in good condition?
checkpoint-status |  |  | checkpoint | 7. Do ladders project 1m above step off point?
checkpoint-group |  |  | section | STEP LADDERS
checkpoint-status |  |  | checkpoint | 1. Is the stepladder suitable for the job?
checkpoint-status |  |  | checkpoint | 2. Are stepladder lock bars in place?
checkpoint-status |  |  | checkpoint | 3. Are stepladders set up on firm level gound?
checkpoint-status |  |  | checkpoint | 4. Are stepladders in good condition?
checkpoint-group |  |  | section | STANDING SCAFFOLD
checkpoint-status |  |  | checkpoint | 1. Is scaffold suitable for the job?
checkpoint-status |  |  | checkpoint | 2. Has scaffold been erected by Certified Scaffolder?
checkpoint-status |  |  | checkpoint | 3. Is scaf-tag/acu-log scaffold register up to date?
checkpoint-status |  |  | checkpoint | 4. Are there adequated baseplates & soleboards?
checkpoint-status |  |  | checkpoint | 5. Are ladders on scaffold secured?
checkpoint-status |  |  | checkpoint | 6. Does ladder extend 1m past step off? (or suitable hand holds)
checkpoint-status |  |  | checkpoint | 7.Is there suitable access to scaffold platforms?
checkpoint-status |  |  | checkpoint | 8. Are work platforms adequate?
checkpoint-status |  |  | checkpoint | 9. Are there guardrails between 0.9m and 1.1m?
checkpoint-status |  |  | checkpoint | 10. Is there an intermediatee rail in place?
checkpoint-status |  |  | checkpoint | 11. Is a toeboard in place?
checkpoint-status |  |  | checkpoint | 12. Is there debris netting in place?
checkpoint-group |  |  | section | MOBILE SCAFFOLD
checkpoint-status |  |  | checkpoint | 1. Is mobile scaffold suitable for the job?
checkpoint-status |  |  | checkpoint | 2. Is mobile scaffold set up on firm level ground?
checkpoint-status |  |  | checkpoint | 3. Is scaf-tag/acu-log in place & up to date?
checkpoint-status |  |  | checkpoint | 4. Are wheels locked?
checkpoint-status |  |  | checkpoint | 5. Are wheels turned out? (increased stability)
checkpoint-status |  |  | checkpoint | 6. Are working levells fully decked & secure?
checkpoint-status |  |  | checkpoint | 7. Is access from within the scaffold frame?
checkpoint-status |  |  | checkpoint | 8. Mobile scaffold at correct base width to height ratio?
checkpoint-status |  |  | checkpoint | 9. Are outriggers fitted where required?
checkpoint-status |  |  | checkpoint | 10. Are there guardrails between 0.9m and 1.1m?
checkpoint-group |  |  | section | SPECIAL SCAFFOLD
checkpoint-status |  |  | checkpoint | 1. Has a Competent Person designed the special scaffold?
checkpoint-status |  |  | checkpoint | 2. Is there a copy of a Registered Engineers Design Certificate?
checkpoint-status |  |  | checkpoint | 3. Does the scaffold structure comply with the Design Certificate?
checkpoint-status |  |  | checkpoint | 4. Has a Certified Scaffolder erected the scaffold?
checkpoint-status |  |  | checkpoint | 5. Is there a current Scaffold Register?
checkpoint-group |  |  | section | SUSPENDED SCAFFOLDS (SWINGING STAGE)
checkpoint-status |  |  | checkpoint | 1. Is there a current Scaffold Register (daily)?
checkpoint-status |  |  | checkpoint | 2. Are roof suspension rigs secured against movement?
checkpoint-status |  |  | checkpoint | 3. Are sufficient counterweights secured in place?
checkpoint-status |  |  | checkpoint | 4. Is the needle overhang and tail lenth ration correct?
checkpoint-status |  |  | checkpoint | 5. Are the suspension ropes secure and in good conditions?
checkpoint-status |  |  | checkpoint | 6. Are all control and emergency buttons operational?
checkpoint-status |  |  | checkpoint | 7. Are operations within the Safe Working Load (SWL) of platform?
checkpoint-status |  |  | checkpoint | 8. Is the path of the suspended scafffold clear of projections?
checkpoint-status |  |  | checkpoint | 9. Is the power cable prevented from becoming dislodged or damaged?
checkpoint-status |  |  | checkpoint | 10. Are Operators all using a safety harness?
checkpoint-status |  |  | checkpoint | 11. Are Workers connected to independent safety line or other engineered anchor system?
checkpoint-status |  |  | checkpoint | 12. Are warning notices and barricades at ground level?
checkpoint-group |  |  | section | ELEVATED WORK PLATFORMS (EWP)
checkpoint-status |  |  | checkpoint | 1. Is EWP set up on firm level ground?
checkpoint-status |  |  | checkpoint | 2. Are outriggers fully extended?
checkpoint-status |  |  | checkpoint | 3. Has area at base of EWP been isolated?
checkpoint-status |  |  | checkpoint | 4. Is EWP at least 4m from power lines?
checkpoint-status |  |  | checkpoint | 5. Are safety harnesses being worn in boom mounted buckets?
checkpoint-status |  |  | checkpoint | 6. Has EWP been inspected & certified within last 6 months?
checkpoint-group |  |  | section | TRANSPORT & MOB MECHANICAL PLANT
checkpoint-status |  |  | checkpoint | 1. Are Drivers/Operators trained?
checkpoint-status |  |  | checkpoint | 2. Are vehicles securely loaded?
checkpoint-status |  |  | checkpoint | 3. Are reversing vehicles controlled?
checkpoint-status |  |  | checkpoint | 4. Are vehicle warning signs displayed?
checkpoint-status |  |  | checkpoint | 5. Does mobile plant have roll over protective structure?
checkpoint-status |  |  | checkpoint | 6. Is protective structure in good repair?
checkpoint-status |  |  | checkpoint | 7. Is seat belt effective and in good repair?
checkpoint-group |  |  | section | EQUIPMENT & MACHINERY & TOOLS
checkpoint-status |  |  | checkpoint | 1. Is machinery in good operation condition?
checkpoint-status |  |  | checkpoint | 2. Are gears, chain drives & shafts, and moving parts guarded?
checkpoint-status |  |  | checkpoint | 3. Are guards secured & in good order?
checkpoint-status |  |  | checkpoint | 4. Do bench saws have a riving knife & hood guard
checkpoint-status |  |  | checkpoint | 5. Does compressed air have matched & secured connections?
checkpoint-group |  |  | section | CRANES & LIFTING APPLIANCES
checkpoint-status |  |  | checkpoint | 1. Are crane outriggers fully extended?
checkpoint-status |  |  | checkpoint | 2. Are loads correctly slung?
checkpoint-status |  |  | checkpoint | 3. Has lift zone been isolated or cleared of people?
checkpoint-status |  |  | checkpoint | 4. Is there a current Test Certificate?
checkpoint-status |  |  | checkpoint | 5. Are Weekly Inspections carried out?
checkpoint-status |  |  | checkpoint | 6. Are the crane slings certified?
checkpoint-status |  |  | checkpoint | 7. Are the Crane Operator & Dogman trained appropriately?
checkpoint-group |  |  | section | POWDER-ACTUATED TOOLS
checkpoint-status |  |  | checkpoint | 1. Is Operator certified?
checkpoint-status |  |  | checkpoint | 2. Does tool have 6 monthly certifcate?
checkpoint-status |  |  | checkpoint | 3. Are tool & cartridges secured when not in use?
checkpoint-status |  |  | checkpoint | 4. Has PAT signage been posted at work area?
checkpoint-status |  |  | checkpoint | 5. Has firing zone been isolated or cleared of people?
checkpoint-status |  |  | checkpoint | 6. Have walls or surfaces been checked for service conduits? (e.g gas or electrical)
checkpoint-status |  |  | checkpoint | 7. Is a 3 second verbal waning given?
checkpoint-status |  |  | checkpoint | 8. Is hearing & eye protection worn?
checkpoint-group |  |  | section | ELECTRICAL
checkpoint-status |  |  | checkpoint | 1. Are electrical tools and leads visually inspected for faults prior to use?
checkpoint-status |  |  | checkpoint | 2. Are electrical leads and tools free from defects and damage?
checkpoint-status |  |  | checkpoint | 3. Are electrical tools and leads tagged quarterly?
checkpoint-status |  |  | checkpoint | 4. Are protected power outlets being used on site (e.g. lifeguards or RCDs)?
checkpoint-status |  |  | checkpoint | 5. Are lifeguard units tagged quarterly?
checkpoint-status |  |  | checkpoint | 6. Are multi-plug boards & double adaptors industrially rated?
checkpoint-status |  |  | checkpoint | 7. Are electrical tools and leads industrial rated?
checkpoint-status |  |  | checkpoint | 8. Does temporary festoon lighting have moulded line sockets?
checkpoint-status |  |  | checkpoint | 9. Are electrical leads clear of pathways and stairs?
checkpoint-status |  |  | checkpoint | 10. Are electrical leads clear of water?
checkpoint-status |  |  | checkpoint | 11. Have electrical leads been protected from traffic?
checkpoint-group |  |  | section | ENVIRONMENTAL ISSUES
checkpoint-status |  |  | checkpoint | 1. Is there an Environmental Protection Plan in place?
checkpoint-status |  |  | checkpoint | 2. Is there a Silt Control Plan in place?
checkpoint-status |  |  | checkpoint | 3. Is there Spill Control in place for refueling operation?
checkpoint-status |  |  | checkpoint | 4. Is Dust controlled?
checkpoint-status |  |  | checkpoint | 5. Is Construction Waste being controlled?
checkpoint-status |  |  | checkpoint | 6. Is Construction Noise being controlled?
checkpoint-group |  |  | section | TRAFFIC MANAGEMENT
checkpoint-status |  |  | checkpoint | 1. Is there a temporary Traffic Management Plan (TMP) on site?
checkpoint-status |  |  | checkpoint | 2. Has the TMP been approved by the Road Controlling Authority?
checkpoint-status |  |  | checkpoint | 3. Are the Traffice Mangagement (TM) measures and signage set up as per the TMP?
checkpoint-status |  |  | checkpoint | 4.Is TM supervised by a qualified (STMS)?
checkpoint-status |  |  | checkpoint | 5. Is there a Traffice Controller (TC ) on site?
checklist-flat |  |  | checklist | Shotchrete - |  |  |  |  | Yes | QA - 03. Shotchrete (RevA) | b3dd793a-4268-4eac-ab9f-83d9fa543ee1
checkpoint-status |  |  | checkpoint | Construction drawings and specification received.
checkpoint-status |  |  | checkpoint | Starter epoxyed in correct depth & centers
checkpoint-status |  |  | checkpoint | Unused drilled holes filled with epoxy
checkpoint-status |  |  | checkpoint | Reinforcing starters in place
checkpoint-status |  |  | checkpoint | Correct size of mesh required
checkpoint-status |  |  | checkpoint | Check surface finish requirements
checkpoint-status |  |  | checkpoint | Check any structural connection requirements (hold down bolts / weld plates)
checkpoint-status |  |  | checkpoint | Identify are area ready to be carried out / check depths pre & post spraying
checkpoint-status |  |  | checkpoint | Confirm drop / overlaps / cover achived
checkpoint-status |  |  | checkpoint | Correct Mpa concrete
checkpoint-status |  |  | checkpoint | Engineers inspection booked for inspection or confirmation received to proceed
checklist-flat |  |  | checklist | Structural Steel - |  |  |  |  | Yes | QA - 11. Structural Steel (RevA) | b62c3460-fcfc-4522-858c-7811fe3b228c
checkpoint-status |  |  | checkpoint | Construction drawings and specification to subcontractor.
checkpoint-status |  |  | checkpoint | CI's/SIR's items of note communicated to subcontractor and actioned
checkpoint-status |  |  | checkpoint | Coordornation with services complete on penetrations
checkpoint-status |  |  | checkpoint | Hold downs in the correct location
checkpoint-status |  |  | checkpoint | RL confirmed
checkpoint-status |  |  | checkpoint | Connections to PCP / Shotcrete correct / façade connections
checkpoint-status |  |  | checkpoint | Site welding complete and checked
checkpoint-status |  |  | checkpoint | Shear studs installed
checkpoint-status |  |  | checkpoint | All bracing installed
checkpoint-status |  |  | checkpoint | Steel checked for plumb & level
checkpoint-status |  |  | checkpoint | All temporary bracing / shoring installed
checkpoint-status |  |  | checkpoint | All bolts checked, marked and torqued up
checkpoint-status |  |  | checkpoint | Engineer inspection received and remedials (if any) closed out
checkpoint-status |  |  | checkpoint | Subs QA provided
checklist-flat |  |  | checklist | Operations - |  |  |  |  | Yes | QA - 32. Operations (RevA) | ba5b38e7-a99e-42d5-963c-3df82ce597c8
checkpoint-status |  |  | checkpoint | All power points checked / Intumescent pads installed for IT walls / cover plates installed
checkpoint-status |  |  | checkpoint | All light fittings operational
checkpoint-status |  |  | checkpoint | Oven cleaned and operational
checkpoint-status |  |  | checkpoint | Dishwasher run through a cycle and operational, condensate drain connected.
checkpoint-status |  |  | checkpoint | Microwave plugged in and working
checkpoint-status |  |  | checkpoint | Sink tested Hot & cold running, overflow operational / check flow rate
checkpoint-status |  |  | checkpoint | Fridge installed and operational
checkpoint-status |  |  | checkpoint | Kitchen cabinetry, inserts, functionality, alignment, screw covers.
checkpoint-status |  |  | checkpoint | HVAC running & tested (min 6 hrs.)
checkpoint-status |  |  | checkpoint | TV running / tuned in
checkpoint-status |  |  | checkpoint | Sliding doors running smooth & painted behind.
checkpoint-status |  |  | checkpoint | Curtains closing & snag free.
checkpoint-status |  |  | checkpoint | Bed and head board installed and dressed inc King splits
checkpoint-status |  |  | checkpoint | Furniture in place.
checkpoint-status |  |  | checkpoint | Side lamps in place and working.
checkpoint-status |  |  | checkpoint | Artwork installed & correct
checkpoint-status |  |  | checkpoint | Accessable requirements installed, grab rails, shower curtain, showes seat shelves
checkpoint-status |  |  | checkpoint | Shower hot & cold running, sealent, soap dish.
checkpoint-status |  |  | checkpoint | Vanity hot & cold working, overflow cap.
checkpoint-status |  |  | checkpoint | Toilet cistern flushing correctly, valve on.
checkpoint-status |  |  | checkpoint | Toilet roll holders, robe hooks, shelves, soap dish, heated towel rail
checkpoint-status |  |  | checkpoint | Run washing machine & dryer
checkpoint-status |  |  | checkpoint | Remove all stickers.
checkpoint-status |  |  | checkpoint | Master key system installed
checkpoint-status |  |  | checkpoint | Front door access control operational / locks working / doorstops.
checklist-flat |  |  | checklist | LV / Data / Security - |  |  |  |  | Yes | QA - 26. LV _ Data _ Security (RevA) | bed7d135-3e92-4202-bd41-b7472ff59273
checkpoint-status |  |  | checkpoint | Construction drawings and specification sent to contractor.
checkpoint-status |  |  | checkpoint | Locations agreed for all fittings.
checkpoint-status |  |  | checkpoint | Type of systems agreed
checkpoint-status |  |  | checkpoint | Fob / readers / key pad positions confirmed
checkpoint-status |  |  | checkpoint | Nogs in place.
checkpoint-status |  |  | checkpoint | All wiring completed.
checkpoint-status |  |  | checkpoint | Interfaces of other services completed, lift, fire panel
checkpoint-status |  |  | checkpoint | Testing and commissioning.
checklist-flat |  |  | checklist | Building Consent - |  |  |  |  | Yes | Add Council BC Upload Checklist | c9385bc6-9cbd-4ee5-8c1a-6e7af34507d1
checkpoint-status |  |  | checkpoint | Latest building consent attached (superseded and attached as required)
checklist-flat |  |  | checklist | Excavation - |  |  |  |  | Yes | QA - 06. Excavation (RevA) | cf4c5abd-86cf-4280-b77c-51e1b5bcc160
checkpoint-status |  |  | checkpoint | Construction drawings and specification sent to subcontractor.
checkpoint-status |  |  | checkpoint | Site set out by surveyor.
checkpoint-status |  |  | checkpoint | Site RL installed by surveyor.
checkpoint-status |  |  | checkpoint | Check existing site RLs are as per drawings.
checkpoint-status |  |  | checkpoint | Surveyors set out drawing supplied by surveyor.
checkpoint-status |  |  | checkpoint | Mark up plans – excavation sizes of pads and footings in relation to grid. Show RL cut levels / site concrete levels.
checkpoint-status |  |  | checkpoint | Geotech inspection.
checklist-flat |  |  | checklist | Concrete Beams/Stitches/Columns - |  |  |  |  | Yes | QA - 14. Concrete Beams_Stitches_Columns (RevA) | db029180-b260-4bc2-9c66-bc2780110fd7
checkpoint-status |  |  | checkpoint | Plans detailing set-out, RLs, sizes and relation to grid.
checkpoint-status |  |  | checkpoint | Formwork drawings for shutters and bracing.
checkpoint-status |  |  | checkpoint | Hire / order formwork if required.
checkpoint-status |  |  | checkpoint | Reinforcing and chairs ordered
checkpoint-status |  |  | checkpoint | Form tube and cones ordered.
checkpoint-status |  |  | checkpoint | Reinforcing in place – correct cover, size and stirrup centres correct.
checkpoint-status |  |  | checkpoint | Level of finish determined to match shutters finish required.
checkpoint-status |  |  | checkpoint | Set any castins that may be required
checkpoint-status |  |  | checkpoint | Correct MPA & slump.
checkpoint-status |  |  | checkpoint | Council inspection or confirmation received to proceed
checkpoint-status |  |  | checkpoint | Structural engineer inspection or confirmation received to proceed
checklist-flat |  |  | checklist | Tanking/Waterproofing - |  |  |  |  | Yes | QA - 07. Tanking_Waterproofing (RevA) | dc61b6f9-641c-4757-9704-1bc40bce6d04
checkpoint-status |  |  | checkpoint | Construction drawings and specification sent to subcontractor.
checkpoint-status |  |  | checkpoint | Correct product confirmed
checkpoint-status |  |  | checkpoint | Correct backing for tanking to be installed
checkpoint-status |  |  | checkpoint | pile cap waterproofing completed
checkpoint-status |  |  | checkpoint | Laps correct to join on to
checkpoint-status |  |  | checkpoint | Swell seal install in the correct locations
checkpoint-status |  |  | checkpoint | independent menbrane inspection
checkpoint-status |  |  | checkpoint | independent inspection report completed
checkpoint-status |  |  | checkpoint | Council inspection.
checklist-flat |  |  | checklist | Facade - |  |  |  |  | Yes | QA - 19. Facade (RevA) | e1e984cb-0bcf-4f52-85e1-c1ce62a50046
checkpoint-status |  |  | checkpoint | Construction drawings and specification onsite
checkpoint-status |  |  | checkpoint | Castin Setout and checked for location & RL, send for Allown approval
checkpoint-status |  |  | checkpoint | Connections to structural steel / precast confirmed
checkpoint-status |  |  | checkpoint | Installation comeplete and confirmed by contractor ti allow grouting of pockets
checkpoint-status |  |  | checkpoint | Installation of GSM closure confimed to allow framign to prgress
checkpoint-status |  |  | checkpoint | Façade contrator to carry out water testing
checkpoint-status |  |  | checkpoint | Framing , waterproofing /water test signed off
checkpoint-status |  |  | checkpoint | Sealant tehstign to eb carried out and approved
checkpoint-status |  |  | checkpoint | Sealants & flashings installed and completed
checklist-sectioned |  |  | checklist | Accident and Incident Investigation Report |  |  |  |  | Yes | H&S - Accident and Incident Investigation Report | e87f4f44-2d6c-433e-a0a3-d1b470116943
checkpoint-group |  |  | section | Accident and Incident Investigation Details
checkpoint-status |  |  | checkpoint | Accident and Incident Investigation Details:
text | 6780ddfd-db41-4af3-b913-0f0aaade9f98 |  | textbox | Employer:
text | 5862b4be-5185-4f6e-bd29-fc97b0a27f77 |  | textbox | Branch/Department:
text | bab79d4d-439d-425d-9a1c-8f5e82e14133 |  | textbox | Name of Investigator:
checkpoint-no-status |  |  | checkpoint | Particulars of Incident
select | 8a8133e4-29cf-4f91-825e-1e521d953d20 |  | dropdown | Day of Incident | Monday, Tuesday, Wednesday, Thursday, Friday, Saturday, Sunday
text | c80069df-215c-45e4-83d5-d11e51bb8ef1 |  | textbox | Time:
text | d52a8d6a-1525-4802-af3a-25870ce400c2 |  | textbox | Project/Site:
text | 35cd8366-3635-48ba-95f2-37d7d1e0fb0c |  | textbox | Date Reported:
checkpoint-no-status |  |  | checkpoint | Injured Person
text | d79fdcea-c033-4ad6-a0bd-51ffb7107d98 |  | textbox | Name:
text | 2b807db7-f5f3-4a08-ac0d-f09e81b2d9ac |  | textbox | Age:
text | f0083564-9542-4a42-a4c6-98dce5d3ca30 |  | textbox | Phone Number:
text | 7a2ba6d0-2a98-4966-9dc8-e6bf09d9dee4 |  | textbox | Address:
text | 91eec609-2864-4c39-8bac-8c67b6e70181 |  | textbox | Reported Date of Incident:
text | 1e69e2e5-fc7a-48c2-a9bb-c2ea88b6009a |  | textbox | Length of Employment:
text | 46ac9d00-3fb5-4a11-a553-72bd81ec28f0 |  | textbox | Time on Job:
label | 4f180bf7-66d0-4e42-a37d-7e5cc9718a00 |  | note | Type of Injury:
boolean | 2cf92751-78ca-4fb3-949e-344273c201a7 |  | tickbox | Strain/sprain
boolean | fca2aa53-5d43-4f70-a5ec-916ef1d5472c |  | tickbox | Fracture
boolean | d3b2fed0-4fb8-4297-99bd-79883c6ce5c9 |  | tickbox | Laceration/cut
boolean | d4d8323a-9bba-4b44-8497-8bbac14ba36d |  | tickbox | Bruising
boolean | 7c47a3d3-5af1-47ee-9a87-ab13ed58e546 |  | tickbox | Scratch/abrasion
boolean | 4536bb5c-7872-4d39-9df8-0f127d80a11f |  | tickbox | Amputation
boolean | c82b1469-7234-4764-a964-730a42cfa425 |  | tickbox | Burn scald
boolean | db1bbb61-1927-4439-b49a-e6c88e046e9d |  | tickbox | Dislocation
boolean | 849df991-671b-4c18-a616-344305deb00c |  | tickbox | Internal
boolean | 52b87f7b-6dee-4324-b048-ff3ec52ee526 |  | tickbox | Foreign body
boolean | a46825dd-2c65-49c0-9e8c-05de42bc45dc |  | tickbox | Chemical reaction
boolean | 2185186c-b20d-4316-a7a6-d932ca38b6c6 |  | tickbox | Other (specify)
text | 9e6a3d37-f584-401d-9830-ffa56a6153a4 |  | textbox | Injured part of body:
text | 11603f64-b3ff-4caa-a521-6fe8385dcb63 |  | textbox | Remarks:
checkpoint-no-status |  |  | checkpoint | Damaged Property
text | f26b21cf-f22a-4b1c-991f-491c7f35fb9e |  | textbox | Property/Material Damaged:
text | 76478196-207b-4f42-aaff-5854a45f30f2 |  | textbox | Nature of Damage:
text | 4c9f7273-fa7a-489d-b06b-ce1d23bfce70 |  | textbox | Object/substance Inflicting Damage:
checkpoint-group |  |  | section | Incident
checkpoint-no-status |  |  | checkpoint | Description
text | 5f409263-1020-4c31-a012-11bade21f661 |  | textbox | Describe what happened:
label | a967bc1f-afaa-4cc8-bd6f-0f712fd7070c |  | note | Attach photo of diagram if required – essential for all vehicle incidents
checkpoint-no-status |  |  | checkpoint | Analysis - What were the causes (root and contributing causes) of the incident?
text | 11422433-33da-4dd5-9808-a44dba6ac86f |  | textbox | Root causes – safety system failures:
text | 43b652a7-7f5a-4b5a-8656-2b3f6eab5484 |  | textbox | Contributing causes – unsafe acts and conditions:
checkpoint-no-status |  |  | checkpoint | Prevention
text | 3af4263c-3058-4fd9-868e-51c98418c432 |  | textbox | 1 - What action has or will be taken to prevent a recurrence?
button | f6b5778b-7cb5-4ade-9b9c-345a28950c0f |  | button | Completed? | Yes, No
text | d46e86b8-d45b-4537-9efd-5d042103e33e |  | textbox | By Whom?
text | 25bc3981-0730-44b6-a1fd-3a3179be4231 |  | textbox | When?
text | 9e11b166-570d-43d2-9fbb-8b71a98ad949 |  | textbox | 2 - What action has or will be taken to prevent a recurrence?
button | 18920729-bc93-4831-bfd8-d59fb0663981 |  | button | Completed? | Yes,No
text | 2a296194-95cd-4d84-ab91-f642b3d453b7 |  | textbox | By Whom?
text | a53ab4d7-abc2-41cc-bd7a-e7215f9d53cc |  | textbox | When?
text | f2e71bc8-bac3-4787-84e9-a6473b8b67dd |  | textbox | 3 - What action has or will be taken to prevent a recurrence?
button | 6cce920a-03aa-42ce-94a3-7839683efb23 |  | button | Completed? | Yes,No
text | 6582db9b-bdb7-4f69-bfa5-40fdeace596c |  | textbox | By Whom?
text | f25f9925-ad36-49d0-92e6-8f2cd453b345 |  | textbox | When?
checkpoint-group |  |  | section | Treatment and Investigation of Incident
checkpoint-no-status |  |  | checkpoint | Treatment and Investigation of Incident:
text | 1cef7e6a-c3d5-4496-9e35-b1937a22d4bc |  | textbox | Type of treatment given:
text | 9113f647-52dd-488a-8f53-03cd74e0fd09 |  | textbox | Name of person giving First Aid:
text | 2ec4c413-5e8a-49d7-b205-bbe1d2151b19 |  | textbox | Doctor/Hospital:
text | 42389cf1-8fff-4f2a-94fe-178d8be235a9 |  | textbox | Incident Investigated by:
text | b69d231d-6ec8-48c4-b55c-882d7bce8436 |  | textbox | Date:
button | fe105571-c7f1-4ec2-b403-280ff9b89388 |  | button | WORKSAFE NZ advised: | Yes, No
text | fda34f83-c24b-49d3-9796-7e289ff0a6b2 |  | textbox | Date:
checkpoint-no-status |  |  | checkpoint | Signed by Employer
holdpoint |  |  | signoff | Signature attached - click here to sign
checkpoint-no-status |  |  | checkpoint | Signed by Employee
holdpoint |  |  | signoff | Signature attached - click here to sign
checklist-flat |  |  | checklist | Suspended Floor (Comfloor) - |  |  |  |  | Yes | QA - 15. Suspended Floor (Comfloor) (RevA) | f86c9d9f-b250-46b3-80e6-0bb9fb1e3c47
checkpoint-status |  |  | checkpoint | Construction drawings and specification to subcontractor.
checkpoint-status |  |  | checkpoint | Structural steel shop drawings sent for coordination
checkpoint-status |  |  | checkpoint | Install/lifting plan agreed into TA and signed onto by all involved
checkpoint-status |  |  | checkpoint | Comflor placed and secured
checkpoint-status |  |  | checkpoint | Propping plan supplied and approved
checkpoint-status |  |  | checkpoint | Propping installed as per approved design
checkpoint-status |  |  | checkpoint | Shear studs installed
checkpoint-status |  |  | checkpoint | Perimeter boxing installed
checkpoint-status |  |  | checkpoint | Set downs / rebates installed
checkpoint-status |  |  | checkpoint | Reinforcing installed correct bars and covers
checkpoint-status |  |  | checkpoint | Construction joints / control joints installed.
checkpoint-status |  |  | checkpoint | Correct MPA / slump.
checkpoint-status |  |  | checkpoint | Council inspection or confirmation received to proceed
checkpoint-status |  |  | checkpoint | Structural engineer inspection or confirmation received to proceed
checkpoint-status |  |  | checkpoint | Curing – water spray / membrane ordered.
checkpoint-status |  |  | checkpoint | Check overspray / clean.