## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 525108ae-2ea5-4980-a9c1-547a4ed17f84 |  | checklist | Chevaline Dexx Checklist |  |  |  |  | Yes | QA - Chevaline Dexx Checklist | 2da25e2d-b58b-4634-89dc-2cac19f8a5cd
checkpoint-status | 93d7e775-741b-4354-8275-b99c66da4ade |  | checkpoint | Substrate clean and dry
checkpoint-status | fb5191fc-cef4-4681-b20f-d9583e9dc2f5 |  | checkpoint | Substrate grinding completed
checkpoint-status | 20ab75b1-1cde-4492-aab8-eb7c896a2cba |  | checkpoint | Chevaline Dexx base coat applied
checkpoint-status | 8e91e02b-c80c-4507-ac7e-434c90224d77 |  | checkpoint | Chop strand matt installed
checkpoint-status | 626e63e3-3417-4e02-b495-5d84d7403d32 |  | checkpoint | Chevaline Dexx second coat applied
checkpoint-status | 48409417-67a4-45c1-99a2-c07652651c0c |  | checkpoint | All upstands and details completed
checkpoint-status | 95e51f86-04b5-47e6-9907-4e1e70ae7d4d |  | checkpoint | Area left clean and tidy
checklist-flat | 61dbfe4c-80fd-42a9-b22d-fb7d7e386d95 |  | checklist | SIKA Sarnafill QA |  |  |  |  | Yes | QA - SIKA Sarnafill | b1c57abd-5702-414f-8854-2c6fc3f5c07b
checkpoint-status | 58b0370a-c62d-47bb-87bb-ae889c0d43b4 |  | checkpoint | Work Are is clean, acceptable with photos
boolean | 93bcab42-158a-5991-89a0-5eff0cee94f8 |  | tickbox | Stand back photo of area taken
checkpoint-status | c33c923a-4648-439a-aba9-70625feee2b1 |  | checkpoint | Install Sarnafil S-Felt 300 protection
boolean | 3eea4e1c-e8ad-5c78-87fa-c2a2322e0f96 |  | tickbox | Stand back photo of area taken
checkpoint-status | 35498b44-052b-4fd6-85ba-fd5324d3574d |  | checkpoint | All Welded laps & Mechanical fixings installed to manufacturers specification
boolean | aeb69381-bb6e-5a56-861f-f8ffda662ead |  | tickbox | 50mm lap photo taken
boolean | b28717a8-904e-5526-9bee-ad0b1ebd57f4 |  | tickbox | Mechanical fixings photo taken
boolean | 62b7e752-d559-5b34-be15-b9a5faea7305 |  | tickbox | 120mm welded laps photo taken
checkpoint-status | a9867695-33ea-4a1b-9f8e-465afd73abfe |  | checkpoint | Peel test completed with photos taken with dates
boolean | 44d95889-5a78-5d64-b0a5-1d2a8cb9c229 |  | tickbox | Peel test photo with dates
boolean | ce709f46-5821-5cd3-aa04-494144136296 |  | tickbox | Peel test sample stored in Sansom site container (no photo needed)
checkpoint-status | 1eddec6f-f675-4e36-ab94-32c3bc6a0fc3 |  | checkpoint | PVC Terminations, Details & product installed to manufacturers specifications
boolean | e222a6b6-9ed7-5543-9a57-01cbeee59685 |  | tickbox | Termination detailed reviewed and signed off
boolean | 24f46a29-cc3d-51f4-b8e9-4a9a416442e1 |  | tickbox | Product details reviewed and completed to clients satisfaction
checkpoint-status | 9acaa32d-aa74-4c6d-8c3d-80cd353e5db4 |  | checkpoint | ILD Test Completed
boolean | 73dbb96a-95c4-5473-b1b6-c4ea2bf28d21 |  | tickbox | ILD Report Submitted & Attached
checkpoint-status | 730d8c72-9521-4ad3-8342-93dc35b982e0 |  | checkpoint | Area left clean & tidy & handed back to Client