## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | fb0aeed3-39ed-4aec-8355-fa8455898bd6 |  | checklist | P - |  |  |  |  | Yes | QA - Pile Caps Second Stage | 298b27ef-7090-4277-8dc7-2d677523ffb7
checkpoint-status | 7d6d589d-94af-49e4-8c0a-c2a20c6e5544 |  | checkpoint | Substrate ready and concrete cured for 28 days (photo taken)
checkpoint-status | 4a6cf42d-946c-4249-9010-c6770865fa90 |  | checkpoint | Apply membrane to top and down the side of pile cap
checkpoint-status | 033b8209-133d-478a-ad23-1e61f04b9472 |  | checkpoint | Completion photos taken
checkpoint-status | 94b14082-5fc3-4526-a902-873de396ace7 |  | checkpoint | Apply protection board
checkpoint-status | 8b3a0540-e4da-4513-90ec-7fd329bcc877 |  | checkpoint | Completion photos taken
checklist-flat | 801377d9-ccae-46fa-97d6-919dfe13a83d |  | checklist | Lift Shafts |  |  |  |  | Yes | QA - Lift Shafts | 2c855f03-793c-4949-988d-17fe80ecd2de
checkpoint-status | 99a9c381-1e34-40f3-825f-ce24a041d4ae |  | checkpoint | Site concrete and piles ready for application (photo taken)
checkpoint-status | b13c7d39-6f77-4a88-863e-5f9d70e98347 |  | checkpoint | Membrane installed to base of lift shaft
checkpoint-status | c26d2677-12eb-4380-b27a-57e9a141b7b6 |  | checkpoint | Completion photos taken
checklist-sectioned | 14d1607f-1ff6-45ea-a14e-85bee94ae166 |  | checklist | Tanking - Pile Remedial Checklist |  |  |  |  | Yes | Tanking - Pile Remedial Checklist | 3354cda6-2026-410e-ad98-22f48136da3d
checkpoint-group | 3f61b7b8-f09e-432e-a84a-2a3270067164 |  | section | Pre-installation QA
checkpoint-status | 65ebce7a-4883-4db5-bf31-34acff62651a |  | checkpoint | Latest consented drawings available, checked and referenced
text | 3b298c73-38ee-4d6e-95f4-fab23f015cbe |  | textbox | Relevant drawings & revisions for reference:
holdpoint | da151ba6-ee5d-4c25-b147-63ce5627c497 |  | signoff | Raise Remedial / Request Review
checkpoint-status | f747e215-09c4-41c6-a463-9cc83f315edf |  | checkpoint | Work area/substrate acceptable & approval given to start work
holdpoint | 35bb7fc5-a87b-471e-9b92-09b514548355 |  | signoff | Raise Remedial / Request Signoff
checkpoint-group | c705f247-121d-4a73-9873-e483b8885a47 |  | section | Installation QA
checkpoint-status | 39192f40-d0be-4dd4-85bb-598cc3ff28f6 |  | checkpoint | Product being used input
select | 51012b58-62ac-419d-9018-57e2ccbf9d6c |  | dropdown | Product name | Other, Preprufe 300, Voltex, Voltex DS, Voltex WSR,Preprufe 160
checkpoint-status | fa009a81-7e4d-46c9-814e-1934583ee884 |  | checkpoint | Location where being applied input.
text | 1b1bc4c9-c797-409a-83f4-e0abf79539fe |  | textbox | Area or pile number:
checkpoint-status | afc3307a-8727-41bf-829f-781fca057b34 |  | checkpoint | Protection core flute installed
checkpoint-status | 28bf625c-199d-4fea-a162-ba576d20b6e9 |  | checkpoint | LM to pile
checkpoint-status | aa84da40-4826-4f6a-af3f-ebc519e2b68e |  | checkpoint | Preprufe embedded to LM
checkpoint-status | b0511612-3487-430a-8fe3-21cf8a18a3ae |  | checkpoint | Preprufe installation and all laps and lap tapes done as per manufacturers requirements
checkpoint-status | 9caf6d5a-6bea-4adf-840a-6857ac6e99b0 |  | checkpoint | All water stops installed
checkpoint-status | 2f47bb07-9435-4cae-a315-7495f9ee7c64 |  | checkpoint | Check membrane for any damage and do repairs to manufacturers requirements. Take photos.
checkpoint-status | bf141245-1ce5-42af-93f9-5e602318f994 |  | checkpoint | Preform work and pour final inspection once other trades are finished. Do any required repairs. Take photos.
checkpoint-group | 9647cd07-4c03-4cc2-8b22-96a8dc35d4ad |  | section | Completion / Handover
checkpoint-status | 0103298e-cbb8-4baa-a03c-a3b98117b4f3 |  | checkpoint | Product installed correctly, checked & reviewed - as per specification
holdpoint | 9a7b785f-1212-42e0-9489-d73caab7772b |  | signoff | Raise Remedial / Request Review
checkpoint-status | 6ac43502-99d9-4f33-9938-445801adcacd |  | checkpoint | Area left clean & tidy
holdpoint | dfddbd2a-a490-4f21-a992-f0e28074e86e |  | signoff | Raise Remedial / Request Review
checklist-flat | 681b94d5-40c1-47fb-a7ff-2f248ab6128f |  | checklist | Date: |  |  |  |  | Yes | Add Daily Underfloor Checklist | 35b0b933-e6d1-4e5b-be32-fb6442e7294c
checkpoint-status | 07908410-e64f-4754-bbe1-791ac077d129 |  | checkpoint | Working area / grid sections input
text | 8dedee52-74e1-4929-a0da-f0c53e83cd15 |  | textbox | Area:
checkpoint-status | b42dafb1-1023-445d-a22c-b116acc6b510 |  | checkpoint | Before photos taken
checkpoint-status | 036e11f6-b573-4905-bf6d-993a5c052d60 |  | checkpoint | Site concrete acceptable
checkpoint-status | ea70e6a3-f58a-4dc4-bdac-c98e582c6a04 |  | checkpoint | Membrane loose laid and 130mm laps maintained
checkpoint-status | 474a59e1-9a17-4014-bf1c-8d29b767add1 |  | checkpoint | Completion photos taken
checklist-flat | 52291a32-bc2d-4c14-a743-636c614d2086 |  | checklist | Lift Shafts |  |  |  |  | Yes | SYS - Lift Shafts | 45ed97c4-d10a-41e7-9271-beadc1fbe0a9
checkpoint-status | 4626bd9f-1f1e-4f3c-91fa-115868e2c70a |  | checkpoint | Substrate ready and concrete cured for 28 days (photo taken)
checkpoint-status | 979130f3-441c-43c2-9411-b4da943b8f3d |  | checkpoint | Apply membrane to side of lift shaft
checkpoint-status | aa2599e1-fe9a-48e0-85bc-df32b2d7f626 |  | checkpoint | Completion photos taken
checkpoint-status | 455c7de5-8402-418f-8edf-2070527d6b83 |  | checkpoint | Apply protection board
checkpoint-status | 2eeb36d2-3aea-4f87-b487-ab64d3cc24af |  | checkpoint | Completion photos taken
checklist-flat | 55aca812-06fe-4ec2-8def-534e1a433c07 |  | checklist | Plywood Substrate |  |  |  |  | Yes | QA - Plywood Substrate | 63068981-25e3-4c4e-bfd2-44154550d668
checkpoint-status | e240a647-7cb2-476c-9b1a-47eb317712e7 |  | checkpoint | Plywood substrate complete with correct fixings
checkpoint-status | 41fc2afe-7d2c-459c-a015-011d54da1635 |  | checkpoint | Fillets installed
checkpoint-status | fb150719-2a49-49d4-8b1a-d134f3b59f4d |  | checkpoint | Substrate primed
checkpoint-status | c62c6dd3-c4d9-46aa-9007-8cbcc7ee5c80 |  | checkpoint | ILD mesh/plate installed
checkpoint-status | 7c36cb6d-10f1-4ef9-8a2c-be0851acd59e |  | checkpoint | Base Sheet installed
checkpoint-status | 2408a34f-6d2f-4669-8a1e-5894479e6855 |  | checkpoint | Cap Sheet installed
checkpoint-status | 10bf7347-36e3-49ac-8cf3-2962021dec34 |  | checkpoint | Outlets/ Penetrations detailed
checkpoint-status | ba871477-cfd0-4ff9-8612-1dda4f366180 |  | checkpoint | ILD test completed and attached
checklist-flat | b111332b-027a-49e9-ac41-f9600c74ae32 |  | checklist | P - |  |  |  |  | Yes | QA - Pile Caps | 7559ae50-ff60-4dd8-b973-9729a25f92d5
checkpoint-status | 8e7ad947-14e9-464d-9c78-7ef59c7b88a9 |  | checkpoint | Site concrete and piles ready for application (photo taken)
checkpoint-status | 27c771c9-34bb-489a-b787-d7f7f1ff1276 |  | checkpoint | Membrane installed to base and up sides of cap
checkpoint-status | 4e6eb42a-6064-40c7-9c22-f63c7959ea18 |  | checkpoint | Completion photos taken
checklist-flat | 2b586fba-c8e2-462c-90bc-b41dab4c2e55 |  | checklist | QA - Level 10 Cap and Base Sheet Checklist |  |  |  |  | Yes | QA - Level 10 Cap and Base Sheet Checklist | 7fd7b7d8-ee83-4648-a1ea-29251f7a48f3
checkpoint-status | 36ed2a0e-5d9a-443a-ac3a-4fdbdc666479 |  | checkpoint | Substrate grind & cured
checkpoint-status | ce4cde8d-c9f2-42af-8feb-6597c472e081 |  | checkpoint | Primed
checkpoint-status | d2d43fa2-afcb-4791-aa6f-e3e5367ba3e5 |  | checkpoint | Bitumen fillet installed
checkpoint-status | 627d72a8-cc8e-486e-9254-0c57cd9f3562 |  | checkpoint | Base sheet
checkpoint-status | ec8aaa1e-3a88-48db-81db-b48095843168 |  | checkpoint | Cap sheet
checkpoint-status | 6fec7427-7b63-4bdb-8a4f-4075ff6258e6 |  | checkpoint | Penetrations / Plinths detailed
checkpoint-status | 47bb9564-9019-4b30-aacb-8951f085b10a |  | checkpoint | Completed
checkpoint-status | d8e50537-879a-4dea-8124-5acf867ac5a3 |  | checkpoint | ILD Attached
checklist-flat | 3645404e-33ac-4313-b00f-d4cc63a3603b |  | checklist | QA - Wall Sections |  |  |  |  | Yes | QA - Wall Sections | 94f7bbf8-9da9-424e-9522-c60fadf9be16
checkpoint-status | 89c4ca8c-59f1-4d18-b148-9c162057b974 |  | checkpoint | Substrate ready
checkpoint-status | 690eb137-59b3-4c0d-84d1-59ec6e0b9229 |  | checkpoint | Membrane applied
checkpoint-status | ac436281-410c-4483-b7fd-d23bbb137520 |  | checkpoint | Completion photos taken
checkpoint-status | c685277a-27a5-40b3-bcae-b3a4bb957a65 |  | checkpoint | Apply protection board
checkpoint-status | 45034799-cf20-4a4b-814f-761ab200cec0 |  | checkpoint | Completion photos taken
checklist-flat | 64ec3ae8-158d-4e42-b634-8d7b5dab5adc |  | checklist | Site Visit Date: |  |  |  |  | Yes | Add Site Visit Checklist | 95ea4e40-27b2-4513-a8fd-f80160ee1951
checkpoint-status | b5519d53-37fe-487e-a799-5c9c04de18c9 |  | checkpoint | Details entered
text | 86734274-df38-49b0-b1c4-5753692d3e5f |  | textbox | Site visit performed by
text | bf0dcb60-603b-45ad-8c14-89a34ae09823 |  | textbox | Site visit completed with / attendees
text | a3cbb780-db9d-4af0-9389-4e957665ad99 |  | textbox | Description of area
checkpoint-status | 1da7e9ec-4801-49a3-bf2b-44c2ac44869d |  | checkpoint | Photos taken
checkpoint-status | 597b14b4-108d-4c68-9a49-96e69bc2b748 |  | checkpoint | General observations and comments
checklist-flat | 6a944280-13f7-40ac-8033-203e7e284b0f |  | checklist | Vertical Stitch Checklist |  |  |  |  | Yes | QA - Vertical Stitch Checklist | 9f6bd50e-1fbb-4a55-a15c-6a8c7b87dba1
checkpoint-status | f8d0e494-43c9-4675-8b84-d1c38af006d5 |  | checkpoint | Work area/substrate is clean, dry and ready to start
holdpoint | aad3625f-416f-4e9c-a987-a4aa799e00f6 |  | signoff | Raise Remedial / Request Signoff
checkpoint-status | 7f304202-945d-4f84-9948-6e763b5f9662 |  | checkpoint | Photograph(s) taken of substrate
checkpoint-status | 181f224c-48ed-46ad-b46d-e5c25fb9d939 |  | checkpoint | Joint width measured
checkpoint-status | af67f007-af07-4546-9a70-f354027be070 |  | checkpoint | Photograph(s) taken of installed backing (before protection board is installed)
checkpoint-status | d3b78004-572e-4f0c-abf5-bdc3ba0ee50c |  | checkpoint | Protection board installed
checkpoint-status | e4e995aa-5fd5-47e7-8ec4-281c58ee69b4 |  | checkpoint | Photograph(s) of protection board
checkpoint-status | 742ec05e-b700-4ecb-abf2-141ca709ec0c |  | checkpoint | All joint sealant installed correctly, checked & reviewed - as per specification
holdpoint | 58745e9b-5082-4089-a958-07ae7937e4b4 |  | signoff | Raise Remedial / Request Review
checkpoint-status | 4a463e3f-2ffc-4379-9e7d-0b83cba9a4ed |  | checkpoint | Area left clean & tidy
checklist-flat | abc8dafb-af11-41f9-9416-4869a3190e93 |  | checklist | P - |  |  |  |  | Yes | QA - Piles | a5b50f86-a41c-42e0-b282-0994294aa421
checkpoint-status | fa56f003-b758-4dfb-ace8-fed567c894a2 |  | checkpoint | Substrate ready (photo taken)
checkpoint-status | f85840d4-1cad-4e6d-810c-c8e02c82cd54 |  | checkpoint | Membrane installed
checkpoint-status | 7daf3bcb-8256-4ef9-ac0f-cacaef5d1fdd |  | checkpoint | Completion photos taken
checklist-flat | 00f99d18-5ac3-4662-a9f6-b7ff8198eee1 |  | checklist | Date: |  |  |  |  | Yes | Add Daily Level 11 Checklist | a79e60e5-2719-48fd-8870-06fb50ec640f
checkpoint-status | 0128a93e-1945-4c57-af26-bd00cf442e71 |  | checkpoint | Substrate Completed
checkpoint-status | 449b106d-a694-4fe4-af24-add3b6b2f563 |  | checkpoint | Primed
checkpoint-status | b272751d-b7e6-4469-836a-1997b8f51ee7 |  | checkpoint | ILD mesh/ plate installed
checkpoint-status | b3b747ac-4e1e-450f-acad-9cae39955c53 |  | checkpoint | Base sheet
checkpoint-status | edd162cc-9503-49f8-ad5d-ae63a4c4e334 |  | checkpoint | Cap sheet
checkpoint-status | f36222ab-f41c-44e6-8940-b706805476e8 |  | checkpoint | Penetrations / Plinths detailed
checkpoint-status | 139bb535-4402-4936-b23c-9ccd07a5d835 |  | checkpoint | Completed
checkpoint-status | 3612d63f-5ef0-495a-8e21-1d6dd16ef658 |  | checkpoint | ILD Attached
checklist-sectioned | 90890430-38bb-41c6-99c3-ae436d215587 |  | checklist | Tanking - Beam and Capping Beam Remedial |  |  |  |  | Yes | Tanking - Beam and Capping Beam Remedial Checklist | b3959c40-cf63-483a-aff1-bcb91ec00268
checkpoint-group | ce1b732f-4782-43e4-85e8-794d4781f361 |  | section | Pre-installation QA
checkpoint-status | a7007dd3-d5b9-43c3-a3d4-7860e649588b |  | checkpoint | Latest consented drawings available, checked and referenced
text | 09d77e74-a713-4c58-b1cf-6d91a86ed48e |  | textbox | Relevant drawings & revisions for reference:
holdpoint | e692b3ce-27f3-4718-95e1-f7ec742e77ac |  | signoff | Raise Remedial / Request Review
checkpoint-status | 900bb37a-0efe-47f7-8890-14f28c267418 |  | checkpoint | Work area/substrate acceptable & approval given to start work
holdpoint | ea2e1cee-20d5-466c-8596-1e85e21e3de6 |  | signoff | Raise Remedial / Request Signoff
checkpoint-group | a8037cfd-e684-4cad-8e53-d5f81fdcf931 |  | section | Installation QA
checkpoint-status | 8574318c-ab21-455b-bb99-6e0d92e23ef4 |  | checkpoint | Product being used input
select | 6a898b34-6793-4ce8-81ea-982684e4fa60 |  | dropdown | Product name | Other, Preprufe 300, Voltex, Voltex DS, Voltex WSR,Preprufe 160
checkpoint-status | 5ad1696d-7852-44ff-b6f8-79a029707c2c |  | checkpoint | Location where being applied input.
text | 3e9dc8b7-b40c-41fc-a0ba-a33b6838f8cf |  | textbox | Area or pile or beam number:
checkpoint-status | 96e32c6b-b862-403c-a573-9bc5ae960825 |  | checkpoint | Protection core flute installed
checkpoint-status | dc241089-abad-496c-8456-4a760935b418 |  | checkpoint | LM to beam/capping beam/pile
checkpoint-status | c2c2da8d-4313-4e96-aa14-e107bb873721 |  | checkpoint | Preprufe embedded to LM
checkpoint-status | e11ae221-6055-498e-9e2a-a58c3582015a |  | checkpoint | Preprufe installation and all laps and lap tapes done as per manufacturers requirements
checkpoint-status | 85b8f482-b79b-4d0d-a9cd-34ac34f09c9a |  | checkpoint | All water stops installed
checkpoint-status | 801c03a6-c208-4038-9d7e-14af02f82238 |  | checkpoint | Check membrane for any damage and do repairs to manufacturers requirements. Take photos.
checkpoint-status | 49c51476-0811-4e56-8d2c-086232862c0b |  | checkpoint | Preform work and pour final inspection once other trades are finished. Do any required repairs. Take photos.
checkpoint-group | 5e41b497-775f-43eb-907d-a0be19c3ff27 |  | section | Completion / Handover
checkpoint-status | 8ac3af07-e2dd-40fe-b9b4-98aea09f46fa |  | checkpoint | Product installed correctly, checked & reviewed - as per specification
holdpoint | cc75b077-fa3f-495e-b585-ebd44705585d |  | signoff | Raise Remedial / Request Review
checkpoint-status | 389bd574-ea5f-479d-95e9-26410354fa1c |  | checkpoint | Area left clean & tidy
holdpoint | 5ca79118-473f-4eca-9343-5ae668a51b9b |  | signoff | Raise Remedial / Request Review
checklist-flat | b44a9bb7-a7e2-4a8c-b60d-f01372210e00 |  | checklist | QA - Internal Plantroom Checklist |  |  |  |  | Yes | QA - Internal Plantroom Checklist | cbd9796c-2e96-49c4-a882-fe2bb530d01e
checkpoint-status | cbc7d769-c986-45d4-99fb-960a08432414 |  | checkpoint | Substrate Complete - Screeds to fall
checkpoint-status | 5c47f765-8bd1-4d9a-a5f1-39b742582095 |  | checkpoint | Primed- Epistixx
checkpoint-status | dbf983e8-2be4-4a8f-b321-5b3ce82a79d3 |  | checkpoint | Internal/ External corners reinforced
checkpoint-status | 6f09c9d5-4bc0-4769-88dc-62642eebae4d |  | checkpoint | Body Coat with Reinforcing
checkpoint-status | ce37f102-7da8-4183-8451-f9d2c4566e1f |  | checkpoint | Top Coat
checkpoint-status | 53fcaa36-4a32-4d57-8648-33f54d096fc8 |  | checkpoint | Penetrations/ Plinths detailed
checkpoint-status | bbbbbeed-df33-4453-a0da-a5671eb4ca35 |  | checkpoint | Completed
checkpoint-status | 0ac8b787-0382-4fe4-9920-07b58bcc8f8f |  | checkpoint | ILD Attached
checklist-flat | 45b749a2-0b06-4a97-8ab8-d7d6e1e19088 |  | checklist | External Plantroom Second System |  |  |  |  | Yes | QA - L10 - External Plantroom Second System | cd356ce5-461d-4448-84b8-8fd58520cf22
checkpoint-status | 54b4c913-e0fa-4730-a318-1954c003f38a |  | checkpoint | Substrate ground
checkpoint-status | 2a0c228a-9c43-4e0d-ac5f-a511eb792e47 |  | checkpoint | Drip edge flashings installed
checkpoint-status | 53292aa0-4026-4d53-915d-423be0f3ee53 |  | checkpoint | Substrate primed
checkpoint-status | e815fe67-1b21-4bb1-8aca-8ffda3531b2d |  | checkpoint | Base Sheet
checkpoint-status | 38a1f954-93f7-4844-919e-b3c4720ef21b |  | checkpoint | Cap Sheet
checkpoint-status | 1b7ca5dc-5e2d-4bc6-8476-3e6d47189864 |  | checkpoint | Edge Angles installed and Sealed
checkpoint-status | 8a394d82-638e-48d4-a1cc-d496b67ff6d9 |  | checkpoint | Completed Photos
checkpoint-status | cd161592-dd6c-4165-a44c-82ff15511242 |  | checkpoint | ILD Attached
checklist-sectioned | 815c6acc-a243-4de8-b863-37487506a38f |  | checklist | Tanking - Wall Pre-Construction Checklist |  |  |  |  | Yes | Tanking - Wall Pre-Construction Checklist | d4addb9e-4660-4920-8408-a4d659094bc6
checkpoint-group | 7eb9538a-3bd4-4642-98be-f0d131497def |  | section | Pre-installation QA
checkpoint-status | 63345381-1b2a-4250-8de4-5638ff069dc3 |  | checkpoint | Latest consented drawings available, checked and referenced
text | af5388dc-956e-48a0-857b-57b98cec6ccd |  | textbox | Relevant drawings & revisions for reference:
holdpoint | edf1e6a1-8dde-466d-9387-ebd0a530c5a1 |  | signoff | Raise Remedial / Request Review
checkpoint-status | 46c63890-5433-4d2a-809c-0f9b3f5b45aa |  | checkpoint | Work area/substrate acceptable & approval given to start work
holdpoint | 05834f51-d875-4098-9fe2-a16c63561c7f |  | signoff | Raise Remedial / Request Signoff
checkpoint-group | cda4b9e3-db91-4504-b58e-7669e8c43d63 |  | section | Installation QA
checkpoint-status | 2e99ed4c-033a-48af-9931-5a6768f0a785 |  | checkpoint | Product being used input
select | b72cd824-5e41-43c9-9e22-dbda330cecdf |  | dropdown | Product name | Other, Preprufe,Voltex
checkpoint-status | 7b757eb8-6098-4435-a48b-3c4895f9144a |  | checkpoint | Location where being applied input.
text | d1e4dce7-6853-4dea-bfcd-6a312e2836ee |  | textbox | Area:
checkpoint-status | 1816353f-f3bf-4c66-b019-cdc768a8f95d |  | checkpoint | Geotextile or coreflute or drainage gecell in place if required
checkpoint-status | 98b24213-b564-4280-86a3-13cc99ecd488 |  | checkpoint | All laps to manufacturer's specifications.
checkpoint-status | 747d96ae-f83b-4dfa-b714-96e2166a3bb3 |  | checkpoint | (Voltex DS only) DPC must be removed 100mm minimum for lapping
checkpoint-status | 3519cd58-e40f-47ad-b0fc-79acad611b9a |  | checkpoint | All water stops installed
checkpoint-status | fcf5df11-17df-40c9-8a00-da4b181b42a7 |  | checkpoint | Check membrane for any damage and do repairs to manufacturers requirements. Take photos.
checkpoint-status | 51adea45-f519-44eb-94e1-9440734b1a7e |  | checkpoint | Preform work and pour final inspection once other trades are finished. Do any required repairs. Take photos.
checkpoint-group | 44c9c2ec-76bd-4359-9ae6-ab8c8f835648 |  | section | Completion / Handover
checkpoint-status | edfdae95-7ffa-4786-9b07-205af9315c56 |  | checkpoint | Product installed correctly, checked & reviewed - as per specification
holdpoint | f3745c06-ea40-4155-9889-00598e8de7c6 |  | signoff | Raise Remedial / Request Review
checkpoint-status | fdd5ffc4-a251-4dbc-b28f-74a3f49ba336 |  | checkpoint | Area left clean & tidy
holdpoint | 7422c093-9f6d-4375-b13c-bf89a3c1dcdc |  | signoff | Raise Remedial / Request Review
checklist-sectioned | d9e5c32c-3012-4085-b48c-6dad6230c683 |  | checklist | Tanking - Wall Post-Construction |  |  |  |  | Yes | Tanking - Wall Post-Construction Checklist | e4844278-72e6-4a9a-939e-05fdf144518c
checkpoint-group | 3647a2ef-a4d0-4b2d-90b2-1db75b189106 |  | section | Pre-installation QA
checkpoint-status | 366ea301-a671-42af-8803-020cc343119f |  | checkpoint | Latest consented drawings available, checked and referenced
text | 7701fb48-4769-4353-b72a-ffdad594269b |  | textbox | Relevant drawings & revisions for reference:
holdpoint | 90a7cff8-c783-4537-9c50-41bc221235a3 |  | signoff | Raise Remedial / Request Review
checkpoint-status | f76684e6-5ad7-44c7-9e4b-a035d77368d7 |  | checkpoint | Work area/substrate acceptable & approval given to start work
holdpoint | 8c38f777-1686-4434-8be1-332da80c2f81 |  | signoff | Raise Remedial / Request Signoff
checkpoint-group | ab06e4ca-1e5d-4203-a42b-e484fa80d405 |  | section | Installation QA
checkpoint-status | 3fcb0222-a0cd-47c1-9291-7549b9f55c7e |  | checkpoint | Product being used input
select | 6e0b0b81-af62-4e96-b652-c75549c9fb66 |  | dropdown | Product name | Bituthene 3000, Other,Swelltite
checkpoint-status | 5b0c74f5-b4af-44fe-b29a-3495506d8bd0 |  | checkpoint | Location where being applied input.
text | 50905c3f-3854-4476-a7e9-691c38484fde |  | textbox | Area:
checkpoint-status | 183d20bd-b5ee-4291-b247-193b66fae22d |  | checkpoint | Check the substrate (are there any voids that need filling, if precast panels are all the joints filled).
checkpoint-status | 9b90a505-0c95-4fd2-ab61-a359e82bf0f1 |  | checkpoint | Check and clean flap.
checkpoint-status | 55778454-885e-4f72-8131-d7379dc92ffd |  | checkpoint | Material installed as per manufacturer's specification.
checkpoint-status | a87cf7ef-b874-45f5-8e14-607ed0ce24a7 |  | checkpoint | Check membrane for any damage and do repairs to manufacturers requirements. Take photos.
checkpoint-status | 6816e400-c033-4d00-bd2a-df68110c3e9d |  | checkpoint | Complete penetrations
checkpoint-status | cc652b83-1587-4f0d-974b-06b1253cba3b |  | checkpoint | Tape the laps
checkpoint-status | 7df22d05-de21-4aae-8a47-95ef4a0878ca |  | checkpoint | Place the termination bar
checkpoint-status | bf54e778-aa52-4136-b852-d876934630a2 |  | checkpoint | Cetcoat applied
checkpoint-status | 44438008-42dc-4417-882a-b0bdfb685d60 |  | checkpoint | Protection layer installed
checkpoint-status | 5e39553f-f47c-40d1-b653-0c757282544b |  | checkpoint | Drainage installed and 100mm away from wall
checkpoint-group | 7f9b5004-f030-45dd-bb65-087b492c477a |  | section | Completion / Handover
checkpoint-status | c7234727-f5cf-4ebe-b7d9-562125882930 |  | checkpoint | Product installed correctly, checked & reviewed - as per specification
holdpoint | fa0bf6f5-6490-4668-ae77-7725b8092cb9 |  | signoff | Raise Remedial / Request Review
checkpoint-status | 1dc6088d-b66d-4a84-aec6-30a322fe59cd |  | checkpoint | Area left clean & tidy
holdpoint | 443e2657-4c53-481f-9316-2c74e2db0692 |  | signoff | Raise Remedial / Request Review
checklist-flat | 922ec543-3551-4be9-9778-8edbd69bee10 |  | checklist | Plantroom Roof North |  |  |  |  | Yes | QA - Level 11 - Plantroom Roof North | e7a96c46-03b4-47e5-a628-3ef1a0224d37
checkpoint-status | e8399e25-e0ee-4ebc-a3e8-60faacf08a95 |  | checkpoint | Substrate Completed
checkpoint-status | 44bfc944-755a-4d06-a8e5-b6376d0027cc |  | checkpoint | Primed
checkpoint-status | 1865ab59-aa13-43ac-ac2a-63f68e391f2d |  | checkpoint | ILD mesh/ plate installed
checkpoint-status | 3dbf3a51-8541-4a1d-87e5-d2a4de6d28e2 |  | checkpoint | Base sheet
checkpoint-status | cadabc59-139a-490b-b1d9-17cdf12622f7 |  | checkpoint | Cap sheet
checkpoint-status | 25e64038-9691-4464-b308-a3cae77497b3 |  | checkpoint | Penetrations / Plinths detailed
checkpoint-status | 572917e9-ebaf-47e8-9e63-384e4bf78970 |  | checkpoint | Completed
checkpoint-status | df9a303c-3dad-4eef-9910-38e3a067598b |  | checkpoint | ILD Attached
checklist-flat | f5e565d4-6bed-41f1-8278-0287e4bedf6a |  | checklist | Ground Beams |  |  |  |  | Yes | QA - Ground Beams | eebb5b37-5a4a-49eb-89a8-a72e52257a4b
checkpoint-status | 3f5ccae4-e44f-4909-8c67-4d75c6816e4e |  | checkpoint | Site concrete ready for application (photo taken)
checkpoint-status | 20700b84-0d84-4a74-b23a-4bbf05925a4d |  | checkpoint | Membrane installed to base and up sides of beam
checkpoint-status | e9ce09fc-9a1b-49d0-b493-007b9aeda6cd |  | checkpoint | Completion photos taken
checklist-flat | 5a83c805-6b9a-4cad-9947-5f2659defcd0 |  | checklist | QA - Level 10 Gutter Checklist |  |  |  |  | Yes | QA - Level 10 Gutter Checklist | fb5d5c6b-fa03-472f-a9a6-aece4e73657f
checkpoint-status | 64489d1f-9952-48cd-b691-ab0a0d63e05d |  | checkpoint | Substrate Completed - Screed to falls
checkpoint-status | 0824581c-e2ab-448b-95b0-a88f94fd0cac |  | checkpoint | Primed
checkpoint-status | 9f91847c-c013-4926-aaa8-1a6dd79cbe6d |  | checkpoint | Bitumen Fillets installed
checkpoint-status | 3edf05ad-9e1f-43b9-9647-56f5751cf973 |  | checkpoint | Base Sheet
checkpoint-status | 4663b3f7-e4ff-46e6-8b75-48e68f3b0161 |  | checkpoint | Cap
checkpoint-status | a77c91a8-88b7-4eb1-b4f4-84afd4e43a6b |  | checkpoint | Penetrations Completed
checkpoint-status | 4b91521d-480f-4b0c-a300-2d40e60cdf6a |  | checkpoint | Completed
checkpoint-status | f4754e38-5524-441c-99ee-f59f5436ab05 |  | checkpoint | ILD Attached
checklist-flat | 8f3fe55f-2d72-4b1b-9227-1aad50d2ae90 |  | checklist | Ground Beams |  |  |  |  | Yes | QA - Ground Beams Second Stage | fba5898a-8c05-490e-97e2-416736bc8c23
checkpoint-status | 289bda05-f446-416e-86f5-1c4846848cc3 |  | checkpoint | Substrate ready and concrete cured for 28 days (photo taken)
checkpoint-status | 0ee06324-4a1c-40d4-b33a-f54052e1f410 |  | checkpoint | Apply membrane to top of pile cap
checkpoint-status | 899e2c67-1bfe-4321-8807-e2065c385b72 |  | checkpoint | Completion photos taken
checkpoint-status | 6c3ae0d9-76dc-496f-bb50-73bd49ed952d |  | checkpoint | Apply protection board
checkpoint-status | 5246986f-69ce-4681-a566-a2f05cd432bf |  | checkpoint | Completion photos taken