## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 54f46206-5372-4d24-a536-07c0170c6c91 |  | checklist | Tanking Beam / Capping Beam - Area: |  |  |  |  | Yes | QA - Tanking Beam and Capping Beam | 03900688-1e4b-4d3b-b70f-bda4c272d967
checkpoint-status | dbe8f64a-ff26-4c72-ae55-fb4eb5c0a474 |  | checkpoint | Substrate to manufacturer's specifications (are there any voids that need filling, clean, etc.)
checkpoint-status | e0a737b6-2225-47c6-8e6a-1babbbb2f541 |  | checkpoint | Protection core flute installed
checkpoint-status | 1021f59c-b3f1-498b-8e0e-5d1a4e3e656a |  | checkpoint | Preprufe installation and all laps and lap tapes done as per manufacturers requirements
checkpoint-status | 4b29cb38-c929-43b2-9736-01261c2d0531 |  | checkpoint | All water stops installed
checkpoint-status | 9ef6a69a-51c0-41dd-8fcf-d0432ae50ee6 |  | checkpoint | Check membrane for any damage and do repairs to manufacturers requirements. Take photos.
checkpoint-status | 49898cc8-f342-4416-95a6-56b0e45a4c22 |  | checkpoint | Preform work and pour final inspection once other trades are finished. Do any required repairs. Take photos.
checkpoint-status | 74683f3e-2537-4dbc-93b6-b03ecfbbb96c |  | checkpoint | Photo of highlighted drawing showing locations of work
checklist-flat | 92455769-a060-4d97-95aa-b11d7d717717 |  | checklist | Tanking Underfloor - Area: |  |  |  |  | Yes | QA - Tanking Underfloor (V2) | 27c5e3a5-6410-436f-96a3-f225ca8c7087
checkpoint-status | 87d90fac-3c54-4eb3-8238-4a9b49225d33 |  | checkpoint | Area of work input and photo of highlighted drawing showing locations of work attached
text | c608c095-6db2-594c-8f97-84c4d3ccce86 |  | textbox | Grid Line:
checkpoint-status | 593adf80-4bcc-4bb1-abf7-9fde226859e5 |  | checkpoint | Substrate to manufacturer's specifications (are there any voids that need filling, clean, etc.)
checkpoint-status | f04223d1-18f9-4fcc-98ef-c22ee33f2394 |  | checkpoint | Membrane installed to manufacturer's specifications
checkpoint-status | 9af04650-4aa4-48fd-a8f4-ed4f1ef0fdd5 |  | checkpoint | Reo installed (by others) checked for damage to membrane and repaired (if necessary)
checkpoint-status | f8727e9d-cedb-4a3a-84c0-7f479108cc69 |  | checkpoint | Final inspection before concrete
checkpoint-status | 17cf2126-7383-4da1-b382-64b0853c161d |  | checkpoint | Waterbar installed to all cold joints
checkpoint-status | eca232e9-38d5-4758-93e4-e95e90c606a5 |  | checkpoint | Joints and laps as per spec
text | 09411afd-71be-558f-88d7-60b11a0d22d8 |  | textbox | Joints and laps: |  |  | mm
boolean | b1bdd89d-b389-510a-b8a0-1c80e4706b82 |  | tickbox | Photo(s) attached
checkpoint-status | 417d5fed-ffb8-48cd-8943-0cd7fa74b8e0 |  | checkpoint | Membrane checked for damages prior to pour and repaired if necessary
checkpoint-status | e3f420bf-a160-40de-b1ea-46086ebec273 |  | checkpoint | Sufficient lap projecting out of Construction Joint
text | 868a3792-8329-50e7-b3af-25ae08d34d96 |  | textbox | Lap projecting by: |  |  | mm
boolean | 769b4510-950e-5a3f-9aa0-48d66cf1a93f |  | tickbox | Photo(s) attached
checklist-flat | b68e3ab4-5267-433c-8c23-1a9dac1e5d63 |  | checklist | C. 25mm Seismic Foam Checklist |  |  |  |  | Yes | C. 25mm Seismic Foam Checklist | 2c794f19-d385-4065-ac2e-6c48927dcd70
checkpoint-status | d16501bc-5f6b-428b-8714-26973c669b21 |  | checkpoint | Work Area/Substrate is clean, dry and ready to start
checkpoint-status | d1ff6507-f73e-4f62-a905-16b58c60e98e |  | checkpoint | Install Compriband 600 to panel recess
checkpoint-status | 31fd71c4-877f-4f28-b475-a04e624883c8 |  | checkpoint | Install BAS Evazite Seismic foam to panel recess
checkpoint-status | 919e5ea5-9910-4e4f-9dde-04900856d4a5 |  | checkpoint | Check if foam is loose? Apply bead of sealant if required
checkpoint-status | e0dc1b8e-f49c-4a2b-adbe-3dbce8920d7c |  | checkpoint | Clean and install closure flashing - bedseal with Sika 11 FC and mechanically fixed
checkpoint-status | b0d37987-04d2-4426-8b3f-69adfa1dba1f |  | checkpoint | Clean and install powdercoated aluminium cover flashing - mechanically fixed
checkpoint-status | a71fc814-53cd-4083-b920-6901c9aa93e8 |  | checkpoint | Site Area - Clean & Tidy
checklist-flat | b66291f6-5b30-442e-99f3-cad1d17192d8 |  | checklist | D. 50mm Seismic Foam Checklist |  |  |  |  | Yes | D. 50mm Seismic Foam Checklist | 2e54d0c3-814d-448b-ba3e-d6fb1a22a665
checkpoint-status | 1f560184-68ab-4852-8ebe-d276194a963c |  | checkpoint | Work Area/Substrate is clean, dry and ready to start
checkpoint-status | f17d7b3f-ca7a-445c-a377-76ef8ca5438e |  | checkpoint | Install Compriband 600 to panel recess
checkpoint-status | b5ca9640-1387-41f1-bc6e-c44baf87fa16 |  | checkpoint | Install BAS Evazite Seismic foam to panel recess
checkpoint-status | 845f83ba-b98b-454a-a2ea-a8ef886f7646 |  | checkpoint | Check if foam is loose? Apply bead of sealant if required
checkpoint-status | 668a12c2-b560-4a21-8deb-0b57f3d0c5c7 |  | checkpoint | Clean and install closure flashing - bedseal with Sika 11 FC and mechanically fixed
checkpoint-status | 7a4e6b4d-9fc5-440f-947a-b5cacf191ab1 |  | checkpoint | Site Area - Clean & Tidy
checklist-flat | 39e029c1-d239-49c9-b985-2ff48f856f30 |  | checklist | Swelltite - Area: |  |  |  |  | Yes | QA - Tanking Swelltite | 4fdfaa91-fc0f-4d10-88a7-a0a2dfd96f20
checkpoint-status | 6f1a975d-53ab-4269-93e0-2456753e7768 |  | checkpoint | Substrate to manufacturer's specifications (are there any voids that need filling, clean, etc.)
checkpoint-status | 06c92e5a-26e7-4997-b4f1-fe54c9b92364 |  | checkpoint | Check and clean the voltex flap for the Swelltite
checkpoint-status | 1819e8b8-75e8-4174-b466-a716a445171e |  | checkpoint | Apply glue to the wall ready for the Swelltite
checkpoint-status | 02d7bd8d-b030-4aeb-b89e-dea20bcb6e69 |  | checkpoint | Place water stoppage granules along the wall floor junction
checkpoint-status | e19cd751-ab15-4de1-8cd0-5aa6cd0a3db4 |  | checkpoint | Complete penetrations
checkpoint-status | 0dadb0e0-ef76-4cbe-b132-875e696b2deb |  | checkpoint | Tape the laps
checkpoint-status | c550daa3-9488-4cf5-bbf7-1c24d9a4d7f6 |  | checkpoint | Place the termination bar
checkpoint-status | 0ba5ba10-630d-4047-84ce-6f83e3c55a7f |  | checkpoint | Apply Cetcoat
checkpoint-status | 262aafb7-5621-41a1-a0fc-c784864ed84a |  | checkpoint | Hang protection layer
checkpoint-status | 3cbaf27b-c984-4ecc-a563-a69f9692c81d |  | checkpoint | Photo of highlighted drawing showing locations of work
checklist-sectioned | bea1b1e5-90c8-40bf-baa9-74c741fdfd38 |  | checklist | E. External Sealant Checklist |  |  |  |  | Yes | E. External Sealant Checklist | 93da1dd0-441f-432f-942f-cf35205ce91a
checkpoint-group | c76dd4fa-cdf0-41eb-8ac8-d26c14c6d3f9 |  | section | Sealant Application
checkpoint-status | 89076706-e0dd-4792-ab3d-45a33fe5978f |  | checkpoint | Work Area/Substrate is clean, dry and ready to start
checkpoint-status | d174b760-b0b3-44dc-8efa-1d62b6b06ed7 |  | checkpoint | Install PEF rod in the external vertical joints
checkpoint-status | 6e37f46f-6259-40be-9260-e36e39712766 |  | checkpoint | Clean and apply Sikaflex AT Façade in the vertical joints (incl. Primer 3N)
checkpoint-status | f9101ea6-3810-4537-b287-64d84342eff8 |  | checkpoint | Install PEF rod in the external horizontal joints
checkpoint-status | 7c9f8e8f-c668-4006-993f-2db5e25f07ab |  | checkpoint | Clean and apply Sikaflex AT Façade in the horizontal joints (incl. Primer 3N)
checkpoint-status | 8a893742-69ab-4a76-9889-d51541df33b8 |  | checkpoint | Joint Sealant installed correctly, checked and reviewed as per specification
checkpoint-status | b9c2e79c-078e-4bdf-aae8-f1112ab55133 |  | checkpoint | Site Area - Clean & Tidy
checklist-flat | 77e1953e-cb60-4c00-a5c5-522922500749 |  | checklist | Hydrotech Podium Checklist |  |  |  |  | Yes | Hydrotech Podium Checklist | 950e019a-af2e-4469-a13f-d17cc6e24211
checkpoint-status | dac436df-ae98-4271-8642-022b51b1470d |  | checkpoint | Substrate Inspected
checkpoint-status | 70a5069c-9c00-44a8-9ebc-570664879684 |  | checkpoint | Surface conditioner
checkpoint-status | f8129c65-a97d-4ada-ab2d-9b97f24bc5d2 |  | checkpoint | Daily bond test
checkpoint-status | 3428e0c3-e54b-4107-8300-887b7dd97904 |  | checkpoint | Detailing of any penetrations
checkpoint-status | bee1b30e-8809-42b4-9dbc-6d4dbc0a5326 |  | checkpoint | Installation of FlexFlash UN where required
checkpoint-status | c0979231-da74-4d12-8c47-1e0e1539430c |  | checkpoint | Hydrotech first layer 3mm
checkpoint-status | 652281be-da1c-4c45-92a5-19a5469ec97f |  | checkpoint | Flex Flash F
checkpoint-status | 19b562f8-3c9f-4454-b644-da612367da04 |  | checkpoint | Hydrotech Second layer 3mm
checkpoint-status | 695a1569-620a-4ab9-986a-a62ecfb0d91c |  | checkpoint | Casali protection sheet
checkpoint-status | 8bccb879-8b23-4ad8-8c46-d2a2335681e8 |  | checkpoint | Termination Bar with Sealant where required
checkpoint-status | 718eaafd-ca3c-4808-b6f3-85b15efefba2 |  | checkpoint | Two layer torch on membrane where required
checkpoint-status | c54a8246-e7af-4bf0-b2ab-26972fcabbdf |  | checkpoint | ILD test report attached
checklist-sectioned | b5b86bd1-6d24-45eb-b827-7c08efe8bb31 |  | checklist | A. Joint Sealant Checklist |  |  |  |  | Yes | A. Joint Sealant Checklist | 97ba1383-3ab7-461b-afbc-026aa2e92d58
checkpoint-group | bbe01aec-10ab-4221-a8c4-105def875340 |  | section | Sealant Application
checkpoint-status | 08085690-1d80-40b2-9ca1-46bcb130263c |  | checkpoint | Work Area/Substrate is clean, dry and ready to start
checkpoint-status | c07468cf-41f6-4af8-a6d2-530a534fd4d2 |  | checkpoint | Apply repair product to lifting eyes and missing upstand
checkpoint-status | 67450bdc-02e2-4e41-885b-859ecdcdddbd |  | checkpoint | Clean and install SS soakers - bedseal with Sikaflex 11 FC & mechanically fixed
checkpoint-status | ef4f2ddf-660f-4806-8100-9e981e23d702 |  | checkpoint | Install SIKA rain screen battle to vertical joints
checkpoint-status | 8746e58c-07e9-42bb-b721-082040282e97 |  | checkpoint | Clean and install SS soakers - bedseal with Sikaflex 11 FC & mechanically fixed
checkpoint-status | ddd0229e-f459-48cb-ad99-242b7d275762 |  | checkpoint | Install SIKA expansion tape in inaccessible areas
checkpoint-status | fea1767c-1c9e-4d43-8e0a-357fbc14b539 |  | checkpoint | Install PEF rod in the vertical joints
checkpoint-status | 1e5b7e38-112f-48da-b7e8-6a21e3772433 |  | checkpoint | Clean and apply Sikaflex AT Façade in the vertical joints (incl. Primer 3N)
checkpoint-status | 002cc593-f5bd-4956-9cc3-f45fc8d73081 |  | checkpoint | Install PEF rod in the horizontal joints
checkpoint-status | c2767cf0-7823-4825-ba1b-fb9cad278e80 |  | checkpoint | Clean and apply Sikaflex AT Façade in the horizontal joints (incl. Primer 3N)
checkpoint-status | 39328c35-8404-4633-9e80-6324b3282709 |  | checkpoint | Joint Sealant installed correctly, checked and reviewed as per specification
checkpoint-status | 097a7d49-c235-4c47-8753-69b2f213e9ed |  | checkpoint | Site Area - Clean & Tidy
checklist-flat | bccb2a2a-2d07-4f3b-aaf7-e7939b55beb8 |  | checklist | Voltex - Area: |  |  |  |  | Yes | QA - Tanking Voltex (V2) | a16345f5-b9cd-4e8e-a377-517e215feb19
checkpoint-status | 31eec38f-8db2-4e52-b54a-23730d5918d3 |  | checkpoint | Area of work input and photo of highlighted drawing showing locations of work attached
text | 2437d888-cc58-589f-8214-a6bb4b03fd84 |  | textbox | Grid Line:
checkpoint-status | bc519b94-72e4-48a2-b343-0a2eb168ce8f |  | checkpoint | Substrate to manufacturer's specifications (are there any voids that need filling, clean, etc.)
checkpoint-status | 0529d2ab-a7ab-452c-b2bd-e60bce2ad8a4 |  | checkpoint | Form work acceptable
checkpoint-status | a068b4c1-f955-43a3-a042-f05e829cdde9 |  | checkpoint | Voltex installed to wall as per specification
checkpoint-status | 5bf786c8-32b6-4f04-a888-e07ecd69e2da |  | checkpoint | Penetration(s) detailed and photo(s) taken of each
checkpoint-status | 71de2bb3-a7f3-4308-b45c-1b1893ed4988 |  | checkpoint | Joints and laps as per spec
text | a87eab79-db59-597b-b5f4-2ca3cca566c8 |  | textbox | Joints and laps: |  |  | mm
boolean | 1ed6de87-7957-581b-b434-22dce4bab588 |  | tickbox | Photo(s) attached
checkpoint-status | d9c9819b-9f11-4166-9581-81cb581c1a69 |  | checkpoint | Membrane checked for damages prior to pour and repaired if necessary
checkpoint-status | 967aae07-8a43-44b5-bc71-afa8c4f0bc22 |  | checkpoint | Sufficient lap projecting out of Construction Joint
text | bb4c6c1f-5401-5281-b483-0c8f3371dc0b |  | textbox | Lap projecting by: |  |  | mm
boolean | 4492f68f-01b4-5dea-9abd-4eb606bf8900 |  | tickbox | Photo(s) attached
checklist-flat | 835c12fe-d334-4117-91a3-bea945c4b554 |  | checklist | Tanking Insitu Walls - Area: |  |  |  |  | Yes | QA - Tanking Insitu Walls | a77b4c81-62f3-4dc0-8263-ea2481e4d1ae
checkpoint-status | 886bf56d-1b27-4feb-b906-e81d10f8eab1 |  | checkpoint | Substrate to manufacturer's specifications (are there any voids that need filling, clean, etc.)
checkpoint-status | 306d628a-e256-4efc-b850-2788ebc6cf52 |  | checkpoint | Check and clean flap.
checkpoint-status | 6d515fe1-1811-4d87-81e6-da7443ec7f0e |  | checkpoint | Material installed as per manufacturer's specification.
checkpoint-status | afcd4be3-bf99-417e-9f61-d1c1c131f5cf |  | checkpoint | Check membrane for any damage and do repairs to manufacturers requirements. Take photos.
checkpoint-status | aba16c68-7208-4c8f-9273-300593dbe723 |  | checkpoint | Complete penetrations
checkpoint-status | 9fe47c29-1313-48d4-82ef-123865eb443c |  | checkpoint | Tape the laps
checkpoint-status | 43bd9c36-38eb-45af-85ab-ad1e7034eb3d |  | checkpoint | Place the termination bar
checkpoint-status | 2a2aef8b-e635-4bc6-9726-0b9a0c5008f5 |  | checkpoint | Cetcoat applied
checkpoint-status | e675c15e-ab82-4d92-990e-cdb0086a7d7c |  | checkpoint | Protection layer installed
checkpoint-status | 50419055-0591-4a2d-9f80-a3e7ba02e25f |  | checkpoint | Drainage installed and 100mm away from wall
checkpoint-status | 86a49a26-caac-4537-8954-8e09075da248 |  | checkpoint | Photo of highlighted drawing showing locations of work
checklist-flat | 89684eab-09bd-4b8a-8a5c-80f38e95bd0a |  | checklist | Waterstop RX - Area: |  |  |  |  | Yes | QA - Tanking Waterstop RX | c5e46d19-0f3f-4aa8-acf7-6ee453c7f751
checkpoint-status | 5e4d1733-a24c-4947-aff1-dc9048c17b83 |  | checkpoint | Substrate to manufacturer's specifications (are there any voids that need filling, clean, etc.)
checkpoint-status | 40e5a68d-4acc-42e9-a320-ce643c90c41c |  | checkpoint | Concrete clearance above manufacturer's specifications
checkpoint-status | f09073d7-04ff-4979-90d8-61b3c5a8269c |  | checkpoint | Applied with sealant or mechanically fastened
checkpoint-status | db2ae27d-bb10-4b75-b964-a65c10fd2d22 |  | checkpoint | Photo of highlighted drawing showing locations of work
checklist-flat | b72e981c-a328-4233-8c69-3410c5cad512 |  | checklist | Nuralite Warm Roof |  |  |  |  | Yes | Nuralite Warm Roof | d7121c7a-1657-4a98-9369-6581d1f9f163
checkpoint-status | 01921acc-b7c0-4ac9-a864-442dec6d026e |  | checkpoint | Substrate inspection
checkpoint-status | e88f5228-029d-4cb3-a822-95d7536b5341 |  | checkpoint | Nuralite Nuraflux primer
checkpoint-status | 658a9a42-74aa-41a9-98f1-39967d941647 |  | checkpoint | Vapour Barrier
checkpoint-status | 6a4b4122-6cc9-4a63-aae2-ca9535f7b653 |  | checkpoint | PIR Board Installed as per board installation design
checkpoint-status | af80ec4c-f08a-4a86-809e-f407de39a6b6 |  | checkpoint | ILD Tape installed across boards
checkpoint-status | 82e7e429-5b7a-4f44-b48d-1098dacbdc8d |  | checkpoint | Nuralite Vented Base sheet installed
checkpoint-status | 4e54bd24-4ed7-46b1-aee2-0e5dbd8c75e3 |  | checkpoint | Nuralite Fully Bonded Base installed to upstands
checkpoint-status | bec898f3-15de-4d04-8c3e-f8de32b1abf1 |  | checkpoint | Nuralite Charcoal Cap sheet
checkpoint-status | 24f9aa6a-ee3b-4ad1-8bef-f9e60b35cade |  | checkpoint | Completed Photos
checkpoint-status | 220dd9a9-d063-4ffb-abf6-f1a24125c37c |  | checkpoint | ILD Report completed and attached
checklist-sectioned | 5e25f264-d510-493f-8f1b-455483f72d00 |  | checklist | B. BOSS Fire Silicone Checklist |  |  |  |  | Yes | B. BOSS Fire Silicone Checklist | f5fb08b3-cb91-4983-8b28-e271f8a92498
checkpoint-group | deee48dc-d15d-4d54-ba59-5d4351691a74 |  | section | Sealant Application
checkpoint-status | 89aa49cb-cc91-4b40-864f-fb607594ce43 |  | checkpoint | Work Area/Substrate is clean, dry and ready to start
checkpoint-status | f17523f3-af8b-4bc3-8c9a-4a2a69ece386 |  | checkpoint | Install PEF rod in the floor joints
checkpoint-status | 16dd5df4-6203-4980-83ae-d77fb282c5f1 |  | checkpoint | Clean and apply BOSS fire silicone sealant
checkpoint-status | 59732dd2-6ca3-46bc-9a67-0695c4a9f8a2 |  | checkpoint | Joint Sealant installed correctly, checked and reviewed as per specification
checkpoint-status | d4944e78-5e63-4a10-9676-ddacf5f6f406 |  | checkpoint | Site Area - Clean & Tidy