## Folder Structure
South Elevation | Level 0 | A. Internal Dowsil Joint Sealant
| Level 1 | A. Internal Dowsil Joint Sealant
| Level 2 | A. Internal Dowsil Joint Sealant
| Level 3 | A. Internal Dowsil Joint Sealant
East Elevation | Level 0 | B. External Dowsil Joint Sealant
| Level 1 | B. External Dowsil Joint Sealant
| Level 2 | B. External Dowsil Joint Sealant
| Level 3 | B. External Dowsil Joint Sealant
West Elevation | Level 0 | C. Internal Spectrum 1 Joint Sealant
| Level 1 | C. Internal Spectrum 1 Joint Sealant
| Level 2 | C. Internal Spectrum 1 Joint Sealant
| Level 3 | C. Internal Spectrum 1 Joint Sealant
North Elevation | Level 0 | D. External Spectrum 1 Joint Sealant
| Level 1 | D. External Spectrum 1 Joint Sealant
| Level 2 | D. External Spectrum 1 Joint Sealant
| Level 3 | D. External Spectrum 1 Joint Sealant

## A.Internal Dowsil Joint Sealant
Type | Name | Value
Checklist | Internal Dowsil Joint Sealant Checklist
Checkpoint | Work Area/Substrate is clean, dry and ready to start | Photo Required
Checkpoint | Record product batch numbers | Photo Required
Checkpoint | Install expansion tape to inaccessible areas | Photo Required
Checkpoint | Install PEF backing rod to horizontal & vertical joints | Photo Required
Checkpoint | Apply primer or complete an alcohol wipe
Checkpoint | Apply DOWSIL 700 to horizontal & vertical joints | Photo Required
Checkpoint | Joint sealant installed correctly and as per drawings/specification | Photo Required
Checkpoint | Work area is left clean & tidy | Photo Required

## B.External Dowsil Joint Sealant
Type | Name | Value
Checklist | External Dowsil Joint Sealant Checklist
Checkpoint | Work Area/Substrate is clean, dry and ready to start | Photo Required
Checkpoint | Record product batch numbers | Photo Required
Checkpoint | Install PEF backing rod to horizontal connection | Photo Required
Checkpoint | Apply primer or complete an alcohol wipe to horizontal connection | Photo Required
Checkpoint | Apply DOWSIL 700 to horizontal connection | Photo Required
Checkpoint | Install PEF backing rod to horizontal & vertical joints | Photo Required
Checkpoint | Apply primer or complete an alcohol wipe | Photo Required
Checkpoint | Form drainage holes with PEF rod | Photo Required
Checkpoint | Apply DOWSIL 700 to horizontal & vertical joints | Photo Required
Checkpoint | Joint sealant installed correctly and as per drawings/specification | Photo Required
Checkpoint | Work area is left clean & tidy | Photo Required

## C.Internal Spectrum 1
Type | Name | Value
Checklist | Internal Spectrum 1 Joint Sealant Checklist
Checkpoint | Work Area/Substrate is clean, dry and ready to start | Photo Required
Checkpoint | Clean and install angle flashing - bedseal with sealant & mechanically fixed | Photo Required
Checkpoint | Install expansion tape to horizontal inaccessible areas | Photo Required
Checkpoint | Work Area/Substrate is clean, dry and ready to start | Photo Required
Checkpoint | Record product batch number | Photo Required
Checkpoint | Install expansion tape to vertical inaccessible areas | Photo Required
Checkpoint | Install PEF backing rod to horizontal & vertical joints | Photo Required
Checkpoint | Apply primer or complete an alcohol wipe | Photo Required
Checkpoint | Apply Spectrum 1 sealant to horizontal & vertical joints | Photo Required
Checkpoint | Joint sealant installed correctly and as per drawings/specification | Photo Required
Checkpoint | Work area is left clean & tidy | Photo Required

## D.External Spectrum 1
Type | Name | Value
Checklist | External Spectrum 1 Joint Sealant Checklist
Checkpoint | Work Area/Substrate is clean, dry and ready to start | Photo Required
Checkpoint | Record product batch numbers | Photo Required
Checkpoint | Install PEF backing rod to horizontal connection | Photo Required
Checkpoint | Apply primer or complete an alcohol wipe to horizontal connection | Photo Required
Checkpoint | Apply Spectrum 1 to horizontal connection | Photo Required
Checkpoint | Install PEF backing rod to horizontal & vertical joints | Photo Required
Checkpoint | Apply primer or complete an alcohol wipe | Photo Required
Checkpoint | Form drainage holes with PEF rod | Photo Required
Checkpoint | Apply Spectrum 1 to horizontal & vertical joints | Photo Required
Checkpoint | Joint sealant installed correctly and as per drawings/specification | Photo Required
Checkpoint | Work area is left clean & tidy | Photo Required