## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 1da93022-3793-47c7-8eec-3e0eaf04194f |  | checklist | Concrete Prep - Grinding |  |  |  |  | Yes | Concrete Prep - Grinding | 0b19a75f-21cc-4944-9d9c-0593d4de316e
checkpoint-status | 72418f4e-8fd8-488a-9c48-39cb1c9edd93 |  | checkpoint | Slab grinding completed
checkpoint-status | a5e3c68f-9aec-4fc2-9e74-37b0981517b9 |  | checkpoint | Nibs/plinths grinding completed
checkpoint-status | 7cca5fbe-fbd7-4fa6-a41a-380e8f081f5a |  | checkpoint | All dust removed
checkpoint-status | 7ec59d61-3c4f-4db8-84dc-8dd2a84a307f |  | checkpoint | Area left clean and rubbish removed
checkpoint-status | 888a5a01-2a8f-40c7-822e-9f07d1bd7233 |  | checkpoint | Defects identified
checkpoint-status | 56a027b7-18a6-4ff6-8826-b55c5dc5a607 |  | checkpoint | Repairs completed
checklist-flat | f1b79f5e-d1f2-4179-adee-96ce812ecf35 |  | checklist | Nibs & Plinths - Membrane installation |  |  |  |  | Yes | Nibs & Plinths - Membrane installation | 197ccf75-32e4-4b13-9f60-09c720e885d6
checkpoint-status | cbda17f5-3cd6-4123-883f-dade16b95bbc |  | checkpoint | Area clean and access unobstructed
checkpoint-status | 66da2515-bcf9-48a2-9f2f-c80704f94ffe |  | checkpoint | Nuraflux membrane primer applied
checkpoint-status | ee2402a7-1c7c-4f1b-b870-604e57abef22 |  | checkpoint | Bitumen fillets installed
checkpoint-status | 0fb823a0-62a9-4df7-bdd7-c539035df628 |  | checkpoint | Nuraply 3PM cap sheet installed
checkpoint-status | 4589007b-cd7b-4d77-b3e0-5e06774c1e39 |  | checkpoint | Laps, details, etc. completed correctly
checkpoint-status | b2709cd2-ec92-40f6-b96f-1cdecdd083e1 |  | checkpoint | Termination flashing and sealant installed
checkpoint-status | 10c1f9d0-7541-49ad-8a4d-082f33d44630 |  | checkpoint | Area left clean and rubbish removed
checklist-flat | 329a4436-6c89-4a67-b7ac-f125ac5b4d69 |  | checklist | Asphalt Reinforcing - Rods, mesh & rails |  |  |  |  | Yes | Asphalt Reinforcing - Rods, mesh & rails | 2d1a3ec0-9026-4e35-a61b-4b7509bc382b
checkpoint-status | 1d91951d-9036-4703-9b02-df6656540ce1 |  | checkpoint | Area clean and access unobstructed
checkpoint-status | adee305f-912e-400f-a95a-3816e3a78594 |  | checkpoint | Survey completed - H&R
checkpoint-status | 76ab0a84-0b26-4acf-b3ac-8158618dd2c0 |  | checkpoint | Rods installed correctly
checkpoint-status | adefe75e-546d-4b97-8345-997299cfed58 |  | checkpoint | Mesh & rails attached to rods
checkpoint-status | c184563e-27d6-4033-bf46-e4fa6b75b4c3 |  | checkpoint | Detailing inspected
checkpoint-status | fceb3756-e820-4280-9467-b780d2be8590 |  | checkpoint | Area left clean and rubbish removed
checklist-flat | 1ae26582-c99f-4634-aac0-5918be03181d |  | checklist | Liquid Waterproofing - Matacryl |  |  |  |  | Yes | Liquid Waterproofing - Matacryl | 4578c94c-da6c-4052-b8d8-0d1c075806f3
checkpoint-status | b8099575-9242-4697-9720-5502e174d7d8 |  | checkpoint | Area clean and access unobstructed
checkpoint-status | a5d9363c-9506-455c-af63-6f7c2712e9c0 |  | checkpoint | Substrate ground clean
checkpoint-status | c62beecb-a975-4432-ac5f-b7f88fcede92 |  | checkpoint | Matacryl Prime coat applied
checkpoint-status | b22ac111-eaf5-45b5-81a6-d47c3e53b428 |  | checkpoint | Matacryl body coat with reinforcing mesh installed
checkpoint-status | 998cd581-8f00-4dcf-91a4-3ee2141a1990 |  | checkpoint | Matacryl topcoat installed
checkpoint-status | 53c57065-ec43-4cea-8aab-68e41132dbea |  | checkpoint | Quartz broadcast into trafficable areas
checkpoint-status | e0cf161f-3f6c-4a68-8a89-102b5980c4cb |  | checkpoint | Outlets and penetrations detailed
checkpoint-status | c20b9d3a-017d-4d6d-89ee-4910d639edf4 |  | checkpoint | Termination flashing and sealant installed
checkpoint-status | 6f3902c4-8a19-434e-9a98-5b48fe70006e |  | checkpoint | Area left clean and rubbish removed
checklist-flat | a2270cca-9e92-4f6e-8b54-1eae0461ce59 |  | checklist | Flat Areas - Membrane Installation |  |  |  |  | Yes | Flat Areas - Membrane Installation | 71ea83fc-36cc-4579-98a8-86e091720a05
checkpoint-status | 9b3baf3c-319d-4b4d-925a-482f4a62efd9 |  | checkpoint | Area clean and access unobstructed
checkpoint-status | 7485972c-dfbe-4e2a-b75a-be8d372fdb05 |  | checkpoint | Nuraflux membrane primer applied
checkpoint-status | 13282da8-c10d-4355-abf1-3e48a87e96c3 |  | checkpoint | Nuraply 3PC membrane installed
checkpoint-status | 30b08163-4e85-483d-8eee-ecab0c0b771a |  | checkpoint | Laps, details, etc. completed correctly
checkpoint-status | 93948ad1-7124-4933-9455-bb5948db1c21 |  | checkpoint | Survey completed - H&R
checkpoint-status | 9cdc9434-4c04-432b-ab66-3c3ae0556ed0 |  | checkpoint | Rods installed correctly - Sansom
checkpoint-status | 6868fb37-19ce-4fea-a8ff-0bebbbfa1b33 |  | checkpoint | Rods installed correctly - H&R
checkpoint-status | f52137fb-2d4e-4481-b4b7-274a7cfad602 |  | checkpoint | Membrane sealed around rods
checkpoint-status | 68049a77-3d0f-41fa-bce6-24639949ecbd |  | checkpoint | LPS sealant applied around rods
checkpoint-status | f3ba2eef-6dea-4fb0-b182-f2ac499e3d25 |  | checkpoint | 8mm thick angles installed
checkpoint-status | e2e5d1f9-aadb-4b5c-97ea-cc34b9343e75 |  | checkpoint | Area left clean and rubbish removed
checkpoint-status | a1821d31-1bcc-4812-bede-645bbd42b941 |  | checkpoint | EFVM test completed
checkpoint-status | e57aba38-ea71-4870-aac9-31d590a22d74 |  | checkpoint | Defects identified
checkpoint-status | 3bea6e3d-fc63-432a-8e5c-dd8dde56d0d3 |  | checkpoint | Repairs completed
checklist-flat | 761e73c3-0859-41f3-bad1-1615b6d44e68 |  | checklist | Area Handover |  |  |  |  | Yes | Area Handover | 785dbff7-51dd-4cf7-907a-37bcfea162f8
checkpoint-status | af9edff3-4832-4694-9ad6-7d93ec8ea1f0 |  | checkpoint | All concrete cured for 28 days
checkpoint-status | 27aa7f26-fe1f-4821-a5c6-d0fc45661195 |  | checkpoint | Area clean and access unobstructed
checkpoint-status | 010ccf25-eeda-40ed-851e-b99c626f3bb4 |  | checkpoint | Slab is defect free
checkpoint-status | a0621c1e-02cf-4427-856a-38b87d42524c |  | checkpoint | Repairs completed
checkpoint-status | 1d704f50-4481-4ebe-a932-e14c8493f198 |  | checkpoint | Nibs/plinths defect free
checkpoint-status | f77cc040-cd38-43b6-9830-36022932ca59 |  | checkpoint | Repairs completed
text | f3352a28-c5f5-52df-8c69-a43cc1b32437 |  | textbox | Handed over from:
checklist-flat | fea3ce41-c674-4d93-82ef-a7693b12b828 |  | checklist | Wheel stops |  |  |  |  | Yes | Wheel stops | b28ba3d0-05a6-4583-8225-9a479281dbaa
checkpoint-status | 382d7c47-5831-4de0-bc5f-89375df2fae7 |  | checkpoint | Rods undamaged
checkpoint-status | 6a0323a1-854d-4814-b261-6fba3dbbc47d |  | checkpoint | Wheel stops bolted down
checkpoint-status | 314059ae-1e3a-44a8-8fe7-86b9b70c4a1f |  | checkpoint | Area left clean and rubbish removed
checklist-flat | 2f105d1e-4fe6-4704-99a9-fb2fdd7f2a0d |  | checklist | Flat Roof - Two-layer membrane installation |  |  |  |  | Yes | Flat Roof - Two-layer membrane installation | fbf77ca3-0711-4841-b790-73eadbf03bf2
checkpoint-status | 69a5eb23-9e91-4e91-a021-583817a62a08 |  | checkpoint | Area clean and access unobstructed
checkpoint-status | 10f2c369-c7c2-4c5b-921a-b295e444a4d7 |  | checkpoint | Substrate meets specification
checkpoint-status | b102985f-fec5-4443-9c99-b1ee222b4d29 |  | checkpoint | Nuraflux membrane primer applied
checkpoint-status | 05842514-7abb-41a6-80e8-71bbad8c2f8f |  | checkpoint | EFVM mesh installed
checkpoint-status | 8f0dd82b-16e1-4a27-8fc6-921f535bc909 |  | checkpoint | Nuraply 3PB base sheet installed
checkpoint-status | 70de4ec5-3b44-45b8-830c-3b7a71d6f7f1 |  | checkpoint | Nuraply 3PM cap sheet installed
checkpoint-status | feb1738a-de2b-45b2-916d-a540442674e3 |  | checkpoint | Outlets and penetrations detailed
checkpoint-status | cffc306a-f729-436b-af9c-a6f1a2e54fda |  | checkpoint | Termination flashing and sealant installed
checkpoint-status | cf59bc3c-0afc-49bc-bf2e-f9ffdc565673 |  | checkpoint | Area left clean and rubbish removed
checkpoint-status | 45ae2c98-b610-49ad-8f00-7316ad603153 |  | checkpoint | EFVM test completed
checkpoint-status | 8ddcab12-594b-423d-833c-da2df941e670 |  | checkpoint | Defects identified
checkpoint-status | 61ca4aad-4d5e-4c26-8247-a3b3e9de7c15 |  | checkpoint | Repairs completed
checklist-flat | c338179e-b2ff-4912-bcdb-4e820921a17a |  | checklist | Asphalt |  |  |  |  | Yes | Asphalt | fc9ffb00-b975-4012-8bd2-ac15f1859368
checkpoint-status | 7831b227-82b3-4391-a816-2fca0ba7ce05 |  | checkpoint | Area clean and access unobstructed
checkpoint-status | 48f9e130-e28c-4b18-a5b9-578e634c6a8e |  | checkpoint | Ramp, column, wall & other protection in place
checkpoint-status | 2b2d791a-3c62-4bb7-8f6c-c0d56ae897a1 |  | checkpoint | Rods, outlets and other penetrations identified
checkpoint-status | 47857c32-8154-41fe-853d-1370d1244e84 |  | checkpoint | Blinding layer installed
checkpoint-status | 369d92e7-da8a-40e9-bed1-567520bbe41c |  | checkpoint | Asphalt installed
checkpoint-status | 954d2288-e6cd-43bc-bb28-8c52cf683de6 |  | checkpoint | Fully compacted and smooth
checkpoint-status | c97dfd87-a6e0-47b8-8af1-5ed95e3ddc3f |  | checkpoint | Asphalt contractor QA completed
checkpoint-status | 8fcfcbc2-dc97-4d3b-bc97-683273b8c1fc |  | checkpoint | Area left clean and rubbish removed
checkpoint-status | f7d15584-de56-4388-a137-4222f774783e |  | checkpoint | Inspected - Sansom
checkpoint-status | 8e0722e8-105c-48c7-aafd-a723bd6ad6b9 |  | checkpoint | Inspected - H&R
checkpoint-status | b14b47b0-be4b-4859-a36b-c0a5a56fe1b9 |  | checkpoint | Defects identified
checkpoint-status | 42ea06f1-6658-47d1-a26d-7ec2e8491680 |  | checkpoint | Repairs completed
text | 5199b3b2-aaaf-5c02-88a5-e959dd9b89c0 |  | textbox | Handed over to: