## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | a531f1a4-841a-4228-99f3-39c68d0b88b1 |  | checklist | External Dowsil Joint Sealant Checklist |  |  |  |  | Yes | B. External Dowsil Joint Sealant | 1e0e4067-e3ef-46da-8c82-fc31d290ee16
checkpoint-status | 0e40fea4-39b4-46e9-b13b-fdd0b9673964 |  | checkpoint | Work Area/Substrate is clean, dry and ready to start
label | 8ddb2d08-8ff3-56ef-acdb-9a12009a454d |  | note | Photo Required
checkpoint-status | 7ad0a5a3-4ad4-4a78-97fc-373ea81cb878 |  | checkpoint | Record product batch numbers
label | 73fcdda4-8dd4-589b-bbbd-9f5795e90095 |  | note | Photo Required
checkpoint-status | e748a9e6-834e-4b17-99d6-4e036b74f190 |  | checkpoint | Install PEF backing rod to horizontal connection
label | d7372b00-a87e-536f-afe5-8c1d1859f012 |  | note | Photo Required
checkpoint-status | f82fdcd6-f01a-48a2-a5aa-d7d9f822eee6 |  | checkpoint | Apply primer or complete an alcohol wipe to horizontal connection
label | a98d5fa5-f536-5e7a-bdde-89a268f83f2f |  | note | Photo Required
checkpoint-status | 0d2d49b1-e453-4b48-b8a2-87d1e7ef84cb |  | checkpoint | Apply DOWSIL 700 to horizontal connection
label | c026f522-390b-577a-b807-ac1a86df03aa |  | note | Photo Required
checkpoint-status | 04bf3283-2f89-4d12-b859-9681764e952d |  | checkpoint | Install PEF backing rod to horizontal & vertical joints
label | bcd0cf33-8121-5358-a2a5-ed15817a040e |  | note | Photo Required
checkpoint-status | f845d4ad-9cd8-41ae-a7a2-6daf87ad48d8 |  | checkpoint | Apply primer or complete an alcohol wipe
label | 1757ccc1-b170-5efc-bbaf-1244e248024e |  | note | Photo Required
checkpoint-status | ac010eca-21e8-4a6e-a728-a367231c5306 |  | checkpoint | Form drainage holes with PEF rod
label | ed4cfc0b-60ff-5b2b-8b15-18ab9eb8c22a |  | note | Photo Required
checkpoint-status | 36a8b0ba-44b1-4432-91a2-dd1d184975b7 |  | checkpoint | Apply DOWSIL 700 to horizontal & vertical joints
label | 2daa6638-c40e-537b-923e-06fd7f9ec39b |  | note | Photo Required
checkpoint-status | 72f22f25-c5e9-4088-8c84-17194fffc65a |  | checkpoint | Joint sealant installed correctly and as per drawings/specification
label | 5997cdc6-8aaf-59f4-b55c-ef6f256548a3 |  | note | Photo Required
checkpoint-status | c7515d93-86f1-419e-b2d5-9da856f71c3a |  | checkpoint | Work area is left clean & tidy
label | fef300ab-6315-5459-b635-c16b3ece8ce3 |  | note | Photo Required
checklist-flat | 900ea042-dddb-40ad-b225-210861bec446 |  | checklist | Site Visit Date: |  |  |  |  | Yes | Add Site Visit Checklist | 305cf093-b302-4a9f-8514-755967b6f8e5
checkpoint-status | c74fd0c8-a643-4db9-8d96-0371ad78ae55 |  | checkpoint | Details entered
text | abb4da4e-fd2a-5790-9d65-3783a5b4641c |  | textbox | Site visit performed by
text | bbe04973-8613-5428-b514-6ae96e2369ed |  | textbox | Site visit completed with / attendees
text | 518ba9a4-2079-5b3c-8b65-ed2a62e73372 |  | textbox | Description of area
checkpoint-status | 8bb62679-1b00-4578-9924-624ca288ccc7 |  | checkpoint | Photos taken
checkpoint-status | fd557c41-10a0-4ffe-b35a-6453cf7b74c0 |  | checkpoint | General observations and comments
checklist-flat | a89ea8ab-d63c-4227-b0c8-fb0ce5e545f8 |  | checklist | Document: |  |  |  |  | Yes | Document Attach | 3864513d-368a-46b5-b7e6-cc760c7a465b
checkpoint-status | 700d5cd3-d75b-4707-b6f5-7eb22e64b1b2 |  | checkpoint | Document Attached
checklist-flat | 86fbcfce-228a-42b9-90dc-c73bdc25d559 |  | checklist | Internal Spectrum 1 Joint Sealant Checklist |  |  |  |  | Yes | C. Internal Spectrum 1 | 756fd959-e56d-4854-9011-d089f1d1d508
checkpoint-status | 94153154-75d6-4a14-9a6b-5ffb4affe280 |  | checkpoint | Work Area/Substrate is clean, dry and ready to start
label | fb386124-b63e-5244-ba64-cc143cc6a133 |  | note | Photo Required
checkpoint-status | cb3090c6-8be2-424b-9cca-ae0599cbf2a3 |  | checkpoint | Clean and install angle flashing - bedseal with sealant & mechanically fixed
label | cb6bea28-ea30-5611-842f-06d5e328015e |  | note | Photo Required
checkpoint-status | 71fe70f5-9c25-4338-80a7-ec195d94ba59 |  | checkpoint | Install expansion tape to horizontal inaccessible areas
label | 5eeb141f-a71c-5a9d-81a9-581b38f45457 |  | note | Photo Required
checkpoint-status | 53672c93-ef7b-4090-92bb-881eda582ea7 |  | checkpoint | Work Area/Substrate is clean, dry and ready to start
label | 10c46565-aeb9-5ae8-a543-3c3b92928dcc |  | note | Photo Required
checkpoint-status | da41e867-224d-448e-a52a-0a13aea9aa3b |  | checkpoint | Record product batch number
label | ae290dac-d063-596d-9543-bce6e48ac32d |  | note | Photo Required
checkpoint-status | 65d66df8-69bd-44fa-bd44-631b3c642a07 |  | checkpoint | Install expansion tape to vertical inaccessible areas
label | acd8a645-6cbf-5c86-882b-1de08aebbc06 |  | note | Photo Required
checkpoint-status | ef2361ff-47f9-4c32-8dda-8d11315bbbdc |  | checkpoint | Install PEF backing rod to horizontal & vertical joints
label | 2a60dc09-6b89-5cf7-9f2b-be3287f5e821 |  | note | Photo Required
checkpoint-status | 3e203401-6f67-4648-9653-b1f585767e91 |  | checkpoint | Apply primer or complete an alcohol wipe
label | 43463d81-afa7-5e67-8805-0c48cb86f3b2 |  | note | Photo Required
checkpoint-status | 23018c4f-c21b-4bbf-ad8d-3946ea182086 |  | checkpoint | Apply Spectrum 1 sealant to horizontal & vertical joints
label | 8d0f560b-0ace-5bf5-806e-550e5a2a927e |  | note | Photo Required
checkpoint-status | 78c86b44-f013-4bed-b596-8d1549bfa7ff |  | checkpoint | Joint sealant installed correctly and as per drawings/specification
label | 4e540375-8beb-5199-a7f1-1093b22bf19e |  | note | Photo Required
checkpoint-status | ec670019-b4e4-4326-a4be-3b4faf680a97 |  | checkpoint | Work area is left clean & tidy
label | 26b336c0-cb92-5787-9496-1e61f742a491 |  | note | Photo Required
checklist-flat | 4c70d9b4-8f2d-45fb-9829-c0a84be350ca |  | checklist | External Spectrum 1 Joint Sealant Checklist |  |  |  |  | Yes | D. External Spectrum 1 | 7eaee5ce-806d-4ccd-ae3e-939b050407dd
checkpoint-status | 8e549a2f-5864-4bda-866f-d06450b71c09 |  | checkpoint | Work Area/Substrate is clean, dry and ready to start
label | 2bb504bc-a7cb-5fcc-9d09-88df19d63cd6 |  | note | Photo Required
checkpoint-status | 946dd183-6c0a-4f42-9ac4-729910a76938 |  | checkpoint | Record product batch numbers
label | 34ff6fff-34fb-5783-9f8c-c07eba7280d3 |  | note | Photo Required
checkpoint-status | 43d8295b-9c46-4a62-b5cb-a52297305341 |  | checkpoint | Install PEF backing rod to horizontal connection
label | b8b6c160-2b3c-55c2-a975-5c1d7714dfc3 |  | note | Photo Required
checkpoint-status | 825fc872-af1b-4634-8b95-89905a8a1f5d |  | checkpoint | Apply primer or complete an alcohol wipe to horizontal connection
label | 529ea91e-d25e-5518-8c74-477ba103282d |  | note | Photo Required
checkpoint-status | 9f290028-7b7c-4a27-bd59-1f99c884be94 |  | checkpoint | Apply Spectrum 1 to horizontal connection
label | 108bf4d3-3a6e-51d3-8f85-09bd39cf8be3 |  | note | Photo Required
checkpoint-status | 29d501b6-a84a-4faf-a7f9-52bb14987792 |  | checkpoint | Install PEF backing rod to horizontal & vertical joints
label | b694d4c4-0c82-5986-b50e-244745e31369 |  | note | Photo Required
checkpoint-status | 2e8c2601-24ea-41b2-a2d6-ab5c4f5297d3 |  | checkpoint | Apply primer or complete an alcohol wipe
label | 55affa65-1e5b-56fd-b47e-a415f073ab35 |  | note | Photo Required
checkpoint-status | 4e46fe48-8fd2-4558-9114-9bb87360e0d3 |  | checkpoint | Form drainage holes with PEF rod
label | 07815286-f8f8-54e8-bf90-c64c34cf8c81 |  | note | Photo Required
checkpoint-status | 1c3440e8-956c-4771-83b7-f093aaa41dd4 |  | checkpoint | Apply Spectrum 1 to horizontal & vertical joints
label | 7cc82547-f892-5778-be60-fc7a8f7c189a |  | note | Photo Required
checkpoint-status | 0a29ad24-a118-4b82-92bc-a42cc4b10300 |  | checkpoint | Joint sealant installed correctly and as per drawings/specification
label | 8c3744a7-5e8f-53f2-aaa6-c0485e6795eb |  | note | Photo Required
checkpoint-status | 08caca36-0aee-409c-8afb-aa3ac01799b7 |  | checkpoint | Work area is left clean & tidy
label | 0ea02f06-4b0f-5633-ac24-f30095cc6445 |  | note | Photo Required
checklist-flat | 22ab731c-95e5-45ad-9d13-7724f9965eaa |  | checklist | Variation Details - |  |  |  |  | Yes | Add Variation | d2c99dbd-1baa-479f-bd3a-dab0f7f5a916
checkpoint-status | e0380a32-b066-4e80-be85-f334f0fa93a8 |  | checkpoint | Variation Details Approved
text | 664a3909-7445-5f16-ab3d-7330809eace9 |  | textbox | Reference/Drawing/Instruction Number
text | 93420d6e-6f8f-57e8-a784-2cf2aea9b6a4 |  | textbox | Variation Area
text | b90454c1-bb76-5eb5-b613-56c271ae327b |  | textbox | Materials & labour breakdown
holdpoint | 45b5c176-8c12-414c-ba05-86814e424c17 |  | signoff | Request Variation Acknowledgement
checkpoint-status | 544d85e3-d68e-4f19-b258-f675555ff19d |  | checkpoint | Variation Completed
holdpoint | 303ffdb1-0f9c-4b25-b7d1-2837c7566589 |  | signoff | Request Variation Signoff
checklist-flat | c42536ec-e489-4bd5-902a-90c05976c563 |  | checklist | Internal Dowsil Joint Sealant Checklist |  |  |  |  | Yes | A. Internal Dowsil Joint Sealant | f0d17550-a1b0-4dca-8555-f2983a8ddab9
checkpoint-status | a69f9249-e7ab-46c0-aab1-8bfa10fb0f86 |  | checkpoint | Work Area/Substrate is clean, dry and ready to start
label | fe505682-6910-5ff7-a795-7401ec930bf9 |  | note | Photo Required
checkpoint-status | 20425c0c-50d5-4814-8da0-52bd32ac4466 |  | checkpoint | Record product batch numbers
label | 90296644-7b3f-53b6-a0ef-325b72e08e68 |  | note | Photo Required
checkpoint-status | 7d9ef28d-b3c3-4638-b9a4-7adab87f7322 |  | checkpoint | Install expansion tape to inaccessible areas
label | 3d5a8c1a-4691-5fb2-a8e8-a0e2d48bd2f0 |  | note | Photo Required
checkpoint-status | 55441191-b793-4169-9717-ccc5e2734651 |  | checkpoint | Install PEF backing rod to horizontal & vertical joints
label | 4f3e938e-f49b-50ef-a3f2-b9f0324f5a5d |  | note | Photo Required
checkpoint-status | a5a8c7a8-f0b1-43f1-8b39-08fb01e3454b |  | checkpoint | Apply primer or complete an alcohol wipe
checkpoint-status | be18973d-37e1-42fd-882c-dbc889cd5117 |  | checkpoint | Apply DOWSIL 700 to horizontal & vertical joints
label | ab0cb1ea-844a-5a0a-b364-13b42e1fc4b0 |  | note | Photo Required
checkpoint-status | 1de9d8ef-540c-4ea4-b88c-8ad967716019 |  | checkpoint | Joint sealant installed correctly and as per drawings/specification
label | 553d3b30-1874-5c10-979b-13af59b2e6a4 |  | note | Photo Required
checkpoint-status | 0468afca-0d7d-4c42-9eae-a9c70d40c3f1 |  | checkpoint | Work area is left clean & tidy
label | 3d52abbd-0666-59db-aab7-244768da2095 |  | note | Photo Required