## Checklists matakana villas
type | name | values
Matakana villas QA lists
checklist | Footings
checkpoint | Surveyor set out Gridlines on profiles
checkpoint | Prepour geotech inspection
checkpoint | DPC installed
checkpoint | Reinforcing as per structural details
checkpoint | Starters at correct centres and correct height
checkpoint | Engineer prepour inspection
checkpoint | Council prepour inspection
checkpoint | Correct MPA concrete and photos of dockets
checkpoint | Well vibrated and poured to correct height
checklist | Blockwork
checkpoint | Surveyor setout gridlines
checkpoint | footings clean and lines marked
checkpoint | Footings level and to the correct height to 100mm module
checkpoint | Starters in correct positions, 100mm from corners
checkpoint | Council and engineer inspection complete prepour
checkpoint | Block fill complete and cleaned up
checkpoint | Blockwork laid to correct FFL
checkpoint | Pointing neat on visable surfaces
checkpoint | Washout boxing removed and site tidy.
checkpoint | DPM complete and QA received
checkpoint | Backfill in layers to achieve correct height to underslab
checkpoint | Geotech inspect sub base
checklist | Raft Slab
section | Prepour Slab
checkpoint | Check set out, spot check for square and legnths
checkpoint | Slab is as per Engineer and contract specification (e.g. ribraft spec)
checkpoint | Polythene taped and no holes in it
checkpoint | All Plumbing serivces installed and in correct location
checkpoint | All electrical conduits including incoming mains, data, phone if req.
checkpoint | Conduit to island bench if req.
checkpoint | Check underfloor heating pipework is pressure tested, away from wall lines. Take video of pipework.
checkpoint | All rebates installed, e.g. shower, windows, garage door, baths
checkpoint | Earth rod installed
checkpoint | Check reinforcing cover, grade and details
checkpoint | Formwork is suitablly braced for concrete pressure
checkpoint | All hold down bolts, or cast in plates etc are installed and set out checked
checkpoint | All insulation perimeter or slab has been installed as per spec.
checkpoint | Adequate site access for Conc pump and trucks
checkpoint | Placers advised of concrete floor finish.
checkpoint | Check preslab inspection passed
checkpoint | Curing in place as req.
section | Post pour
checkpoint | Skip on site
checkpoint | Site left clean and tidy
checkpoint | Check finish of slab is acceptable
checkpoint | Expansion cuts in correct locations
checkpoint | visiual check for level, humps and hollows, blowouts
checklist | QA - Timber Framing
checkpoint | Dimensions / locations checked and accurate
checkpoint | All frames are square
checkpoint | Frames are straight and level
checkpoint | Fixings are correct
checkpoint | Any bracing requirements installed
checkpoint | Nogs / service nogs installed correctly as per plan
checkpoint | General photos, comments and observations during install
checkpoint | Timber Framing completed within specified tolerance, checked and approved
checklist | Midfloor cassettes
checkpoint | Perimeter scaffold complete
checkpoint | Wall framing braced and secure, nail plates complete
checkpoint | Cassettes placed and straight on perimeter
checkpoint | Joins screwed off and complete
checkpoint | Flitch beams installed
checkpoint | All fixings complete
checkpoint | Any defect reported to Carters
checkpoint | Stair handrail installed
checklist | Roof
checkpoint | Area tidy and accessible
checkpoint | Trusses at 900c max
checkpoint | Velux in correct position
checkpoint | All brackets / hold downs fixed
checkpoint | Roof brace and blue screws installed
checkpoint | Barrierline and 16mm Gib to underside of Purlins
checkpoint | Insulation ready for laying under roofing
checkpoint | Council Inspection pass
checkpoint | Engineer Inspection pass
checkpoint | Area left tidy and accessible
checkpoint | Photos
checklist | QA - RAB
checkpoint | Plans / specs followed
checkpoint | Flashings in place
checkpoint | Sheet neatly cut and 1-2 mm gaps at join
checkpoint | Correct nails / nailing pattern
checkpoint | All nails flat and not puncturing board
checkpoint | Taped / Sealed
checkpoint | Council inspection complete
checkpoint | Area RAB complete
checklist | Cavity
checkpoint | Spec followed for timber type
checkpoint | Windows installed and PEF rod inspected by council, QA received
checkpoint | Flashings Installed ( Tape with aluband)
checkpoint | Ventstrip Install
checkpoint | Cavity battens fixed plumb
checkpoint | Horizontal battens complete
checkpoint | Cavity battens at correct Centres
checkpoint | Continous top batten
checkpoint | Structural fixings checked - 300mm centres
checkpoint | Council Inspection pass
checkpoint | Signed off ready for Board/Cladding
checklist | Post Cladding - Linea
checkpoint | Product installation guide printed for installers to read
checkpoint | All cuts primed
checkpoint | All cladding complete, penetrations flashed and tidy
checkpoint | Correct fixings used
checkpoint | Battens installed and primed all 4 sides, full paint system behind battens
checkpoint | Junctions between claddings are tidy
checkpoint | Silicon seals have been done and are tidy
checkpoint | Check heights of cladding at the bottom to ensure they match around house
checkpoint | Check defects and send defect reports if neccesary
checklist | Preline
checkpoint | Electrical walk through with client complete, variations signed off
checkpoint | All first fix plumbing items delivered to site
checkpoint | Rondo or timber ceiling battens complete
checkpoint | 1st fix plumbing ware delviered to site, shower trays installed level
checkpoint | Plumbing pressure test complete
checkpoint | Electrical pre wire complete checked against updated plan from walk through
checkpoint | Heating pipework installed and under test
checkpoint | Any stud penetrations over 25mm have stud stiffeners in place
checkpoint | Walls straighened and braces removed
checkpoint | All blocking in place for fixed furniture, tv blocking, shower screens
checkpoint | Man holes framed out
checkpoint | Tile niches framed out and flashed
checkpoint | Internal flashings installed for tiled showers
checkpoint | Internal doors, door finish checked, floor clearance, installed correct, hung the right way, general quality check
checkpoint | Insulation installed as per spec and R values checked.
checkpoint | Polished conc floors have had a first cut if req
checkpoint | Air seals on external windows and doors
checkpoint | Check bracing elements do not have flush boxes in wrong location
checkpoint | Garage door measured and blocking installed
checkpoint | Check wingback set back position allowing for tiles and setout for bowls
checkpoint | All bulkheads formed if required
checkpoint | Preline plumbing inspection passed
checklist | Prestop
checkpoint | Check all bracing elements are screwed correctly
checkpoint | Correct linings in wet areas, villaboard for tiles aqualine for wet areas
checkpoint | Fire collars and fire stopping installed and checked through fire walls
checkpoint | All gib off cuts removed and slab swept
checkpoint | Postline inspection complete
checklist | Pre paint
checkpoint | Kitchen sign off by client and Measure complete
checkpoint | Skiting on site correct profile and size
checkpoint | Plasterer has sanded and light checked
checkpoint | All skirtings and architraves installed glued and bradded in place
checkpoint | Electrial lighting cut outs and check for flush boxes
checkpoint | Tiled areas marked to be not painted
checkpoint | Confirm areas of floor to be masked for floor finishes
checkpoint | Confirm colour scheudle Interior and exterior has been sent to the painter
checkpoint | Painted cladidngs installed correct to manufacturers guidelines
checkpoint | Painting complete and defected with lights, stickers applied
checkpoint | Final check of painting
checkpoint | Garage door installed and in good working order

## High End Resi House
type | name | values
checklist | Services Second Fix
checkpoint | Sanitary ware items delviered and checked against spec
checkpoint | All items installed as per manufacturers guidelines and tested
checkpoint | Lighting either supplied by us or client on site ready for install
checkpoint | Electrical inspection booked for mains power
checkpoint | Electical fit off as per spec and checked against client walk through
checkpoint | Heat pumps fitted and tested
checkpoint | Heat pump drains in place
checklist | Excavation
checkpoint | Initial site visit with contractor to agree heights and confirm Geo Inspection and compaction testing if req
checkpoint | Has Geotech inspection been completed after subgrade dig
checkpoint | Has client been informed and signed off any additional excavation scope, if any.
checkpoint | Has compaction testing been done if req.
checkpoint | Heights of finsihed excavation checked against datum
checkpoint | Thickenings for load bearing walls checked for setout
checkpoint | Sand layer installed to correct depth
checkpoint | Final profiles for slab installed and checked by Surveryor if req
checkpoint | Are the drains running underslab or outside
checklist | Tiling
checkpoint | Tiles on site photos taken, drains on site checked against spec, and grout colour agreed with client
checkpoint | Grout colour and trims agreed with client
checkpoint | Screeds complete with adequate falls
checkpoint | Tanking applied and inspection passed
checkpoint | Tile layout confirmed with Client sign off
checkpoint | Tiles installed defect report sent
checkpoint | Defect remedied
checkpoint | Shower screens and mirrors measured and confirmed
checklist | Drainage
checkpoint | Has the plumber/drainlayer received signed off sanitary spec
checkpoint | Has the drainlayer booked an inspection date
checkpoint | Check all plumbing items are installed
checkpoint | Check inspection has passed
checkpoint | All sand and excavation returned to level and clean
checkpoint | Temporary water feed installed from toby box
checkpoint | Site left tidy.
checklist | Final Internal
checkpoint | General comments and photos from final walk through
checklist | Roof
checkpoint | Fascia installed as per plan and spec
checkpoint | Membrane installed as per manufacturers guidelines if req.
checkpoint | Roof Colour, profile and material correct
checkpoint | All flashings installed and tidy
checkpoint | Any penetrations, skylights and suntunnels correctly flashed
checkpoint | Site left clean and tidy
checkpoint | Range hood ducts and venitlation installed and flashed
checkpoint | Full check of roof for defects and quality
checkpoint | Scaffold to be removed
checklist | Joinery
checkpoint | Vanities delivered and installed by builder
checkpoint | Kitchen Installed, all hinges and runners working correctly
checkpoint | Colours checked against spec
checkpoint | Confirm basin and tap locations for bench tops
checkpoint | Template complete for bench top, Holes for sink and taps confirmed to bench manufacturer
checkpoint | Appliances delivered ready for install
checkpoint | Wardrobes installed and in good working order
checklist | Preclad
checkpoint | Install danband on between nog lines, prior to building paper/wrap
checkpoint | Building wrap/RAB installed as per spec and manufacturers installation guide
checkpoint | Flashing tapes are in place
checkpoint | Soffits material checked against plan and spec, sheets pre painted prior to going up. Colours sent to painter
checkpoint | Windows installed, screwed off at 400crs plumb and level. Correct colour
checkpoint | All MEP penetrating the building installed and flashed
checkpoint | All associated flashings installed as per plan and E2.
checkpoint | Correct cavity battens installed, including battens by subs e.g. solid plaster
checkpoint | Spot check batten spacings
checkpoint | Garage door reveal installed
checklist | Floor Finishes
checkpoint | Installed as per spec and drawings
checkpoint | defected and checed for quality, record sent to flooring contractor
checklist | Raft Slab
section | Prepour Slab
checkpoint | Check set out, spot check for square and legnths
checkpoint | Slab is as per Engineer and contract specification (e.g. ribraft spec)
checkpoint | Polythene taped and no holes in it
checkpoint | All Plumbing serivces installed and in correct location
checkpoint | All electrical conduits including incoming mains, data, phone if req.
checkpoint | Conduit to island bench if req.
checkpoint | Check underfloor heating pipework is pressure tested, away from wall lines. Take video of pipework.
checkpoint | All rebates installed, e.g. shower, windows, garage door, baths
checkpoint | Earth rod installed
checkpoint | Check reinforcing cover, grade and details
checkpoint | Formwork is suitablly braced for concrete pressure
checkpoint | All hold down bolts, or cast in plates etc are installed and set out checked
checkpoint | All insulation perimeter or slab has been installed as per spec.
checkpoint | Adequate site access for Conc pump and trucks
checkpoint | Placers advised of concrete floor finish.
checkpoint | Check preslab inspection passed
checkpoint | Curing in place as req.
section | Post pour
checkpoint | Skip on site
checkpoint | Site left clean and tidy
checkpoint | Check finish of slab is acceptable
checkpoint | Expansion cuts in correct locations
checkpoint | visiual check for level, humps and hollows, blowouts
checklist | Post Cladding
checkpoint | All cladding complete, penetrations flashed and tidy
checkpoint | Correct fixings used
checkpoint | Junctions between claddings are tidy
checkpoint | Silicon seals have been done and are tidy
checkpoint | Check heights of cladding at the bottom to ensure they match around house
checkpoint | Check defects and send defect reports if neccesary
checklist | Trusses
checkpoint | All trusses and hardware and layouts have been delivered
checkpoint | Trusses installed as per plan
checkpoint | Bottom chord restraints in place
checkpoint | Gable end bracing as per 3604
checkpoint | All hardware and fixings installed
checkpoint | Confirm purlin layout as per roofing material and wind zone
checkpoint | Valleys, hips and ridges are installed straight with solid blocking
checkpoint | Roof bracing installed as per plan or 3604
checkpoint | Firewalls if requires installed as per specification.
checkpoint | Framing and bracing/Pre wrap inspection passed
checkpoint | Skylights or Suntunnels installed if req.
checkpoint | Site left clean and tidy
checklist | Preliminary and Site Setup
checkpoint | Has Contract Works Insurance been put in place
checkpoint | Has Temporary power been connected
checkpoint | Fencing set up
checkpoint | Hazard Board
checkpoint | Sign and site box (first aid kit, mini fire extinguisher)
checkpoint | Site Toilet
checkpoint | Plans, Specs and Consent docs printed and put in site box
checkpoint | Site mark out, Inlcude datum complete ready for excavation (dazzle only)
checkpoint | Delapidation Survey Complete Photos
checklist | Prestop
checkpoint | Check all bracing elements are screwed correctly
checkpoint | Correct linings in wet areas, villaboard for tiles aqualine for wet areas
checkpoint | Fire collars and fire stopping installed and checked through fire walls
checkpoint | All gib off cuts removed and slab swept
checkpoint | Check if cornices are required
checklist | Preline
checkpoint | Electrical walk through with client complete, variations signed off
checkpoint | All first fix plumbing items delivered to site
checkpoint | Rondo or timber ceiling battens complete
checkpoint | 1st fix plumbing ware delviered to site, shower trays installed level
checkpoint | Plumbing pressure test complete
checkpoint | Electrical pre wire complete checked against updated plan from walk through
checkpoint | Heating pipework installed and under test
checkpoint | Any stud penetrations over 25mm have stud stiffeners in place
checkpoint | Walls straighened and braces removed
checkpoint | All blocking in place for fixed furniture, tv blocking, shower screens
checkpoint | Man holes framed out
checkpoint | Tile niches framed out and flashed
checkpoint | Internal flashings installed for tiled showers
checkpoint | Internal doors, door finish checked, floor clearance, installed correct, hung the right way, general quality check
checkpoint | Insulation installed as per spec and R values checked.
checkpoint | Polished conc floors have had a first cut if req
checkpoint | Air seals on external windows and doors
checkpoint | Check bracing elements do not have flush boxes in wrong location
checkpoint | Garage door measured and blocking installed
checkpoint | Check wingback set back position allowing for tiles and setout for bowls
checkpoint | All bulkheads formed if required
checkpoint | Preline plumbing inspection passed
checklist | Pre paint
checkpoint | Kitchen sign off by client and Measure complete
checkpoint | Skiting on site correct profile and size
checkpoint | Plasterer has sanded and light checked
checkpoint | All skirtings and architraves installed glued and bradded in place
checkpoint | Electrial lighting cut outs and check for flush boxes
checkpoint | Tiled areas marked to be not painted
checkpoint | Confirm areas of floor to be masked for floor finishes
checkpoint | Confirm colour scheudle Interior and exterior has been sent to the painter
checkpoint | Painted cladidngs installed correct to manufacturers guidelines
checkpoint | Painting complete and defected with lights, stickers applied
checkpoint | Final check of painting
checkpoint | Garage door installed and in good working order
checklist | Exterior Site Works
checkpoint | Paved areas marked out and confirmed with Client
checkpoint | Mark up sent to paving contractor, concrete or landscape
checkpoint | Adequate protection to house cladding
checkpoint | Prep, box and pour as per mark up
checkpoint | Site left clean and tidy, slurry removed if exposed ag. Ensure all concrete is cleaned off house
checklist | Framing
checkpoint | Frames on site ready for builder, inluding loose timber, layouts and hardware
checkpoint | Adquate 4x2 on site for bracing
checkpoint | Organised nets and scaffold
checkpoint | Frames plumb and square
checkpoint | Check ceiling battens are correct as per the double top plate
checkpoint | All frames are nailed together at corners
checkpoint | Check all window openeings and reveal depth and type (groove or arch) as per factory shop drawings and window schedule check against both
checkpoint | Check wall to wall shower and vanity enclosue alcoves are correct to specification, and square
checkpoint | Check glass spec
checkpoint | All fixings and holdowns in place, bracing elements marked out on slab
checkpoint | Adequate bracing is in place to hold frames straight and plumb
checkpoint | Scaffold and nets in place ready for trusses, ensure truss delivery booked
checklist | Weatherboard Cladding
checkpoint | Weatherboards & all cut edges sealed prior to installation
checkpoint | Framing Straight and plumb within tolerance
checkpoint | All nogs/ special nogs in place.
checkpoint | Wall underlay and strapping inspected and installed correct.
checkpoint | All aluminium joinery Doors/Windows installed
checkpoint | Cavity batten installed at 400 centres
checkpoint | Cavity closer installed correctly
checkpoint | Aluminium Flashings to internal/external installed as per manufacturer's drawing.
tick box | Head Flashings to Doors & windows installed by others
checkpoint | Fixing Method Checked and correct as per installation manual.
checkpoint | All cladding installation checks completed & inspections carried out

## Kaipatiki Interior Fitout
type | name | values
checklist | QA - Interior Fitout
section | Plumbing First Fix
checkpoint | Plumbing first fix complete
tick box | Mixers are in correct position (hole allowance to work with tiles)
tick box | All water & gas risers are complete
tick box | All stacks are level/plumb
checkpoint | Trades QA received & attached as applicable
section | Electrical First Fix
checkpoint | Electrical first fix complete
tick box | Power points have been installed as per the electrical plans
tick box | All comms are installed to allow for good detailing around
tick box | GPO's are correct for air conditioning & functional
checkpoint | Trades QA received & attached as applicable
section | Mechanical First Fix
checkpoint | Electrical first fix complete
tick box | All aircon has been roughed in & tested
tick box | All mech has been roughed in & completed
tick box | All services that go through fire rated walls to be treated with collars/fire rated sealant
tick box | Duct work to be tear free & sealed prior to cleaning
checkpoint | Trades QA received & attached as applicable
section | Passive Fire
checkpoint | Ensure all penetrations have been installed as per specifications
checkpoint | Ensure all fire collars have been installed in accordance with manufacturer's specifications
checkpoint | Ensure that mechanical ductwork is suitably sealed when passing through firewalls
checkpoint | Ensure that suitable access is provided to mechanical fire dampers
checkpoint | Ensure electrical cables have been suitably sealed when passing through a fire element in
checkpoint | Check that fire doors have been filled
checkpoint | Trades QA received & attached as applicable
section | Post Wall Linings
checkpoint | Ensure installation guide has been followed for insulation
checkpoint | Ensure installation guide has been followed for fire rated walls
checkpoint | Trades QA received & attached as applicable
section | Bathroom & Laundry Waterproofing
checkpoint | Waterproofing completed as per specifications
checkpoint | Trades QA received & attached as applicable
section | Tiling
checkpoint | All floors fall to wastes & don't hold water
checkpoint | Ensure all tiles are fixed correctly
checkpoint | Trades QA received & attached as applicable
section | Joinery Fit Out
checkpoint | All bathroom joinery installed as per specifications
checkpoint | All kitchen joinery installed as per specifications
checkpoint | Trades QA received & attached as applicable
section | Services Fit Out
checkpoint | Plumbing fitout have been tested & commissioned
checkpoint | Electrical fitout have been tested & commissioned
checkpoint | Air Conditioning / Mech fitout have been tested & commissioned
checkpoint | Trades QA received & attached as applicable
section | Internal Painting, Framing & Carpet
checkpoint | All studs are set out correct, and are plumb level, square & installed as per manufacturer's recommendations
checkpoint | Painting completed as per specs, correct paint product and colour used
checkpoint | Carpet installed as per specifications
checkpoint | Trades QA received & attached as applicable
section | Fire System
checkpoint | Smoke detectors & sensors fit off completed
checkpoint | Smoke detectors & sensors tested as per manufacturer's instructions
checkpoint | Sprinkler rough fit off completed
checkpoint | Sprinklers commissioned
checkpoint | Trades QA received & attached as applicable
section | Scarbro Final Sign - Off
checkpoint | All apartment work is completed as per specifications / drawings. All relevant trade QA reviewed & approved
tick box | Scarbro - apartment final sign off
label | Click to attach signature sign off below