## Sheet1
type | name | values | type | name
checklist | Insulation |  | checklist | Insulation
section | Material Inspection |  | section | Material Inspection
checkpoint | Insulation: Roof sarking on Proctor Wrap HTR |  | checkpoint | Insulation: Roof sarking on - Proctor Wrap HTR
| 80mm glasswool on medium sarking |  |  | 80mm glasswool on medium sarking
checkpoint | Thermal spacer: 60mm thermal spacer - Ashgrid 1200mm - 60mm |  | checkpoint | Thermal spacer: 60mm thermal spacer - Ashgrid 1200mm - 60mm
section | Installation |  | section | Installation
checkpoint | insulation to entire roof area |  | checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined |  | checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters |  | checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations. |  | checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly |  | checkpoint | Thermal Spacer Located correctly
checkpoint | Area clean and free of debris |  | checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears |  | checkpoint | Materials in good condition with no tears
section | Signoffs |  | section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation |  | checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by: |  | text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative |  | checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by: |  | text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor |  | checkpoint | Reinspection requested by Subcontractor
text | Date: |  | text | Date:
checkpoint | Non-Conforming Items to be Rectified |  | checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily |  | checkpoint | Follow up work satisfactorily
text | Site Supervisor: |  | text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily |  | checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative: |  | text | Client Representative:
checklist | Roof Installation
section | Material Inspection:
checkpoint | Roof Sheets: 0.48mm Zincalume Spandek
checkpoint | Insulation Type: 80mm glasswool on medium sarking
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Screws: Hex Head with Neo
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.55mm Zincalume
checkpoint | Capping Material 0.55mm Zincalume
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations
checkpoint | Flashing Material: 0.55mm Zincalume
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | to fit the purpose.
checkpoint | Adequate support around penetration to prevent roof
checkpoint | sheet from buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Fascia Gutter
section | Material Inspection
checkpoint | Fascia Gutter Brackets: Half Round 250mm Zincalume
checkpoint | Fascia Gutter: Half Round 250mm Zincalume
checkpoint | Gutter Flashing: 1.0mm Zincalume
section | Installation
checkpoint | Spout Brackets installed with fall as per Specification
checkpoint | Spouting installed to sizes shown in spec & drawings.
checkpoint | Outlets installed to correct sizes.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative: