## Project Breakdown
Queenscliff Ferry Terminal |  |  | Checklists
QA / ITP's
Roof Insulation
|  | Insulation | Insulation Checklist
Wall Substrate External
|  | Wall Cladding | Wall Cladding Checklist
Wall Substrate Internal
|  | Wall Cladding | Wall Cladding Checklist
Eave and Box Gutters
|  | Box Gutter Intstallion | Box Gutter Installation Checklist
|  | Quad Gutter Installation | Quad Installation Checklist
Roof Straight Standing Seam
|  | Insulation | Insulation Checklist
|  | Roof Installation | Roof Installation Checklist
|  | Flashing / Capping Installation | Flashing/Capping Installation Checklist
|  | Roof Penetration | Roof Penetrations Checklist
Soffit Straight
|  | Soffit Cladding | Soffit Cladding Checklist
External Wall North
|  | Wall Cladding | Wall Cladding Checklist
External Wall South
|  | Wall Cladding | Wall Cladding Checklist
Internal Wall North
|  | Wall Cladding | Wall Cladding Checklist
Internal Wall South
|  | Wall Cladding | Wall Cladding Checklist
Plant Area Cladding
|  | Wall Cladding | Wall Cladding Checklist
Variations
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
OH&S
Daily Prestart Toolbox Forms
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Weekly Toolbox Forms
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
SWMS
Onsite Material Install Form1
Foremans Diary Reports
COVID Tracking Reports

## Roof Insulation
Queenscliff Ferry Ternimal
type | name | values
checklist | Insulation
section | Material Inspection
checkpoint | Insulation: Aircell Insulation to Safebridge
Safebridge Glasswool - 130mm (main)
checkpoint | Roof safety mesh - Galvanised (main)
checkpoint | Roof safety mesh - Galvanised Safebridge 1200mm (main)
checkpoint | Roof safety mesh fixing strips
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Wall Substrate External
Queenscliff Ferry Terminal
type | name | values
checklist | Wall Cladding
section | Material Inspection
checkpoint | Wall Cladding type: 19mm CFC Board (North)
checkpoint | Wall Cladding type: 19mm CFC Board (South)
checkpoint | Top hat support: to CFC (North)
checkpoint | Top hat support: to CFC (South)
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Wall Substrate Internal
Queenscliff Ferry Terminal
type | name | values
checklist | Wall Cladding
section | Material Inspection
checkpoint | Wall Cladding type: 19mm CFC Board (North)
checkpoint | Wall Cladding type: 19mm CFC Board (South)
checkpoint | Top hat support: to CFC (North)
checkpoint | Top hat support: to CFC (South)
checkpoint | 19mm CFC Board (north infill strips)
checkpoint | 19mm CFC Board (south infill strips)
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Eave and Box Gut
Queenscliff Ferry Terminal
type | name | values
checklist | Box Gutter Installation
section | Material Inspection
checkpoint | Box Gutter Brackets: 1.2mm Zam Coated
checkpoint | Box Gutter - 0.70mm 445 Stainless Steel
checkpoint | Insulation under gutter: Box gutter insulation and Barrier
checkpoint | Gutter Board: Colorbond Ultra
checkpoint | Gutter Flashing: 0.70mm 445 Stainless Steel
checkpoint | Mesh to Box Gutter
checkpoint | Stop Ends - 0.70mm 445 Stainless Steel
checkpoint | Angle: Box gutter Angle
checkpoint | Expansion Join: Box Gutter Expansion Join
checkpoint | Sumps / Outlets: Fix Only Syphonic Sump
checkpoint | Overflows: Fix Only Syphonic Overflow
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed.
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Quad Gutter Installation Checklist
section | Material Inspection
checkpoint | Quad Gutter: 125mm Quad Spouting - 0.70mm 445 Stainless Steel
checkpoint | Quad Gutter Brackets: Quad gutter 125mm
checkpoint | Stop ends: Quad Gutter 125mm
checkpoint | Pops: Custom 90mm
checkpoint | Downpipe Spreader - 0.70mm 445 Stainless Steel
checkpoint | Downpipe: 90mm dia - 0.70mm 445 Stainless Steel
checkpoint | Downpipe: 90mm dia - 0.70mm 445 Stainless Steel
section | Installation
checkpoint | Spout Brackets installed with fall as per Specification
checkpoint | Spouting installed to sizes shown in spec & drawings.
checkpoint | Outlets installed to correct sizes.
checkpoint | Downpipe installed as shown on drawings and correct
checkpoint | size and connected to stormwater
checkpoint | Downpipe installed straight and bolted to downpipe clip
checkpoint | Downpipe spreader installed as shown on drawing
checkpoint | Overflow outlets installed at each downpipe location
checkpoint | Outlets installed to correct sizes.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Roof Straight Standing Seam
Queenscliff Ferry Terminal
type | name | values
checklist | Insulation
section | Material Inspection
checkpoint | Insulation: Proctor HTR Vapour Barrier
Proctor Tape
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation
section | Material Inspection:
checkpoint | Roof Sheets: Single Lock Standing Seam 200mm
checkpoint | Insulation Type: Proctor HTR Vapour Barrier
checkpoint | Proctor Tape
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: SLSS Clips 40mm
checkpoint | Roof Screws: Class 5 Screws
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Parapet Capping - curved
checkpoint | Parapet Capping
checkpoint | Barge Capping - (gutterline to north wall)
checkpoint | Barge Capping - (to plant room wall)
checkpoint | Barge Capping - (gutterline to central box gutter)
checkpoint | Barge Capping - (to plant room wall)
checkpoint | Footmould
checkpoint | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations
checkpoint | Dektite #1 - 5mm to 60mm
checkpoint | Dektite #2 - 45mm to 80mm
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | to fit the purpose.
checkpoint | Adequate support around penetration to prevent roof
checkpoint | sheet from buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Soffit-Straight
Queenscliff Ferry Terminal
type | name | values
checklist | Soffit Cladding
section | Material Inspection
checkpoint | Soffit Cladding type: Single Lock Standing Seam 200mm - Reverse Roll
checkpoint | Insulation: Proctor HTR Vapour Barrier
checkpoint | Proctor Tape
checkpoint | Flashing Material: Soffit Flashing
checkpoint | Stainless Steel Screws - to reverse rolled panels
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## External Wall North
Queenscliff Ferry Terminal
type | name | values
checklist | Wall Cladding
section | Material Inspection
checkpoint | Wall Cladding type: Single Lock Standing Seam 200mm
checkpoint | Clips: SLSS Clips 40mm
checkpoint | Screws: Class 5 Scews to clips
checkpoint | Insulation: Proctor HTR Vapour Barrier
checkpoint | Proctor Tape
checkpoint | Footmould - 300mm
checkpoint | Corner Trim
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## External Wall South
Queenscliff Ferry Terminal
type | name | values
checklist | Wall Cladding
section | Material Inspection
checkpoint | Wall Cladding type: Single Lock Standing Seam 200mm
checkpoint | Clips: SLSS Clips 40mm
checkpoint | Screws: Class 5 Scews to clips
checkpoint | Insulation: Proctor HTR Vapour Barrier
checkpoint | Proctor Tape
checkpoint | Footmould
checkpoint | Corner Trim - Curved
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Internal Wall North
Queenscliff Ferry Terminal
type | name | values
checklist | Wall Cladding
section | Material Inspection
checkpoint | Wall Cladding type: Single Lock Standing Seam 200mm Reverse Roll
checkpoint | Screws: Stainless Steel Screws to reverse rolled panels
checkpoint | Insulation: Proctor HTR Vapour Barrier
checkpoint | Proctor Tape
checkpoint | Footmould
checkpoint | Corner Trim - Curved
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Internal Wall South
Queenscliff Ferry Terminal
type | name | values
checklist | Wall Cladding
section | Material Inspection
checkpoint | Wall Cladding type: Single Lock Standing Seam 200mm Reverse Roll
checkpoint | Screws: Stainless Steel Screws to reverse rolled panels
checkpoint | Insulation: Proctor HTR Vapour Barrier
checkpoint | Proctor Tape
checkpoint | Footmould
checkpoint | Corner Trim - Curved
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Plant Area Cladding
Queenscliff Ferry Terminal
type | name | values
checklist | Wall Cladding
section | Material Inspection
checkpoint | Wall Cladding type: Single Lock Standing Seam 200mm Reverse Roll
checkpoint | Clips: SLSS Clips 40mm
checkpoint | Screws: Class 5 Screws to clips
checkpoint | Insulation: Proctor HTR Vapour Barrier
checkpoint | Proctor Tape
checkpoint | Footmould
checkpoint | Window/Door Trim
checkpoint | Corner Trim
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative: