## Project Breakdown
VSBA Hayes Hill |  |  | Checklists
QA / ITP's
11-PS-ALS-Roof
|  | Insulation | Insulation Checklist
|  | Roof Installation | Roof Installation Checklist
|  | Flashing / Capping Installation | Flashing/Capping Installation Checklist
|  | Roof Penetration | Roof Penetrations Checklist
|  | Fascia Gutter | Fascia Gutter
11-PS-ALS - Wall
|  | Wall Cladding | Wall Cladding Checklist
13-PS-CH - Gym Roof
|  | Insulation | Insulation Checklist
|  | Roof Installation | Roof Installation Checklist
|  | Flashing / Capping Installation | Flashing/Capping Installation Checklist
|  | Fascia Gutter | Fascia Gutter
13-PS-CH - Gym Wall
|  | Wall Cladding | Wall Cladding Checklist
13-PS-CH - Roof
|  | Insulation | Insulation Checklist
|  | Roof Installation | Roof Installation Checklist
|  | Flashing / Capping Installation | Flashing/Capping Installation Checklist
|  | Roof Penetration | Roof Penetrations Checklist
|  | Fascia Gutter | Fascia Gutter
13-PS-CH - Wall
|  | Wall Cladding | Wall Cladding Checklist
21-PS-LNG - Roof
|  | Insulation | Insulation Checklist
|  | Roof Installation | Roof Installation Checklist
|  | Flashing / Capping Installation | Flashing/Capping Installation Checklist
|  | Roof Penetration | Roof Penetrations Checklist
|  | Fascia Gutter | Fascia Gutter
21-PS-LNG - Roof (1)
|  | Insulation | Insulation Checklist
|  | Roof Installation | Roof Installation Checklist
|  | Flashing / Capping Installation | Flashing/Capping Installation Checklist
|  | Roof Penetration | Roof Penetrations Checklist
|  | Fascia Gutter | Fascia Gutter
21-PS-LNG - Wall
|  | Wall Cladding | Wall Cladding Checklist
21-PS-LNG - Wall (1)
|  | Wall Cladding | Wall Cladding Checklist
Bike Store - Roof
|  | Insulation | Insulation Checklist
|  | Roof Installation | Roof Installation Checklist
|  | Flashing / Capping Installation | Flashing/Capping Installation Checklist
|  | Fascia Gutter | Fascia Gutter
Covered Shelter 1 - Roof
|  | Insulation | Insulation Checklist
|  | Roof Installation | Roof Installation Checklist
|  | Flashing / Capping Installation | Flashing/Capping Installation Checklist
|  | Fascia Gutter | Fascia Gutter
Covered Shelter 2 - Roof
|  | Insulation | Insulation Checklist
|  | Roof Installation | Roof Installation Checklist
|  | Flashing / Capping Installation | Flashing/Capping Installation Checklist
|  | Fascia Gutter | Fascia Gutter
Variations
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
OH&S
Daily Prestart Toolbox Forms
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Weekly Toolbox Forms
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
SWMS
Onsite Material Install Form1
Foremans Diary Reports
COVID Tracking Reports

## 11-PS-ALS-ROOF
VSBA Hayes Hill
type | name | values
checklist | Insulation
section | Material Inspection
checkpoint | Insulation: Roof sarking on Proctor Wrap HTR
80mm glasswool on medium sarking
checkpoint | Thermal spacer: 40mm thermal spacer - 1.0mm galvanised strap (over 5 degree pitch)
checkpoint | Thermal spacer: 60mm thermal spacer - Ashgrid 1200mm - 60mm
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation
section | Material Inspection:
checkpoint | Roof Sheets: 0.48mm Spandek Zincalume
checkpoint | Roof Sheets: 0.48mm Spandek Colorbond Manor Red
checkpoint | Coating Type: Standard Colorbond
checkpoint | Insulation Type: Roof sarking on medium weight paper
checkpoint | 80mm glasswool on medium sarking
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip:
checkpoint | Roof Screws: 12g Class 3 screws
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Ridge Capping Hip 600mm - 0.55mm Zincalume
checkpoint | Roof Expansion Flashing 400mm - 0.55mm Zincalume
checkpoint | Apron Flashing 400mm - 0.55mm Zincalume
checkpoint | Apron Flashing 400mm notched - 0.55mm Zincalume
checkpoint | Apron Flashing 400mm raked - 0.55mm Zincalume
checkpoint | Barge Capping - 400mm - 0.55mm Zincalume
checkpoint | Parapet Capping - 400mm - 0.55mm Zincalume
checkpoint | Soaker Flashing - 600mm - 0.55mm Zincalume
checkpoint | Flashing 400mm - 1.0mm Zincalume behind eaves gutter
checkpoint | Flashing - 800mm - 1.0mm Zincalume - behind Eaves Gutter
checkpoint | Barge Capping - 400mm - 0.61mm Colorbond
checkpoint | Barge Capping - 400mm notched - 0.61mm Colorbond
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations
checkpoint | Penetration 0.55mm Zincalume - Up to 200mm x 200mm
checkpoint | Penetration 0.55mm Zincalume - Up to 400mm x 400mm
checkpoint | Penetration 0.55mm Zincalume - Up to 600mm x 600mm
checkpoint | Penetration 0.55mm Zincalume - Backtray Flashing - 400mm
checkpoint | Penetration 0.55mm Zincalume - Backtray Flashing - 600mm
checkpoint | Penetration 0.61mm Colorbond - Up to 400mm x 400mm
checkpoint | Penetration 0.61mm Colorbond - Backtray Flashing - 400mm
checkpoint | Dektite #2 - 45mm to 80mm
checkpoint | Dektite #2 - 45mm to 80mm
checkpoint | Dektite #3 - 65mm to 125mm
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | to fit the purpose.
checkpoint | Adequate support around penetration to prevent roof
checkpoint | sheet from buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Fascia Gutter
section | Material Inspection
checkpoint | Half Round 250mm - Zincalume
checkpoint | Brackets - Half Round 250mm - Zincalume External
checkpoint | Stop Ends - Half Round 250mm - Zincalume
checkpoint | Pops 0.55mm Zincalume - 150mm
checkpoint | Downpipe - Stormwater PVC - 150mm dia
checkpoint | Downpipe - Clips - Standoff - 150mm
checkpoint | 150mm dia PVC - bends
section | Installation
checkpoint | Spout Brackets installed with fall as per Specification
checkpoint | Spouting installed to sizes shown in spec & drawings.
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location
checkpoint | Outlets installed to correct sizes.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## 11-PS-ALS-WALL
VSBA Hayes Hill
type | name | values
checklist | Wall Cladding
section | Material Inspection
checkpoint | Wall Cladding type: 0.48mm Sapndek Zincalume
checkpoint | Wall Cladding type: 0.48mm Spandek Colorbond Manor Red
checkpoint | Top hat support: 0.75mm - 120mm Top Hat
checkpoint | Top Hats - Thermal Break Tape
checkpoint | Insulation: Enviroseal Proctor Wall Membrane
checkpoint | Screws: 12g Class 3
checkpoint | Wall - Multicell Polycarbonate 16mm x 1040mm - Danpalon
checkpoint | Multicell Polycarbonate Wall Cladding - Custom Fixings
checkpoint | Wall Flashing - 0.55mm Zincalume - Wall Trim - 400mm
checkpoint | Wall Flashing - 0.55mm Zincalume - Foot Flashing 400mm
checkpoint | Wall Flashing - 0.55mm Zincalume C flashing - 400mm infill panel
checkpoint | Wall Flashing - 0.55mm Zincalume - Wall Trim - 400mm
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## 13-PS-CH-GYM ROOF
VSBA Hayes Hill
type | name | values
checklist | Insulation
section | Material Inspection
checkpoint | Insulation: Roof sarking on White Perforated Paper - Proctor Wrap HTR
100mm (R2.5) glasswool on medium sarking
checkpoint | Insulation - Acoustigard 50mm 24kgm3
checkpoint | Thermal spacer: 150mm thermal spacer - Ashgrid 1200mm - 150mm
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation
section | Material Inspection:
checkpoint | Roof Sheets: 0.48mm Spandek Zincalume
checkpoint | Coating Type:
checkpoint | Insulation Type: Roof sarking on White Perforated Paper - Proctor Wrap HTR
checkpoint | 100mm (R2.5) glasswool on medium sarking
checkpoint | Insulation - Acoustigard 50mm 24kgm3
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip:
checkpoint | Roof Screws: 12g Class 3 screws
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Roof Expansion Flashing 400mm - 0.55mm Zincalume
checkpoint | Barge Capping - 400mm - 0.55mm Zincalume
checkpoint | Barge Capping - 400mm notched - 0.55mm Zincalume
checkpoint | Flashing 400mm - 1.0mm Zincalume behind eaves gutter
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations
checkpoint | Dektite #2 - 45mm to 80mm
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | to fit the purpose.
checkpoint | Adequate support around penetration to prevent roof
checkpoint | sheet from buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Fascia Gutter
section | Material Inspection
checkpoint | Half Round 250mm - Zincalume
checkpoint | Brackets - Half Round 250mm - Zincalume External
checkpoint | Stop Ends - Half Round 250mm - Zincalume
checkpoint | Pops 0.55mm Zincalume - 150mm
checkpoint | Downpipe - Stormwater PVC - 150mm dia
checkpoint | Aluminium plates behind clips to danpalon walls
checkpoint | Downpipe - Clips - Standoff - 150mm
section | Installation
checkpoint | Spout Brackets installed with fall as per Specification
checkpoint | Spouting installed to sizes shown in spec & drawings.
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location
checkpoint | Outlets installed to correct sizes.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## 13-PS-CH-GYM WALL
VSBA Hayes Hill
type | name | values
checklist | Wall Cladding
section | Material Inspection
checkpoint | Wall Cladding type: 0.48mm Sapndek Zincalume
checkpoint | Insulation - Wall Sarking - White Perforated Paper
checkpoint | Insulation - Wall Sarking - Proctor Wrap HTR
checkpoint | Insulation - Wall - Acoustigard 75mm - IN21
checkpoint | Wall Cladding Top Hat - 0.75mm - 75mm Top Hat / Junction Stud
checkpoint | Top Hats - Thermal Break Tape
checkpoint | Screws: 12g Class 3
checkpoint | Wall - Multicell Polycarbonate 16mm x 1040mm - Danpalon
checkpoint | Multicell Polycarbonate Wall Cladding - Custom Fixings
checkpoint | Wall Flashing - 0.55mm Zincalume - Wall Trim - 400mm
checkpoint | Wall Flashing - 0.55mm Zincalume - Louvre Trim - 400mm
checkpoint | Wall Flashing - 0.55mm Zincalume - Foot Flashing 400mm
checkpoint | Wall Flashing - 0.55mm Zincalume - Top Trim - 200mm
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## 13-PS-CH ROOF
VSBA Hayes Hill
type | name | values
checklist | Insulation
section | Material Inspection
checkpoint | Insulation: Roof sarking on - Proctor Wrap HTR
80mm glasswool on medium sarking
checkpoint | Thermal spacer: 40mm thermal spacer - 1.0mm galvanised strap (over 5 degree pitch)
checkpoint | Thermal spacer: 60mm thermal spacer - Ashgrid 1200mm - 60mm
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation
section | Material Inspection:
checkpoint | Roof Sheets: 0.48mm Spandek Zincalume
checkpoint | Coating Type:
checkpoint | Insulation Type: Roof sarking on - Proctor Wrap HTR
checkpoint | 80mm glasswool on medium sarking
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip:
checkpoint | Roof Screws: 12g Class 3 screws
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Ridge Capping 600mm - 0.55mm Zincalume
checkpoint | Roof Expansion Flashing 400mm - 0.55mm Zincalume
checkpoint | Apron Flashing 400mm - 0.55mm Zincalume
checkpoint | Apron Flashing 400mm notched - 0.55mm Zincalume
checkpoint | Barge Capping - 400mm - 0.55mm Zincalume
checkpoint | Flashing - 800mm - 1.0mm Zincalume - behind Eaves Gutter
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations
checkpoint | Penetration 0.55mm Zincalume - Up to 400mm x 400mm
checkpoint | Penetration 0.55mm Zincalume - Backtray Flashing - 400mm
checkpoint | Penetration 0.61mm Colorbond - Up to 400mm x 400mm
checkpoint | Dektite #2 - 45mm to 80mm
checkpoint | Dektite #2 - 45mm to 80mm
checkpoint | Dektite #3 - 65mm to 125mm
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | to fit the purpose.
checkpoint | Adequate support around penetration to prevent roof
checkpoint | sheet from buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Fascia Gutter
section | Material Inspection
checkpoint | Half Round 250mm - Zincalume
checkpoint | Brackets - Half Round 250mm - Zincalume External
checkpoint | Stop Ends - Half Round 250mm - Zincalume
checkpoint | Pops 0.55mm Zincalume - 150mm
checkpoint | Downpipe - Stormwater PVC - 150mm dia
checkpoint | 150mm dia PVC - bends
checkpoint | Downpipe - Clips - Standoff - 150mm
section | Installation
checkpoint | Spout Brackets installed with fall as per Specification
checkpoint | Spouting installed to sizes shown in spec & drawings.
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location
checkpoint | Outlets installed to correct sizes.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## 13-PS-CH-WALL
VSBA Hayes Hill
type | name | values
checklist | Wall Cladding
section | Material Inspection
checkpoint | Wall Cladding type: 0.48mm Sapndek Zincalume
checkpoint | Insulation - Wall Sarking - Proctor Wrap HTR
checkpoint | Wall Cladding Top Hat - 0.75mm - 120mm Top Hat / Junction Stud
checkpoint | Top Hats - Thermal Break Tape
checkpoint | Screws: 12g Class 3
checkpoint | Wall - Multicell Polycarbonate 16mm x 1040mm - Danpalon
checkpoint | Multicell Polycarbonate Wall Cladding - Custom Fixings
checkpoint | Wall Flashing - 0.55mm Zincalume - Wall Trim - 400mm
checkpoint | Wall Flashing - 0.55mm Zincalume - Foot Flashing 400mm
checkpoint | Wall Flashing - 0.55mm Zincalume - Top Trim - 200mm
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## 21-PS-LNG-ROOF
VSBA Hayes Hill
type | name | values
checklist | Insulation
section | Material Inspection
checkpoint | Insulation: Roof sarking on Proctor Wrap HTR
80mm glasswool on medium sarking
checkpoint | Thermal spacer: 40mm thermal spacer - 1.0mm galvanised strap (over 5 degree pitch)
checkpoint | Thermal spacer: 60mm thermal spacer - Ashgrid 1200mm - 60mm
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation
section | Material Inspection:
checkpoint | Roof Sheets: 0.48mm Spandek Zincalume
checkpoint | Coating Type:
checkpoint | Insulation Type: Roof sarking on Proctor Wrap HTR
checkpoint | 80mm glasswool on medium sarking
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip:
checkpoint | Roof Screws: 12g Class 3 screws
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Apron Flashing 400mm notched - 0.55mm Zincalume
checkpoint | Barge Capping - 400mm - 0.55mm Zincalume
checkpoint | Barge Capping - 400mm notched - 0.55mm Zincalume
checkpoint | Flashing - 800mm - 1.0mm Zincalume - behind Eaves Gutter
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations
checkpoint | Penetration 0.55mm Zincalume - Up to 400mm x 400mm
checkpoint | Penetration 0.55mm Zincalume - Up to 800mm x 800mm
checkpoint | Penetration 0.55mm Zincalume - Backtray Flashing - 400mm
checkpoint | Penetration 0.55mm Zincalume - Backtray Flashing - 800mm
checkpoint | Dektite #2 - 45mm to 80mm
checkpoint | Dektite #2 - 45mm to 80mm
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | to fit the purpose.
checkpoint | Adequate support around penetration to prevent roof
checkpoint | sheet from buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Fascia Gutter
section | Material Inspection
checkpoint | Half Round 150mm - Zincalume
checkpoint | Half Round 250mm - Zincalume
checkpoint | Brackets - Half Round 150mm - Zincalume External
checkpoint | Brackets - Half Round 250mm - Zincalume External
checkpoint | Stop Ends - Half Round 150mm - Zincalume
checkpoint | Stop Ends - Half Round 250mm - Zincalume
checkpoint | Pops 0.55mm Zincalume - 100mm
checkpoint | Pops 0.55mm Zincalume - 150mm
checkpoint | Downpipe - Stormwater PVC - 100mm dia
checkpoint | Downpipe - Stormwater PVC - 150mm dia
checkpoint | Downpipe - Clips - Standoff - 150mm
checkpoint | Downpipe - Clips - Standoff - 100mm
checkpoint | 100mm dia PVC - bends
checkpoint | 150mm dia PVC - bends
section | Installation
checkpoint | Spout Brackets installed with fall as per Specification
checkpoint | Spouting installed to sizes shown in spec & drawings.
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location
checkpoint | Outlets installed to correct sizes.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## 21-PS-LNG-ROOF (1)
VSBA Hayes Hill
type | name | values
checklist | Insulation
section | Material Inspection
checkpoint | Insulation: Roof sarking on Proctor Wrap HTR
80mm glasswool on medium sarking
checkpoint | Thermal spacer: 40mm thermal spacer - 1.0mm galvanised strap (over 5 degree pitch)
checkpoint | Thermal spacer: 60mm thermal spacer - Ashgrid 1200mm - 60mm
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation
section | Material Inspection:
checkpoint | Roof Sheets: 0.48mm Spandek Zincalume
checkpoint | Coating Type:
checkpoint | Insulation Type: Roof sarking on Proctor Wrap HTR
checkpoint | 80mm glasswool on medium sarking
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip:
checkpoint | Roof Screws: 12g Class 3 screws
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Apron Flashing 400mm notched - 0.55mm Zincalume
checkpoint | Barge Capping - 400mm - 0.55mm Zincalume
checkpoint | Barge Capping - 400mm notched - 0.55mm Zincalume
checkpoint | Flashing - 800mm - 1.0mm Zincalume - behind Eaves Gutter
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations
checkpoint | Penetration 0.55mm Zincalume - Up to 400mm x 400mm
checkpoint | Penetration 0.55mm Zincalume - Up to 800mm x 800mm
checkpoint | Penetration 0.55mm Zincalume - Backtray Flashing - 400mm
checkpoint | Penetration 0.55mm Zincalume - Backtray Flashing - 800mm
checkpoint | Dektite #2 - 45mm to 80mm
checkpoint | Dektite #2 - 45mm to 80mm
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | to fit the purpose.
checkpoint | Adequate support around penetration to prevent roof
checkpoint | sheet from buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Fascia Gutter
section | Material Inspection
checkpoint | Half Round 150mm - Zincalume
checkpoint | Half Round 250mm - Zincalume
checkpoint | Brackets - Half Round 150mm - Zincalume External
checkpoint | Brackets - Half Round 250mm - Zincalume External
checkpoint | Stop Ends - Half Round 150mm - Zincalume
checkpoint | Stop Ends - Half Round 250mm - Zincalume
checkpoint | Pops 0.55mm Zincalume - 100mm
checkpoint | Pops 0.55mm Zincalume - 150mm
checkpoint | Downpipe - Stormwater PVC - 100mm dia
checkpoint | Downpipe - Stormwater PVC - 150mm dia
checkpoint | Downpipe - Clips - Standoff - 150mm
checkpoint | Downpipe - Clips - Standoff - 100mm
checkpoint | 100mm dia PVC - bends
checkpoint | 150mm dia PVC - bends
section | Installation
checkpoint | Spout Brackets installed with fall as per Specification
checkpoint | Spouting installed to sizes shown in spec & drawings.
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location
checkpoint | Outlets installed to correct sizes.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## 21-PS-LNG-WALL
VSBA Hayes Hill
type | name | values
checklist | Wall Cladding
section | Material Inspection
checkpoint | Wall Cladding type: 0.48mm Sapndek Zincalume
checkpoint | Insulation - Wall Sarking - Proctor Wrap HTR
checkpoint | Wall Cladding Top Hat - 0.75mm - 120mm Top Hat / Junction Stud
checkpoint | Top Hats - Thermal Break Tape
checkpoint | Screws: 12g Class 3
checkpoint | Wall - Multicell Polycarbonate 16mm x 1040mm - Danpalon
checkpoint | Multicell Polycarbonate Wall Cladding - Custom Fixings
checkpoint | Wall / Soffit - Aluminium angle 100mm x 50mm
checkpoint | Wall Flashing - 0.55mm Zincalume - Wall Trim - 400mm
checkpoint | Wall Flashing - 0.55mm Zincalume - Foot Flashing 400mm
checkpoint | Wall Flashing - 0.55mm Zincalume C flashing - 400mm infill panel
checkpoint | Wall Flashing - 0.55mm Zincalume - Top Trim - 200mm
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## 21-PS-LNG-WALL (1)
VSBA Hayes Hill
type | name | values
checklist | Wall Cladding
section | Material Inspection
checkpoint | Wall Cladding type: 0.48mm Sapndek Zincalume
checkpoint | Insulation - Wall Sarking - Proctor Wrap HTR
checkpoint | Wall Cladding Top Hat - 0.75mm - 120mm Top Hat / Junction Stud
checkpoint | Top Hats - Thermal Break Tape
checkpoint | Screws: 12g Class 3
checkpoint | Wall - Multicell Polycarbonate 16mm x 1040mm - Danpalon
checkpoint | Multicell Polycarbonate Wall Cladding - Custom Fixings
checkpoint | Wall / Soffit - Aluminium angle 100mm x 50mm
checkpoint | Wall Flashing - 0.55mm Zincalume - Wall Trim - 400mm
checkpoint | Wall Flashing - 0.55mm Zincalume - Foot Flashing 400mm
checkpoint | Wall Flashing - 0.55mm Zincalume C flashing - 400mm infill panel
checkpoint | Wall Flashing - 0.55mm Zincalume - Top Trim - 200mm
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## BIKE STORE - ROOF
VSBA Hayes Hill
type | name | values
checklist | Insulation
section | Material Inspection
checkpoint | Insulation: Roof sarking on medium weight paper
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation
section | Material Inspection:
checkpoint | Roof Sheets: 0.48mm Spandek Zincalume
checkpoint | Coating Type:
checkpoint | Insulation Type: Roof sarking on medium weight paper
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip:
checkpoint | Roof Screws: 12g Class 3 screws
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Ridge Capping 600mm - 0.55mm Zincalume
checkpoint | Ridge Capping Hip 600mm - 0.55mm Zincalume
checkpoint | Flashing - 600mm - 1.0mm Zincalume - behind Eaves Gutter
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Fascia Gutter
section | Material Inspection
checkpoint | Half Round 150mm - Colorbond
checkpoint | Brackets - Half Round 150mm - Colorbond
checkpoint | Angles - Half Round 150mm - Zincalume
checkpoint | Pops 0.55mm Zincalume - 100mm
checkpoint | Downpipe - Stormwater PVC - 100mm dia
checkpoint | Downpipe - Clips - Standoff - 100mm
section | Installation
checkpoint | Spout Brackets installed with fall as per Specification
checkpoint | Spouting installed to sizes shown in spec & drawings.
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location
checkpoint | Outlets installed to correct sizes.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Covered Shelter 1 - ROOF
VSBA Hayes Hill
type | name | values
checklist | Insulation
section | Material Inspection
checkpoint | Insulation: Roof sarking on medium weight paper
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation
section | Material Inspection:
checkpoint | Roof Sheets: 0.48mm Spandek Zincalume
checkpoint | Coating Type:
checkpoint | Insulation Type: Roof sarking on medium weight paper
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip:
checkpoint | Roof Screws: 12g Class 3 screws
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Ridge Capping 600mm - 0.55mm Zincalume
checkpoint | Ridge Capping Hip 600mm - 0.55mm Zincalume
checkpoint | Flashing - 400mm - 1.0mm Zincalume - behind Eaves Gutter
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Fascia Gutter
section | Material Inspection
checkpoint | Half Round 150mm - Colorbond
checkpoint | Brackets - Half Round 150mm - Colorbond
checkpoint | Angles - Half Round 150mm - Zincalume
checkpoint | Pops 0.55mm Zincalume - 100mm
checkpoint | Downpipe - Stormwater PVC - 100mm dia
checkpoint | Downpipe - Clips - Standoff - 100mm
section | Installation
checkpoint | Spout Brackets installed with fall as per Specification
checkpoint | Spouting installed to sizes shown in spec & drawings.
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location
checkpoint | Outlets installed to correct sizes.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Covered Shelter 2 - ROOF
VSBA Hayes Hill
type | name | values
checklist | Insulation
section | Material Inspection
checkpoint | Insulation: Roof sarking on medium weight paper
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation
section | Material Inspection:
checkpoint | Roof Sheets: 0.48mm Spandek Zincalume
checkpoint | Coating Type:
checkpoint | Insulation Type: Roof sarking on medium weight paper
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip:
checkpoint | Roof Screws: 12g Class 3 screws
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Ridge Capping 600mm - 0.55mm Zincalume
checkpoint | Ridge Capping Hip 600mm - 0.55mm Zincalume
checkpoint | Flashing - 400mm - 1.0mm Zincalume - behind Eaves Gutter
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Fascia Gutter
section | Material Inspection
checkpoint | Half Round 150mm - Colorbond
checkpoint | Brackets - Half Round 150mm - Colorbond
checkpoint | Angles - Half Round 150mm - Zincalume
checkpoint | Pops 0.55mm Zincalume - 100mm
checkpoint | Downpipe - Stormwater PVC - 100mm dia
checkpoint | Downpipe - Clips - Standoff - 100mm
section | Installation
checkpoint | Spout Brackets installed with fall as per Specification
checkpoint | Spouting installed to sizes shown in spec & drawings.
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location
checkpoint | Outlets installed to correct sizes.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative: