## Project Breakdown
Jubilee Park |  |  | Checklists
QA / ITP's
Canopy West
|  | Insulation | Insulation Checklist
|  | Roof Installation | Roof Installation Checklist
|  | Flashing / Capping Installation | Flashing/Capping Installation Checklist
|  | Box Gutter Intstallion | Box Gutter Installation Checklist
Cricket Roof
|  | Flashing / Capping Installation | Flashing/Capping Installation Checklist
|  | Roof Penetration | Roof Penetrations Checklist
|  | Parapet Wall Cladding | Parapet Wall Cladding Checklist
|  | Ampelite | Ampelite EEFAS Installation Checklist
|  | Kingspan | Kingspan Installation Checklist
|  | Box Gutter Intstallion | Box Gutter Installation Checklist
Cricket Wall
|  | Eurobond Installation | Eurobond Installation Checklist
Cricket Wall Internal
|  | Wall Cladding | Wall Cladding Checklist
Functional Room Roof
|  | Flashing / Capping Installation | Flashing/Capping Installation Checklist
|  | Roof Penetration | Roof Penetrations Checklist
|  | Parapet Wall Cladding | Parapet Wall Cladding Checklist
|  | Kingspan | Kingspan Installation Checklist
|  | Box Gutter Intstallion | Box Gutter Installation Checklist
Functional Room Wall
|  | Eurobond Installation | Eurobond Installation Checklist
Functional Wall Snaplock
|  | Wall Cladding | Wall Cladding Checklist
Level 1 Admin & Café
|  | Flashing / Capping Installation | Flashing/Capping Installation Checklist
|  | Roof Penetration | Roof Penetrations Checklist
|  | Kingspan | Kingspan Installation Checklist
|  | Box Gutter Intstallion | Box Gutter Installation Checklist
Level 1 Amenities Roof
|  | Flashing / Capping Installation | Flashing/Capping Installation Checklist
|  | Parapet Wall Cladding | Parapet Wall Cladding Checklist
|  | Kingspan | Kingspan Installation Checklist
|  | Box Gutter Intstallion | Box Gutter Installation Checklist
Lower Canopy Roof
|  | Insulation | Insulation Checklist
|  | Roof Installation | Roof Installation Checklist
|  | Flashing / Capping Installation | Flashing/Capping Installation Checklist
|  | Box Gutter Intstallion | Box Gutter Installation Checklist
Show Court Lower Roof
|  | Flashing / Capping Installation | Flashing/Capping Installation Checklist
|  | Parapet Wall Cladding | Parapet Wall Cladding Checklist
|  | Kingspan | Kingspan Installation Checklist
|  | Box Gutter Intstallion | Box Gutter Installation Checklist
Show Court Lower Wall
|  | Eurobond Installation | Eurobond Installation Checklist
Show Court Lower Wall Snaplock
|  | Wall Cladding | Wall Cladding Checklist
Show Court Roof
|  | Flashing / Capping Installation | Flashing/Capping Installation Checklist
|  | Roof Penetration | Roof Penetrations Checklist
|  | Parapet Wall Cladding | Parapet Wall Cladding Checklist
|  | Ampelite | Ampelite EEFAS Installation Checklist
|  | Kingspan | Kingspan Installation Checklist
|  | Box Gutter Intstallion | Box Gutter Installation Checklist
Show Court Wall
|  | Eurobond Installation | Eurobond Installation Checklist
Show Court Wall Snaplock
|  | Wall Cladding | Wall Cladding Checklist
Sports Court Lower Roof
|  | Flashing / Capping Installation | Flashing/Capping Installation Checklist
|  | Parapet Wall Cladding | Parapet Wall Cladding Checklist
|  | Kingspan | Kingspan Installation Checklist
|  | Box Gutter Intstallion | Box Gutter Installation Checklist
Sports Courts Roof
|  | Flashing / Capping Installation | Flashing/Capping Installation Checklist
|  | Parapet Wall Cladding | Parapet Wall Cladding Checklist
|  | Ampelite | Ampelite EEFAS Installation Checklist
|  | Kingspan | Kingspan Installation Checklist
|  | Box Gutter Intstallion | Box Gutter Installation Checklist
Sports Court Wall
|  | Eurobond Installation | Eurobond Installation Checklist
Sports Court Wall Snaplock
|  | Wall Cladding | Wall Cladding Checklist
Variations
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
OH&S
Daily Prestart Toolbox Forms
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Weekly Toolbox Forms
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
SWMS
Onsite Material Install Form1
Foremans Diary Reports
COVID Tracking Reports

## Canopy West
JUBILEE PARK
type | name | values
checklist | Insulation
section | Material Inspection
checkpoint | Insulation: Roof sarking on medium weight paper
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation
section | Material Inspection:
checkpoint | Roof Sheets: 0.48mm Colorbond Kliplok
checkpoint | Coating Type: Standard Colorbond
checkpoint | Insulation Type: Roof sarking on medium weight paper
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Apron Flashing 400mm - 0.61mm Colorbond Whitehaven
checkpoint | Apron Flashing 400mm notched - 0.61mm Colorbond Whitehaven
checkpoint | Gutter Apron Flashing - 300mm - 0.61mm Colorbond Whitehaven
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation
section | Material Inspection
checkpoint | Box Gutter - 0.61mm Colorbond - Up to 600mm girth
checkpoint | Box Gutter Brackets #1
checkpoint | Box Gutter Flashing - Colorbond
checkpoint | Box Gutter Gutterboard - Spandek Zincalume - 700mm wide
checkpoint | Box Gutter Insulation - Sisalation
checkpoint | Box Gutter Stop Ends - 0.61mm Colorbond - up to 600mm girth
checkpoint | Box Gutter Expansion Join - 600mm
checkpoint | Inline Sump - 0.61mm Colorbond - 400mm x 400mm
checkpoint | Overflow Outlet 0.61mm Colorbond
checkpoint | Downpipe - 304 Stainless Steel - 150mm dia
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed.
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Cricket Roof
JUBILEE PARK
type | name | values
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Apron Flashing - 0.61mm Colorbond
checkpoint | Apron Flashing notched - 0.61mm Colorbond
checkpoint | Gutter Apron Flashing - 300mm - 0.61mm Colorbond
checkpoint | Parapet Capping - - 0.61mm Colorbond
checkpoint | Parapet Capping - - 0.61mm Colorbond
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations
checkpoint | Penetration 0.61mm Colorbond - Budget allowance for cutting penetration for motorized roof vents
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | to fit the purpose.
checkpoint | Adequate support around penetration to prevent roof
checkpoint | sheet from buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation
section | Material Inspection
checkpoint | Box Gutter - Insulated Membrane - Kingspan - 1200mm girth
checkpoint | Box Gutter Brackets #3
checkpoint | Box Gutter Flashing - Colorbond
checkpoint | Membrane Gutter Stop Ends - up to 1200mm girth - fitted to gutter- 0.61mm Colorbond
checkpoint | Box Gutter Expansion Join - welding of joins
checkpoint | Syphonic sump installation
checkpoint | Syphonic overflow installation
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed.
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Parapet Wall Cladding
section | Material Inspection
checkpoint | Parapet Wall Cladding - 0.42mm Colorbond - Panelrib
checkpoint | Insulation - Wall Sarking - Proctor Wrap HTR
checkpoint | Metal Wall Cladding - Spandek Screws
checkpoint | Wall Cladding Top Hat - 0.75mm - 25mm Top Hat / Junction Stud
checkpoint | Parapet Wall Flashing - 0.61mm Colorbond - Wall Trim - 400mm
checkpoint | Soffit Flashing - 0.61mm Colorbond Coolmax Color to match Bright white - Soffit Trim 200mm
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Kingspan Installation
section | Material Inspection
checkpoint | Roofing - 100mm Insulated Panel - Kingspan with Standard Liner
checkpoint | Roofing - 100mm Insulated Panel - E.o. for laps
checkpoint | Insulated Panel - Butyl Tape to End Laps
checkpoint | Insulated Panel - Butyl Tape to Gutter
checkpoint | Insulated Panel - Ridge Foam Filler - Kingspan
checkpoint | Insulated Panel - 100mm Panel Screws
checkpoint | Insulated Panel - Side Lap Stitching Screws
checkpoint | Insulated Panel - End Lap Stitching Screws
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Kingspan Spec
checkpoint | Panels located correctly
checkpoint | Fixings as per Kingspan Spec
checkpoint | Stitching screws 350mm centres
checkpoint | Four way lapped joins installed correctly
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Ampelite EEFAS Installation
section | Material Inspection
checkpoint | Roofing -EEFAS skylight system - 1000mm
checkpoint | Roofing - Purlin Support for EEFAS / Kingspan Join
checkpoint | Roofing - Purlin Strips for Fibreglass
checkpoint | Roofing - Screws for Fibreglass
checkpoint | Roofing - Washers for Fibreglass
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Ampelite EEFAS system spec
checkpoint | Panels located correctly
checkpoint | Fixings as per EEFAS system Spec
checkpoint | Stitching screws 350mm centres
checkpoint | Four way lapped joins installed correctly
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Cricket Wall
JUBILEE PARK
type | name | values
checklist | Eurobond Installation
section | Material Inspection
checkpoint | Wall Cladding - 150mm Insulated Panel - Eurobond Europanel
checkpoint | Insulated Panel Wall Cladding - Butyl Tape to Side Laps
checkpoint | EBS1 - Base Support to bottom of panels (Europanel)
checkpoint | Insulated Panel Wall Cladding - Butyl Tape to Panel Top & Bottom
checkpoint | Insulated Panel Wall Cladding - Spreader plates (Europanel)
checkpoint | Insulated Panel Wall Cladding - 150mm Panel (6 screws per m2)
checkpoint | Wall Cladding Top Hat - 1.6mm - Ledger Angle to base of panels
checkpoint | Wall Flashing - 0.61mm Colorbond - Wall Trim - 200mm - Internal
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Top Trim - 200mm
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Internal Trim - 200mm
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Wall Trim - 400mm
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Door / Window Trim - 400mm
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Foot Flashing 400mm
checkpoint | Wall Penetration - Downpipe penetrations
checkpoint | Wall Penetration - Outrigger screen penetrations
checkpoint | Wall Penetration - Overflows through facade
checkpoint | Wall Penetration - Overflows through facade
checkpoint | Wall Penetration - Outrigger screen penetrations
checkpoint | Butyl tape to wall flashings
section | Installation
checkpoint | Eurobond Firemaster panel to span between floor levels
checkpoint | Fireban caulking inserted to all panel joins
checkpoint | Gal support angles installed with masonry fixings
checkpoint | 300mm centres and caulked to concrete
checkpoint | 3mm top movement angle with slotted holes to allow minus 10mm + 25mm movement as per project engineer
checkpoint | All flashings installed with fireban caulking and compliant fixings
checkpoint | Panel fixed at base with stainless steel 197mm screws x 4 in each panel
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Cricket Wall Internal
JUBILEE PARK
type | name | values
checklist | Wall Cladding
section | Material Inspection
checkpoint | Wall Cladding - 0.60mm Snaplock Whitehaven - MWP-1
checkpoint | Insulation - Wall Sarking - Proctor Wrap HTR
checkpoint | Wall Clips - Snaplock
checkpoint | Wall Cladding Top Hat - 0.75mm - 50mm Top Hat / Junction Stud
checkpoint | Wall Support - Multiboard X-bound 15mm
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Top Trim - 200mm
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Wall Trim - 400mm
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Foot Flashing 400mm
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Function Room Roof
JUBILEE PARK
type | name | values
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Apron Flashing - 0.61mm Colorbond
checkpoint | Apron Flashing notched - 0.61mm Colorbond
checkpoint | Gutter Apron Flashing - - 0.61mm Colorbond
checkpoint | Barge Capping - - 0.61mm Colorbond
checkpoint | Barge Capping - notched - 0.61mm Colorbond
checkpoint | Parapet Capping - - 0.61mm Colorbond
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations
checkpoint | Penetration 0.61mm Colorbond - Up to 600mm x 600mm
checkpoint | Penetration 0.61mm Colorbond - Up to 800mm x 800mm
checkpoint | Penetration 0.61mm Colorbond - Up to 1200mm x 1200mm
checkpoint | Penetration 0.61mm Colorbond - Up to 2000mm x 2000mm
checkpoint | Penetration 0.61mm Colorbond - Up to 200mm dia
checkpoint | Penetration 0.61mm Colorbond - Platform Leg
checkpoint | Penetration 0.61mm Colorbond - Backtray Flashing - 400mm
checkpoint | Penetration 0.61mm Colorbond - Backtray Flashing - 800mm
checkpoint | Penetration 0.61mm Colorbond - Backtray Flashing - 1000mm
checkpoint | Penetration 0.61mm Colorbond - Backtray Flashing - 1500mm
checkpoint | Penetration 0.61mm Colorbond - Roof Batten Support to 400mm Backtray Flashing
checkpoint | Penetration 0.61mm Colorbond - Roof Batten Support to 800mm Backtray Flashing
checkpoint | Penetration 0.61mm Colorbond - Roof Batten Support to 1000mm Backtray Flashing
checkpoint | Penetration 0.61mm Colorbond - Roof Batten Support to 1500mm Backtray Flashing
checkpoint | Penetration 0.61mm Colorbond - Capping to 1500mm Backtray Flashing
checkpoint | Dektite #2 - 45mm to 80mm
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | to fit the purpose.
checkpoint | Adequate support around penetration to prevent roof
checkpoint | sheet from buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation
section | Material Inspection
checkpoint | Box Gutter - Insulated Membrane - Kingspan - 1200mm girth
checkpoint | Box Gutter Brackets #3
checkpoint | Box Gutter Flashing - Colorbond
checkpoint | Membrane Gutter Stop Ends - up to 1200mm girth - fitted to gutter- 0.61mm Colorbond
checkpoint | Box Gutter Expansion Join - welding of joins
checkpoint | Syphonic sump installation
checkpoint | Syphonic overflow installation
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed.
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Parapet Wall Cladding
section | Material Inspection
checkpoint | Parapet Wall Cladding - 0.42mm Colorbond - Panelrib
checkpoint | Insulation - Wall Sarking - Proctor Wrap HTR
checkpoint | Metal Wall Cladding - Spandek Screws
checkpoint | Wall Cladding Top Hat - 0.75mm - 25mm Top Hat / Junction Stud
checkpoint | Parapet Wall Flashing - 0.61mm Colorbond - Wall Trim - 400mm
checkpoint | Soffit Flashing - 0.61mm Colorbond Coolmax Color to match Bright white - Soffit Trim 200mm
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Kingspan Installation
section | Material Inspection
checkpoint | Roofing - 100mm Insulated Panel - Kingspan with Standard Liner
checkpoint | Insulated Panel - Butyl Tape to End Laps
checkpoint | Insulated Panel - Butyl Tape to Gutter
checkpoint | Insulated Panel - Ridge Foam Filler - Kingspan
checkpoint | Insulated Panel - 100mm Panel Screws
checkpoint | Insulated Panel - Side Lap Stitching Screws
checkpoint | Insulated Panel - End Lap Stitching Screws
checkpoint | Roof Safety Mesh - Mesh allowed under - ceiling to all areas
checkpoint | Roof - 19mm CD Plywood under plant deck
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Kingspan Spec
checkpoint | Panels located correctly
checkpoint | Fixings as per Kingspan Spec
checkpoint | Stitching screws 350mm centres
checkpoint | Four way lapped joins installed correctly
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Function Roof Wall
JUBILEE PARK
type | name | values
checklist | Eurobond Installation
section | Material Inspection
checkpoint | Wall Cladding - 175mm Mineral Wool Panel - Eurobond Rainspan
checkpoint | Insulated Panel Wall Cladding - Butyl Tape to Side Laps
checkpoint | RS2 - Base Support to bottom of panels (Rainscreen 175mm)
checkpoint | Insulated Panel Wall Cladding - Butyl Tape to Panel Top & Bottom
checkpoint | Insulated Panel Wall Cladding - 175mm Panel Screws
checkpoint | Wall Cladding Top Hat - 1.6mm - Ledger Angle to base of panels
checkpoint | Wall Flashing - 0.61mm Colorbond - Wall Trim - 200mm - Internal
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Top Trim - 200mm
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Internal Trim - 200mm
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Wall Trim - 400mm
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Foot Flashing 400mm
checkpoint | Wall Penetration - Outrigger screen penetrations
checkpoint | Wall Penetration - Overflows through facade
checkpoint | Butyl tape to wall flashings
section | Installation
checkpoint | Eurobond Firemaster panel to span between floor levels
checkpoint | Fireban caulking inserted to all panel joins
checkpoint | Gal support angles installed with masonry fixings
checkpoint | 300mm centres and caulked to concrete
checkpoint | 3mm top movement angle with slotted holes to allow minus 10mm + 25mm movement as per project engineer
checkpoint | All flashings installed with fireban caulking and compliant fixings
checkpoint | Panel fixed at base with stainless steel 197mm screws x 4 in each panel
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Function Room Wall Snaplock
JUBILEE PARK
type | name | values
checklist | Wall Cladding
section | Material Inspection
checkpoint | Wall Cladding - 0.60mm Snaplock Whitehaven - MWP-1
checkpoint | Insulation - Wall Sarking - Proctor Wrap HTR
checkpoint | Wall Clips - Snaplock
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Wall Trim - 200mm
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Level 1 Admin & Cafe
JUBILEE PARK
type | name | values
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Ridge Capping - Internal flashing - 0.61mm Colorbond
checkpoint | Ridge Capping Hip - 0.61mm Colorbond
checkpoint | Apron Flashing - 0.61mm Colorbond
checkpoint | Apron Flashing notched - 0.61mm Colorbond
checkpoint | Gutter Apron Flashing - - 0.61mm Colorbond
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations
checkpoint | Penetration 0.61mm Colorbond - Up to 600mm x 600mm
checkpoint | Penetration 0.61mm Colorbond - Backtray Flashing - 800mm
checkpoint | Penetration 0.61mm Colorbond - Roof Batten Support to 800mm Backtray Flashing
checkpoint | Dektite #2 - 45mm to 80mm
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | to fit the purpose.
checkpoint | Adequate support around penetration to prevent roof
checkpoint | sheet from buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation
section | Material Inspection
checkpoint | Box Gutter - Insulated Membrane - Kingspan -
checkpoint | Box Gutter - Insulated Membrane -
checkpoint | Box Gutter Brackets #3
checkpoint | Box Gutter Flashing - Colorbond
checkpoint | Membrane Gutter Stop Ends - up to 800mm girth - fitted to gutter- 0.61mm Colorbond
checkpoint | Box Gutter Angle
checkpoint | Box Gutter Expansion Join - welding of joins
checkpoint | Syphonic sump installation
checkpoint | Syphonic overflow installation
checkpoint | Soffit Flashing - 0.61mm Colorbond - Soffit Trim 200mm
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed.
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Kingspan Installation
section | Material Inspection
checkpoint | Roofing - 100mm Insulated Panel - Kingspan with Standard Liner
checkpoint | Insulated Panel - Butyl Tape to Gutter
checkpoint | Insulated Panel - Ridge Foam Filler - Kingspan
checkpoint | Insulated Panel - 100mm Panel Screws
checkpoint | Insulated Panel - Side Lap Stitching Screws
checkpoint | Roof Safety Mesh - Mesh allowed under - ceilings to all areas
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Kingspan Spec
checkpoint | Panels located correctly
checkpoint | Fixings as per Kingspan Spec
checkpoint | Stitching screws 350mm centres
checkpoint | Four way lapped joins installed correctly
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Level 1 Amenities Roof
JUBILEE PARK
type | name | values
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Apron Flashing - 0.61mm Colorbond
checkpoint | Apron Flashing notched - 0.61mm Colorbond
checkpoint | Gutter Apron Flashing - - 0.61mm Colorbond
checkpoint | Barge Capping - - 0.61mm Colorbond
checkpoint | Parapet Capping - - 0.61mm Colorbond
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation
section | Material Inspection
checkpoint | Box Gutter - Insulated Membrane - Kingspan - 600mm girth
checkpoint | Box Gutter - Insulated Membrane - labour to install
checkpoint | Box Gutter Brackets #3
checkpoint | Box Gutter Flashing - Colorbond
checkpoint | Membrane Gutter Stop Ends - up to 800mm girth - fitted to gutter - 0.61mm Colorbond
checkpoint | Box Gutter Expansion Join - welding of joins
checkpoint | Syphonic sump installation
checkpoint | Syphonic overflow installation
checkpoint | Downpipe - 304 Stainless Steel - 150mm dia
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed.
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Parapet Wall Cladding
section | Material Inspection
checkpoint | Parapet Wall Cladding - 0.42mm Colorbond - Panelrib
checkpoint | Insulation - Wall Sarking - Proctor Wrap HTR
checkpoint | Metal Wall Cladding - Spandek Screws
checkpoint | Wall Cladding Top Hat - 0.75mm - 25mm Top Hat / Junction Stud
checkpoint | Soffit Flashing - 0.61mm Colorbond Coolmax Color to match Bright white - Soffit Trim 200mm
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Kingspan Installation
section | Material Inspection
checkpoint | Roofing - 100mm Insulated Panel - Kingspan with Standard Liner
checkpoint | Insulated Panel - Butyl Tape to End Laps
checkpoint | Insulated Panel - Butyl Tape to Gutter
checkpoint | Insulated Panel - Ridge Foam Filler - Kingspan
checkpoint | Insulated Panel - 100mm Panel Screws
checkpoint | Insulated Panel - Side Lap Stitching Screws
checkpoint | Insulated Panel - End Lap Stitching Screws
checkpoint | Roof Safety Mesh - Mesh allowed - full ceiling under
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Kingspan Spec
checkpoint | Panels located correctly
checkpoint | Fixings as per Kingspan Spec
checkpoint | Stitching screws 350mm centres
checkpoint | Four way lapped joins installed correctly
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Lower Canopy Roof
JUBILEE PARK
type | name | values
checklist | Insulation
section | Material Inspection
checkpoint | Insulation: Roof sarking on medium weight paper
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation
section | Material Inspection:
checkpoint | Roof Sheets: 0.48mm Colorbond Kliplok
checkpoint | Coating Type: Standard Colorbond
checkpoint | Insulation Type: Roof sarking on medium weight paper
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Apron Flashing 400mm - 0.61mm Colorbond Whitehaven
checkpoint | Apron Flashing 400mm notched - 0.61mm Colorbond Whitehaven
checkpoint | Gutter Apron Flashing - 300mm - 0.61mm Colorbond Whitehaven
checkpoint | Parapet Capping - 400mm - 0.61mm Colorbond Whitehaven
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation
section | Material Inspection
checkpoint | Box Gutter - 0.61mm Colorbond - Up to 600mm girth
checkpoint | Box Gutter Brackets #1
checkpoint | Box Gutter Flashing - Colorbond
checkpoint | Box Gutter Gutterboard - Spandek Zincalume - 700mm wide
checkpoint | Box Gutter Insulation - Sisalation
checkpoint | Box Gutter Stop Ends - 0.61mm Colorbond - up to 600mm girth
checkpoint | Syphonic sump installation
checkpoint | Syphonic overflow installation
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed.
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Show Court Lower Roof
JUBILEE PARK
type | name | values
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Apron Flashing - 0.61mm Colorbond
checkpoint | Apron Flashing notched - 0.61mm Colorbond
checkpoint | Gutter Apron Flashing - - 0.61mm Colorbond
checkpoint | Parapet Capping - - 0.61mm Colorbond
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation
section | Material Inspection
checkpoint | Box Gutter - Insulated Membrane - Kingspan - 600mm girth
checkpoint | Box Gutter - Insulated Membrane - labour to install
checkpoint | Box Gutter Brackets #3
checkpoint | Box Gutter Flashing - Colorbond
checkpoint | Membrane Gutter Stop Ends - up to 800mm girth - fitted to gutter - 0.61mm Colorbond
checkpoint | Box Gutter Expansion Join - welding of joins
checkpoint | Syphonic sump installation
checkpoint | Syphonic overflow installation
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed.
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Parapet Wall Cladding
section | Material Inspection
checkpoint | Parapet Wall Cladding - 0.42mm Colorbond - Panelrib
checkpoint | Insulation - Wall Sarking - Proctor Wrap HTR
checkpoint | Metal Wall Cladding - Spandek Screws
checkpoint | Wall Cladding Top Hat - 0.75mm - 25mm Top Hat / Junction Stud
checkpoint | Parapet Wall Flashing - 0.61mm Colorbond - Wall Trim - 400mm
checkpoint | Soffit Flashing - 0.61mm Colorbond Coolmax Color to match Bright white - Soffit Trim 200mm
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Kingspan Installation
section | Material Inspection
checkpoint | Roofing - 100mm Insulated Panel - Kingspan with Standard Liner
checkpoint | Insulated Panel - Butyl Tape to End Laps
checkpoint | Insulated Panel - Butyl Tape to Gutter
checkpoint | Insulated Panel - Ridge Foam Filler - Kingspan
checkpoint | Insulated Panel - 100mm Panel Screws
checkpoint | Insulated Panel - Side Lap Stitching Screws
checkpoint | Roof Safety Mesh - Mesh allowed - full ceiling under
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Kingspan Spec
checkpoint | Panels located correctly
checkpoint | Fixings as per Kingspan Spec
checkpoint | Stitching screws 350mm centres
checkpoint | Four way lapped joins installed correctly
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Show Court Lower Wall
JUBILEE PARK
type | name | values
checklist | Eurobond Installation
section | Material Inspection
checkpoint | Wall Cladding - 175mm Mineral Wool Panel - Eurobond Rainspan
checkpoint | Insulated Panel Wall Cladding - Butyl Tape to Side Laps
checkpoint | RS2 - Base Support to bottom of panels (Rainscreen 175mm)
checkpoint | Insulated Panel Wall Cladding - Airseal tape to Panel Top & Bottom
checkpoint | Insulated Panel Wall Cladding - 175mm Panel Screws
checkpoint | Wall Cladding Top Hat - 1.6mm - Ledger Angle to base of panels
checkpoint | Wall Flashing - 0.61mm Colorbond - Wall Trim - 200mm - Internal
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Top Trim - 200mm
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Internal Trim - 200mm
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Wall Trim - 400mm
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Foot Flashing 400mm
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Door / Window Trim - 400mm
checkpoint | Wall Penetration - Outrigger screen penetrations
checkpoint | Wall Penetration - Overflows through facade
checkpoint | Butyl tape to wall flashings
section | Installation
checkpoint | Eurobond Firemaster panel to span between floor levels
checkpoint | Fireban caulking inserted to all panel joins
checkpoint | Gal support angles installed with masonry fixings
checkpoint | 300mm centres and caulked to concrete
checkpoint | 3mm top movement angle with slotted holes to allow minus 10mm + 25mm movement as per project engineer
checkpoint | All flashings installed with fireban caulking and compliant fixings
checkpoint | Panel fixed at base with stainless steel 197mm screws x 4 in each panel
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Show Court Lower Wall Snaplock
JUBILEE PARK
type | name | values
checklist | Wall Cladding
section | Material Inspection
checkpoint | Wall Cladding - 0.60mm Snaplock Whitehaven - MWP-1
checkpoint | Insulation - Wall Sarking - Proctor Wrap HTR
checkpoint | Wall Clips - Snaplock
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Wall Trim - 200mm
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Show Court Roof
JUBILEE PARK
type | name | values
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Ridge Capping - Internal flashing - 0.61mm Colorbond
checkpoint | Ridge Capping - 0.61mm Colorbond
checkpoint | Apron Flashing - 0.61mm Colorbond
checkpoint | Apron Flashing notched - 0.61mm Colorbond
checkpoint | Gutter Apron Flashing - - 0.61mm Colorbond
checkpoint | Parapet Capping - - 0.61mm Colorbond
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations
checkpoint | Penetration 0.61mm Colorbond - Up to 2000mm x 2000mm
checkpoint | Penetration 0.61mm Colorbond - Backtray Flashing - 2000mm
checkpoint | Penetration 0.61mm Colorbond - Roof Batten Support to 2000mm Backtray Flashing
checkpoint | Penetration 0.61mm Colorbond - Capping to 2000mm Backtray Flashing
checkpoint | Dektite #2 - 45mm to 80mm
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | to fit the purpose.
checkpoint | Adequate support around penetration to prevent roof
checkpoint | sheet from buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation
section | Material Inspection
checkpoint | Box Gutter - Insulated Membrane - Kingspan - 1200mm girth
checkpoint | Box Gutter Brackets #3
checkpoint | Box Gutter Flashing - Colorbond
checkpoint | Membrane Gutter Stop Ends - up to 1200mm girth - fitted to gutter- 0.61mm Colorbond
checkpoint | Box Gutter Expansion Join - welding of joins
checkpoint | Syphonic sump - install only
checkpoint | Syphonic overflow
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed.
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Parapet Wall Cladding
section | Material Inspection
checkpoint | Parapet Wall Cladding - 0.42mm Colorbond - Panelrib
checkpoint | Insulation - Wall Sarking - Proctor Wrap HTR
checkpoint | Metal Wall Cladding - Spandek Screws
checkpoint | Wall Cladding Top Hat - 0.75mm - 25mm Top Hat / Junction Stud
checkpoint | Parapet Wall Flashing - 0.61mm Colorbond - Wall Trim - 400mm
checkpoint | Soffit Flashing - 0.61mm Colorbond Coolmax Color to match Bright white - Soffit Trim 200mm
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Kingspan Installation
section | Material Inspection
checkpoint | Roofing - 100mm Insulated Panel - Kingspan with Standard Liner
checkpoint | Roofing - 100mm Insulated Panel - E.o. for laps
checkpoint | Insulated Panel - Butyl Tape to End Laps
checkpoint | Insulated Panel - Butyl Tape to Gutter
checkpoint | Insulated Panel - Ridge Foam Filler - Kingspan
checkpoint | Insulated Panel - 100mm Panel Screws
checkpoint | Insulated Panel - Side Lap Stitching Screws
checkpoint | Insulated Panel - End Lap Stitching Screws
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Kingspan Spec
checkpoint | Panels located correctly
checkpoint | Fixings as per Kingspan Spec
checkpoint | Stitching screws 350mm centres
checkpoint | Four way lapped joins installed correctly
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Ampelite EEFAS Installation
section | Material Inspection
checkpoint | Roofing -EEFAS skylight system - 1000mm
checkpoint | Roofing - Purlin Support for EEFAS / Kingspan Join
checkpoint | Roofing - Purlin Strips for Fibreglass
checkpoint | Roofing - Screws for Fibreglass
checkpoint | Roofing - Washers for Fibreglass
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Ampelite EEFAS system spec
checkpoint | Panels located correctly
checkpoint | Fixings as per EEFAS system Spec
checkpoint | Stitching screws 350mm centres
checkpoint | Four way lapped joins installed correctly
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Show Court Wall
JUBILEE PARK
type | name | values
checklist | Eurobond Installation
section | Material Inspection
checkpoint | Wall Cladding - 175mm Mineral Wool Panel - Eurobond Rainspan
checkpoint | Insulated Panel Wall Cladding - Butyl Tape to Side Laps
checkpoint | RS2 - Base Support to bottom of panels (Rainscreen 175mm)
checkpoint | Insulated Panel Wall Cladding - Airseal tape to Panel Top & Bottom
checkpoint | Insulated Panel Wall Cladding - 175mm Panel Screws
checkpoint | Wall Cladding Top Hat - 1.6mm - Ledger Angle to base of panels
checkpoint | Wall Flashing - 0.61mm Colorbond - Wall Trim - 200mm - Internal
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Top Trim - 200mm
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Internal Trim - 200mm
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Wall Trim - 400mm
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Foot Flashing 400mm
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Door / Window Trim - 400mm
checkpoint | Wall Penetration - 3300mm x 10000mm
checkpoint | Wall Penetration - Overflows through facade
checkpoint | Butyl tape to wall flashings
section | Installation
checkpoint | Eurobond Firemaster panel to span between floor levels
checkpoint | Fireban caulking inserted to all panel joins
checkpoint | Gal support angles installed with masonry fixings
checkpoint | 300mm centres and caulked to concrete
checkpoint | 3mm top movement angle with slotted holes to allow minus 10mm + 25mm movement as per project engineer
checkpoint | All flashings installed with fireban caulking and compliant fixings
checkpoint | Panel fixed at base with stainless steel 197mm screws x 4 in each panel
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Show Court Wall Snaplock
JUBILEE PARK
type | name | values
checklist | Wall Cladding
section | Material Inspection
checkpoint | Wall Cladding - 0.60mm Snaplock Whitehaven - MWP-1
checkpoint | Insulation - Wall Sarking - Proctor Wrap HTR
checkpoint | Wall Clips - Snaplock
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Wall Trim - 200mm
checkpoint | Wall Penetration - 3300mm x 10000mm
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Sports Court Lower Roof
JUBILEE PARK
type | name | values
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Apron Flashing - 0.61mm Colorbond
checkpoint | Apron Flashing notched - 0.61mm Colorbond
checkpoint | Gutter Apron Flashing - - 0.61mm Colorbond
checkpoint | Parapet Capping - = - 0.61mm Colorbond
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation
section | Material Inspection
checkpoint | Box Gutter - Insulated Membrane - Kingspan - 600mm girth
checkpoint | Box Gutter - Insulated Membrane - labour to install
checkpoint | Box Gutter Brackets #3
checkpoint | Box Gutter Flashing - Colorbond
checkpoint | Membrane Gutter Stop Ends - up to 800mm girth - fitted to gutter - 0.61mm Colorbond
checkpoint | Box Gutter Expansion Join - welding of joins
checkpoint | Syphonic sump install
checkpoint | Syphonic overflow install
checkpoint | Standard Rainhead - 0.61mm Colorbond
checkpoint | Downpipe - 304 Stainless Steel - 150mm dia
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed.
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Parapet Wall Cladding
section | Material Inspection
checkpoint | Parapet Wall Cladding - 0.42mm Colorbond - Panelrib
checkpoint | Insulation - Wall Sarking - Proctor Wrap HTR
checkpoint | Metal Wall Cladding - Spandek Screws
checkpoint | Wall Cladding Top Hat - 0.75mm - 25mm Top Hat / Junction Stud
checkpoint | Soffit Flashing - 0.61mm Colorbond Coolmax Color to match Bright white - Soffit Trim 200mm
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Kingspan Installation
section | Material Inspection
checkpoint | Roofing - 100mm Insulated Panel - Kingspan with Standard Liner
checkpoint | Insulated Panel - Butyl Tape to Gutter
checkpoint | Insulated Panel - Ridge Foam Filler - Kingspan
checkpoint | Insulated Panel - 100mm Panel Screws
checkpoint | Insulated Panel - Side Lap Stitching Screws
checkpoint | Insulated Panel - End Lap Stitching Screws (xx screws)
checkpoint | Roof Safety Mesh - Mesh allowed - full ceiling under
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Kingspan Spec
checkpoint | Panels located correctly
checkpoint | Fixings as per Kingspan Spec
checkpoint | Stitching screws 350mm centres
checkpoint | Four way lapped joins installed correctly
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Sports Court Roof
JUBILEE PARK
type | name | values
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Apron Flashing 400mm - 0.61mm Colorbond Whitehaven
checkpoint | Apron Flashing 400mm notched - 0.61mm Colorbond Whitehaven
checkpoint | Gutter Apron Flashing - 300mm - 0.61mm Colorbond Whitehaven
checkpoint | Parapet Capping - 800mm - 0.61mm Colorbond Whitehaven
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation
section | Material Inspection
checkpoint | Box Gutter - Insulated Membrane - Kingspan - 1200mm girth
checkpoint | Box Gutter Brackets #3
checkpoint | Box Gutter Flashing - Colorbond
checkpoint | Membrane Gutter Stop Ends - up to 1200mm girth - fitted to gutter- 0.61mm Colorbond
checkpoint | Box Gutter Expansion Join - welding of joins
checkpoint | Syphonic sump install
checkpoint | Syphonic overflow install
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed.
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Parapet Wall Cladding
section | Material Inspection
checkpoint | Parapet Wall Cladding - 0.42mm Colorbond - Panelrib
checkpoint | Insulation - Wall Sarking - Proctor Wrap HTR
checkpoint | Metal Wall Cladding - Spandek Screws
checkpoint | Wall Cladding Top Hat - 0.75mm - 25mm Top Hat / Junction Stud
checkpoint | Parapet Wall Flashing - 0.61mm Colorbond - Wall Trim - 400mm
checkpoint | Soffit Flashing - 0.61mm Colorbond Coolmax Color to match Bright white - Soffit Trim 200mm
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Kingspan Installation
section | Material Inspection
checkpoint | Roofing - 100mm Insulated Panel - Kingspan with Standard Liner
checkpoint | Insulated Panel - Butyl Tape to End Laps
checkpoint | Insulated Panel - Butyl Tape to Gutter
checkpoint | Insulated Panel - Ridge Foam Filler - Kingspan
checkpoint | Insulated Panel - 100mm Panel Screws
checkpoint | Insulated Panel - Side Lap Stitching Screws
checkpoint | Insulated Panel - End Lap Stitching Screws
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Kingspan Spec
checkpoint | Panels located correctly
checkpoint | Fixings as per Kingspan Spec
checkpoint | Stitching screws 350mm centres
checkpoint | Four way lapped joins installed correctly
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Ampelite EEFAS Installation
section | Material Inspection
checkpoint | Roofing -EEFAS skylight system - 1000mm
checkpoint | Roofing - Purlin Support for EEFAS / Kingspan Join
checkpoint | Roofing - Purlin Strips for Fibreglass
checkpoint | Roofing - Screws for Fibreglass
checkpoint | Roofing - Washers for Fibreglass
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Ampelite EEFAS system spec
checkpoint | Panels located correctly
checkpoint | Fixings as per EEFAS system Spec
checkpoint | Stitching screws 350mm centres
checkpoint | Four way lapped joins installed correctly
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Sports Court Wall
JUBILEE PARK
type | name | values
checklist | Eurobond Installation
section | Material Inspection
checkpoint | Wall Cladding - 150mm Insulated Panel - Eurobond Rainspan
checkpoint | Insulated Panel Wall Cladding - Butyl Tape to Side Laps
checkpoint | RS1 - Base Support to bottom of panels (Rainscreen 150mm)
checkpoint | Insulated Panel Wall Cladding - Airseal tape to Panel Top & Bottom
checkpoint | Insulated Panel Wall Cladding - 150mm Panel Screws
checkpoint | Wall Cladding Top Hat - 1.6mm - Ledger Angle to base of panels
checkpoint | Wall Flashing - 0.61mm Colorbond - Wall Trim - 200mm - Internal
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Top Trim - 200mm
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Internal Trim - 200mm
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Wall Trim - 400mm
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Foot Flashing 400mm
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Louvre Trim - 400mm
checkpoint | Wall Penetration - 1000mm x 1000mm
checkpoint | Wall Penetration - Downpipe penetrations
checkpoint | Wall Penetration - Outrigger screen penetrations
checkpoint | Wall Penetration - Overflows through facade
checkpoint | Butyl tape to wall flashings
section | Installation
checkpoint | Eurobond Firemaster panel to span between floor levels
checkpoint | Fireban caulking inserted to all panel joins
checkpoint | Gal support angles installed with masonry fixings
checkpoint | 300mm centres and caulked to concrete
checkpoint | 3mm top movement angle with slotted holes to allow minus 10mm + 25mm movement as per project engineer
checkpoint | All flashings installed with fireban caulking and compliant fixings
checkpoint | Panel fixed at base with stainless steel 197mm screws x 4 in each panel
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Sports Court Wall Snaplock
JUBILEE PARK
type | name | values
checklist | Wall Cladding
section | Material Inspection
checkpoint | Wall Cladding - 0.60mm Snaplock Whitehaven - MWP-1
checkpoint | Insulation - Wall Sarking - Proctor Wrap HTR
checkpoint | Wall Clips - Snaplock
checkpoint | Wall Flashing - 0.61mm Colorbond Coolmax - Wall Trim - 200mm
checkpoint | Wall Penetration - Outrigger screen penetrations
checkpoint | Wall Penetration - Downpipe penetrations
checkpoint | Wall Penetration - Overflows through facade
checkpoint | Wall Penetration - 1000mm x 1000mm
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative: