## Project Breakdown
MT East Precinct |  |  | Checklists
QA / ITP's
Domain Canopy Soffit Flashings
|  | Soffit Cladding | Soffit Cladding Checklist
Domain Road Glazed Roof Lift 3
|  | Box Gutter Intstallion | Box Gutter Installation Checklist
|  | Fascia Gutter Installation | Fascia Gutter Installation Checklist
Albert Rd Glazed Roof Lift 6
|  | Box Gutter Intstallion | Box Gutter Installation Checklist
|  | Fascia Gutter Installation | Fascia Gutter Installation Checklist
Albert Rd Goods Lift
|  | Insulation | Insulation Checklist
|  | Roof Installation | Roof Installation Checklist
|  | Flashing / Capping Installation | Flashing/Capping Installation Checklist
|  | Box Gutter Intstallion | Box Gutter Installation Checklist
Domian Rd Portal Roof
|  | Insulation | Insulation Checklist
|  | Roof Installation | Roof Installation Checklist
|  | Flashing / Capping Installation | Flashing/Capping Installation Checklist
|  | Box Gutter Intstallion | Box Gutter Installation Checklist
Albert Rd Portal Roof
|  | Insulation | Insulation Checklist
|  | Roof Installation | Roof Installation Checklist
|  | Flashing / Capping Installation | Flashing/Capping Installation Checklist
|  | Box Gutter Intstallion | Box Gutter Installation Checklist
Kiosk Roof
|  | Insulation | Insulation Checklist
|  | Roof Installation | Roof Installation Checklist
|  | Flashing / Capping Installation | Flashing/Capping Installation Checklist
|  | Box Gutter Intstallion | Box Gutter Installation Checklist
Domain Canopy Roof
|  | Insulation | Insulation Checklist
|  | Roof Installation | Roof Installation Checklist
|  | Flashing / Capping Installation | Flashing/Capping Installation Checklist
|  | Box Gutter Intstallion | Box Gutter Installation Checklist
External Lifts Flashings North & South
|  | Flashing / Capping Installation | Flashing/Capping Installation Checklist
Chiller Plant Roof North
|  | Insulation | Insulation Checklist
|  | Roof Installation | Roof Installation Checklist
|  | Flashing / Capping Installation | Flashing/Capping Installation Checklist
|  | Box Gutter Intstallion | Box Gutter Installation Checklist
Chiller Plant Roof South
|  | Insulation | Insulation Checklist
|  | Roof Installation | Roof Installation Checklist
|  | Flashing / Capping Installation | Flashing/Capping Installation Checklist
|  | Box Gutter Intstallion | Box Gutter Installation Checklist
Eastern Portal Flashing and Cappings
|  | Flashing / Capping Installation | Flashing/Capping Installation Checklist
Eastern Portal Roof
|  | Insulation | Insulation Checklist
|  | Roof Installation | Roof Installation Checklist
|  | Flashing / Capping Installation | Flashing/Capping Installation Checklist
Variations
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
OH&S
Daily Prestart Toolbox Forms
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Weekly Toolbox Forms
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
SWMS
Onsite Material Install Form1
Foremans Diary Reports
COVID Tracking Reports

## Domain Canopy Soffit Flashing
MT East Precinct
type | name | values
checklist | Soffit Cladding
section | Material Inspection
checkpoint | Soffit Cladding type:
checkpoint | Top hat support:
checkpoint | Soffit Trims: 600mm Soffit Trims
checkpoint | Flashing Material: 0.90mm Anodised Aluminium
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Domain Rd Glazed Roof Lift 3
MT East Precinct
type | name | values
checklist | Box Gutter Installation
section | Material Inspection
checkpoint | Box Gutter Brackets:
checkpoint | Insulation under gutter:
checkpoint | Gutter Board:
checkpoint | Box Gutter: 1.2mm 316 Stainless Steel (curved)
checkpoint | Gutter Flashing:
checkpoint | Sumps / Outlets:
checkpoint | Overflows:
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed.
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Fascia Gutter
section | Material Inspection
checkpoint | Fascia Gutter Brackets:
checkpoint | Fascia Gutter: 1.2mm 316 Stainless Steel Eaves Gutter (curved)
checkpoint | Downpipes: Rainhead with 100mm stainless steel downpipe
checkpoint | Gutter Flashing:
checkpoint | Fascia Board Accessories:
section | Installation
checkpoint | Spout Brackets installed with fall as per Specification
checkpoint | Spouting installed to sizes shown in spec & drawings.
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location
checkpoint | Outlets installed to correct sizes.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Albert Rd Glazed Roof Lift 6
MT East Precinct
type | name | values
checklist | Box Gutter Installation
section | Material Inspection
checkpoint | Box Gutter Brackets:
checkpoint | Insulation under gutter:
checkpoint | Gutter Board:
checkpoint | Box Gutter: 1.2mm 316 Stainless Steel (curved)
checkpoint | Gutter Flashing:
checkpoint | Sumps / Outlets:
checkpoint | Overflows:
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed.
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Fascia Gutter
section | Material Inspection
checkpoint | Fascia Gutter Brackets:
checkpoint | Fascia Gutter: 1.2mm 316 Stainless Steel Eaves Gutter (curved)
checkpoint | Downpipes: Rainhead with 100mm stainless steel downpipe
checkpoint | Gutter Flashing:
checkpoint | Fascia Board Accessories:
section | Installation
checkpoint | Spout Brackets installed with fall as per Specification
checkpoint | Spouting installed to sizes shown in spec & drawings.
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location
checkpoint | Outlets installed to correct sizes.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Albert Rd Goods Lift
MT East Precinct
type | name | values
checklist | Insulation
section | Material Inspection
checkpoint | Insulation: Proctor HTS-IT Vapour Barrier
50mm x 40kg/m3 Rockwool Insulation (INS-140)
checkpoint | Thermal spacer:
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation
section | Material Inspection:
checkpoint | Roof Sheets: 0.60mm 340 Maxline
checkpoint | Coating Type:
checkpoint | Roof Support: Plyboard Support to roof
checkpoint | Insulation: Proctor HTS-IT Vapour Barrier
50mm x 40kg/m3 Rockwool Insulation (INS-140)
checkpoint | Safety Mesh:
checkpoint | Roof Clip:
checkpoint | Roof Screws:
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.55mm Stainless Steel
checkpoint | Capping Material 0.55mm Stainless Steel
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation
section | Material Inspection
checkpoint | Box Gutter Brackets:
checkpoint | Insulation under gutter:
checkpoint | Gutter Board:
checkpoint | Box Gutter: 1.2mm 316 Stainless Steel box gutter
checkpoint | Gutter Flashing:
checkpoint | Sumps / Outlets:
checkpoint | Overflows:
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed.
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Domain Rd Portal Roof
MT East Precinct
type | name | values
checklist | Insulation
section | Material Inspection
checkpoint | Insulation: Proctor HTS-IT Vapour Barrier
50mm x 40kg/m3 Rockwool Insulation (INS-140)
checkpoint | Thermal spacer:
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation
section | Material Inspection:
checkpoint | Roof Sheets: 0.60mm 340 Maxline
checkpoint | Coating Type:
checkpoint | Insulation: Proctor HTS-IT Vapour Barrier
50mm x 40kg/m3 Rockwool Insulation (INS-140)
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip:
checkpoint | Roof Screws:
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.55mm NEXTStrip
checkpoint | Capping Material 0.55mm NEXTStrip
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation
section | Material Inspection
checkpoint | Box Gutter Brackets:
checkpoint | Insulation under gutter:
checkpoint | Gutter Board:
checkpoint | Box Gutter: 1.2mm 316 Stainless Steel box gutter
checkpoint | Gutter Flashing:
checkpoint | Sumps / Outlets:
checkpoint | Overflows:
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed.
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Albert Rd Portal Roof
MT East Precinct
type | name | values
checklist | Insulation
section | Material Inspection
checkpoint | Insulation: Proctor HTS-IT Vapour Barrier
50mm x 40kg/m3 Rockwool Insulation (INS-140)
checkpoint | Thermal spacer:
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation
section | Material Inspection:
checkpoint | Roof Sheets: 0.60mm 340 Maxline
checkpoint | Coating Type:
checkpoint | Insulation: Proctor HTS-IT Vapour Barrier
50mm x 40kg/m3 Rockwool Insulation (INS-140)
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip:
checkpoint | Roof Screws:
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.55mm NEXTStrip
checkpoint | Capping Material 0.55mm NEXTStrip
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation
section | Material Inspection
checkpoint | Box Gutter Brackets:
checkpoint | Insulation under gutter:
checkpoint | Gutter Board:
checkpoint | Box Gutter: 1.2mm 316 Stainless Steel box gutter
checkpoint | Gutter Flashing:
checkpoint | Sumps / Outlets:
checkpoint | Overflows:
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed.
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Kiosk Roof
MT East Precinct
type | name | values
checklist | Insulation
section | Material Inspection
checkpoint | Insulation: Proctor HTS-IT Vapour Barrier
50mm x 40kg/m3 Rockwool Insulation (INS-140)
checkpoint | Thermal spacer:
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation
section | Material Inspection:
checkpoint | Roof Sheets: 0.60mm 340 Maxline
checkpoint | Coating Type:
checkpoint | Insulation: Proctor HTS-IT Vapour Barrier
50mm x 40kg/m3 Rockwool Insulation (INS-140)
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip:
checkpoint | Roof Screws:
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.55mm NEXTStrip
checkpoint | Capping Material 0.55mm NEXTStrip
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation
section | Material Inspection
checkpoint | Box Gutter Brackets:
checkpoint | Insulation under gutter:
checkpoint | Gutter Board:
checkpoint | Box Gutter: 1.2mm 316 Stainless Steel box gutter
checkpoint | Gutter Flashing:
checkpoint | Sumps / Outlets:
checkpoint | Overflows:
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed.
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Domain Canopy Roof
MT East Precinct
type | name | values
checklist | Insulation
section | Material Inspection
checkpoint | Insulation: Proctor HTS-IT Vapour Barrier
50mm Glasswool Insulation
checkpoint | Thermal spacer:
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation
section | Material Inspection:
checkpoint | Roof Sheets: 0.60mm 340 Maxline
checkpoint | Coating Type:
checkpoint | Insulation: Proctor HTS-IT Vapour Barrier
50mm Glasswool Insulation
checkpoint | Installation: Only of Timber Battens
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip:
checkpoint | Roof Screws:
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.55mm Stainless Steel Flashings to end of roof sumps
checkpoint | Flashing Material: 0.55mm NEXTStrip Flashings to the roof
checkpoint | Soffit Flashing: 0.90mm Anodised Soffit flashings
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation
section | Material Inspection
checkpoint | Box Gutter Brackets:
checkpoint | Insulation under gutter:
checkpoint | Gutter Board:
checkpoint | Box Gutter: 1.2mm 316 Stainless Steel box gutter
checkpoint | Gutter Flashing:
checkpoint | Sumps / Outlets:
checkpoint | Overflows:
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed.
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## External Lift Flashings - N & S
MT East Precinct
type | name | values
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.90mm Powdercoated Aluminium
checkpoint | Capping Material: 0.90mm Powdercoated Aluminium
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Chiller Plant Roof North
MT East Precinct
type | name | values
checklist | Insulation
section | Material Inspection
checkpoint | Insulation: Proctor HTS-IT Vapour Barrier
75mm x 60kg/m3 and 50mm x 80kg/m3 Rockwool Insulation (INS-130)
checkpoint | Thermal spacer:
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation
section | Material Inspection:
checkpoint | Roof Sheets: 0.60mm 340 Maxline
checkpoint | Coating Type:
checkpoint | Insulation: Proctor HTS-IT Vapour Barrier
75mm x 60kg/m3 and 50mm x 80kg/m3 Rockwool Insulation (INS-130)
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip:
checkpoint | Roof Screws:
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material:
checkpoint | Capping Material
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation
section | Material Inspection
checkpoint | Box Gutter Brackets:
checkpoint | Insulation under gutter:
checkpoint | Gutter Board:
checkpoint | Box Gutter: 1.2mm 316 Stainless Steel box gutter
checkpoint | Gutter Flashing:
checkpoint | Sumps / Outlets:
checkpoint | Overflows:
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed.
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Chiller Plant Roof South
MT East Precinct
type | name | values
checklist | Insulation
section | Material Inspection
checkpoint | Insulation: Proctor HTS-IT Vapour Barrier
75mm x 60kg/m3 and 50mm x 80kg/m3 Rockwool Insulation (INS-130)
checkpoint | Thermal spacer:
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation
section | Material Inspection:
checkpoint | Roof Sheets: 0.60mm 340 Maxline
checkpoint | Coating Type:
checkpoint | Insulation: Proctor HTS-IT Vapour Barrier
75mm x 60kg/m3 and 50mm x 80kg/m3 Rockwool Insulation (INS-130)
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip:
checkpoint | Roof Screws:
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material:
checkpoint | Capping Material
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation
section | Material Inspection
checkpoint | Box Gutter Brackets:
checkpoint | Insulation under gutter:
checkpoint | Gutter Board:
checkpoint | Box Gutter: 1.2mm 316 Stainless Steel box gutter
checkpoint | Gutter Flashing:
checkpoint | Sumps / Outlets:
checkpoint | Overflows:
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed.
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Eastern Portal Flashings & Capp
MT East Precinct
type | name | values
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.90mm Powdercoated Aluminium
checkpoint | Capping Material: 0.90mm Powdercoated Aluminium
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Eastern Portal Roof
MT East Precinct
type | name | values
checklist | Insulation
section | Material Inspection
checkpoint | Insulation:
50mm Glasswool Insulation
checkpoint | Thermal spacer:
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation
section | Material Inspection:
checkpoint | Roof Sheets: 0.60mm 340 Maxline
checkpoint | Coating Type:
checkpoint | Insulation:
50mm Glasswool Insulation
checkpoint | Safety Mesh:
checkpoint | Roof Clip:
checkpoint | Roof Screws:
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.90mm Powdercoated Aluminium
checkpoint | Capping Material: 0.90mm Powdercoated Aluminium
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative: