## Proj Structure
Tier 1 | Tier 2 | Tier 3 | Tier 4 | resource
Site QA
Site QA | Lot 1
Site QA | Lot 1 | Slab Down |  | Slab Down
Site QA | Lot 1 | Frames Up |  | Frames Up
Site QA | Lot 1 | Roof On |  | Roof On
Site QA | Lot 1 | Lock Up |  | Lock Up
Site QA | Lot 1 | Linings Complete |  | Linings Complete
Site QA | Lot 1 | Kitchen Install |  | Kitchen Install
Site QA | Lot 1 | Practical Completion |  | Practical Completion
Site QA | Lot 1 | Code Compliance |  | Code Compliance
Site QA | Lot 2
Site QA | Lot 2 | Slab Down |  | Slab Down
Site QA | Lot 2 | Frames Up |  | Frames Up
Site QA | Lot 2 | Roof On |  | Roof On
Site QA | Lot 2 | Lock Up |  | Lock Up
Site QA | Lot 2 | Linings Complete |  | Linings Complete
Site QA | Lot 2 | Kitchen Install |  | Kitchen Install
Site QA | Lot 2 | Practical Completion |  | Practical Completion
Site QA | Lot 2 | Code Compliance |  | Code Compliance
Site QA | Lot 3
Site QA | Lot 3 | Slab Down |  | Slab Down
Site QA | Lot 3 | Frames Up |  | Frames Up
Site QA | Lot 3 | Roof On |  | Roof On
Site QA | Lot 3 | Lock Up |  | Lock Up
Site QA | Lot 3 | Linings Complete |  | Linings Complete
Site QA | Lot 3 | Kitchen Install |  | Kitchen Install
Site QA | Lot 3 | Practical Completion |  | Practical Completion
Site QA | Lot 3 | Code Compliance |  | Code Compliance
Site QA | Lot 4
Site QA | Lot 4 | Slab Down |  | Slab Down
Site QA | Lot 4 | Frames Up |  | Frames Up
Site QA | Lot 4 | Roof On |  | Roof On
Site QA | Lot 4 | Lock Up |  | Lock Up
Site QA | Lot 4 | Linings Complete |  | Linings Complete
Site QA | Lot 4 | Kitchen Install |  | Kitchen Install
Site QA | Lot 4 | Practical Completion |  | Practical Completion
Site QA | Lot 4 | Code Compliance |  | Code Compliance
Site QA | Lot 5
Site QA | Lot 5 | Slab Down |  | Slab Down
Site QA | Lot 5 | Frames Up |  | Frames Up
Site QA | Lot 5 | Roof On |  | Roof On
Site QA | Lot 5 | Lock Up |  | Lock Up
Site QA | Lot 5 | Linings Complete |  | Linings Complete
Site QA | Lot 5 | Kitchen Install |  | Kitchen Install
Site QA | Lot 5 | Practical Completion |  | Practical Completion
Site QA | Lot 5 | Code Compliance |  | Code Compliance
Site QA | Lot 6
Site QA | Lot 6 | Slab Down |  | Slab Down
Site QA | Lot 6 | Frames Up |  | Frames Up
Site QA | Lot 6 | Roof On |  | Roof On
Site QA | Lot 6 | Lock Up |  | Lock Up
Site QA | Lot 6 | Linings Complete |  | Linings Complete
Site QA | Lot 6 | Kitchen Install |  | Kitchen Install
Site QA | Lot 6 | Practical Completion |  | Practical Completion
Site QA | Lot 6 | Code Compliance |  | Code Compliance
Site QA | Lot 7
Site QA | Lot 7 | Slab Down |  | Slab Down
Site QA | Lot 7 | Frames Up |  | Frames Up
Site QA | Lot 7 | Roof On |  | Roof On
Site QA | Lot 7 | Lock Up |  | Lock Up
Site QA | Lot 7 | Linings Complete |  | Linings Complete
Site QA | Lot 7 | Kitchen Install |  | Kitchen Install
Site QA | Lot 7 | Practical Completion |  | Practical Completion
Site QA | Lot 7 | Code Compliance |  | Code Compliance
Site QA | Lot 8
Site QA | Lot 8 | Slab Down |  | Slab Down
Site QA | Lot 8 | Frames Up |  | Frames Up
Site QA | Lot 8 | Roof On |  | Roof On
Site QA | Lot 8 | Lock Up |  | Lock Up
Site QA | Lot 8 | Linings Complete |  | Linings Complete
Site QA | Lot 8 | Kitchen Install |  | Kitchen Install
Site QA | Lot 8 | Practical Completion |  | Practical Completion
Site QA | Lot 8 | Code Compliance |  | Code Compliance
Site QA | Lot 9
Site QA | Lot 9 | Slab Down |  | Slab Down
Site QA | Lot 9 | Frames Up |  | Frames Up
Site QA | Lot 9 | Roof On |  | Roof On
Site QA | Lot 9 | Lock Up |  | Lock Up
Site QA | Lot 9 | Linings Complete |  | Linings Complete
Site QA | Lot 9 | Kitchen Install |  | Kitchen Install
Site QA | Lot 9 | Practical Completion |  | Practical Completion
Site QA | Lot 9 | Code Compliance |  | Code Compliance
Site QA | Lot 10
Site QA | Lot 10 | Slab Down |  | Slab Down
Site QA | Lot 10 | Frames Up |  | Frames Up
Site QA | Lot 10 | Roof On |  | Roof On
Site QA | Lot 10 | Lock Up |  | Lock Up
Site QA | Lot 10 | Linings Complete |  | Linings Complete
Site QA | Lot 10 | Kitchen Install |  | Kitchen Install
Site QA | Lot 10 | Practical Completion |  | Practical Completion
Site QA | Lot 10 | Code Compliance |  | Code Compliance

## Proj Resources
1 | Slab Down
section | Slab Down | CUBICON COMMENTS | SS DISCUSSION | CHANGES REQUIRED
| Survey | Moved prior to start
Profiles
Form Work
Drainage/services
| Council inspections | Separate inspection for foundations/piling? | As per required | Change to: Council Inspections
Back fill & fines
DPM
PODS
| Steel placement | image of tags on steel |  | Add: include pic of tags on steel
Engineer inspection
Council inspection
| Pour concrete | image Pour reciept |  | Add: attach pour reciept
Cut concrete
section | Handover
Plumbing & services photos required
Survey correct position of boxing prior to pour, surveyors certificate required
Provide copies of all inspection records
2 | Frames Up
section | Ground Floor Framing
Timber framing
Hardware
| Scaffolding Up |  |  | Add: no pic required
section | Mid Floor
| Floor joists |  | PS1 required for casettes, engineer sign off
Add: PS1 required for casettes, engineer sign off
Ply flooring
section | First Floor Framing
| Scaffold Up | delete |  | Delete
Wall framing
| Truss install/purlins/soffit framing |  |  | New QA to Add
section | Handover
| Walls plumb. Photos required and daily log confirmation that all walls checked | both at preline once bracing has been removed and 2nd fix done when other trades move nogs etc. | agree
New QA to Add: Walls plumb. At preline once bracing has been removed (pic required)
New QA to Add: Walls plumb. 2nd fix complete when other trades remove nogs (pic required)
Stairwell wall between upper & lower & straightened - photo required showing line with straight edge
Nogs planed
| Brackets & tie down complete | image lintel straps |  | Add: Pic required of lintel straps
Finished framing photos required
| Recorded inspections for claims | No inspection until roof framing complete |  | Add: (if applicable)
3 | Roof On
section | Roof Structure
| Truss install/purlins/soffit framing | add to framing to complete inspection AC won’t complete partials | relocte to roof structure? 1st floor framing | Delete
| Fascia install |  | add barrier line? | Shannon - where does 'add barrier line' go?
Spouting
section | Roofing
| Roof Measure | delete |  | Delete
| Roof manufacture | delete |  | Delete
Roof install
section | Handover
Roofing screw patterns - photo required
Flashings & junctions - photo required
Flashings around penetrations - photos required
| Recorded inspections for claims | framing inspection? There is no roof inspection with council until cladding complete. |  | Delete
| Survey height in relation to boundary | tick box item |  | Add: No pic required
4 | Lock Up
section | External Wrap/Cladding
Soffit install
| RAB/wrap | add in rab inspection if brick cladding
| RAB inspection if brick cladding |  |  | New QA to add
Joinery install
Cavity Batten install
Cavity inspection
Weatherboard & cladding
Painting
Scaffolding Drop
section | Handover
Building wrap photos
Flashing photos
| Joinery installed properly - opening & closing photos | move to "Practical Completion" | leave it there
Cladding completion photos required
| External painting complete - builder to provide high end QA to show houses have been painted & finished to a higher standard prior to scaffold drop | Needs to be client inspection along with Council inspection - tick box |  | Change to: External painting complete - client to inspect before scaffolding removed. Council inspection.
Ensure all downpipes are functioning with no leaks
Recorded inspections for claims
5 | Linings Complete
section | Gib Lining On
Internal frames & nogs
| Stair install | moved |  | Delete
1st fix plumbing
1st fix electrical
| Complete ceiling grids/ceiling insulation into IT walls | moved |  | Delete
Insulation
Preline council inspection
| Linings IT 1st layer | delete | n/a tick box leave, add in | Add: (if applicable). No pic requried
| Council inspection 1st layer | delete | n/a | Add: (if applicable). No pic requried
| Second layer IT | delete | n/a | Add: (if applicable). No pic requried
| Council second layer inspection | delete | n/a | Add: (if applicable). No pic requried
New QA to add: Complete ceiling grids/ceiling insulation into IT walls
Stopping IT walls only
Council IT wall inspection & stopping
New QA to add: Stair install
| Council inspection 1st layer |  | add as sperate line after/before? gib up: postline line inspection of bracing prior to stopping
Complete GIB
New QA to add: Postline inspection of bracing prior to stopping
Stopping
section | Handover
Plumbing location in walls - both kitchen & bathroom
Power & data to all allocated points
Nogs in place for additional fittings - HTR/toilet roll holder
Second check framing prior to wall linings - plane & straighten
Gib completion
Recorded inspections for claims
6 | Kitchen Install
section | Install
Doors/finishing lines
Painting
Waterproof & vinyl/tiles
Joinery/showers
Kitchen Install
2nd fix
| Top coat |  | delete | Delete
Hardware
Flooring
Carpet
| Appliance install |  | add | New QA to add: Appliance install
section | Interior Detailing
All manuals are in the kitchen drawer
All keys tested and noteled are in the kitchen drawer
All doors slide/latch correctly and internal door locks working
All kitchen and bathroom joinery drawers and doors open and shut correctly
The blue film removed from the range hood around the vents
All appliances fitted correctly and tested – Oven – Rangehood – Dishwasher – Air Conditioner – Alarm – Heated Towel Rails - Hob
Test all bathroom & laundry run on vents do not run longer than the required time
All silver floor grate grills have no rubbish in them
All excess vinyl glue is removed and joins are too our standard
| All carpet stair pins are removed and carpet is fixed properly into the corners of each room and in particular on the stairs | separate defecting lists? Leave
Stair hand rail is finished to our quality standard
The shower sealing is completed to our standard
Wardrobe interior systems installed to be level
Laundry tubs and taps installed to our standard and position
Interior Painting is finished on walls, skirting boards and ceiling to our quality control standard
Check all lights and light switches working
Kitchen, laundry, bathroom taps run hot/cold and water pressure acceptable
Stickers removed from exterior of appliances & toilet
Silicon finished in wet areas to our standard
Blinds fitted correctly & functioning smoothly
Adhesive screw buttons fitted over screws in kitchen & bathroom cabinetry
section | Handover
Check upstairs floor for creaks & screw down/check all wet areas have correct flooring installed
Stopping & complete first coat paint check with light touch up if required
Door installation - check all margins are equal & doors are workimg
Install skirtings & finish lines - check to ensure that all joints are sanded & ready for paint
Kitchen checklist & QA
Final check painting - photos required upon completion
Recorded inspections for claims
Shower door installed correctly are level
7 | Practical Completion
section | Site Works Units
Hard landscaping
Fencing
Patios
Landscaping
| pergolas/shrouds/canopies |  | add | New QA to add: Pergolas/shrouds/canopies
CCC Inspection passed
section | Exterior Detailing
Keys all tested and noteled doors letterboxes
Keyless door entry lock tested
Entrance Door numbered
Clothesline installed as per plan
Clothesline works
Outdoor taps work
Any gates tested and shut and open easily
Car park numbering aligns to plans
Letterboxes installed in correct place
section | Handover
Landscaping handover package complete
Fencing complete
Patio area in perfect condition
Pergola installed/QA by contractor
Photos logged & sent through to Solution Street
Recorded inspections for claims
CCC inspection passed
Photo of ICP number on Power meter uploaded to daily log
8 | Code Compliance
section | Completion
Trade clean
| QA/defects |  | leave
CCC Issued
| Work through list |  | leave remaining remedial items | Add: (including remaining remedial items).
Building Complete
section | Interior & Exterior Detailing
All exterior walls cleaned to our standard
All exterior windows cleaned to our standard
section | Handover
Recorded inspections for claims
multiple photos at the same time?
retrospective uploading