## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | 60c2b040-aa6e-4961-9f36-569d1c8d77aa |  | checklist | Fire Hydrant QA |  |  |  |  | Yes | Fire Hydrant QA | 2fb995c0-88d8-46e2-adf9-0ce58625416f
checkpoint-group | 83d6b6d9-37e2-4043-a928-f45b1682a833 |  | section | Fire Hydrant - First Fix
checkpoint-status | 68e68a15-7034-4ddb-bf3f-449d998bbde2 |  | checkpoint | Substrate acceptable
checkpoint-status | 349e7b80-fa59-4a7d-a880-e201a76505af |  | checkpoint | Area accessible
checkpoint-status | e04c3425-1045-419e-9389-de7e8fda2e3c |  | checkpoint | First Fix completed and area cleared of waste (photos attached)
holdpoint | 3dcac318-350a-4696-a7d4-b7d1ea7b5641 |  | signoff | Main contractor sign off
checklist-flat | 011c65b5-0fd9-49f7-ba74-2dda0516b80f |  | checklist | B03&B04 - BCO10298055-2, BCO10298055-3, BCO10298055-4 |  |  |  |  | Yes | Completion Documentation | 587f9d12-fb28-4997-aab4-315b9ed6ea78
checkpoint-status | 3a996ff4-73d6-4d0a-b586-b896a45babc0 |  | checkpoint | Sprinkler and fire alarm system PS3 - Type 4 & Type 7
checkpoint-status | a40397ed-6d90-4e26-b436-ee4897c87404 |  | checkpoint | Monitoring of fire system - Confirmation letter
checkpoint-status | 62fae368-2726-45a7-9697-ded8c4e97ec2 |  | checkpoint | Fire alarm and sprinkler system - Cert of Completion (COC) Letter from AON for inspection
checkpoint-status | 32227875-a08c-466f-8a32-abd5d2417803 |  | checkpoint | Pressure Test results (per zone)
checkpoint-status | 9906d5d7-4f25-4c54-af1e-2524e1697fbe |  | checkpoint | As Built Plans for ALL installed systems (Fire Alarms & Sprinklers)
checkpoint-status | 0c01343c-2159-473c-96de-40690dd7db6a |  | checkpoint | Hydrant Flow Testing Results (for risers)
checkpoint-status | 3e7aefb1-4841-43a0-bdf0-ed1410e797f6 |  | checkpoint | Hydrant Riser Installation and schematic as built plans - PS3
checkpoint-status | 9cc442dd-53c1-40db-98c5-1e1d5d9eb881 |  | checkpoint | Letter from Fire engineer for safe occupancy
checkpoint-status | 988c5adf-51a3-4df1-afd2-11c2c7425437 |  | checkpoint | Fire Hold open - PS3 & As Built Plans
checkpoint-status | da6063bb-0e55-4118-9188-51a5b501542c |  | checkpoint | Fire Alarm Monitoring System monitoring letter from ADT Ltd
checkpoint-status | a5cf5c6f-2db9-4bc0-850d-131bcd6578ba |  | checkpoint | NZ Fire Service - Site visit required to familiarise themselves with the site layout in case of emergency
checklist-sectioned | a809e724-577f-49d0-9bda-9ca48b2d2f98 |  | checklist | Fire Alarm QA |  |  |  |  | Yes | Fire Alarm QA | c1f09f69-812d-4061-99f4-a794881ed6f0
checkpoint-group | 1c805be8-e16f-4803-84c1-dc45ec16a925 |  | section | Fire Alarm - First Fix
checkpoint-status | dfc953bd-9a5a-4243-a6dc-5008395018c8 |  | checkpoint | Substrate acceptable
checkpoint-status | 7ca3c2d3-4837-4c40-8120-1d1d7eeca987 |  | checkpoint | Area accessible
checkpoint-status | cfed5e03-d101-47fa-a917-e2fc89d6143c |  | checkpoint | Flush boxes fitted
checkpoint-status | d744981d-e067-4705-bc51-fb073de8945c |  | checkpoint | Ready to line walls
checkpoint-status | 2be62f00-1bc7-4bdd-ad9b-363201f6f995 |  | checkpoint | Ready to line ceiling
checkpoint-status | 53cfc1bb-f84e-4670-8a6b-81f8d8eac9f1 |  | checkpoint | First fix completed and area cleared of waste (photos attached)
holdpoint | ffdf0056-4cad-490a-bba2-3569ce517cf5 |  | signoff | Main contractor sign off
checkpoint-group | d0419d73-36fd-444c-b9dd-890320c8da79 |  | section | Fire Alarm - Second Fix
checkpoint-status | 6d5e70dc-0ee5-4254-902b-fb9cc4634dfe |  | checkpoint | Ceiling fitted off
checkpoint-status | c5941c25-987c-4ae0-8e16-fb165ba09210 |  | checkpoint | Walls fitted off
checkpoint-status | e7706016-22d6-4c60-9d84-c5ec780c990d |  | checkpoint | Second fix completed in all aspects and area cleared of waste (photos attached)
holdpoint | 4ba6cfa7-f189-4335-9146-383094513b09 |  | signoff | Main contractor sign off
checklist-flat | 2042ffd6-ccfb-4d64-a8d7-93368c0ee0de |  | checklist | Pre-Commencement Checks (B03 & B04) |  |  |  |  | Yes | Pre-Commencement Checklist | d7b3bdea-4a9e-4280-9461-ed29a7116d7d
checkpoint-status | c36b8f4d-a21b-410c-9763-ca5ffb400252 |  | checkpoint | Quality Management Plan Completed, Agreed and Attached
checkpoint-status | 110a3db7-c456-4888-bbf3-c5a7ebeb9415 |  | checkpoint | Inspection & Test Plan Completed, Agreed & Attached
checkpoint-status | ed4a2f8e-3711-475f-bae0-541c24169f74 |  | checkpoint | Relevant Breakdown & Checklist Setup on Conqa & Reviewed by Main Contractor
checkpoint-status | 2613dc1b-12c3-4d5c-9c55-4dbd970b9848 |  | checkpoint | Conqa Setup & Project Team Trained & Given Access
checkpoint-status | 043e90ad-37fc-4a44-97e5-e07f63bc9f07 |  | checkpoint | Review Access Granted to Main Contractor & Relevant Parties
checkpoint-status | 9c9b7aa3-d2ae-44f7-8cc4-d810ee25195e |  | checkpoint | Matrix/Insight Setup (if required)
checklist-sectioned | e3f9623a-410d-441a-a6bc-c9d0a69281a3 |  | checklist | Fire Sprinkler QA |  |  |  |  | Yes | Fire Sprinkler QA | f8c66e04-6990-4dd8-bead-8d8973c24f8c
checkpoint-group | b261ae28-4f08-409b-ac5d-7d81b7feb30f |  | section | Fire Sprinkler - First Fix
checkpoint-status | dc032c48-c7a3-4706-a12e-c83733f3dbae |  | checkpoint | Substrate acceptable
checkpoint-status | 722a6470-fdcc-4b93-9ecd-c138e6d3a198 |  | checkpoint | Area accessible
checkpoint-status | 73196fdb-5863-4645-8045-fc38291a4174 |  | checkpoint | First fix completed and area cleared of waste (photos attached)
holdpoint | 0c10e677-cede-49aa-a25e-51635c5ffd4e |  | signoff | Main contractor sign off
checkpoint-group | 695632f0-38ad-4a5f-bedd-e5e1c6cf03a3 |  | section | Fire Sprinkler - Second Fix
checkpoint-status | 035bab11-b20d-41b9-9763-831c3ef932ff |  | checkpoint | Second fix completed in all aspects and area cleared of waste (photos attached)
holdpoint | f38d873e-d215-40ae-ae99-59640779b354 |  | signoff | Main contractor sign off
checkpoint-group | 31e044a3-73e3-4442-abf9-55cfbc1fa543 |  | section | Pressure Test
checkpoint-status | 28f930c0-7b63-4776-8dbd-2fc70e4b5b24 |  | checkpoint | Pressure Test Info
checkpoint-status | d34f415d-2539-4e71-a474-9d79fb193749 |  | checkpoint | System pressure test details
checkpoint-status | 91573a46-5d2c-45bf-80b1-a31e8514b36e |  | checkpoint | Installation conforms to accepted plans
checkpoint-status | e2514af9-4dc9-4a4c-81e0-2049da14fd95 |  | checkpoint | Equipment used is approved
checkpoint-status | ccd38ef1-84b3-43e2-bf51-e3857865ec39 |  | checkpoint | Test Results
checkpoint-status | dd7a46df-a24a-4823-8f4a-759a182c2e50 |  | checkpoint | Retest required
checkpoint-status | bba664b4-722a-40d3-b943-2a97716e63dc |  | checkpoint | Installer review completed
checkpoint-status | 45a8bca6-2d4b-4f49-98b9-f23568572a09 |  | checkpoint | Main contractor review completed
holdpoint | 7b93aa21-c4f6-436b-9102-bef4a840a39b |  | signoff | Main contractor sign off