## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | General Behavioural Safety Observation (BSO) Date - |  |  |  |  | Yes | H&S - General Behavioural Safety Observation (BSO) | 02c9e4ed-70c4-405b-9c23-aa21e952ac82
checkpoint-group |  |  | section | General
checkpoint-status |  |  | checkpoint | Discuss with the supervisor
button | a1eda16b-1ee7-45ec-8861-af71c6546457 |  | button | Is an incident form required? | No,Yes
text | 3b16d385-073f-407d-9fbb-605d0d7a6826 |  | textbox | Area:
button | 0522e7a9-2111-451f-9a9c-6a4108cf47ef |  | button | Discuss at the next Hook-Up? | No,Yes
text | 1dffdf6b-ec73-4711-abe9-2127dfc41323 |  | textbox | Auditor/Team:
text | d7d25531-60cf-470d-9e3d-77942d716f04 |  | textbox | Time Spent on Audit:
text | 9133c360-ee14-4c55-9f56-eb0c287b84a8 |  | textbox | Actions to be completed & Date:
boolean | 03096560-25a1-4257-8c85-fb23b76ef146 |  | tickbox | 1. Safety Rule Violation (SRV)
label | a1f76e1b-1184-43d3-9086-c2b77f59c068 |  | note | Behavioural Safety Observation Guide
label | 976fde98-f74b-49be-b3e8-bff40227c738 |  | note | Purpose - To provide a guide to the tasks and behaviours required of a person when conducting a safety observation.
text | d7ceb481-80a9-401d-94fe-279247c6bdb0 |  | textbox | Number:
boolean | 77e78dd0-1c8f-48ad-80d0-b36eaae95b0f |  | tickbox | 2. Unsafe Condition (UC)
label | 09466fcc-5791-4d7a-83e5-dc96d1149ca1 |  | note | Scope - 1. If you are a team leader, ensure you are familiar with this guide before attempting to conduct a safety observation. 2. If you are an assessor or are auditing a person conducting a safety observation, then use this checklist as an assessment / auditing instrument.
text | 03026f96-9e9a-416e-abb7-637b56d1d464 |  | textbox | Number:
boolean | f5cbb493-4a47-4ca5-8cef-563f79e490b6 |  | tickbox | 3. Positive Safety Act (PSA)
text | a193d4cb-efa3-45a9-a5a5-88a0bf5e382d |  | textbox | Number:
boolean | 5c36d417-7e69-402d-af7c-22659d770e02 |  | tickbox | 4. Unsafe Act (UA) POTENTIAL KILLER
text | 4924fd70-887f-43de-8f71-beea0a32bdee |  | textbox | Number:
boolean | 5973b56b-a4d3-482f-b340-bb811efda172 |  | tickbox | 5. Unsafe Act (UA) - Potential Serious Injury
text | 08ffb67e-39a5-4cbd-aa67-2bd5997acbb7 |  | textbox | Number:
boolean | 424ee3ff-adce-4e82-a008-d33fbfc82a6c |  | tickbox | 6. Unsafe Act (UA) - Potential Minor Injury
text | ab89c3e5-5ed4-44dc-95f9-8a11e4a9e877 |  | textbox | Number:
checkpoint-status |  |  | checkpoint | Gather area-specific data before starting (review past audits; Hazard Register; use an SOP as reference; specific hazards or conditions today).
checkpoint-status |  |  | checkpoint | Check the area is safe – observe from a safe position first before entering
checkpoint-status |  |  | checkpoint | TASK OBSERVED - KEY ISSUES - Is it a killer?
checkpoint-status |  |  | checkpoint | In the first 30 seconds after entering the area check for: 1. Evaporative behaviour (How people are behaving). 2. The hazards
checkpoint-status |  |  | checkpoint | If you observe an unsafe act or condition: (IMMEDIATE DANGER) 1. Stop the work until it is made safe. Never walk past or ‘look the other way’. Inform the supervisor later, if he is not present.
checkpoint-status |  |  | checkpoint | If you observe a behaviour or situation that doesn’t ‘feel’ right: 1. When it is safe to gain the person’s attention, check the behaviour/situation. 2. If the person’s answer again doesn’t feel right, tell the person you will check with the area owner, and do so immediately if necessary
checkpoint-status |  |  | checkpoint | ENGAGEMENT WITH THE EMPLOYEE - Greet / introduce / clarify the purpose of the observation 1. Always praise the positive behaviour observed - FIRST
checkpoint-status |  |  | checkpoint | INVOLVE THE PERSON - PROMPTS 1. What are the hazards of the task? 2. Is this how you would normally do the task 3. Why do you do it that way? 4. Are you following the operating procedure? (pre-check etc) 5. Are there other ways to do the task? 6. What are the emergency stop procedures? 7. What has gone wrong/ nearly gone wrong before? 8. When and what was the last incident in this area? 9. How can the task be made safer?
checkpoint-status |  |  | checkpoint | At risk behaviour is discussed (if applicable):
checkpoint-status |  |  | checkpoint | Employee committed to adopt safe behaviour: (plan)
checkpoint-status |  |  | checkpoint | Discuss the plan with the operator’s supervisor / manager.
checkpoint-group |  |  | section | Behavioural Safety Observations Details
checkpoint-status |  |  | checkpoint | Details Complete
text | 3b16d385-073f-407d-9fbb-605d0d7a6826 |  | textbox | Area:
text | 1dffdf6b-ec73-4711-abe9-2127dfc41323 |  | textbox | Auditor/Team:
text | 64595593-4ef5-4026-8417-6d5e78487224 |  | textbox | Date
text | d7d25531-60cf-470d-9e3d-77942d716f04 |  | textbox | Time Spent on Audit:
boolean | 03096560-25a1-4257-8c85-fb23b76ef146 |  | tickbox | 1. Safety Rule Violation (SRV)
text | d7ceb481-80a9-401d-94fe-279247c6bdb0 |  | textbox | Number:
boolean | 77e78dd0-1c8f-48ad-80d0-b36eaae95b0f |  | tickbox | 2. Unsafe Condition (UC)
text | 03026f96-9e9a-416e-abb7-637b56d1d464 |  | textbox | Number:
boolean | f5cbb493-4a47-4ca5-8cef-563f79e490b6 |  | tickbox | 3. Positive Safety Act (PSA)
text | a193d4cb-efa3-45a9-a5a5-88a0bf5e382d |  | textbox | Number:
boolean | 5c36d417-7e69-402d-af7c-22659d770e02 |  | tickbox | 4. Unsafe Act (UA) POTENTIAL KILLER
text | 4924fd70-887f-43de-8f71-beea0a32bdee |  | textbox | Number:
boolean | 5973b56b-a4d3-482f-b340-bb811efda172 |  | tickbox | 5. Unsafe Act (UA) - Potential Serious Injury
text | 08ffb67e-39a5-4cbd-aa67-2bd5997acbb7 |  | textbox | Number:
boolean | 424ee3ff-adce-4e82-a008-d33fbfc82a6c |  | tickbox | 6. Unsafe Act (UA) - Potential Minor Injury
text | ab89c3e5-5ed4-44dc-95f9-8a11e4a9e877 |  | textbox | Number:
checkpoint-status |  |  | checkpoint | What are the hazards?
checkpoint-status |  |  | checkpoint | Identify the positive safety acts
checkpoint-status |  |  | checkpoint | Areas of concern are (if any)
checkpoint-status |  |  | checkpoint | Reason provided for UA or SRV
checkpoint-status |  |  | checkpoint | Remedial action(s) agreed
checkpoint-status |  |  | checkpoint | Discuss with the supervisor
button | 5203adff-abea-42ac-b59b-a209913ace5f |  | button | Is an incident form required? | No,Yes
button | 7ecae69f-a73d-4faf-a8fd-fce7dfb42169 |  | button | Discuss at the next Hook-Up? | No,Yes
text | 15bb4fd1-8eb3-4e99-9533-d2c4409e9d39 |  | textbox | Actions Completed & Date
checkpoint-group |  |  | section | Behavioural Safety Observations Task
checkpoint-status |  |  | checkpoint | Any evaporative behaviour?
checkpoint-status |  |  | checkpoint | What are the hazards?
checkpoint-status |  |  | checkpoint | Identify the positive safety acts
checkpoint-status |  |  | checkpoint | Areas of concern are (if any)
text | 888d9e1d-f5f9-409c-a943-7861e4f817af |  | textbox | Category:
checkpoint-status |  |  | checkpoint | Reason provided for UA or SRV
checkpoint-status |  |  | checkpoint | Remedial action(s) agreed
checkpoint-status |  |  | checkpoint | ENGAGEMENT WITH THE EMPLOYEE - Greet / introduce / clarify the purpose of the observation 1. Always praise the positive behaviour observed - FIRST
checkpoint-status |  |  | checkpoint | INVOLVE THE PERSON - PROMPTS 1. What are the hazards of the task? 2. Is this how you would normally do the task 3. Why do you do it that way? 4. Are you following the operating procedure? (pre-check etc) 5. Are there other ways to do the task? 6. What are the emergency stop procedures? 7. What has gone wrong/ nearly gone wrong before? 8. When and what was the last incident in this area? 9. How can the task be made safer?
checkpoint-status |  |  | checkpoint | At risk behaviour is discussed (if applicable):
checkpoint-status |  |  | checkpoint | Employee committed to adopt safe behaviour: (plan)
checkpoint-status |  |  | checkpoint | Discuss the plan with the operator’s supervisor / manager.
checklist-sectioned |  |  | checklist | Prestart Checklist - Date: |  |  |  |  | Yes | Add Daily Prestart checks | e66bd5cc-12a9-406b-abb7-e0afcaf966af
checkpoint-group |  |  | section | Prestart Checklist
checkpoint-status |  |  | checkpoint | Have all workers on site reviewed, understood and signed onto the SSSP, and confirmed all their details are correct.
checkpoint-status |  |  | checkpoint | All workers wearing required PPE
checkpoint-status |  |  | checkpoint | Weather conditions (Existing drop down boxes to remain)
select | 68c04772-0bca-455d-aeb0-6d02d506fe4e | DataPoint is missing 'select' values | dropdown | Select most appropriate description
select | 30f81c6c-0793-41a8-8b37-d8dcc9087c66 | DataPoint is missing 'select' values | dropdown | Wind Strength
text | b25cd943-dfb8-4af0-8d6d-d7dbc264fd6e |  | textbox | Time lost due to weather if applicable
checkpoint-status |  |  | checkpoint | Planned Tasks for the day and hazards discussed
button | c4521d21-7ba9-4c5d-b3f2-46e0acc44108 |  | button | Are there any people working above or below you | Yes,No
text | 92ceb0b6-81d5-447a-82d1-586f5dab8a9f |  | textbox | If YES, are workers at risk of falling objects, and how is this risk controlled?
text | f06ac455-a3f9-4d65-b8f9-fbf97566d687 |  | textbox | How many staff at each workface
checkpoint-status |  |  | checkpoint | Are there any issues from the previous day not resolved.
checkpoint-group |  |  | section | Risk Assessment
checkpoint-no-status |  |  | checkpoint | Task Description
text | 40d1f3c8-5524-4916-a9b7-f5fe22a0a9e6 |  | textbox
select | 0d140c76-8220-43df-80d6-0b0885a00c16 |  | dropdown | What is your first task for the day | Bend bar by hand,Bend bar with mechanical bender,Cut steel with Grinder,Cut steel with mechanical cutter,Install and tighten Couplers with Wrench,Install steel at height,Install steel in Trench,Install steel off scaffold,Install steel on Ground,Moving steel to workface,Stacking and storage,Unloading truck with material
label | c00d369a-a47a-41bd-b197-88ffb4bcbfc1 |  | note | Hazards (Select)
boolean | 1095c486-c483-421a-ba31-5a7f72f4ace3 | Hidden property width:100 | tickbox | Heavy items
boolean | 1e4d10b0-a727-4dd4-b932-3df091bfba1b | Hidden property width:100 | tickbox | Sharp ends of bars
boolean | 62bc9757-0f2f-4022-bd9a-0d57749bf31a | Hidden property width:100 | tickbox | Working on elevated areas
boolean | 0cc6da97-1dec-47e8-ac54-e076c54a2510 | Hidden property width:100 | tickbox | Working on Scaffold platforms
boolean | 761b8202-75e7-475a-b6d2-fbf07c68a288 | Hidden property width:100 | tickbox | Cutting bars with a Grinder
boolean | 28239c1a-c238-455b-b534-9cb950fc7486 | Hidden property width:100 | tickbox | Un protected bar ends
boolean | 77541b5c-a701-4bfb-95db-a73a2dfbe5a4 | Hidden property width:100 | tickbox | Stacked material
boolean | 69f2935c-f480-4629-afd9-0e8e22eb5a09 | Hidden property width:100 | tickbox | Holes on Floors
boolean | 5db78b1d-c363-4165-b82d-e40979497971 | Hidden property width:100 | tickbox | Trap doors for access on elevated sections
boolean | b7d7e162-89b8-460d-89f4-f7c82abb4812 | Hidden property width:100 | tickbox | Installing long bars that can fall into adjacent area
boolean | c674bf4c-d9f8-4c8b-91e3-67f97c942595 | Hidden property width:100 | tickbox | Installed reinforcing on surface area to be walked on
label | 3b9089f1-1e55-4f30-be09-835315e348e6 |  | note | What could go wrong?
boolean | eb3e854a-c79b-4b93-866b-93ecab0a7cea | Hidden property width:100 | tickbox | Small items falling from height
boolean | 53e2520e-f00a-4a6c-b96d-56c668977613 | Hidden property width:100 | tickbox | Bars falling from height
boolean | a31ac59a-5be0-46c9-aaa6-a601d13436dc | Hidden property width:100 | tickbox | Injure back
boolean | e977385b-096c-49fa-bcf3-31f79c6e8410 | Hidden property width:50 | tickbox | Injure Ankle
boolean | d0a9bf19-f2ce-429c-a283-72cda88e8955 | Hidden property width:100 | tickbox | Injure Eyes
boolean | 5e5ba559-bd7a-4c36-b576-73472a93ec27 | Hidden property width:100 | tickbox | Falling from height
boolean | 42f39406-57be-481c-8157-8cc4982592dd | Hidden property width:100 | tickbox | Cuts on hands, legs or other body parts
boolean | 98afe031-c46c-48ff-9a65-31be1718e74e | Hidden property width:100 | tickbox | Falling through hole
boolean | e638e471-4d72-4d70-8b6a-3808c4ee474b | Hidden property width:100 | tickbox | Stacked material could collapse and roll or fall on people
boolean | ce65a7ed-3c99-476d-bede-b1a9246352fd | Hidden property width:100 | tickbox | Fingers cut or amputated
boolean | 4a1662e0-5f4b-4e76-b389-cac436485016 | Hidden property width:100 | tickbox | Sparks into eyes or burns on skin from sparks
boolean | 50852f28-1452-4eae-998d-c634d853a07a | Hidden property width:100 | tickbox | Finger or foot can get pinched
select | 0e89fb44-fc47-4d27-a88a-8df3de70269f |  | dropdown | Risk Before? | Critical,High,Low,Moderate,Very low
text | 7b0abd26-0f83-4c5a-88fa-2f18df3ff98e |  | textbox | How will you eliminate, isolate or minimise the hazard in order to make it safe?
select | 23b4ff69-cd2c-4440-99bb-e0ce2162f1fa |  | dropdown | Risk After? | Critical,High,Low,Moderate,Very Low
checkpoint-status |  |  | checkpoint | Individual Task / Risk Assessment Complete
checkpoint-group |  |  | section | Covid 19 checks
checkpoint-status |  |  | checkpoint | Is the temperature check conducted by the assigned personnel?
checkpoint-status |  |  | checkpoint | Is there any staff who has temperature of over 37.2 ° C or feeling unwell?
checkpoint-status |  |  | checkpoint | Is there anyone who recently in contact with a possible COVID-19 patient?
checkpoint-status |  |  | checkpoint | Do you have enough COVID-19 PPE?
checkpoint-status |  |  | checkpoint | Is the travel to the site (vehicle policy) followed?
checkpoint-status |  |  | checkpoint | Can today’s job be undertaken by the staff in the same bubble?
checkpoint-status |  |  | checkpoint | Is everyone equipped with enough sanitizers and wipes?
checkpoint-group |  |  | section | Signoffs
checkpoint-status |  |  | checkpoint | All workers on site today were present for prestart & risk assessment (attach signatures below)
checklist-sectioned |  |  | checklist | Area: |  |  |  |  | Yes | Add New Area (All checklists) | 5e3e26cd-7d82-4cf3-8619-f952ea16143e
checkpoint-group |  |  | section | Drawings, Detail sheets & General Notes
checkpoint-no-status |  |  | checkpoint | Attach document
checkpoint-group |  |  | section | Workface handover
checkpoint-status |  |  | checkpoint | Start date
checkpoint-status |  |  | checkpoint | Safe and suitable access provided by H.C. at workface (attach photos)
checkpoint-status |  |  | checkpoint | Scaffold tagged, Stairs and safety railing inspected, no openings to floors (attach photos)
checkpoint-status |  |  | checkpoint | Cranage arranged or reinforcement at workface
checkpoint-status |  |  | checkpoint | Grid lines set out by H.C. at workface and visible
checkpoint-status |  |  | checkpoint | Datums provided by H.C. at workface and visible
checkpoint-status |  |  | checkpoint | Site concrete poured
checkpoint-status |  |  | checkpoint | Formwork installed to minimum 1 face
checkpoint-status |  |  | checkpoint | Tanking, waterproofing complete
checkpoint-status |  |  | checkpoint | All cast in items set out or in place (Hold down bolts, Weld plates, plumbing etc)
checkpoint-status |  |  | checkpoint | Starting point for Precast foundation starters set out by H.C.
checkpoint-status |  |  | checkpoint | Couplers, Threaded inserts cleaned out and prepared by H.C.
checkpoint-status |  |  | checkpoint | Is there any uncompleted work by the H.C. that will hinder the progress of your work?
checkpoint-status |  |  | checkpoint | All pre install checks completed and approved - Ready to start work
checkpoint-group |  |  | section | Reinforcing QA checks
checkpoint-status |  |  | checkpoint | Specified covers checked/correct (attach photos)
checkpoint-status |  |  | checkpoint | Cover blocks (attach photos)
checkpoint-status |  |  | checkpoint | Size, position & spacing of reinforcement as per drawing (attach photos)
checkpoint-status |  |  | checkpoint | Lap lengths and locations as per drawing (attach photos)
checkpoint-status |  |  | checkpoint | Correct stirrup sets
checkpoint-status |  |  | checkpoint | Horizontal / Vertical starter bars installed correctly (Location, position, size, spacing) attach photos
checkpoint-status |  |  | checkpoint | Reid bars tightened in full with wrench
checkpoint-status |  |  | checkpoint | Couplers, Threaded inserts, Foot plates installed correctly (Location, position, size, spacing)
checkpoint-status |  |  | checkpoint | All reinforcement tied, secured and rigid
checkpoint-status |  |  | checkpoint | Any additional items considered, installed & completed e.g. trimmer bars, drag bars etc
checkpoint-status |  |  | checkpoint | All excess reinforcing, tie wire and debris removed - clean & tidy
checkpoint-status |  |  | checkpoint | Completion date
checkpoint-group |  |  | section | Handover to HC
checkpoint-status |  |  | checkpoint | QA complete, area left clean and tidy
checkpoint-status |  |  | checkpoint | Work completed as per drawing and specifications
holdpoint |  |  | signoff | Steel & Tube Sign off
checkpoint-status |  |  | checkpoint | Accepted and approved for concrete by H.C. (attach 4 photos)
holdpoint |  |  | signoff | HC Sign off
checklist-flat |  |  | checklist | Observation Remedial: |  |  |  |  | Yes | Add Observation/Remedial | 25a704c0-53fb-45e1-b775-eb6a5a25cdb9
checkpoint-status |  |  | checkpoint | Remedial Required
text | 28d26279-c304-4689-8317-1deb797dc8fe |  | textbox | Action Required
text | 2247155b-6de8-434c-a1e1-058d724a6a62 |  | textbox | Remedial Reference (if applicable)
text | ae7fc046-dca9-4fab-98f8-374caeb044ec |  | textbox | Location
holdpoint |  | Invalid dependant | signoff | Request Observation Approval
checklist-sectioned |  |  | checklist | Accident & Incident Investigation Report |  |  |  |  | Yes | H&S - Accident Report | 52b015a5-fc25-4ae3-9cba-c76e07ca2e30
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details Completed
text | e9de5bfb-8771-4638-b38c-6460b4a51ce3 |  | textbox | Name of Investigator:
checkpoint-group |  |  | section | Particulars of Incident
checkpoint-status |  |  | checkpoint | Particulars of Incident Details Completed
select | 6b525f4e-f45b-4da7-8df5-23fe6bff84be |  | dropdown | Day of Incident: | Friday,Monday,Saturday,Sunday,Thursday,Tuesday,Wednesday
text | 7e5d562b-6c37-42a1-8dac-2df84d546b73 |  | textbox | Time:
text | 77139ee8-1724-49ec-b32f-6297f71fb24d |  | textbox | Project/Site:
text | a3d0113e-1792-4d2a-81a4-c196efecce04 |  | textbox | Date Reported:
checkpoint-group |  |  | section | Injured Person Details
checkpoint-status |  |  | checkpoint | Injured Person Details Completed
text | bcbcce61-cfa2-48bc-982c-c5b5e71a5820 |  | textbox | Name:
text | 557319b1-18ca-4e15-8145-bf19756ed742 |  | textbox | Age:
text | 17d87fda-3003-4f2f-800d-c104d51100a6 |  | textbox | Phone Number:
text | b250bb03-568c-46a4-930f-063d05523218 |  | textbox | Address:
text | 183cd7d2-02cd-4259-8bcf-687060e2ae22 |  | textbox | Reported date of incident:
text | cb2b501a-8ccb-408b-9bb5-195476e5b88e |  | textbox | Length of employment:
text | 9df08fae-8517-426e-a3fc-1ebb04a7daf1 |  | textbox | Time on job:
checkpoint-status |  |  | checkpoint | Type Of Injury:
boolean | 7ade6143-a0ba-43c7-94c8-17ffd8a461cb |  | tickbox | Strain/sprain
boolean | 5738b1fe-e0ff-4949-ba49-7c573b173ca4 |  | tickbox | Fracture
boolean | 6b4511fb-6c5c-4a9b-b2a1-9c48b3371cfa |  | tickbox | Laceration/cut
boolean | 24005c68-47eb-4552-ba5b-1dc0d9723144 |  | tickbox | Bruising
boolean | 769c2254-a4b9-40f7-8c98-a1b987acd4f0 |  | tickbox | Scratch/abrasion
boolean | 8e754d90-98ee-4346-8ef7-4e37d0cd0355 |  | tickbox | Amputation
boolean | 0f62ffbd-d654-4a44-b6ca-c8c5fd6bcf05 |  | tickbox | Burn scald
boolean | c8c5f313-eb09-4171-b9df-32520fffab31 |  | tickbox | Dislocation
boolean | 7e48ef93-56fc-4c31-8441-2b6734f61a1c |  | tickbox | Internal
boolean | 74f4e66e-8287-4131-ab3d-ea35d3e9e914 |  | tickbox | Foreign body
boolean | c0050bb4-329d-4731-b3b6-b00f4fe27d01 |  | tickbox | Chemical reaction
boolean | 4e1cd37b-f7a7-49d4-b988-e1a523b2d87e |  | tickbox | Other
text | 7e4b43c5-0b61-4b6b-ba7e-ec7748fc5de3 |  | textbox | If other please specify:
text | 18e138ea-f591-4403-a2ad-9bddb2e1f2f8 |  | textbox | Injured Part of Body:
checkpoint-group |  |  | section | Damaged Property
checkpoint-status |  |  | checkpoint | Damaged Property Details Completed
text | b40e64d9-5932-48a4-9420-88c8273d482f |  | textbox | Property/material damaged:
text | 7aa7cc35-9187-4c4d-96be-4b44ec4ab825 |  | textbox | Nature of damage:
text | 6eb6370f-545a-42cd-8129-fe259589d2bf |  | textbox | Object/substance inflicting damage:
checkpoint-group |  |  | section | Incident
checkpoint-status |  |  | checkpoint | Incident Details Complete
text | 4cd700c0-230d-460a-83f9-fd60b8704fb7 |  | textbox | Describe what happened (space overleaf for diagram – essential for all vehicle incidents):
checkpoint-group |  |  | section | Analysis
checkpoint-status |  |  | checkpoint | Analysis Details Completed
text | 04e074f8-e295-4677-856b-5c28255dd0ae |  | textbox | What were the causes (root and contributing causes) of the incident?
text | 1daea218-712c-4f70-9767-9a8134812e18 |  | textbox | Root causes – safety system failures:
text | c6818664-ec27-40a9-a8a7-26f7ef16536b |  | textbox | Contributing causes – unsafe acts and conditions:
checkpoint-group |  |  | section | Prevention
checkpoint-status |  |  | checkpoint | Prevention Details Completed
text | 68d803a6-e0f5-415b-a68d-026a47c8da2f |  | textbox | What action has or will be taken to prevent a recurrence? Tick items already actioned
boolean | bc67a7a4-86be-476f-be81-80038ecf4d50 |  | tickbox | Completed
text | bfa9b6c8-e5a0-4595-b25a-fe1bafc23161 |  | textbox | By Whom:
text | e03e6bef-8361-4a24-8eef-856453f85d7a |  | textbox | When:
checkpoint-group |  |  | section | Treatment and Investigation of Incident
checkpoint-status |  |  | checkpoint | Treatment and Investigation of Incident Details Completed
text | 659ceae3-0e40-4182-9989-845fda6a338f |  | textbox | Treatment and Investigation of Incident :
text | 0a690191-d11c-4abd-975b-a7dccd78628d |  | textbox | Name of person giving First Aid:
text | 26885b6b-063a-4c38-a2cc-5794f0204418 |  | textbox | Doctor/Hospital:
text | 1c479a88-1f1b-42c5-b9e7-6ce977689cb3 |  | textbox | Incident investigated by:
text | c19b857e-6fb6-4c5d-bb32-996e3a28f9fb |  | textbox | Date:
select | fc88a287-6242-4d70-8e73-0d2270065565 |  | dropdown | Worksafe NZ advised | No,Yes
text | 913c4a48-55ec-4ab0-aa2e-c6e004b75fe5 |  | textbox | Date:
checklist-flat |  |  | checklist | Instruction - |  |  |  |  | Yes | Add Client Instruction | 818f758f-f76f-4908-b2b7-92c3df29db47
checkpoint-status |  |  | checkpoint | Client Instruction reviewed and approved
text | c0f0333e-8bb0-41ae-9957-bc2d9c93085c |  | textbox | Who is giving the instruction:
text | 8e91a07a-adbf-4e44-ab19-e57e131ac87e |  | textbox | Instruction Details and Specifics
button | ca2207e2-9658-479c-b8ad-90879fa0556b |  | button | Will this Instruction generate a Variation | No,Yes
text | 2296ecaf-2ca7-49b8-ba06-7db3cebae22c |  | textbox | If yes please input relevant instruction number below and attach specifics
checklist-flat |  |  | checklist | Waste Report |  |  |  |  | Yes | Waste Report | 9af12c3c-fefd-4288-b0f9-4543a77390bb
checkpoint-status |  |  | checkpoint | Photo of Detail sheets effected
text | c4145202-fccb-478b-8ce2-877ec6f8965e |  | textbox
text | 55551471-c2f3-46f5-869e-6dc83f8259c9 |  | textbox
text | 1aabc98b-4937-472b-af50-5854da1bee51 |  | textbox
text | 9971b797-d266-4bfe-aaee-ef4df70dbb0e |  | textbox
text | a0dcb0d1-cec9-4128-8f3e-36b1f322bb4c |  | textbox
checkpoint-status |  |  | checkpoint | Stock take of material to be removed
text | e6037276-0b19-48aa-a9cf-b71269e849c0 |  | textbox
text | b6400356-4331-40a3-8710-47780756570c |  | textbox
text | 85687f80-6856-45ed-964f-c5bb51f0ad54 |  | textbox
text | 55929030-66fd-4123-8cb7-6cd9bbe9b43f |  | textbox
text | 2c84051a-f986-4c0c-ac22-c74c7d80d8d4 |  | textbox
text | cf8dcc5a-3fea-499b-8688-1b430c569264 |  | textbox
text | f532e883-f018-416c-93be-ba74de8736df |  | textbox
text | 626dfbeb-45aa-4106-868c-e0776a458000 |  | textbox
text | dbcb7228-0c1e-4ca4-b979-9b6a5fc7a2ef |  | textbox
text | d2708f41-f574-42b2-ac2e-454840aee168 |  | textbox
checkpoint-status |  |  | checkpoint | Photos of material to be removed
checkpoint-status |  |  | checkpoint | Reason for removal
checkpoint-status |  |  | checkpoint | Preventative action taken
checklist-sectioned |  |  | checklist | Site Inspection Checklist |  |  |  |  | Yes | H&S - Site Safety Inspection | e9e234ad-8ec2-44e6-82ab-f8e7531a9d4d
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details Complete
text | 8b03cbae-c408-4ae9-a756-cca7018dea83 |  | textbox | Site/Location :
text | 52914ecc-91b7-4603-9495-6a1e5ad3bd75 |  | textbox | Date
text | 8ff362f0-afb9-45ca-87d4-347265a7e11e |  | textbox | Name of Inspector :
checkpoint-group |  |  | section | Site Control
checkpoint-status |  |  | checkpoint | Hazard Board and signage up-to-date
checkpoint-status |  |  | checkpoint | Environmental plan - issues
text | cae0f94e-0878-4302-855f-50626b9940cc |  | textbox | Toolbox talk last date:
checkpoint-status |  |  | checkpoint | Safety inductions for all on-site
checkpoint-status |  |  | checkpoint | Safety notice board current
checkpoint-group |  |  | section | Site Facilities
checkpoint-status |  |  | checkpoint | Offices clean, adequate & good lighting
checkpoint-status |  |  | checkpoint | Smoko sheds - clean, portable water
checkpoint-status |  |  | checkpoint | Toilets - clean, washing water
checkpoint-status |  |  | checkpoint | Tool /equipment sheds adequate
checkpoint-group |  |  | section | General Site Tidiness and Access ways
checkpoint-status |  |  | checkpoint | Clear, safe access to work areas
checkpoint-status |  |  | checkpoint | Stairways and accessways clear
checkpoint-status |  |  | checkpoint | Hoardings /fence and gates secure
checkpoint-status |  |  | checkpoint | Loose materials secure from wind
checkpoint-group |  |  | section | Personal Safety Equipment
checkpoint-status |  |  | checkpoint | Signage displayed and legible
checkpoint-status |  |  | checkpoint | Hardhats being worn
checkpoint-status |  |  | checkpoint | Correct footwear being worn
checkpoint-status |  |  | checkpoint | Glasses /ear muffs /vests /masks used
checkpoint-group |  |  | section | First Aid/Fire Prevention
checkpoint-status |  |  | checkpoint | First Aid Box Available
checkpoint-status |  |  | checkpoint | Accident register
checkpoint-status |  |  | checkpoint | Fire Extinguishers
boolean | 12bab111-d5d2-4ba9-87f2-979c842a9df6 |  | tickbox | Available
boolean | 61ea2b23-6ac8-44f8-9d40-86c8daf1dd62 |  | tickbox | Current (12mth)
boolean | 3f3e012d-918a-4137-9689-dcced1049dcc |  | tickbox | Sufficient number
checkpoint-status |  |  | checkpoint | Evacuation
boolean | 7aa1d51b-82ee-46ea-a2d8-8922b951f5d1 |  | tickbox | Procedure current
boolean | 62e3bbb3-5108-4954-b02d-7071877274bd |  | tickbox | All emergencies incl
checkpoint-group |  |  | section | Cranes/hoist/lifting equipment
checkpoint-status |  |  | checkpoint | Proper lift assessment plan done
checkpoint-status |  |  | checkpoint | Crane certification current
checkpoint-status |  |  | checkpoint | Slings/chains certified
checkpoint-status |  |  | checkpoint | Operator procedures in place
checkpoint-status |  |  | checkpoint | Inspections being done
checkpoint-status |  |  | checkpoint | Man cage available
checkpoint-status |  |  | checkpoint | Emergency plan in place
checkpoint-group |  |  | section | Compressed air equipment
checkpoint-status |  |  | checkpoint | In good condition
checkpoint-status |  |  | checkpoint | Appropriate guards fitted
checkpoint-status |  |  | checkpoint | Trained user
checkpoint-group |  |  | section | Excavations
checkpoint-status |  |  | checkpoint | Correctly Shored
checkpoint-group |  |  | section | Welding/gas cutting
checkpoint-status |  |  | checkpoint | Hot work permits being issued
checkpoint-status |  |  | checkpoint | Fire extinguishers on hand
checkpoint-status |  |  | checkpoint | Operators using PPE
checkpoint-group |  |  | section | Electrical Equipment
checkpoint-status |  |  | checkpoint | Main board lockable /weatherproof
checkpoint-status |  |  | checkpoint | Current tagged and damage-free leads
checkpoint-status |  |  | checkpoint | Current tagged plant
checkpoint-status |  |  | checkpoint | Current tagged lifeguards
checkpoint-status |  |  | checkpoint | Leads safely placed
checkpoint-status |  |  | checkpoint | Equipment in good condition
checkpoint-status |  |  | checkpoint | Appropriate guards on equipment
checkpoint-status |  |  | checkpoint | Adequate temporary lighting
checkpoint-group |  |  | section | Chemicals
checkpoint-status |  |  | checkpoint | Correctly stored
checkpoint-status |  |  | checkpoint | Safety Data Sheet (SDS) available
checkpoint-status |  |  | checkpoint | Operators using PPE
checkpoint-group |  |  | section | Tools
checkpoint-status |  |  | checkpoint | PAT tool WoF current and secure
checkpoint-status |  |  | checkpoint | Staff trained in tool use (SWPS)
checkpoint-status |  |  | checkpoint | PAT signage on site
checkpoint-group |  |  | section | Scaffolding
checkpoint-status |  |  | checkpoint | Notifiable weekly Scaftag/current
checkpoint-status |  |  | checkpoint | Handrails/mid-rails
checkpoint-status |  |  | checkpoint | Toe boards
checkpoint-status |  |  | checkpoint | Platforms
checkpoint-status |  |  | checkpoint | Ladders/stairs
checkpoint-status |  |  | checkpoint | Base sound
checkpoint-status |  |  | checkpoint | Work platforms clear
checkpoint-status |  |  | checkpoint | Platforms trip free
checkpoint-status |  |  | checkpoint | Planks tied down
checkpoint-status |  |  | checkpoint | Headroom clear
checkpoint-status |  |  | checkpoint | Ties/bracing adequate
checkpoint-group |  |  | section | Ladders
checkpoint-status |  |  | checkpoint | Good condition
checkpoint-status |  |  | checkpoint | Secured top and bottom
checkpoint-status |  |  | checkpoint | Stays to step ladders
checkpoint-status |  |  | checkpoint | Working 2 steps down
checkpoint-group |  |  | section | Fall Hazards
checkpoint-status |  |  | checkpoint | Fall Hazards
checkpoint-status |  |  | checkpoint | Floor openings
checkpoint-status |  |  | checkpoint | Lift shafts
checkpoint-status |  |  | checkpoint | Stairs
checklist-sectioned |  |  | checklist | Prefabrication - |  |  |  |  | Yes | Add Prefabrication QA Checklist | c5962bc2-57db-47de-9e9d-3dab8a83e92b
checkpoint-group |  |  | section | Prefabrication QA Checks
checkpoint-status |  |  | checkpoint | Steel Grade Checked & Approved
boolean | ff670a5e-231e-4dcb-8c66-50d6bdb15775 |  | tickbox | Checked by Prefabricator
boolean | 725a6a6d-f591-4d3b-a43c-0fa1ab0a9926 |  | tickbox | Checked by Steel & Tube Checker
checkpoint-status |  |  | checkpoint | Bar Size(s) Checked & Approved
boolean | 31a4d3f7-4f65-4691-aa15-3658b0dca8f9 |  | tickbox | Checked by Prefabricator
boolean | db20809b-2d94-40b5-ba6b-d610119d6ea1 |  | tickbox | Checked by Steel & Tube Checker
checkpoint-status |  |  | checkpoint | Bar Spacings Checked & Approved
boolean | 870f2437-06e9-4ef5-82e3-028f541cb052 |  | tickbox | Checked by Prefabricator
boolean | a75de1a6-2d0c-4811-b0a5-7c0e52a45bf3 |  | tickbox | Checked by Steel & Tube Checker
checkpoint-status |  |  | checkpoint | Spiral Spacings Checked & Approved
boolean | 84e8b154-84e7-4207-aa8f-860bca42aad3 |  | tickbox | Checked by Prefabricator
boolean | 2d6435ec-fba6-46cb-80b9-d35df69a2f03 |  | tickbox | Checked by Steel & Tube Checker
checkpoint-status |  |  | checkpoint | ALL Dimensions Checked
boolean | 0346e4a9-eb23-4413-bfa6-6541e6de6019 |  | tickbox | Checked by Prefabricator
boolean | c7655ef9-65a1-44a6-be90-85f456685413 |  | tickbox | Checked by Steel & Tube Checker
checkpoint-status |  |  | checkpoint | Adequate Bracing (if required for handling/transport
boolean | 08cffc4b-54c6-4bab-8216-1bfb0f106f36 |  | tickbox | Checked by Prefabricator
boolean | f43559b5-4688-4755-995f-e0fdd50bfc7c |  | tickbox | Checked by Steel & Tube Checker
checkpoint-status |  |  | checkpoint | Lap Lengths Checked & Approved
boolean | 6a31c4ba-3fea-462e-88b8-2e60e7299300 |  | tickbox | Checked by Prefabricator
boolean | cfc054cf-3d38-41d1-928a-3ddf8ebc9ff3 |  | tickbox | Checked by Steel & Tube Checker
checkpoint-status |  |  | checkpoint | Sufficient Tie Wire Securing Bars Checked & Approved
boolean | fa8c0aa6-7d4c-491b-91fd-9e576b313276 |  | tickbox | Checked by Prefabricator
boolean | 284ff03f-eb1d-4582-9d38-c72bd4b23f2a |  | tickbox | Checked by Steel & Tube Checker
checkpoint-status |  |  | checkpoint | Offcuts / Surplus Tie Wire Removed
boolean | d262411a-171b-43e4-baad-a69fa5894418 |  | tickbox | Checked by Prefabricator
boolean | b7f90cea-b5fa-44e7-858d-a8e67a7a2d38 |  | tickbox | Checked by Steel & Tube Checker
checkpoint-status |  |  | checkpoint | Tie Wire Pointing Inwards
boolean | 5bcfe2dd-b616-4848-93b4-bef5d55f013c |  | tickbox | Checked by Prefabricator
boolean | bac0cacd-c477-4d4c-8adb-4e0989c26b3d |  | tickbox | Checked by Steel & Tube Checker
checkpoint-status |  |  | checkpoint | Welding complete
boolean | dcbc9ce5-8333-419f-8204-edc2c264f77a |  | tickbox | Checked by Prefabricator
boolean | 853a8213-c081-4b8b-bbc6-768ca468fd26 |  | tickbox | Checked by Steel & Tube Checker
checkpoint-status |  |  | checkpoint | Welding Inspected
boolean | 285ac887-fab2-40fe-9b9a-d7127a7415ff |  | tickbox | Checked by Prefabricator
boolean | 5ee99bc0-1b25-420d-9281-5e54a1582d87 |  | tickbox | Checked by Steel & Tube Checker
text | 9c53b16b-84fc-463e-9760-dab6c5c688f9 |  | textbox | Welding Inspection By:
text | a7d17272-6ae3-4e9a-b042-429e0d3e753e |  | textbox | Welding Inspection Date:
text | 7400eaa3-0f8c-4526-afbc-9faeb48ab0b9 |  | textbox | Delivery Docket No:
text | 9701d3a3-9a02-40b8-ac7d-55141e33ec63 |  | textbox | Delivery Date:
text | 87e5ae6e-c6d1-4fdc-a336-6546362907a3 |  | textbox | Delivery By:
checkpoint-group |  |  | section | Handover
checkpoint-status |  |  | checkpoint | Area left clean, neat and tidy
holdpoint |  |  | signoff | Request fabricator Signoff
checkpoint-status |  |  | checkpoint | Area completed as per required specifications, attached min 4 photos for reference
holdpoint |  |  | signoff | Request Contractor Acceptance
checkpoint-status |  |  | checkpoint | Signature Required
holdpoint |  |  | signoff | Signature Request
folder-normal |  | Not allowed as a child of checklist-sectioned. | folder-normal | Observations
checklist-sectioned |  |  | checklist | Area: |  |  |  |  | Yes | Area: | 30978e0f-863c-4144-b25b-2378d7367654
checkpoint-group |  |  | section | Drawings, Detail sheets & General Notes
checkpoint-status |  |  | checkpoint | Attach document
checkpoint-group |  |  | section | Workface Diary
checkpoint-status |  |  | checkpoint | Start date
checkpoint-status |  |  | checkpoint | Safe and suitable access provided by H.C. at workface (attach photos)
checkpoint-status |  |  | checkpoint | Scaffold tagged, Stairs and safety railing inspected, no openings to floors (attach photos)
checkpoint-status |  |  | checkpoint | Cranage arranged or reinforcement at workface
checkpoint-status |  |  | checkpoint | Grid lines set out by H.C. at workface and visible
checkpoint-status |  |  | checkpoint | Datums provided by H.C. at workface and visible
checkpoint-status |  |  | checkpoint | Site concrete poured
checkpoint-status |  |  | checkpoint | Formwork installed to minimum 1 face
checkpoint-status |  |  | checkpoint | Tanking, waterproofing complete
checkpoint-status |  |  | checkpoint | All cast in items set out or in place (Hold down bolts, Weld plates, plumbing etc)
checkpoint-status |  |  | checkpoint | Starting point for Precast foundation starters set out by H.C.
checkpoint-status |  |  | checkpoint | Couplers, Threaded inserts cleaned out and prepared by H.C.
checkpoint-status |  |  | checkpoint | Is there any uncompleted work by the H.C. that will hinder the progress of your work?
checkpoint-status |  |  | checkpoint | All pre install checks completed and approved - Ready to start work
checkpoint-group |  |  | section | Reinforcing QA checks
checkpoint-status |  |  | checkpoint | Specified covers checked/correct (attach photos)
checkpoint-status |  |  | checkpoint | Cover blocks (attach photos)
checkpoint-status |  |  | checkpoint | Size, position & spacing of reinforcement as per drawing (attach photos)
checkpoint-status |  |  | checkpoint | Lap lengths and locations as per drawing (attach photos)
checkpoint-status |  |  | checkpoint | Correct stirrup sets
checkpoint-status |  |  | checkpoint | Horizontal / Vertical starter bars installed correctly (Location, position, size, spacing) attach photos
checkpoint-status |  |  | checkpoint | Reid bars tightened in full with wrench
checkpoint-status |  |  | checkpoint | Couplers, Threaded inserts, Foot plates installed correctly (Location, position, size, spacing)
checkpoint-status |  |  | checkpoint | All reinforcement tied, secured and rigid
checkpoint-status |  |  | checkpoint | Any additional items considered, installed & completed e.g. trimmer bars, drag bars etc
checkpoint-status |  |  | checkpoint | All excess reinforcing, tie wire and debris removed - clean & tidy
checkpoint-status |  |  | checkpoint | Completion date
checkpoint-group |  |  | section | Handover to HC
checkpoint-status |  |  | checkpoint | QA complete, area left clean and tidy
checkpoint-status |  |  | checkpoint | Work completed as per drawing and specifications
holdpoint |  |  | signoff | Steel & Tube Sign off
checkpoint-status |  |  | checkpoint | Accepted and approved for concrete by H.C. (attach 4 photos)
holdpoint |  |  | signoff | HC Sign off
checklist-flat |  |  | checklist | Demonstrate Knowledge of (DKO) |  |  |  |  | Yes | Add Demonstrate Knowledge of (DKO) | 49afd7c2-e6d5-4e0f-a54b-4031073280fc
text | f4130b31-afa2-4bce-a8dc-fbd99613c79f | Data not allowed on checklist-flat. | textbox | Employee's Name:
text | 395f67d7-e8f9-45cb-8530-deaa908b5b32 | Data not allowed on checklist-flat. | textbox | Assessor's Name:
text | 929502ea-df0f-4bc6-8653-13f852439a4e | Data not allowed on checklist-flat. | textbox | Position:
text | 6a06d55f-31d2-4173-b715-cb3bab195dcf | Data not allowed on checklist-flat. | textbox | What is the task?
label | cb844f62-30f0-4ab5-90ce-c94927fe9df2 | Data not allowed on checklist-flat. | note | Performance Requirements - based on SOP or JSA
text | 65583157-961b-4372-9f33-74122f316d44 | Data not allowed on checklist-flat. | textbox | Name of SOP or JSA
checkpoint-status |  |  | checkpoint | The employee understands not to operate any plant or equipment unless signed off as competent or he/she is being trained to operate plant or equipment under supervision.
text | 52e0a5f6-8d6e-452a-a464-cd28fe8beda1 |  | textbox | Date:
text | a14fa3a5-26c5-402c-a411-066db56662d5 |  | textbox | Employee's Name:
text | 342979f4-b963-4820-9807-eede98b6c4fc |  | textbox | Assessor's Name:
text | 45f6d051-b6d8-42f5-b8b5-5cfcb583030c |  | textbox | Position:
checkpoint-status |  |  | checkpoint | Employee identifies the hazards:
checkpoint-status |  |  | checkpoint | Employee explains the safe operating controls:
checkpoint-status |  |  | checkpoint | Employee performs the task(s) safely in line with the controls:
radio | e96d0331-f731-43b6-8797-d257eb5fd306 |  | radio | Assessor Assessment | Competent,Not yet Competent
text | 8fb8d6cc-454a-4260-b4f3-853f3c917c22 |  | textbox | Assessor Comments
checklist-flat |  |  | checklist | Variation Details - |  |  |  |  | Yes | Add Variation | 1b9c108e-9f96-47e5-bd13-a2ba1d6e98b8
checkpoint-status |  |  | checkpoint | Variation Details Approved
text | 28d26279-c304-4689-8317-1deb797dc8fe |  | textbox | Reference/Drawing/Instruction Number
text | 2247155b-6de8-434c-a1e1-058d724a6a62 |  | textbox | Variation Area
text | ae7fc046-dca9-4fab-98f8-374caeb044ec |  | textbox | Materials & labour breakdown
holdpoint |  |  | signoff | Request Variation Acknowledgement
checkpoint-no-status |  |  | checkpoint | Staff & Time Details
text | bc9e0873-f032-484d-86a6-d3dfa4709a87 |  | textbox | Total number of staff involved
text | 994d6c3a-86bd-474a-ac6e-5f5b1ebbb2a6 |  | textbox | Total hours taken to do the work
label | 31a6bfbb-61f2-4a45-b21a-476d0cd8db83 |  | note | Once staff and time details are inputted above please attach client approval and signoff (click the paperclip below)
checkpoint-status |  |  | checkpoint | Variation Completed
holdpoint |  |  | signoff | Request Variation Signoff
checklist-sectioned |  |  | checklist | Toolbox Checklist |  |  |  |  | Yes | H&S - Toolbox Talks | b45b1326-7741-4815-b9c7-7b4e1e7e1c72
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details Complete
text | 305f2185-4e3a-4417-ae95-885bb0b1de8a |  | textbox | Office location:
text | b2fd07dc-8f92-4010-8a71-46e71c03ff63 |  | textbox | Who is running this meeting:
text | 1d3d0b15-a56a-498c-b16b-2afa5f8e2573 |  | textbox | Company
text | 88e78785-0eea-4ad8-a896-1622379eacfc |  | textbox | Agenda items:
text | ce0224f5-54b8-47a5-b890-7a5416c69623 |  | textbox | Theme of the week (topic for focus):
checkpoint-group |  |  | section | Health and safety issues
checkpoint-status |  |  | checkpoint | 1.
text | 2ec0fc9e-b14f-43a5-bb60-4df5d5ab3ab4 |  | textbox | Issues raised from site safety inspection:
text | 1b5fcc97-f30c-4727-a783-29c22206fa41 |  | textbox | Actions:
text | b5107b7c-d991-4507-a1a9-6180db10057c |  | textbox | By who and when:
checkpoint-status |  |  | checkpoint | 2.
text | 8978adff-e266-4646-b125-178fba33a0dd |  | textbox | Issues outstanding from previous briefings:
text | 507afe6b-4ee7-4485-bd4b-99698d8e8f47 |  | textbox | Actions:
text | 7d92f59d-ce24-4ec9-8428-a92c87f559e3 |  | textbox | By who and when:
checkpoint-status |  |  | checkpoint | 3.
text | 305b3039-3f3d-45b4-8536-fb028ee2010b |  | textbox | Employee-raised issues:
text | c98f50a5-1fb4-45b7-86e0-301132ec8b7c |  | textbox | Actions:
text | c250b53e-5070-459c-b01f-af8fcce5cdb7 |  | textbox | By who and when:
checkpoint-status |  |  | checkpoint | 4.
text | 26f6b1aa-3048-4106-a64b-dc4e2cf75ec3 |  | textbox | Positive safe-action observations:
text | dd2ab926-5b94-46f6-a93f-eed5fa00233e |  | textbox | Actions:
text | 464cc30b-c155-4299-b08c-242a1821bd72 |  | textbox | By who and when:
checkpoint-status |  |  | checkpoint | 5.
text | ba0166ff-1cef-49fe-a54e-fce60528feea |  | textbox | Incidents or injuries:
text | 8f9035d5-30e5-4ea2-9ec4-4d19df05b3fd |  | textbox | Actions:
text | 1a84fee3-7466-42bd-a3ff-39c2785201a3 |  | textbox | By who and when:
checkpoint-group |  |  | section | Job plans reviewed
checkpoint-status |  |  | checkpoint | Job/Task & Action/Outcome
text | cb9c1ca7-7b79-4c62-8f74-3a1d70af5886 |  | textbox | 1.
text | d396585a-1ce3-4d1e-b838-375ab4165dd0 |  | textbox | 2.
text | 4657beed-8141-41c2-926d-0d7204a497a2 |  | textbox | 3.
text | 1e162112-08ad-40c3-9d33-6c4bac52a906 |  | textbox | 4.
text | fd629f21-4050-47b3-b236-26daf8c94903 |  | textbox | 5.
text | a08ea05c-aa58-425b-9cb6-e2fa8951a414 |  | textbox | 6.
checkpoint-group |  |  | section | Operational issues
checkpoint-status |  |  | checkpoint | Issue & Action
text | 301f9ad4-6682-45c0-aa57-7b074b0e8a13 |  | textbox | 1.
text | 1373bee6-816f-408a-97a0-72f99b461b6e |  | textbox | 2.
text | c487e999-fa82-493c-b540-e056d94778fb |  | textbox | 3.
text | 5341a99d-52f8-4c86-8e11-6e8adfb0627e |  | textbox | 4.
text | 8e55092c-df52-43d0-b019-a8e67550ae09 |  | textbox | 5.
text | b87136a8-71c4-41f7-9cdb-74d4b55b5521 |  | textbox | 6.
checkpoint-group |  |  | section | Other business
checkpoint-status |  |  | checkpoint | Item & Action
text | 2e63def1-4462-4998-b972-d5125960181e |  | textbox | 1.
text | 044404a1-6065-4d33-8f96-7da9ab2eaf3a |  | textbox | 2.
text | 1e321545-4537-44dd-9443-3ae2c58d572b |  | textbox | 3.
text | e3214f18-5e4b-42bf-856b-435adffda167 |  | textbox | 4.
checkpoint-group |  |  | section | Attendees
checkpoint-status |  |  | checkpoint | Add name and Photo of attendees
checkpoint-group |  |  | section | Review by management
checkpoint-status |  |  | checkpoint | Reviewed and signed off
text | 054479d9-523d-4c50-88ce-626d6600059d |  | textbox | 1.
text | e1ea14ce-04e9-4c55-b0e6-131f75ee169d |  | textbox | 2.
checklist-flat |  |  | checklist | Date / Details - |  |  |  |  | Yes | Add Delivery | 97fe7ecb-0eef-41d2-b941-862611689d07
checkpoint-status |  |  | checkpoint | Photo of the all material tags attached
checkpoint-status |  |  | checkpoint | Material Verified and correct
checkpoint-status |  |  | checkpoint | All control codes recorded individually and photographed
text | e7feda4d-7c07-4a87-a996-2530d63d1735 |  | textbox | Control codes specified individually below:
text | f0a5dbc3-adf6-4e56-815d-3efb4015c1bf |  | textbox
text | 1d261350-6ea1-4d6c-8778-36c4bfa5d8e2 |  | textbox
text | 1c6b1756-4105-497b-b64f-1eb234d98b40 |  | textbox
text | 71022f24-529f-44bc-a30b-dff10d9a83de |  | textbox
text | 953c4aa5-0dd9-4d1a-b7ab-4bb4c7c8c0a0 |  | textbox
checkpoint-status |  |  | checkpoint | Stored/stacked in appropriate location
checklist-flat |  |  | checklist | Near Miss - |  |  |  |  | Yes | H&S - Near Miss Report | b19330f6-f60f-4530-8726-d6c0fcecc9f2
checkpoint-status |  |  | checkpoint | Near Miss Details Recorded
text | d1aae015-767b-4094-9e33-cc08af06fb28 |  | textbox | Area:
text | 3fa29c0c-943f-4ebd-8157-39f93cc23f43 |  | textbox | Time:
text | 7142aa3b-8f0e-493f-855b-714cdbd121eb |  | textbox | Date
label | 04a03143-a927-4a21-94ab-58fe526bea79 |  | note | Mark All Appropriate Conditions
boolean | 10d7a4bc-c881-4309-8f85-413e0bf8a4c2 |  | tickbox | Near Miss
boolean | e127552a-b748-4ea3-ab8a-b4dbe637b07a |  | tickbox | Safety Concern
boolean | 84da0ab9-b476-4f63-96d1-28caf734be3c |  | tickbox | Safety Suggestion
boolean | eaacee57-2998-4b87-840d-1df9b1aa280e |  | tickbox | Other
text | 8313515a-48a4-46ad-aa58-fbec2129df4c |  | textbox | Describe Other:
label | e5729c93-ad01-4c3b-ab6a-4d2889924281 |  | note | Type of Concern
boolean | 27906794-0c73-49cb-8ef6-f49dd6eeb3b8 |  | tickbox | Unsafe Act
boolean | d24214af-1253-4c2d-bec3-3beccba62ef5 |  | tickbox | Unsafe Condition of Area
boolean | 741eaeb4-6684-40f4-a036-0dc3dae3c11f |  | tickbox | Unsafe Condition of Equipment
boolean | 24309c0a-cca2-4c95-aad7-f1c81959a544 |  | tickbox | Unsafe Use of Equipment
boolean | 261f6faf-3b2c-46f2-ae18-e2ad6aded2de |  | tickbox | Other
text | de62b064-8f7e-45f4-8f3c-91088ac1c279 |  | textbox | Describe Other:
label | 057efcc8-2505-4268-9b95-9de97d2f675c |  | note | Please Tick All Items Relating To Near-Miss Below
boolean | 7308f129-3b1f-49ac-94c3-da7ee4e135a4 |  | tickbox | Slip/Trip & Fall
boolean | 8af46b10-10ce-4883-ab93-f6f4fc153a1a |  | tickbox | Falling Object
boolean | 584e6c17-fb00-4182-8dc6-64a1eedeb49c |  | tickbox | House Keeping
boolean | 3216bef4-a7ab-4351-8bb5-d15afb299efc |  | tickbox | Restricted Access
boolean | 3177a73d-a120-4b84-a334-62961e05342a |  | tickbox | Working at Height
boolean | 52d77b93-11f6-4d58-b44f-f4453a86c525 |  | tickbox | PPE
boolean | b01dca54-2964-4813-83bd-994313457d65 |  | tickbox | Manual Lifting
boolean | 48b02fb5-1ce7-4995-be53-ae4086f5d8a9 |  | tickbox | Lifting Operations
boolean | 738795e2-1e78-461e-94e6-9b797019ee9a |  | tickbox | Confined Space
boolean | f042c6c2-f270-4bcb-8dda-20584752b16e |  | tickbox | Excavations
boolean | bc1962ea-d1f6-410e-b6c9-d799e3cce27b |  | tickbox | Environment
boolean | 044fff31-d6d8-4d0a-af18-a45371d7fa5e |  | tickbox | Plant & Equipment
boolean | 746db4c1-da40-47fd-8072-ece76451ca84 |  | tickbox | Vehicles
boolean | a1a082ac-c149-42f9-a59c-82d5a4a971d5 |  | tickbox | Utilities
boolean | a50abeb5-4b65-49c9-a99b-f3a4d044b3bf |  | tickbox | Other
text | 8a893d6e-c62c-482b-b680-35bb23181fda |  | textbox | Describe Other:
text | 3c4eb72c-c46b-4f09-b967-b0cd0d932a72 |  | textbox | Describe the Potential Incident/Hazard/Concern and Possible Outcome (In as much possible detail)
text | 05d4df75-3a84-4f94-86fa-b9c9d6c59beb |  | textbox | Safety Suggestion:
checkpoint-status |  |  | checkpoint | Near Miss Incident report reviewed and closed out