## Project Breakdown
Tire 1 | Tire 2 | Tire 3 | Tire 4 | Tire 5
Miriam Corban(Steel Fab)
QA
B05
Structural steel Installation
|  |  |  | Level 1 | Pre-populate | ST - S - Structural Steel Installation - Pre-Commencement
[5 empty] | Pre-populate | ST - S - Structural Steel Installation
|  |  |  | Roof | Pre-populate | ST - S - Structural Steel Installation - Pre-Commencement
[5 empty] | Pre-populate | ST - S - Structural Steel Installation
|  |  | Steel Paint QA Documents |  | Pre-populate | ST - S - Steel Paint QA Documents
|  |  | Handover Documents |  | Pre-populate | ST - S - Steel Handover Documents - SFC Accredited and Non-SFC Contractors

## Sheet2
Type | Name | Value
checklist | ST - S - Structural Steel Installation - Pre-Commencement
section | Steel Delivery
checkpoint | Corrosion protection accepatble
checkpoint | GA Building Plans Attached
checkpoint | Numbers stamped / ID tags attached
section | Erection
checkpoint | Grid Lines marked for Set out and acceptable
checkpoint | Wall heights marked and checked and acceptable
checkpoint | Walls plumb / cast in plates correct and acceptable
checkpoint | Base plate / top plate orientation are correct and all bolts to base plates in place and tight and acceptable
checklist | ST - S - Structural Steel Installation
section | Pre-commencement
checkpoint | Hold down bolts in the correct location
checkpoint | Pre erection checks complete
section | Installation
checkpoint | Steel correct size and type
checkpoint | Welding certificates sited
checkpoint | Installed in the correct location and orientation
checkpoint | Installed in corrct level, plumb, correct pitch and braced
checkpoint | All bolts secure/ correctly tensioned
checkpoint | All structural steel correctly installed in respective area and acceptable
section | Post-Installation
checkpoint | Welding Visual/Scanning inspections completed
checkpoint | Chemical anchor proof tests conducted on the sample selected by the MV Engineer
bool | Chemical anchors are tested to 0.7xdesign load
bool | The test load of the bar is provided by the MV Engineer
bool | Proof load tests maintained for a minimum of 30 seconds
bool | The load did not drop more than 10% during the testing
checkpoint | If the proof of tests show failure of the anchors, installation of anchors should stop, cause of failure investigated and installation methodology should be reviewed. If failure is recorded, the minimum test sample shall be increased to 6 specimens or 5% of the total relevant anchor population, whichever is greater.
checkpoint | Mechanical anchor testing conducted on the sample selected by the MV Engineer and witnessed by the MV Engineer
bool | For trubolt or similar anchors the maximum tightening torque is reviewed
checkpoint | If the proof of tests show failure of the anchors, installation of anchors should stop, cause of failure investigated and installation methodology should be reviewed. If failure is recorded, the minimum test sample shall be increased to 6 specimens or 5% of the total relevant anchor population, whichever is greater.
checklist | ST - S - Roof structure - Steel
section | Pre-commencement
checkpoint | Hold down bolts in the correct location
checkpoint | Pre erection checks complete
section | Installation
checkpoint | Steel correct size and type
checkpoint | Welding certificates sited
checkpoint | Installed in the correct location and orientation
checkpoint | Installed in corrct level, plumb, correct pitch and braced
checkpoint | All bolts secure/ correctly tensioned
checkpoint | All structural steel correctly installed in respective area and acceptable
checklist-flat | ST - S - Steel Paint QA Documents
checkpoint | Paint QA Documents, Uploaded and all supporting documentation attached
signoff | Raise Remedial / Request Signoff
Checklist-flat | ST - S - Steel Handover Documents - SFC Accredited and Non-SFC Contractors
Checkpoint | Provide PS3 – Construction from the fabricator and erector.
Checkpoint | Copy of ITP checklist
Checkpoint | Steel source list and declaration of conformity
Checkpoint | Bolts Docs - to verify compliance to relevant standards
Checkpoint | Subcontractor SFC certification
Checkpoint | Steel erection sequence methodology
Checkpoint | Bolt installation inspection record, including any that differ from design or not fully documented.
Checkpoint | Detail of proposed markings if members and/or connections are to exposed to view. (only applicable for Architecturally Exposed Structural Steel, AESS)
Checkpoint | Survey erected structural steelwork. (AC steelwork survey work document)