## QA Folder Structure
QA Folder Structure |  |  | Checklists | Product
Site QA
Basement 1
|  | Fire Pump Room | 3 Coat Checklist
|  | Future Hydrant Water Storage Tanks | PVC Tanks Checklist
|  | Recycle & Waste Room | 3 Coat Checklist
Ground
|  | W/C | 3 Coat Checklist
|  | Pool Deck | 3 Coat Checklist
|  | Pool House, BBQ Area & Pool Amenities Roof | 3 Coat Checklist
|  | Pool House, BBQ Area & Pool Amenities Planters | 3 Coat Checklist
|  | Pool House, BBQ Area & Pool Amenities Block Wall | 3 Coat Checklist
|  | Pool House Pool Pump/ Store Room/ Mech Switch Board | 3 Coat Checklist
|  | Pool Structure | 3 Coat Checklist
|  | Entry Pool Fountain | 3 Coat Checklist
|  | External Tiled Areas | 3 Coat Checklist
|  | Planter Boxes | 3 Coat Checklist
|  | Bin Store/ Washout/ Cleaners Room | 3 Coat Checklist
|  | Entry Fire Stair Lid/Roof | 3 Coat Checklist
Apartments
|  | Wet Areas | 3 Coat Checklist
|  | Window & Door Reveals | 3 Coat Checklist
|  | Balconies | 3 Coat Checklist
|  | Planter Boxes L1 | 3 Coat Checklist
|  | Water Meter Cupboard/Service Rooms | 3 Coat Checklist
|  | Entry Fire Stair Lid | 3 Coat Checklist
Rooftop
|  | Exposed Concrete Roof, Lift Lid & Fire Stair Lid | 3 Coat Checklist

## Copy of ITPs Checklists
type | name | values | prefix | postfix
checklist-flat | 3 Coat Checklist
checkpoint | Surface conditions suitable for installation - details in comments below
checkpoint | Moisture test complete - result in comments below
label | Must be below 5% to pass
checkpoint | Substrate inspected and accepted
label | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint | Application of Primer as per specification
checkpoint | Application of Caulking / Bond Breaker / Bandage (if required) completed
checkpoint | Application of membrane as per project specification - 1st Coat
select | Product Used | Mapei AquaDefense waterproofing membrane,Waterstop Angle,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint | Application of reinforcement sheet (if pedestal pavers)
checkpoint | Application of membrane as per project specification - 2nd Coat
select | Product Used | Mapei AquaDefense waterproofing membrane,Waterstop Angle,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint | Application of membrane as per project specification - 3rd Coat
select | Product Used | Mapei AquaDefense waterproofing membrane,Waterstop Angle,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint | Additional products / elements installed - selected all that apply below
select | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell
select | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell
select | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell
checkpoint | Final DFT Thickness of Membrane
checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
checkpoint | Test 1 Flood Test
checkpoint | Works completed, area Tidy - builder signature attached below if applicable
checklist-flat | 2 Coat Checklist
checkpoint | Surface conditions suitable for installation - details in comments below
checkpoint | Moisture test complete - result in comments below
label | Must be below 5% to pass
checkpoint | Substrate inspected and accepted
label | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint | Application of Primer as per specification
label | Cementious Coving completed (if required)
checkpoint | Application of Caulking / Bond Breaker / Bandage (if required) completed
checkpoint | Application of membrane as per project specification - 1st Coat
select | Product Used | Mapei AquaDefense waterproofing membrane,Waterstop Angle,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint | Application of membrane as per project specification - 2nd Coat
select | Product Used | Mapei AquaDefense waterproofing membrane,Waterstop Angle,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint | Additional products / elements installed - selected all that apply below
select | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell
select | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell
select | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell
checkpoint | Final DFT Thickness of Membrane
checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
checkpoint | Test 1 Flood Test Pass/Fail
checkpoint | Works completed, area Tidy - builder signature attached below if applicable
checklist-flat | Screed Checklist
checkpoint | Mixing of Topcem Pronto
checkpoint | Application of Topcem Pronto
checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
checkpoint | Works completed, area Tidy - builder signature attached below if applicable
checklist-flat | PVC Tanks Checklist
checkpoint | Surface conditions suitable for installation - details in comments below
checkpoint | Moisture test complete - result in comments below
label | Must be below 5% to pass
checkpoint | Substrate inspected and accepted
label | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint | Application of Geofabric to substrate
checkpoint | Application of PVC Sheet Membrane
checkpoint | PVC Sheet Membrane detailing as required
checkpoint | Final Walk over and inspection by main contractor, Supplier and Appliactor if Applicable.
checkpoint | Test 1 Probe Test
checkpoint | Test 2 Air Test Test (if double seam weld is done otherwise revert test 1)
checkpoint | Works completed, area Tidy - builder signature attached below if applicable