## Sheet1
Inspection Test Plan - Waterproofing
The Superseal Group (QLD) Pty Ltd supervisor to complete and issue to Builder prior to handover
Project Details
ITP Ref. No: | Rev Date: |  |  | Rev No:
Project Name: |  | Project Location:
Description of works: |  |  |  |  | Job Number:
Building / Level & Grid Reference : | Inspection: |  | NAME:
Area: |  |  | DATE:
Activity |  |  | Completed |  | Builder Witness Point | SSQLD Sign off
Ambient Conditions ('C)
Surface Temperature: pass Dew Point: pass Moisture Test %: below 5% pass RH %: pass
Substrate has fall is sound and accepted. Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
Application of Primer as per specification
Application of Caulking and or Bandage (if required) completed
Application of membrane as per project specification - 1st Coat
Application of reinforcement sheet (if pedestal pavers)
Application of membrane as per project specification - 2nd Coat
Application of membrane as per project specification - 3rd Coat
Final DFT Thickness of Membrane
Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
Test 1 Flood Test Pass/Fail?
Comments / Photos:
Builder Final Inspection
Name:
Signature: |  |  |  | Date:
SSQLD Final Inspection
Name:
Signature: |  |  |  | Date: