## Master ITPs Checklists
type | name | values | prefix | postfix
checklist-flat | 3 Coat Checklist
checkpoint | Surface conditions suitable for installation - details in comments below
checkpoint | Moisture test complete - result in comments below
label | Must be below 5% to pass
checkpoint | Substrate inspected and accepted
label | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint | Application of Primer as per specification
checkpoint | Application of Caulking / Bond Breaker / Bandage (if required) completed
checkpoint | Application of membrane as per project specification - 1st Coat
select | Product Used | Mapei AquaDefense waterproofing membrane,Waterstop Angle,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N,Primer SN,Mapeflex PU,Mapecoat PU,Aquaflex WPU,Penetron Blockseal
checkpoint | Application of reinforcement sheet (if pedestal pavers)
checkpoint | Application of membrane as per project specification - 2nd Coat
select | Product Used | Mapei AquaDefense waterproofing membrane,Waterstop Angle,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N,Primer SN,Mapeflex PU,Mapecoat PU,Aquaflex WPU,Penetron Blockseal
checkpoint | Application of membrane as per project specification - 3rd Coat
select | Product Used | Mapei AquaDefense waterproofing membrane,Waterstop Angle,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N,Primer SN,Mapeflex PU,Mapecoat PU,Aquaflex WPU,Penetron Blockseal
checkpoint | Additional products / elements installed - selected all that apply below
select | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle,Penetron Penebar SW55
select | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle,Penetron Penebar SW55
select | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle,Penetron Penebar SW55
checkpoint | Final DFT Thickness of Membrane
checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
checkpoint | Test 1 Flood Test
checkpoint | Works completed, area Tidy - builder signature attached below if applicable
checklist-flat | 2 Coat Checklist
checkpoint | Surface conditions suitable for installation - details in comments below
checkpoint | Moisture test complete - result in comments below
label | Must be below 5% to pass
checkpoint | Substrate inspected and accepted
label | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint | Application of Primer as per specification
label | Cementious Coving completed (if required)
checkpoint | Application of Caulking / Bond Breaker / Bandage (if required) completed
checkpoint | Application of membrane as per project specification - 1st Coat
select | Product Used | Mapei AquaDefense waterproofing membrane,Waterstop Angle,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N,Primer SN,Mapeflex PU,Mapecoat PU,Aquaflex WPU
checkpoint | Application of membrane as per project specification - 2nd Coat
select | Product Used | Mapei AquaDefense waterproofing membrane,Waterstop Angle,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N,Primer SN,Mapeflex PU,Mapecoat PU,Aquaflex WPU
checkpoint | Additional products / elements installed - selected all that apply below
select | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
select | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
select | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
checkpoint | Final DFT Thickness of Membrane
checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
checkpoint | Test 1 Flood Test Pass/Fail
checkpoint | Works completed, area Tidy - builder signature attached below if applicable
checklist-flat | Screed Checklist
checkpoint | Mixing of Topcem Pronto
checkpoint | Application of Topcem Pronto
checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
checkpoint | Works completed, area Tidy - builder signature attached below if applicable
checklist-flat | PVC Tanks Checklist
checkpoint | Surface conditions suitable for installation - details in comments below
checkpoint | Moisture test complete - result in comments below
label | Must be below 5% to pass
checkpoint | Substrate inspected and accepted
label | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint | Application of Geofabric to substrate
checkpoint | Application of PVC Sheet Membrane
checkpoint | PVC Sheet Membrane detailing as required
checkpoint | Final Walk over and inspection by main contractor, Supplier and Appliactor if Applicable.
checkpoint | Test 1 Probe Test
checkpoint | Test 2 Air Test Test (if double seam weld is done otherwise revert test 1)
checkpoint | Works completed, area Tidy - builder signature attached below if applicable

## Sandbar ITP
QA Folder Structure |  |  | Checklists
Site QA
Basement 1
|  | WASTE ENCLOSURE | 3 Coat Checklist
|  | CABLE CLOSET | 3 Coat Checklist
Basement 3
|  | LIFT PIT | 3 Coat Checklist
Level 1
|  | SPRINKLER & PUMP CONTROL ROOM | 3 Coat Checklist
|  | FIRE CONTROL ROOM | 3 Coat Checklist
|  | MAILBOXES | 3 Coat Checklist
|  | TEMP WASTE | 3 Coat Checklist
|  | PLANTERS | Planter ITP
|  | CAFÉ PWDR | Waterproofing Installation Checklist
Level 2
|  | PLANT | 3 Coat Checklist
|  | POOL HEATER | 3 Coat Checklist
|  | POOL EQUIP | Waterproofing Installation Checklist
|  | PWD BATH | Waterproofing Installation Checklist
|  | CLEANERS | Waterproofing Installation Checklist
|  | STORE ROOM 4 | 3 Coat Checklist
|  | SPK HYD TANK | PVC Tanks Checklist
|  | SPK HYD TANK | PVC Tanks Checklist
|  | BALCONY | Balcony ITP
Level 3
|  | PLANT | 3 Coat Checklist
|  | STORE ROOM 1 | 3 Coat Checklist
|  | STORE ROOM 2 | 3 Coat Checklist
|  | STORE ROOM 3 | Balcony ITP
|  | BALCONY | 3 Coat Checklist
|  | ENS 2A.08 | Waterproofing Installation Checklist
|  | ENS 2A.06 | Waterproofing Installation Checklist
|  | L'DRY | Waterproofing Installation Checklist
|  | L'DRY | Waterproofing Installation Checklist
|  | ENS 2B.08 | Waterproofing Installation Checklist
|  | ENS 2B.07 | Waterproofing Installation Checklist
|  | ENS 2C.07 | Waterproofing Installation Checklist
|  | ENS 2C.08 | Waterproofing Installation Checklist
|  | L'DRY | Waterproofing Installation Checklist
|  | ENS 2D.07 | Waterproofing Installation Checklist
|  | L'DRY | Waterproofing Installation Checklist
|  | BATH 2D.08 | Waterproofing Installation Checklist
|  | BATH 2Dm.08 | Waterproofing Installation Checklist
|  | L'DRY | Waterproofing Installation Checklist
|  | ENS 2Dm.07 | Waterproofing Installation Checklist
Level 4-26
|  | PLANT | Planter ITP
|  | BATH | Waterproofing Installation Checklist
|  | ENS | Waterproofing Installation Checklist
|  | L'DRY | Waterproofing Installation Checklist
|  | L'DRY | Waterproofing Installation Checklist
|  | BATH | Waterproofing Installation Checklist
|  | ENS | Waterproofing Installation Checklist
|  | L'DRY | Waterproofing Installation Checklist
|  | BATH | Waterproofing Installation Checklist
|  | ENS | Waterproofing Installation Checklist
|  | ENS | Waterproofing Installation Checklist
|  | BATH | Waterproofing Installation Checklist
|  | L'DRY | Waterproofing Installation Checklist
|  | ENS | Waterproofing Installation Checklist
|  | L'DRY | Waterproofing Installation Checklist
|  | BATH | Waterproofing Installation Checklist
|  | BATH | Waterproofing Installation Checklist
|  | L'DRY | Waterproofing Installation Checklist
|  | ENS | Waterproofing Installation Checklist
|  | L'DRY | Waterproofing Installation Checklist
|  | BATH | Waterproofing Installation Checklist
|  | ENS | Waterproofing Installation Checklist
|  | ENS | Waterproofing Installation Checklist
|  | BATH | Waterproofing Installation Checklist
|  | L'DRY | Waterproofing Installation Checklist
|  | BALCONY | Balcony ITP
| ROOF |  | 3 Coat Checklist
| PLANT |  | 3 Coat Checklist