## ITP
QA Folder Structure |  |  | Checklists
Site QA
Lift Pit
|  | Base | 3 Coat Checklist
|  | Walls | 3 Coat Checklist
|  | Penetrations | Waterstop ITP
|  | Perimeter | Waterstop ITP
Basement
|  | Shotcrete Walls | 3 Coat Checklist
|  | Basement perimeter | Waterstop ITP
|  | Vertical Rearguard | Waterstop ITP
|  | Pile Caps | Waterstop ITP
|  | Deep Planting | 3 Coat Checklist
|  | Landscaped Planter | 3 Coat Checklist
|  | Refuse Store & Wash down area | 3 Coat Checklist
|  | Bins | 3 Coat Checklist
Ground Floor
|  | Deep Planting Zone | 3 Coat Checklist
|  | Landscaped planter | 3 Coat Checklist
|  | Pool | 3 Coat Checklist
|  | Shower and Sauna | 3 Coat Checklist
|  | Hydrant Cupboards | 3 Coat Checklist
|  | Booster | 3 Coat Checklist
|  | Sprinkler System Water Tank | PVC Tank Checklist
|  | Fire Pump Room | 3 Coat Checklist
|  | Exposed Terrace-Entrance | 3 Coat Checklist
|  | Exposed Terrace-Pool | 3 Coat Checklist
|  | Balcony | 3 Coat Checklist
Lower Ground-Level 1
|  | Landscaped Planter | 3 Coat Checklist
|  | Mech Plant Room | 3 Coat Checklist
|  | Hydrant Cupboards | 3 Coat Checklist
|  | Balcony | 3 Coat Checklist
Lower Ground-Level 2
|  | Landscaped Planter | 3 Coat Checklist
|  | Balcony | 3 Coat Checklist
|  | Hydrant Cupboards | 3 Coat Checklist
Level 1
|  | Concrete Roof | 3 Coat Checklist
|  | Landscaped Planter | 3 Coat Checklist
|  | Mech Plant | 3 Coat Checklist
|  | Balcony | 3 Coat Checklist
|  | Hydrant Cupboards | 3 Coat Checklist
Level 2-5
|  | Balcony | 3 Coat Checklist
|  | Hydrant Cupboards | 3 Coat Checklist
|  | Mech Plant | 3 Coat Checklist
Level 6
|  | Balcony | 3 Coat Checklist
|  | Hydrant Cupboards | 3 Coat Checklist
|  | Mech Plant | 3 Coat Checklist
Level 7
|  | Balcony | 3 Coat Checklist
|  | Hydrant Cupboards | 3 Coat Checklist
|  | Mech Plant | 3 Coat Checklist
Roof
|  | Roof Terrace | 3 Coat Checklist
|  | Planter | 3 Coat Checklist

## Master ITPs Checklists
type | name | values | prefix | postfix
checklist-flat | 3 Coat Checklist
checkpoint | Surface conditions suitable for installation - details in comments below
checkpoint | Moisture test complete - result in comments below
label | Must be below 5% to pass
checkpoint | Substrate inspected and accepted
label | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint | Application of Primer as per specification
checkpoint | Application of Caulking / Bond Breaker / Bandage (if required) completed
checkpoint | Application of membrane as per project specification - 1st Coat
select | Product Used | Mapei AquaDefense waterproofing membrane,Waterstop Angle,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N,Primer SN,Mapeflex PU,Mapecoat PU,Aquaflex WPU,Penetron Blockseal,Primer 460,Hychem E100,Primer 230UV,WPA 992UV,Hychem Supafloor,WPA 230UV,WPA 500,WPA 200,Penetron Admix
checkpoint | Application of reinforcement sheet (if pedestal pavers)
checkpoint | Application of membrane as per project specification - 2nd Coat
select | Product Used | Mapei AquaDefense waterproofing membrane,Waterstop Angle,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N,Primer SN,Mapeflex PU,Mapecoat PU,Aquaflex WPU,Penetron Blockseal,Primer 460,Hychem E100,Primer 230UV,WPA 992UV,Hychem Supafloor,WPA 230UV,WPA 500,WPA 200,Penetron Admix
checkpoint | Application of membrane as per project specification - 3rd Coat
select | Product Used | Mapei AquaDefense waterproofing membrane,Waterstop Angle,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N,Primer SN,Mapeflex PU,Mapecoat PU,Aquaflex WPU,Penetron Blockseal,Primer 460,Hychem E100,Primer 230UV,WPA 992UV,Hychem Supafloor,WPA 230UV,WPA 500,WPA 200,Penetron Admix
checkpoint | Additional products / elements installed - selected all that apply below
select | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle,Penetron Penebar SW55
select | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle,Penetron Penebar SW55
select | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle,Penetron Penebar SW55
checkpoint | Final DFT Thickness of Membrane
checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
checkpoint | Test 1 Flood Test
checkpoint | Works completed, area Tidy - builder signature attached below if applicable
checklist-flat | 2 Coat Checklist
checkpoint | Surface conditions suitable for installation - details in comments below
checkpoint | Moisture test complete - result in comments below
label | Must be below 5% to pass
checkpoint | Substrate inspected and accepted
label | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint | Application of Primer as per specification
label | Cementious Coving completed (if required)
checkpoint | Application of Caulking / Bond Breaker / Bandage (if required) completed
checkpoint | Application of membrane as per project specification - 1st Coat
select | Product Used | Mapei AquaDefense waterproofing membrane,Waterstop Angle,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N,Primer SN,Mapeflex PU,Mapecoat PU,Aquaflex WPU,Penetron Blockseal,Primer 460,Hychem E100,Primer 230UV,WPA 992,Hychem Supafloor,WPA 230UV,WPA 500,WPA 200,Penetron Admix
checkpoint | Application of membrane as per project specification - 2nd Coat
select | Product Used | Mapei AquaDefense waterproofing membrane,Waterstop Angle,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N,Primer SN,Mapeflex PU,Mapecoat PU,Aquaflex WPU,Penetron Blockseal,Primer 460,Hychem E100,Primer 230UV,WPA 992,Hychem Supafloor,WPA 230UV,WPA 500,WPA 200,Penetron Admix
checkpoint | Additional products / elements installed - selected all that apply below
select | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
select | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
select | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
checkpoint | Final DFT Thickness of Membrane
checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
checkpoint | Test 1 Flood Test Pass/Fail
checkpoint | Works completed, area Tidy - builder signature attached below if applicable
checklist-flat | Screed Checklist
checkpoint | Mixing of Topcem Pronto
checkpoint | Application of Topcem Pronto
checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
checkpoint | Works completed, area Tidy - builder signature attached below if applicable
checklist-flat | PVC Tanks Checklist
checkpoint | Surface conditions suitable for installation - details in comments below
checkpoint | Moisture test complete - result in comments below
label | Must be below 5% to pass
checkpoint | Substrate inspected and accepted
label | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint | Application of Geofabric to substrate
checkpoint | Application of PVC Sheet Membrane
checkpoint | PVC Sheet Membrane detailing as required
checkpoint | Final Walk over and inspection by main contractor, Supplier and Appliactor if Applicable.
checkpoint | Test 1 Probe Test
checkpoint | Test 2 Air Test Test (if double seam weld is done otherwise revert test 1)
checkpoint | Works completed, area Tidy - builder signature attached below if applicable