## ITP
QA Folder Structure |  |  | Checklists
Site QA
Lift Pit
|  | Base and Walls | PVC Sheet Membrane Checklist
|  | Base and Walls | Waterstop-Penebar
Basement 01
|  | Mech Plant | Trafficable Liquid Membrane Checklist
|  | Mech Riser Store | Trafficable Liquid Membrane Checklist
Lower Ground
|  | Mech Intake | Trafficable Liquid Membrane Checklist
|  | Refuse Store | Trafficable Liquid Membrane Checklist
|  | Mech Plant | Trafficable Liquid Membrane Checklist
|  | Switch Room | Trafficable Liquid Membrane Checklist
|  | Comms/NBN | Trafficable Liquid Membrane Checklist
|  | Substation | Trafficable Liquid Membrane Checklist
|  | Mech Intake | Trafficable Liquid Membrane Checklist
|  | Gas Meters | Trafficable Liquid Membrane Checklist
Ground Floor
|  | Deep Bed Planting | Planters Checklist
|  | Exposed Forecourt | External Liquid Membrane Checklist
|  | Bike Stores | Trafficable Liquid Membrane Checklist
|  | EOT Female | Internal Wet Areas Checklist
|  | UAT | Internal Wet Areas Checklist
|  | EOT Male | Internal Wet Areas Checklist
|  | Cleaner | Internal Wet Areas Checklist
|  | Booster Cupboard | Internal Wet Areas Checklist
|  | Water Meter Assembly | Internal Wet Areas Checklist
Mezzanine
|  | FH/Sprinkler Tank | PVC Tanks Checklist
|  | Fire Pump Room | Trafficable Liquid Membrane Checklist
Level 1
|  | External Play Area | External Liquid Membrane Checklist
|  | Planters | Planters Checklist
|  | Exposed Forecourt | External Liquid Membrane Checklist
Level 2
|  | External Play Area | External Liquid Membrane Checklist
|  | Planters | Planters Checklist
|  | Exposed Forecourt | External Liquid Membrane Checklist
Level 3-7
|  | Male WC | Internal Wet Areas Checklist
|  | UAT | Internal Wet Areas Checklist
|  | Female WC | Internal Wet Areas Checklist
|  | CLNR | Internal Wet Areas Checklist
|  | Planters | Planters Checklist
Level 8
|  | Roof | External Liquid Membrane Checklist
| Upper Roof |  | External Liquid Membrane Checklist

## Master ITPs Checklists
type | name | values | prefix | postfix
checklist-flat | 3 Coat Checklist
checkpoint | Surface conditions suitable for installation - details in comments below
checkpoint | Moisture test complete - result in comments below
label | Must be below 5% to pass
checkpoint | Substrate inspected and accepted
label | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint | Application of Primer as per specification
checkpoint | Application of Caulking / Bond Breaker / Bandage (if required) completed
checkpoint | Application of membrane as per project specification - 1st Coat
select | Product Used | Mapei AquaDefense waterproofing membrane,Waterstop Angle,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N,Primer SN,Mapeflex PU,Mapecoat PU,Aquaflex WPU,Penetron Blockseal,Primer 460,Hychem E100,Primer 230UV,WPA 992,Hychem Supafloor,WPA 230UV,WPA 500,WPA 200
checkpoint | Application of reinforcement sheet (if pedestal pavers)
checkpoint | Application of membrane as per project specification - 2nd Coat
select | Product Used | Mapei AquaDefense waterproofing membrane,Waterstop Angle,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N,Primer SN,Mapeflex PU,Mapecoat PU,Aquaflex WPU,Penetron Blockseal,Primer 460,Hychem E100,Primer 230UV,WPA 992UV,Hychem Supafloor,WPA 230UV,WPA 500,WPA 200
checkpoint | Application of membrane as per project specification - 3rd Coat
select | Product Used | Mapei AquaDefense waterproofing membrane,Waterstop Angle,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N,Primer SN,Mapeflex PU,Mapecoat PU,Aquaflex WPU,Penetron Blockseal,Primer 460,Hychem E100,Primer 230UV,WPA 992,Hychem Supafloor,WPA 230UV,WPA 500,WPA 200
checkpoint | Additional products / elements installed - selected all that apply below
select | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle,Penetron Penebar SW55,Hydrophilic Waterstop
select | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle,Penetron Penebar SW55,Hydrophilic Waterstop
select | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle,Penetron Penebar SW55,Hydrophilic Waterstop
checkpoint | Final DFT Thickness of Membrane
checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
checkpoint | Test 1 Flood Test
checkpoint | Works completed, area Tidy - builder signature attached below if applicable
checklist-flat | 2 Coat Checklist
checkpoint | Surface conditions suitable for installation - details in comments below
checkpoint | Moisture test complete - result in comments below
label | Must be below 5% to pass
checkpoint | Substrate inspected and accepted
label | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint | Application of Primer as per specification
label | Cementious Coving completed (if required)
checkpoint | Application of Caulking / Bond Breaker / Bandage (if required) completed
checkpoint | Application of membrane as per project specification - 1st Coat
select | Product Used | Mapei AquaDefense waterproofing membrane,Waterstop Angle,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N,Primer SN,Mapeflex PU,Mapecoat PU,Aquaflex WPU,Penetron Blockseal,Primer 460,Hychem E100,Primer 230UV,WPA 992,Hychem Supafloor,WPA 230UV,WPA 500,WPA 200,Sika Sarnifil G410-15, MAPEI Mapeplan TU 2mm PVC Sheet Membrane
checkpoint | Application of membrane as per project specification - 2nd Coat
select | Product Used | Mapei AquaDefense waterproofing membrane,Waterstop Angle,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N,Primer SN,Mapeflex PU,Mapecoat PU,Aquaflex WPU,Penetron Blockseal,Primer 460,Hychem E100,Primer 230UV,WPA 992,Hychem Supafloor,WPA 230UV,WPA 500,WPA 200,Sika Sarnifil G410-15, MAPEI Mapeplan TU 2mm PVC Sheet Membrane
checkpoint | Additional products / elements installed - selected all that apply below
select | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle,Hydrophilic Waterstop
select | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle,Hydrophilic Waterstop
select | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle,Hydrophilic Waterstop
checkpoint | Final DFT Thickness of Membrane
checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
checkpoint | Test 1 Flood Test Pass/Fail
checkpoint | Works completed, area Tidy - builder signature attached below if applicable
checklist-flat | Screed Checklist
checkpoint | Mixing of Topcem Pronto
checkpoint | Application of Topcem Pronto
checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
checkpoint | Works completed, area Tidy - builder signature attached below if applicable
checklist-flat | PVC Tanks Checklist
checkpoint | Surface conditions suitable for installation - details in comments below
checkpoint | Moisture test complete - result in comments below
label | Must be below 5% to pass
checkpoint | Substrate inspected and accepted
label | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint | Application of Geofabric to substrate
checkpoint | Application of PVC Sheet Membrane
checkpoint | PVC Sheet Membrane detailing as required
checkpoint | Final Walk over and inspection by main contractor, Supplier and Appliactor if Applicable.
checkpoint | Test 1 Probe Test
checkpoint | Test 2 Air Test Test (if double seam weld is done otherwise revert test 1)
checkpoint | Works completed, area Tidy - builder signature attached below if applicable