## Folder Structure
Site QA
Unit Types
| Ground Floor |  | Entrance Lobby | Common Area Checklist
| Level 1 | Unit | 1A | Balcony Checklist
|  | Unit | 1B | Balcony Checklist
|  | Unit | 1C | Balcony Checklist
|  | Unit | 1D | Balcony Checklist
|  | Unit | 1E | Balcony Checklist
|  | Unit | 1F | Balcony Checklist
|  | Unit | 1G | Balcony Checklist
|  | Unit | 1H | Balcony Checklist
|  | Unit | 1J | Balcony Checklist
|  | Unit | 1K | Balcony Checklist
|  | Unit | 1L | Balcony Checklist
|  | Unit | 1P | Balcony Checklist
|  | Unit | 1Q | Balcony Checklist
|  | Unit | 1R | Balcony Checklist
|  | Unit | 1S | Balcony Checklist
|  | Unit | 1T | Balcony Checklist
|  | Unit | 1U | Balcony Checklist
|  | Unit | 1V | Balcony Checklist
|  | Unit | 1W | Balcony Checklist
|  | Unit | 1X | Balcony Checklist
|  | Unit | 1Y | Balcony Checklist
|  | Unit | 1Z | Balcony Checklist
| Level 2 | Unit | 2A | Balcony Checklist
|  | Unit | 2B | Balcony Checklist
|  | Unit | 2C | Balcony Checklist
|  | Unit | 2D | Balcony Checklist
|  | Unit | 2E | Balcony Checklist
|  | Unit | 2F | Balcony Checklist
|  | Unit | 2G | Balcony Checklist
|  | Unit | 2H | Balcony Checklist
|  | Unit | 2J | Balcony Checklist
|  | Unit | 2K | Balcony Checklist
|  | Unit | 2L | Balcony Checklist
|  | Unit | 2P | Balcony Checklist
|  | Unit | 2Q | Balcony Checklist
|  | Unit | 2R | Balcony Checklist
|  | Unit | 2S | Balcony Checklist
|  | Unit | 2T | Balcony Checklist
|  | Unit | 2U | Balcony Checklist
|  | Unit | 2V | Balcony Checklist
|  | Unit | 2W | Balcony Checklist
|  | Unit | 2X | Balcony Checklist
|  | Unit | 2Y | Balcony Checklist
|  | Unit | 2Z | Balcony Checklist
| Level 3 | Unit | 3A | Balcony Checklist
|  | Unit | 3B | Balcony Checklist
|  | Unit | 3C | Balcony Checklist
|  | Unit | 3D | Balcony Checklist
|  | Unit | 3E | Balcony Checklist
|  | Unit | 3F | Balcony Checklist
|  | Unit | 3G | Balcony Checklist
|  | Unit | 3H | Balcony Checklist
|  | Unit | 3J | Balcony Checklist
|  | Unit | 3K | Balcony Checklist
|  | Unit | 3L | Balcony Checklist
|  | Unit | 3M | Balcony Checklist
|  | Unit | 3N | Balcony Checklist
|  | Unit | 3P | Balcony Checklist
|  | Unit | 3Q | Balcony Checklist
|  | Unit | 3R | Balcony Checklist
|  | Unit | 3S | Balcony Checklist
|  | Unit | 3T | Balcony Checklist
|  | Unit | 3U | Balcony Checklist
|  | Unit | 3V | Balcony Checklist
|  | Unit | 3W | Balcony Checklist
|  | Unit | 3X | Balcony Checklist
| Level 4 | Unit | 4A | Balcony Checklist
|  | Unit | 4B | Balcony Checklist
|  | Unit | 4C | Balcony Checklist
|  | Unit | 4D | Balcony Checklist
|  | Unit | 4E | Balcony Checklist
|  | Unit | 4F | Balcony Checklist
|  | Unit | 4G | Balcony Checklist
|  | Unit | 4H | Balcony Checklist
|  | Unit | 4J | Balcony Checklist
|  | Unit | 4K | Balcony Checklist
|  | Unit | 4L | Balcony Checklist
|  | Unit | 4M | Balcony Checklist
|  | Unit | 4N | Balcony Checklist
|  | Unit | 4P | Balcony Checklist
|  | Unit | 4Q | Balcony Checklist
|  | Unit | 4R | Balcony Checklist
|  | Unit | 4S | Balcony Checklist
|  | Unit | 4T | Balcony Checklist
|  | Unit | 4U | Balcony Checklist
|  | Unit | 4V | Balcony Checklist
| Level 5 | Unit | 5A | Balcony Checklist
|  | Unit | 5B | Balcony Checklist
|  | Unit | 5C | Balcony Checklist
|  | Unit | 5D | Balcony Checklist
|  | Unit | 5E | Balcony Checklist
|  | Unit | 5F | Balcony Checklist
|  | Unit | 5G | Balcony Checklist
|  | Unit | 5H | Balcony Checklist
|  | Unit | 5J | Balcony Checklist
|  | Unit | 5K | Balcony Checklist
|  | Unit | 5L | Balcony Checklist
|  | Unit | 5M | Balcony Checklist
|  | Unit | 5N | Balcony Checklist
|  | Unit | 5P | Balcony Checklist
|  | Unit | 5Q | Balcony Checklist
|  | Unit | 5R | Balcony Checklist
| Level 6 | Unit | 6A | Balcony Checklist
|  | Unit | 6B | Balcony Checklist
|  | Unit | 6C | Balcony Checklist
|  | Unit | 6D | Balcony Checklist
|  | Unit | 6E | Balcony Checklist
|  | Unit | 6F | Balcony Checklist
|  | Unit | 6G | Balcony Checklist
|  | Unit | 6H | Balcony Checklist
|  | Unit | 6J | Balcony Checklist
|  | Unit | 6K | Balcony Checklist
|  | Unit | 6L | Balcony Checklist
|  | Unit | 6M | Balcony Checklist
|  | Unit | 6N | Balcony Checklist
|  | Unit | 6P | Balcony Checklist
|  | Unit | 6Q | Balcony Checklist
|  | Unit | 6R | Balcony Checklist

## Balcony Checklists
checklist | Balcony Checklist
Section | Substrate inspection
checkpoint | All prior works done
Substrate has no damages and sound
Floor free from any latent, contaminants or cracks
Ceiling installed
Section | Soundproofing (Regupol 4515)
Checkpoint | Primer Applied
PE Foam tape to all relevant substrate
Installed Soundproofing
Section | Tiling
Checkpoint | Setting out tiles according to construction drawing / Site confirmation
Primer applied prior to tiling
Full coverage of tiles with adhesive
Tile lippiness checked and to acceptable standard
Finishing trims & transition bars edge alignment
Section | Grout and Silicone
Checkpoint | Tiles adhesive cured and cleaned properly
Grout work properly into all joint
Excess grout cleaned properly
Silicon applied and installed to a neat continuously finish
Excess silicone cleaned properly
Section | Final check and Sign off
Checkpoint | Tiling Completed
Final clean done
Photo Taken of Completed Area
Sign off and Handover

## Common Area Checklist
checklist | Common Area Checklist
Section | Substrate inspection
checkpoint | All prior works done
Substrate has no damages and sound
Floor grinded or free from any latent, contaminants or cracks
Floor level surveyed and prep to acceptable substrate finish height
Wall Square and Plumb
Wall stopped and lined
Section | Tiling
Checkpoint | Setting out tiles according to construction drawing / Site confirmation
Primer applied prior to tiling
Full coverage of tiles with adhesive
Tile lippiness checked and to acceptable standard
Finishing trims & transition bars edge alignment
Skirting Tile Installed
Section | Grout and Silicone
Checkpoint | Tiles adhesive cured and cleaned properly
Grout work properly into all joint
Excess grout cleaned properly
Silicon applied and installed to a neat continuously finish
Excess silicone cleaned properly
Section | Final check and Sign off
Checkpoint | Tiling Completed
Final clean done
Photo Taken of Completed Area
Sign off and Handover