## Folder Structure
External Tile Cladding QA - Oceania Waimarie
Elevation
1
| 2 | External Tile Cladding Checklist
| 3 | External Tile Cladding Checklist
| 4 | External Tile Cladding Checklist
| 5 | External Tile Cladding Checklist
| 6 | External Tile Cladding Checklist
| 7 | External Tile Cladding Checklist
| 8 | External Tile Cladding Checklist
| 9 | External Tile Cladding Checklist
| 10 | External Tile Cladding Checklist
| 11 | External Tile Cladding Checklist
| 12 | External Tile Cladding Checklist
| 13 | External Tile Cladding Checklist
| 14 | External Tile Cladding Checklist
| 15 | External Tile Cladding Checklist
| 16 | External Tile Cladding Checklist
| 17 | External Tile Cladding Checklist

## Checklists
checklist | External Tile Cladding Checklist
Section | Substrate inspection
checkpoint | Check for visible cracks
Assess if wall out of plumb/square and if packers can accommodate the issue
No damage on waterproofing
Section | Setting Out
Checkpoint | RL provided by main contractor
Control of horizontal and vertical lines
Control of Plumb Line
Setting out follows shop drawings
Section | Sub-structure Installation
Subsection | Fixing rail to concrete with M8 Stainless Steel Concrete Screw
Min Embedment 50mm
Min Edge Distance 45mm
Max Spacing 1000mm
Subsection | Fixing rail to timber with 12G Tek Screw
Min Embedment 45mm
Min Edge Distance 25mm
Max Spacing 1000mm
Subsection | Fixing rail to Flatbar with 8G Tek Screw
| Max Spcaing 1000mm | Note: Max Spacing 600mm
| Overhang 80mm | Note: Please Delete This
Subsection | Fixing Flatbar to concrete with M8 Stainless Steel Concrete Screw
Min Embedment 50mm
Min Edge Distance 45mm
| Max Spacing 600mm | Note: Max Spacing 1000mm
Subsection | Fixing Soffit L-Bracket to concrete with M8 Stainless Steel Concrete Screw
Min Embedment 50mm
Min Edge Distance 45mm
Subsection | Fixing Soffit L-Bracket to timber with 12G Tek Screw
Min Embedment 45mm
Min Edge Distance 25mm
Check Point | Vaporbond silicone sealant applied for every fixing to substrate
Bottom drip flashing installed
Section | Tempio Tiles Installation
Checkpoint | Setting out according to shop drawing
No chipping / damage / crack
Tiles installed are fix properly and not moving or rattling
Section | Final Clean
Checkpoint | Clean all debris and stain
Clean all visible marks
Section | Sign Off
Check Point | Sign Off and Handover
Section | Grout and Silicone
Checkpoint | Tiles adhesive cured and clean properly
Grout work properly into all joint
Silicon applied and tolled to a neat continuously finish
Section | Final check and Sign off