## Folder Structure
Site QA
Unit Types
Block 3A
|  | TYPE A3(a) | Grid A-B | Unit Checklist
|  |  | Ground Floor | Unit Checklist
|  |  | L1 | Unit Checklist
|  |  | L2 | Unit Checklist
|  | TYPE C | Grid B-C | Unit Checklist
|  |  | Ground Floor | Unit Checklist
|  |  | L1 | Unit Checklist
|  |  | L2 | Unit Checklist
|  | TYPE C | Grid C-D | Unit Checklist
|  |  | Ground Floor | Unit Checklist
|  |  | L1 | Unit Checklist
|  |  | L2 | Unit Checklist
|  | TYPE A3(a) | Grid D-E | Unit Checklist
|  |  | Ground Floor | Unit Checklist
|  |  | L1 | Unit Checklist
|  |  | L2 | Unit Checklist
Block 3B
|  | TYPE A3(a) | Grid F-G | Unit Checklist
|  |  | Ground Floor | Unit Checklist
|  |  | L1 | Unit Checklist
|  |  | L2 | Unit Checklist
|  | TYPE A2(a) | Grid G-H | Unit Checklist
|  |  | Ground Floor | Unit Checklist
|  |  | L1 | Unit Checklist
|  |  | L2 | Unit Checklist
|  | TYPE A2(a) | Grid H-I | Unit Checklist
|  |  | Ground Floor | Unit Checklist
|  |  | L1 | Unit Checklist
|  |  | L2 | Unit Checklist
|  | TYPE A3(a) | Grid I-J | Unit Checklist
|  |  | Ground Floor | Unit Checklist
|  |  | L1 | Unit Checklist
|  |  | L2 | Unit Checklist
Block 3C
|  | TYPE A3(a) | Grid K-L | Unit Checklist
|  |  | Ground Floor | Unit Checklist
|  |  | L1 | Unit Checklist
|  |  | L2 | Unit Checklist
|  | TYPE C | Grid L-M | Unit Checklist
|  |  | Ground Floor | Unit Checklist
|  |  | L1 | Unit Checklist
|  |  | L2 | Unit Checklist
|  | TYPE C | Grid M-N | Unit Checklist
|  |  | Ground Floor | Unit Checklist
|  |  | L1 | Unit Checklist
|  |  | L2 | Unit Checklist
|  | TYPE A3(a) | Grid N-O | Unit Checklist
|  |  | Ground Floor | Unit Checklist
|  |  | L1 | Unit Checklist
|  |  | L2 | Unit Checklist
Block 3D
|  | TYPE A3(a) | Grid P-Q | Unit Checklist
|  |  | Ground Floor | Unit Checklist
|  |  | L1 | Unit Checklist
|  |  | L2 | Unit Checklist
|  | TYPE A2(a) | Grid Q-R | Unit Checklist
|  |  | Ground Floor | Unit Checklist
|  |  | L1 | Unit Checklist
|  |  | L2 | Unit Checklist
|  | TYPE A2(a) | Grid R-S | Unit Checklist
|  |  | Ground Floor | Unit Checklist
|  |  | L1 | Unit Checklist
|  |  | L2 | Unit Checklist
|  | TYPE A3(a) | Grid S-T | Unit Checklist
|  |  | Ground Floor | Unit Checklist
|  |  | L1 | Unit Checklist
|  |  | L2 | Unit Checklist

## Checklists
Checklist | Bathroom Checklist
Section | Substrate inspection
checkpoint | All prior works done
Tile Slate underlay installed by others and checked if all the nailed in flush
Wall square and plumb
Showerbase installed
Ceiling installed and painted
Section | Soundproofing (Regupol)
checkpoint | Pe foam tape to perimeter
Primed 3296 make sure it dry before install regupol
Install acoustic underlay w/ VS90 plus
Joint to be butt joint, if big gap need to fill in with silicone
Make sure regupol not touching perimeter wall
Section | Waterproofing
checkpoint | Mapeband SA to wall and floor junction/ penetration
Mapeband SA Gasket to floor waste
Specified waterproofing 1st coat
Mapenet 150 install with 1st coat waterproofing if using Mapelastic Smart
Mapenet 150 not toucing Mapeband SA if using Mapelastic Smart
Specified waterproofing 2nd coat
Mapenet 150 mesh should be invincible or less visible after 2nd coat to ensure required thickness achieve.
Section | Tiling
checkpoint | Setting out tiles according to construction drawing / Site confirmation
Primer applied prior to tiling
Full coverage of tiles with adhesive
Ensure no glue spill out and touching the perimeter wall , acoustic purposes
Tile lippiness checked and to acceptable standard
Finishing trims & transition bars edge alignment
Skirting Tile Installed
Section | Grout and silicone
checkpoint | Adhesive fully cured and clean properly
Grout work properly into all joint
Silicone applied to a acceptable finish
Section | Completion
checkpoint | Tiling complete
Photo taken of completed area
Sign off and handover
Checklist | Balcony
Section | Subtrate inspection
checkpoint | All prior works done
Waterproofing completed by others
Section | Balcony deck tiling
Setting out refer to drawing/ COS
Nurajack NM install follow manufacturer specification
Paver lippiness checked and to acceptable standard
Paver interlocked with each others, stable and not moving/rocking
Cladding spacer install between cladding/ balustrate to stop the paver moving
Section | Final check and Sign off
Checkpoint | Tiling Completed
Photo Taken of Completed Area
Sign off and Handover
Checklist | Laundry Checklist
Section | Substrate inspection
checkpoint | All prior works done
Tile Slate underlay installed by others and checked if all the nailed in flush
Section | Soundproofing (Regupol)
checkpoint | Pe foam tape to perimeter
Install acoustic underlay w/ VS90 plus
Joint to be butt joint, if big gap need to fill in with silicone
Make sure regupol not touching perimeter wall
Section | Waterproofing
checkpoint | Mapeband SA to wall and floor junction/ penetration
Specified waterproofing 1st coat
Mapenet 150 install with 1st coat waterproofing if using Mapelastic Smart
Mapenet 150 not toucing Mapeband SA
Specified waterproofing 2nd coat
Mapenet 150 mesh should be invincible or less visible after 2nd coat to ensure required thickness achieve.
Section | Tiling
checkpoint | Setting out tiles according to construction drawing / Site confirmation
Primer applied prior to tiling
Full coverage of tiles with adhesive
Tile lippiness checked and to acceptable standard
Finishing trims & transition bars edge alignment
Skirting Tile Installed 150 height
Section | Grout and silicone
checkpoint | Adhesive fully cured and clean properly
Grout work properly into all joint
Silicone applied to an acceptable finish
Section | Completion
checkpoint | Tiling complete
Photo taken of completed area
Sign off and handover
Checklist | Kitchen splashback / Vanity Splashback
Section | Waterproofing
checkpoint | Mapeband SA to all wall penetration
Specified waterproofing 1st coat
Specified waterproofing 2nd coat
Section | Tiling
checkpoint | Setting out tiles according to construction drawing / Site confirmation
Primer applied prior to tiling
Full coverage of tiles with adhesive
Tile lippiness checked and to acceptable standard
Finishing trims & transition bars edge alignment
Section | Grout and silicone
checkpoint | Adhesive fully cured and clean properly
Grout work properly into all joint
Silicone applied to an acceptable finish
Section | Completion
checkpoint | Tiling complete
Photo taken of completed area
Sign off and handover