## Breakdown
Lincoln Rd - Henderson
QA
B05
|  |  | Pre-Commencment Checks |  |  |  |  | Pre-commencement checks
Building B05 - On Site QA
APARTMENTS
Ground Level
[6 empty] | Apartment G1 | Split HW | Extract Fan | Kitch Ext
[6 empty] | Apartment G2 | Split HW | Extract Fan | Kitch Ext
[6 empty] | Apartment G3 | Split HW | Extract Fan | Kitch Ext
[6 empty] | Apartment G4 | Split HW | Extract Fan | Kitch Ext
[6 empty] | Apartment G5 | Split HW | Extract Fan | Kitch Ext
[6 empty] | Apartment G6 | Split HW | Extract Fan | Kitch Ext
[6 empty] | Apartment G7 | Split HW | Extract Fan | Kitch Ext
[6 empty] | Apartment G8 | Split HW | Extract Fan | Kitch Ext
Level 1
[6 empty] | Apartment 101 | Split HW | Extract Fan | Kitch Ext
[6 empty] | Apartment 102 | Split HW | Extract Fan | Kitch Ext
[6 empty] | Apartment 103 | Split HW | Extract Fan | Kitch Ext
[6 empty] | Apartment 104 | Split HW | Extract Fan | Kitch Ext
[6 empty] | Apartment 105 | Split HW | Extract Fan | Kitch Ext
[6 empty] | Apartment 106 | Split HW | Extract Fan | Kitch Ext
[6 empty] | Apartment 107 | Split HW | Extract Fan | Kitch Ext
[6 empty] | Apartment 108 | Split HW | Extract Fan | Kitch Ext
[6 empty] | Apartment 109 | Split HW | Extract Fan | Kitch Ext
[6 empty] | Apartment 110 | Split HW | Extract Fan | Kitch Ext
[6 empty] | Apartment 111 | Split HW | Extract Fan | Kitch Ext
[6 empty] | Apartment 112 | Split HW | Extract Fan | Kitch Ext
[6 empty] | Apartment 113 | Split HW | Extract Fan | Kitch Ext
[6 empty] | Apartment 114 | Split HW | Extract Fan | Kitch Ext
Ventilation
Ground Level
[6 empty] | Carpark | CPEF 0.1 | Jet Pulse Fan
[6 empty] | Carpark | CPEF 0.2 | Jet Pulse Fan
[6 empty] | MSB Room | EF 0.1 | Extract Fan
[6 empty] | Rubbish Room | EF 0.2 | Extract Fan
[6 empty] | Corridor | SF 0.1 | SA FAN
Level 1
[6 empty] | Corridors | SF 1.1 | SA FAN
[7 empty] | SF 1.2 | SA FAN
|  |  | Completion documents |  |  |  |  | Completion documents

## Checklists
Checklist | SPLIT HIGH WALL
Section | Pre-Start HW
Checkpoint | Area clear, access good, enough space for install
Checkpoint | Area/base ready for outdoor unit
Checkpoint | Any required drains for outdoor unit in place
Checkpoint | Pipework route all clear, penetrations complete
Checkpoint | Nogs in place
Checkpoint | Drain 1m from Indoor unit location by plumber
Section | First Fix HW
Checkpoint | Pipework Insulated complete length
Checkpoint | Drain installed and insulated
Checkpoint | Supply cable installed correctly, protected and secured
Checkpoint | Interconnecting cables correctly installed and protected
Section | Second Fix HW
Checkpoint | System pressure checked and still holding 1st fix pressure
Checkpoint | Indoor unit secure, level and tight to wall
Checkpoint | Correct Indoor unit installed
Checkpoint | Outdoor unit secure and level
Checkpoint | Correct Outdoor unit installed
Checkpoint | Indoor unit serial no. recorded
Checkpoint | Outdoor Unit serial no. recorded
Checkpoint | Area left clean and tidy, finger prints removed
Section | Commission
Checkpoint | Installer confirmed commissioned and paperwork submitted
Checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
Checkpoint | Electrical testing complete
Checklist | Extract Fan
Section | Pre-Start Ext Fan
Checkpoint | Area clear, access good, enough space for install
Checkpoint | Duct Route clear, Penetrations complete
Checkpoint | Nogs/Supports in place
Section | First Fix Ext Fan
Checkpoint | Fan installed straight and level and correct orientation.
Checkpoint | Fan or Cowl sealed to Upstand
Checkpoint | Correct Fan installed
Checkpoint | Fan serial No. recorded
Checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
Checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
Checkpoint | Flexible ducts run straight/tight/well supported/secured close to grille location
Checkpoint | Flexible ducts taped then cable tied
Checkpoint | Supply cable installed correctly, protected and secured
Checkpoint | Interconnecting cables correctly installed and protected
Checkpoint | Plans marked up for As Builts and 2nd fix grille locations
Section | Second Fix Ext Fan
Checkpoint | Grilles installed square and level
Checkpoint | Flexible ducts taped then cable tied to grilles/boots
Checkpoint | Boots sealed to grilles
Checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
Checkpoint | Controllers fitted off
Checkpoint | Power fitted off
Checkpoint | Area left clean and tidy, finger prints removed
Checkpoint | Plant and controllers labelled
Section | Commission Ext Fan
Checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
Checkpoint | Electrical testing complete
Checkpoint | COC issued
Checklist | Extract Fan
Section | Pre-Start Ext Fan
Checkpoint | Area clear, access good, enough space for install
Checkpoint | Duct Route clear, Penetrations complete
Checkpoint | Nogs/Supports in place
Section | First Fix Ext Fan
Checkpoint | Fan installed straight and level and correct orientation.
Checkpoint | Fan or Cowl sealed to Upstand
Checkpoint | Correct Fan installed
Checkpoint | Fan serial No. recorded
Checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
Checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
Checkpoint | Flexible ducts run straight/tight/well supported/secured close to grille location
Checkpoint | Flexible ducts taped then cable tied
Checkpoint | Supply cable installed correctly, protected and secured
Checkpoint | Interconnecting cables correctly installed and protected
Checkpoint | Plans marked up for As Builts and 2nd fix grille locations
Section | Second Fix Ext Fan
Checkpoint | Grilles installed square and level
Checkpoint | Flexible ducts taped then cable tied to grilles/boots
Checkpoint | Boots sealed to grilles
Checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
Checkpoint | Controllers fitted off
Checkpoint | Power fitted off
Checkpoint | Area left clean and tidy, finger prints removed
Checkpoint | Plant and controllers labelled
Section | Commission Ext Fan
Checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
Checkpoint | Electrical testing complete
Checkpoint | COC issued
Checklist | SA FAN
Section | Pre-Start SA Fan
Checkpoint | Area clear, access good, enough space for install
Checkpoint | Duct Route clear, Penetrations complete
Checkpoint | Nogs/Supports in place
Section | First Fix SA Fan
Checkpoint | Fan installed straight and level and correct orientation.
Checkpoint | Fan or Cowl sealed to Upstand
Checkpoint | Correct Fan installed
Checkpoint | Fan serial No. recorded
Checkpoint | Fan seismically braced and vibration isolated
Checkpoint | Heater Bank installed to Manufacturers instructions
Checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
Checkpoint | Ductwork straight/level and well supported incl any seismic restraints
Checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
Checkpoint | Flexible ducts run straight/tight/well supported/secured close to grille location
Checkpoint | Flexible ducts taped then cable tied
Checkpoint | Supply cable installed correctly, protected and secured
Checkpoint | Interconnecting cables correctly installed and protected
Checkpoint | Plans marked up for As Builts and 2nd fix grille locations
Section | Second Fix SA Fan
Checkpoint | Grilles installed square and level
Checkpoint | Flexible ducts taped then cable tied to grilles/boots
Checkpoint | Boots sealed to grilles
Checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
Checkpoint | Controllers fitted off. Heater Bank THT set
Checkpoint | Power fitted off
Checkpoint | Area left clean and tidy, finger prints removed
Checkpoint | Plant and controllers labelled
Section | Commission SA Fan
Checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
Checkpoint | Electrical testing complete
Checkpoint | COC issued
Checklist | Completion documents
checkpoint | O&M
checkpoint | PS3 Mechanical Service - BCO10328723
checkpoint | Carbon Monitor & Fantech Checksheet
checkpoint | HVAC - As built
checkpoint | PS3 HVAC - BCO10328723
checkpoint | Electrical Safety Certification
checkpoint | PS4 Seismic Support - BCO10328723