## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 1b0a4b49-8a0c-4d2e-bb63-6e3edea49d4d |  | checklist | Completion documents |  |  |  |  | Yes | Completion documents | 05d19ddd-ad66-4e6f-8b6f-4a26a794e0d7
checkpoint-status | 21405333-da65-4a54-8626-69a291b6e202 |  | checkpoint | O&M
checkpoint-status | de13e88e-1a75-4822-9613-6acb567e1685 |  | checkpoint | PS3 Mechanical Service - BCO10328723
checkpoint-status | f69cd0fe-17c6-4fb5-bdb3-047d88a5092a |  | checkpoint | Carbon Monitor & Fantech Checksheet
checkpoint-status | 4578a1e9-4c24-4686-a7d3-0082112ae7c5 |  | checkpoint | HVAC - As built
checkpoint-status | 4bb19ec2-08ce-41ee-b356-a0ea1e2c4dde |  | checkpoint | PS3 HVAC - BCO10328723
checkpoint-status | 10017f0c-3bb9-4e97-a4ca-67fd6ad31ced |  | checkpoint | Electrical Safety Certification
checkpoint-status | d80bf36b-c85c-4c37-9267-95531d1bec66 |  | checkpoint | PS4 Seismic Support - BCO10328723
checklist-sectioned | 533259f1-5a54-4df4-84fa-6db1168a2aa2 |  | checklist | SA FAN |  |  |  |  | Yes | SA FAN | 104cf838-1e31-43f4-968a-c028ab83473d
checkpoint-group | 00128593-245e-466a-80d6-a6679f0dff45 |  | section | Pre-Start SA Fan
checkpoint-status | 3a2b1683-fae4-4b20-a432-1d9fd5845690 |  | checkpoint | Area clear, access good, enough space for install
checkpoint-status | 5355f9ea-d3da-4886-8b20-5f73a5802365 |  | checkpoint | Duct Route clear, Penetrations complete
checkpoint-status | 7ce70ffc-e1f9-464d-8a72-7dc9b0d4b3a4 |  | checkpoint | Nogs/Supports in place
checkpoint-group | 87176826-abc4-4939-90c7-3f00940c0538 |  | section | First Fix SA Fan
checkpoint-status | 4cd434a4-03e0-41de-ba3f-5ca1544afaaa |  | checkpoint | Fan installed straight and level and correct orientation.
checkpoint-status | 629f9149-669c-4480-ab11-e48d91fa5fe9 |  | checkpoint | Fan or Cowl sealed to Upstand
checkpoint-status | 82d3ded8-6425-4144-b9ec-65dd930deaed |  | checkpoint | Correct Fan installed
checkpoint-status | 186cb580-5f83-42d1-9d5c-f148e8243cbd |  | checkpoint | Fan serial No. recorded
checkpoint-status | e31c99f3-a63e-418a-ac30-54200bc110fa |  | checkpoint | Fan seismically braced and vibration isolated
checkpoint-status | d6227a4c-5201-4834-a175-903676c7fec6 |  | checkpoint | Heater Bank installed to Manufacturers instructions
checkpoint-status | 9535a3d7-e2cb-4eb1-92a0-9cdb291e8cf7 |  | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
checkpoint-status | 9b5a97a2-b806-4e71-be16-fb9da0826165 |  | checkpoint | Ductwork straight/level and well supported incl any seismic restraints
checkpoint-status | 6ef1d040-04be-41cf-b293-c73da2bc9245 |  | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
checkpoint-status | f6964fc0-807f-4213-abc4-d917ca347726 |  | checkpoint | Flexible ducts run straight/tight/well supported/secured close to grille location
checkpoint-status | 439ae54a-7de7-4bf7-9559-c2f2cd1da26d |  | checkpoint | Flexible ducts taped then cable tied
checkpoint-status | ba772db1-270a-40a6-9570-d787e0a2caaf |  | checkpoint | Supply cable installed correctly, protected and secured
checkpoint-status | 954f4cb2-c912-4205-af69-32aadf09d925 |  | checkpoint | Interconnecting cables correctly installed and protected
checkpoint-status | 7842b09c-6059-463b-87f1-831534cfe4df |  | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
checkpoint-group | bef6b770-cddc-46a9-9ddb-557c1de6941a |  | section | Second Fix SA Fan
checkpoint-status | 4bef0442-d37b-4f92-9db5-2398b00f28a7 |  | checkpoint | Grilles installed square and level
checkpoint-status | 385a8aaa-994c-442b-9b29-f7f01ab1b62a |  | checkpoint | Flexible ducts taped then cable tied to grilles/boots
checkpoint-status | fa1f9917-9865-4519-a8e8-9989d0a29975 |  | checkpoint | Boots sealed to grilles
checkpoint-status | 5087305f-30d3-44bf-90fe-320869038750 |  | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
checkpoint-status | 7806e55b-ba4d-4b0e-8198-acb1e968b6ba |  | checkpoint | Controllers fitted off. Heater Bank THT set
checkpoint-status | f84fb844-9423-474f-b9c3-98c4993a6646 |  | checkpoint | Power fitted off
checkpoint-status | 8fc3d683-f33c-4c88-a7b2-7563861ab2d6 |  | checkpoint | Area left clean and tidy, fingerprints removed
checkpoint-status | 0803f5c6-3997-4786-beb8-8393df8922c6 |  | checkpoint | Plant and controllers labelled
checkpoint-group | 96cbdca3-bc5d-4fdf-9261-713459859ddf |  | section | Commission SA Fan
checkpoint-status | f23d1782-d17f-497f-823c-0a91900cc362 |  | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
checkpoint-status | 7a69c5a2-0773-4211-b399-556d9c11abc4 |  | checkpoint | Electrical testing complete
checkpoint-status | 530ae2a8-4a04-491d-9cb2-abcdfcc0567b |  | checkpoint | COC issued
checklist-sectioned | b025fd65-15d5-4c06-8f0d-b0c3c5287608 |  | checklist | SPLIT HIGH WALL |  |  |  |  | Yes | SPLIT HIGH WALL | 17bf6d88-dbed-491b-b052-208f0f8e039b
checkpoint-group | 093b2e5a-4a94-415b-a438-8cee3ef75367 |  | section | Pre-Start HW
checkpoint-status | d65b0904-eab9-4afb-8e59-7b6b8dbb87cf |  | checkpoint | Area clear, access good, enough space for install
checkpoint-status | 6011abd1-57f4-4afe-9f46-6abfc2544cc2 |  | checkpoint | Area/base ready for outdoor unit
checkpoint-status | 5ca25a48-6f59-436a-ac1a-d4656776914e |  | checkpoint | Any required drains for outdoor unit in place
checkpoint-status | ac748339-f730-4da9-bb8f-46171a9cc8c6 |  | checkpoint | Pipework route all clear, penetrations complete
checkpoint-status | 041b4fa4-1590-4d23-9108-af4705d5a193 |  | checkpoint | Nogs in place
checkpoint-status | b2938345-85e5-4e84-9cdb-655cd028439b |  | checkpoint | Drain 1m from Indoor unit location by plumber
checkpoint-group | e8ca27b9-6479-4b47-a31b-9123cecaeb32 |  | section | First Fix HW
checkpoint-status | 774d711f-09da-4dd3-8a48-d09890689060 |  | checkpoint | Pipework Insulated complete length
checkpoint-status | 4b498e21-3c13-4ca7-a82a-7916df7cadb1 |  | checkpoint | Drain installed and insulated
checkpoint-status | 547e7c73-f828-4c7d-ba7a-45d521367a22 |  | checkpoint | Supply cable installed correctly, protected and secured
checkpoint-status | 9cb83c0f-19e0-426e-9b4c-49ef4d7b7507 |  | checkpoint | Interconnecting cables correctly installed and protected
checkpoint-group | 7c64e59f-8c03-4791-a540-766e39096f46 |  | section | Second Fix HW
checkpoint-status | 2341d03b-9e34-442e-9012-e2fd85bfe608 |  | checkpoint | System pressure checked and still holding 1st fix pressure
checkpoint-status | 6fbd7af6-3e39-44fd-8bec-dc35e694f372 |  | checkpoint | Indoor unit secure, level and tight to wall
checkpoint-status | 86102b73-e9c2-4251-bf83-141f7d1fcb2f |  | checkpoint | Correct Indoor unit installed
checkpoint-status | d03aa8f9-7e26-435e-942a-2cae9ae6416c |  | checkpoint | Outdoor unit secure and level
checkpoint-status | 63f10872-8a3a-4ff0-be94-11a929d29916 |  | checkpoint | Correct Outdoor unit installed
checkpoint-status | c42fd5bd-67c6-41a8-bb00-2de993765393 |  | checkpoint | Indoor unit serial no. recorded
checkpoint-status | d545cedb-76db-40b5-853a-7ce00923fd22 |  | checkpoint | Outdoor Unit serial no. recorded
checkpoint-status | f9ef278b-2836-457c-9f4c-6624898ad552 |  | checkpoint | Area left clean and tidy, fingerprints removed
checkpoint-group | d6a2f93d-69aa-43d8-bd14-0cdb28fdfdcf |  | section | Commission
checkpoint-status | 4214b773-6eea-4874-8ce9-58666e847230 |  | checkpoint | Installer confirmed commissioned and paperwork submitted
checkpoint-status | ac76e613-0fda-41a9-9d0f-1e97a2a9d61d |  | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
checkpoint-status | 66e08c15-8706-4427-a0e7-22d9a885bc24 |  | checkpoint | Electrical testing complete
checklist-flat | f4cf5fc9-e78f-4838-afb0-ab8261a078ce |  | checklist | Pre-Commencement Checks |  |  |  |  | Yes | Pre-Commencement Checks | 201b9631-0294-4c44-b129-d1f49cbb2bb2
checkpoint-status | 5ac79c7c-2d5a-4eb1-bbc6-aed9d7a5ec66 |  | checkpoint | Quality Management Plan Completed, Agreed and Attached
checkpoint-status | 887b7e91-a489-4f16-91d2-bd6d861ac12e |  | checkpoint | Inspection & Test Plan Completed, Agreed & Attached
checkpoint-status | c4b0df3e-4082-4e1e-bf3d-c9b80e777887 |  | checkpoint | Relevant Breakdown & Checklist Setup on Conqa & Reviewed by Main Contractor
checkpoint-status | b0a4fd5d-c743-4e1a-a991-28aebcb20aa4 |  | checkpoint | Conqa Setup & Project Team Trained & Given Access
checkpoint-status | f9cc1b91-4e86-4bef-8a0e-14a148d4be86 |  | checkpoint | Review Access Granted to Main Contractor & Relevant Parties
checkpoint-status | a62de021-85e7-4a98-8c88-693905035154 |  | checkpoint | Matrix/Insight Setup (if required)
checklist-sectioned |  |  | checklist | Jet Pulse Fan |  |  |  |  | Yes | Jet Pulse Fan | 2fd4e2c3-3876-48b8-a750-d8f19f87bcc0
checkpoint-group |  |  | section | Pre-Start SA Fan
checkpoint-status |  |  | checkpoint | Area clear, access good, enough space for install
checkpoint-status |  |  | checkpoint | Duct Route clear, Penetrations complete
checkpoint-status |  |  | checkpoint | Nogs/Supports in place
checkpoint-group |  |  | section | First Fix SA Fan
checkpoint-status |  |  | checkpoint | Fan installed straight and level and correct orientation.
checkpoint-status |  |  | checkpoint | Correct Fan installed
checkpoint-status |  |  | checkpoint | Fan serial No. recorded
checkpoint-status |  |  | checkpoint | Fan seismically braced and vibration isolated
checkpoint-status |  |  | checkpoint | Supply cable installed correctly, protected and secured
checkpoint-status |  |  | checkpoint | Supply cable type, size and manufacturer
checkpoint-status |  |  | checkpoint | Circuit protection type and rating
checkpoint-status |  |  | checkpoint | Correctly rated isolator installed to standards
checkpoint-status |  |  | checkpoint | Interconnecting cables correctly installed and protected
checkpoint-status |  |  | checkpoint | Control cables correct rating and type
checkpoint-status |  |  | checkpoint | Screened cables drain to earth as per specifications
checkpoint-status |  |  | checkpoint | Control cables maintain minimum distance from power cables
checkpoint-status |  |  | checkpoint | Daisy chain loops complete and correct
checkpoint-status |  |  | checkpoint | Remote controller cable installed
checklist-sectioned | a8d7560c-0328-4b02-8bac-e58e149d554c |  | checklist | Extract Fan |  |  |  |  | Yes | Extract Fan | b66e72b6-95d6-40f6-a891-bb81a64a91d3
checkpoint-group | bfc4c44b-fcb7-46fa-9a72-19dc9f0b8659 |  | section | Pre-Start Ext Fan
checkpoint-status | 1c090a2a-d831-467e-8bd1-db439d363997 |  | checkpoint | Area clear, access good, enough space for install
checkpoint-status | 308e032f-5c04-44b1-a9b9-083728ea1259 |  | checkpoint | Duct Route clear, Penetrations complete
checkpoint-status | 971d7327-caec-4b0c-bf0b-173e2701c8b7 |  | checkpoint | Nogs/Supports in place
checkpoint-group | 948458c9-b74d-4e8d-bc47-e7c2f5d1baed |  | section | First Fix Ext Fan
checkpoint-status | 898f9753-77b4-46b6-acac-3b4ed0f58eaa |  | checkpoint | Fan installed straight and level and correct orientation.
checkpoint-status | a4e85487-8bb1-40fe-bc23-8afc7d0e39f7 |  | checkpoint | Fan or Cowl sealed to Upstand
checkpoint-status | 75fb9abc-0ceb-4917-932c-1fcbba624f49 |  | checkpoint | Correct Fan installed
checkpoint-status | ba06da6c-7bbe-4bbb-90f8-0db8d685476d |  | checkpoint | Fan serial No. recorded
checkpoint-status | 340e7f48-0a23-41d3-842d-a26adefdd3a9 |  | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
checkpoint-status | ded0344c-52a5-4523-bf42-bd96482b5ea5 |  | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
checkpoint-status | 307db7bf-6bd6-45ab-8fca-6f9dce083352 |  | checkpoint | Flexible ducts run straight/tight/well supported/secured close to grille location
checkpoint-status | 05c5af82-0f1f-4fcb-83be-8d6f027f2432 |  | checkpoint | Flexible ducts taped then cable tied
checkpoint-status | 703887bf-5560-4545-8f2c-a1337d73051b |  | checkpoint | Supply cable installed correctly, protected and secured
checkpoint-status | f2494147-463c-452f-8b96-fc42291dd509 |  | checkpoint | Interconnecting cables correctly installed and protected
checkpoint-status | cee4e101-bd9b-4f5a-9443-564e0f307c1b |  | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
checkpoint-group | 08c3fcf3-5b52-47f2-9ffc-3906cac2a2a1 |  | section | Second Fix Ext Fan
checkpoint-status | 07e96289-bae6-456e-b477-b13b96e7b174 |  | checkpoint | Grilles installed square and level
checkpoint-status | 77f8d6e9-1218-49cc-bce0-6587bdc71266 |  | checkpoint | Flexible ducts taped then cable tied to grilles/boots
checkpoint-status | 9aa1e7f9-5e08-49d5-97a0-6d265f3a97d5 |  | checkpoint | Boots sealed to grilles
checkpoint-status | 81c915c9-670e-49f7-b76e-294238a72ec0 |  | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
checkpoint-status | edbc13e0-ba64-4932-81c4-90a2e26ff5fb |  | checkpoint | Controllers fitted off
checkpoint-status | cc7b3e2a-c9d8-4f53-9a61-787ad696c58a |  | checkpoint | Power fitted off
checkpoint-status | 334eea21-4378-42d9-b0e2-8112672a884b |  | checkpoint | Area left clean and tidy, fingerprints removed
checkpoint-status | 96fc09d8-7cef-4e90-8473-bc785f805fe4 |  | checkpoint | Plant and controllers labelled
checkpoint-group | 487a9565-65d1-46da-a7f9-1972e3471d37 |  | section | Commission Ext Fan
checkpoint-status | 87916ffe-c6ec-4550-89d5-7d33097e305d |  | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
checkpoint-status | 4e33162e-ac1e-4ec3-a358-893b3a85df26 |  | checkpoint | Electrical testing complete
checkpoint-status | fa4be4bb-6727-4771-87a7-1d5977199aac |  | checkpoint | COC issued
checklist-sectioned | a7ea4423-4627-4bf6-a349-013e78fae846 |  | checklist | Kitchen Extract Fan |  |  |  |  | Yes | Kitchen Extract Fan | eb666037-e9a8-413d-9582-200595b0ed5e
checkpoint-group | f80aa660-a6d1-4c6b-a606-0b49c7811313 |  | section | Pre-Start Ext Fan
checkpoint-status | 74f12232-33ad-4e4d-987c-a09780b085c1 |  | checkpoint | Area clear, access good, enough space for install
checkpoint-status | 03a9d0c2-7bca-4561-9b58-b0954a65c4a0 |  | checkpoint | Duct Route clear, Penetrations complete
checkpoint-status | be8220b8-fe65-4262-b4b0-a499ae3c5223 |  | checkpoint | Nogs/Supports in place
checkpoint-group | 5fd663a2-c77d-46aa-81dd-4bdfe8f1919b |  | section | First Fix Ext Fan
checkpoint-status | a44c5136-f01d-4476-8b5b-04757fbd3807 |  | checkpoint | Fan installed straight and level and correct orientation.
checkpoint-status | 53e405e0-fe57-4773-b48a-06d6f542215f |  | checkpoint | Fan or Cowl sealed to Upstand
checkpoint-status | 35330a94-b91c-4f24-bd1c-ebdbe457296f |  | checkpoint | Correct Fan installed
checkpoint-status | 50706214-c1c4-4301-bb19-e6510faee410 |  | checkpoint | Fan serial No. recorded
checkpoint-status | d40ac509-15df-4054-b635-4d9163d7708a |  | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
checkpoint-status | 0642e4a6-7661-4831-ae34-bd2638122881 |  | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
checkpoint-status | 4214649d-828f-4d5a-8fb5-551711c43c6b |  | checkpoint | Flexible ducts run straight/tight/well supported/secured close to grille location
checkpoint-status | 1484200d-bfb2-4d8b-aa61-baa541b0345f |  | checkpoint | Flexible ducts taped then cable tied
checkpoint-status | 2d3d6ee2-39b1-4214-beb4-cb1a288d42be |  | checkpoint | Supply cable installed correctly, protected and secured
checkpoint-status | 8cee5050-aaec-4b73-b127-f7246e656c04 |  | checkpoint | Interconnecting cables correctly installed and protected
checkpoint-status | 03782186-917b-4b4e-92f6-425e8189d0db |  | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
checkpoint-group | 5768f924-2c0a-443a-a8bb-9088d30cf8b8 |  | section | Second Fix Ext Fan
checkpoint-status | 4c547e3f-ee04-4f0b-a607-6dfb31f8b6f0 |  | checkpoint | Grilles installed square and level
checkpoint-status | b757ea2f-905c-421d-94d3-0edec7481d43 |  | checkpoint | Flexible ducts taped then cable tied to grilles/boots
checkpoint-status | f6b8b24a-dfbf-4a13-a972-3ad8c6bc0967 |  | checkpoint | Boots sealed to grilles
checkpoint-status | 7da2fcad-8618-4f22-9e9e-09cadce29940 |  | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
checkpoint-status | c33a6059-f0df-4939-8c74-4865c56b147e |  | checkpoint | Controllers fitted off
checkpoint-status | c97528f5-50cc-436a-bd3c-6196f4e856ec |  | checkpoint | Power fitted off
checkpoint-status | 790f0f4c-79b6-46b4-8cee-3b2ac839ead7 |  | checkpoint | Area left clean and tidy, fingerprints removed
checkpoint-status | a1d26f7b-644b-4bdc-8e90-55af845f100f |  | checkpoint | Plant and controllers labelled
checkpoint-group | 27c3790f-3f1b-4395-9341-4d19de4271ca |  | section | Commission Ext Fan
checkpoint-status | 7c71ea12-e083-4467-a0aa-7e8ee1047102 |  | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
checkpoint-status | 3a170b85-4a13-4332-8830-4498cf0bcda8 |  | checkpoint | Electrical testing complete
checkpoint-status | c06bcaf5-53f5-452f-9de9-da865389b024 |  | checkpoint | COC issued