## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | 19ef01d2-5e07-41a3-acdd-79215dedd440 |  | checklist | SA FAN |  |  |  |  | Yes | SA FAN | 2078abc7-e5ad-410c-b17c-8cc058611f2a
checkpoint-group | cfad8343-f8c5-4eac-b92a-5dcb630b3d81 |  | section | Pre-Start SA Fan
checkpoint-status | c9da187b-8768-41b4-a064-9a5afdaeb61b |  | checkpoint | Area clear, access good, enough space for install
checkpoint-status | 14759a29-c4eb-4049-aded-cd869fb0cae3 |  | checkpoint | Duct Route clear, Penetrations complete
checkpoint-status | ea99b6bf-f83c-48e0-bd18-5369033198dd |  | checkpoint | Nogs/Supports in place
checkpoint-group | 08c8a946-f056-4246-84a2-d73c66a6f8a3 |  | section | First Fix SA Fan
checkpoint-status | ccde4110-bb35-433c-8332-7487ba857e98 |  | checkpoint | Fan installed straight and level and correct orientation.
checkpoint-status | 3b7fa667-4330-4c29-a3e1-b231c9384cbc |  | checkpoint | Fan or Cowl sealed to Upstand
checkpoint-status | d720de10-4ad4-4a0a-81fe-498574178409 |  | checkpoint | Correct Fan installed
checkpoint-status | 2d15a3a6-3e81-4ffb-9781-025cfa3b9dce |  | checkpoint | Fan serial No. recorded
checkpoint-status | 1f3b75e5-2625-4a4a-817b-d9b67e5859df |  | checkpoint | Fan seismically braced and vibration isolated
checkpoint-status | 5fce4c98-c2d9-4b94-a27c-14ea33fae317 |  | checkpoint | Heater Bank installed to Manufacturers instructions
checkpoint-status | cb4c7cc9-fd7f-4bd7-b85f-bfea2c78c693 |  | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
checkpoint-status | 5bb3e0f6-f0e7-457c-9343-ffd1cfe23e08 |  | checkpoint | Ductwork straight/level and well supported incl any seismic restraints
checkpoint-status | feb47491-e454-4e15-85f7-4a022a1e9f98 |  | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
checkpoint-status | 2caf5bde-dd8c-4d00-badf-a9731748d597 |  | checkpoint | Flexible ducts run straight/tight/well supported/secured close to grille location
checkpoint-status | a4579235-2ad8-4a4b-b842-6a5acd6f8036 |  | checkpoint | Flexible ducts taped then cable tied
checkpoint-status | dc94b0d0-3172-47b8-914e-bbca3113dd0f |  | checkpoint | Supply cable installed correctly, protected and secured
checkpoint-status | a0743053-3bc6-40ec-bf6a-51d98e926170 |  | checkpoint | Interconnecting cables correctly installed and protected
checkpoint-status | 7c1e1e62-ad62-423a-8a3f-878314d07ffa |  | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
checkpoint-group | 380bf9ee-6069-475d-815c-9fff8cffb20d |  | section | Second Fix SA Fan
checkpoint-status | d8501bac-6149-4c62-a9c8-4c4a1e49fd32 |  | checkpoint | Grilles installed square and level
checkpoint-status | 227d9e5f-1f27-4118-89ce-59ecdc9cf964 |  | checkpoint | Flexible ducts taped then cable tied to grilles/boots
checkpoint-status | 5418e44e-525a-45f8-aa6b-aeb639a266f5 |  | checkpoint | Boots sealed to grilles
checkpoint-status | b11d2d1a-609a-40be-9ae0-8d6a74dcab76 |  | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
checkpoint-status | dc069d3f-bacf-4255-ba7f-62e0769447ef |  | checkpoint | Controllers fitted off. Heater Bank THT set
checkpoint-status | 74931b5a-6410-4d80-8bb2-38b1e2badd68 |  | checkpoint | Power fitted off
checkpoint-status | 7a9abe83-d8ad-491a-9f79-27cab172fef3 |  | checkpoint | Area left clean and tidy, fingerprints removed
checkpoint-status | 7bad3642-64d5-4e4d-9885-502907d7ba8d |  | checkpoint | Plant and controllers labelled
checkpoint-group | 62cebbfc-23bd-4544-90f1-ea12bcf6d3ba |  | section | Commission SA Fan
checkpoint-status | 3968ff3b-5f15-4191-8441-c3b3bff01001 |  | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
checkpoint-status | dd10b8d0-9774-446b-b5c0-5fd95f27be8a |  | checkpoint | Electrical testing complete
checkpoint-status | 8a71ab93-a54f-497b-9db8-b697389f8f52 |  | checkpoint | COC issued
checklist-sectioned | d636fa5d-dc9f-4601-b5ac-ba8530ea9fc5 |  | checklist | Extract Fan |  |  |  |  | Yes | Extract Fan | 2cbc6aea-1c7e-4423-bad7-c8e8491f64eb
checkpoint-group | 265ec06d-ae8b-4618-a89d-8cac152fed47 |  | section | Pre-Start Ext Fan
checkpoint-status | f37e52a5-e75b-4392-b06e-97ba9857b23d |  | checkpoint | Area clear, access good, enough space for install
checkpoint-status | f09da787-5861-4735-b6c6-22bd3b220059 |  | checkpoint | Duct Route clear, Penetrations complete
checkpoint-status | f5b941fa-f94d-4072-8d89-b504b75b457b |  | checkpoint | Nogs/Supports in place
checkpoint-group | afcb5c10-eeac-4264-a6de-dca651e54c13 |  | section | First Fix Ext Fan
checkpoint-status | d866d5ad-62ca-47f5-82ea-1e75422993d1 |  | checkpoint | Fan installed straight and level and correct orientation.
checkpoint-status | 23c2a066-7148-4984-9634-b4629150ded3 |  | checkpoint | Fan or Cowl sealed to Upstand
checkpoint-status | c1693ca9-a0ed-4013-8a06-ecb44064c81f |  | checkpoint | Correct Fan installed
checkpoint-status | f4cb3844-afad-4a1f-8df5-7cbcf269da85 |  | checkpoint | Fan serial No. recorded
checkpoint-status | 1986f37e-29e4-4a09-b334-f9bba2971e4a |  | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
checkpoint-status | 3c67c747-9d4b-44eb-a3ee-7659eec68bbd |  | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
checkpoint-status | b80fa446-cf4c-4987-89b8-39f02fd40459 |  | checkpoint | Flexible ducts run straight/tight/well supported/secured close to grille location
checkpoint-status | 033ac7e1-ae12-41a6-b748-895cd5ba25cb |  | checkpoint | Flexible ducts taped then cable tied
checkpoint-status | 5250f953-0541-47fa-b71f-43b37fca8f0f |  | checkpoint | Supply cable installed correctly, protected and secured
checkpoint-status | 0d0b0252-4826-4b94-ae8c-37133cc6b32d |  | checkpoint | Interconnecting cables correctly installed and protected
checkpoint-status | 42b23fa9-16fa-48f7-b205-96e24ccb79d8 |  | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
checkpoint-group | a866035f-df81-4896-9528-9fe43633ef2c |  | section | Second Fix Ext Fan
checkpoint-status | cbc17682-8c09-4ea7-b4b9-44a8492ccdbe |  | checkpoint | Grilles installed square and level
checkpoint-status | 5e585314-3535-44f4-af31-b2ebe70e6cbe |  | checkpoint | Flexible ducts taped then cable tied to grilles/boots
checkpoint-status | ba999298-f2ff-4eb6-a065-a6315dba5636 |  | checkpoint | Boots sealed to grilles
checkpoint-status | 7a597fd4-98af-4198-bd72-860437eaf096 |  | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
checkpoint-status | 9c63ed63-00fa-49d4-ab01-6a8c27da50e6 |  | checkpoint | Controllers fitted off
checkpoint-status | dd91e5d3-f23d-4aa9-83b4-6618ab6c5773 |  | checkpoint | Power fitted off
checkpoint-status | c12389bb-4e20-4252-9d91-91d45c863698 |  | checkpoint | Area left clean and tidy, fingerprints removed
checkpoint-status | 74c54ab6-481e-4b03-bff1-69b8552204d4 |  | checkpoint | Plant and controllers labelled
checkpoint-group | 367d2224-8a2f-4c3d-8b6b-590e408d376f |  | section | Commission Ext Fan
checkpoint-status | 4ddbe99e-e198-4b94-bc1f-cf447f162025 |  | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
checkpoint-status | 3bbb3535-8554-4b64-ada3-bdc5f41932ba |  | checkpoint | Electrical testing complete
checkpoint-status | 16615620-1495-4f1b-8e84-eaa5b0868400 |  | checkpoint | COC issued
checklist-sectioned | 12fbc86d-47a2-415e-86ff-923f7fb2968f |  | checklist | Kitch Ext |  |  |  |  | Yes | Kitch Ext | 717f319c-ffaa-4a5f-9885-25bdc3afad9d
checkpoint-group | f33104fc-7ba7-4871-b65f-05c7c4767b72 |  | section | Pre-Start Ext Fan
checkpoint-status | fa00a3b9-7e36-46bf-95bb-2e384d0d8e35 |  | checkpoint | Area clear, access good, enough space for install
checkpoint-status | e2c176a3-906e-4270-bbb1-4fc8d75c8e4a |  | checkpoint | Duct Route clear, Penetrations complete
checkpoint-status | a24e0f4d-51b5-4eb0-8225-344f48287ed6 |  | checkpoint | Nogs/Supports in place
checkpoint-group | c6586b71-5d65-4357-be6c-7662167aeff6 |  | section | First Fix Ext Fan
checkpoint-status | 4de6324c-faae-49b8-aee8-c97994594232 |  | checkpoint | Fan installed straight and level and correct orientation.
checkpoint-status | 4349d719-364d-4a52-84cb-5daef34d5d5f |  | checkpoint | Fan or Cowl sealed to Upstand
checkpoint-status | 514edde1-8e3f-46a6-a9d2-70ac1596230d |  | checkpoint | Correct Fan installed
checkpoint-status | 472d64cb-e2b8-4707-988a-788cac0b292c |  | checkpoint | Fan serial No. recorded
checkpoint-status | 92c77a5d-a413-4e36-aaf5-c1b50cac7ced |  | checkpoint | Access Panels in duct for fire dampers, filters, cleaning etc
checkpoint-status | f6fd26ea-2371-419c-a7ea-760dbceadb30 |  | checkpoint | Duct fittings/joins sealed and mechanically fixed to duct. SAB joins sealed
checkpoint-status | 8a8d9d5c-0380-4da3-8906-b16961389c86 |  | checkpoint | Flexible ducts run straight/tight/well supported/secured close to grille location
checkpoint-status | ff8a1e6a-a610-4deb-b7bf-ea46afc6c61f |  | checkpoint | Flexible ducts taped then cable tied
checkpoint-status | 0b12fdc8-76a7-4897-8429-a7007a73500b |  | checkpoint | Supply cable installed correctly, protected and secured
checkpoint-status | 19073390-e016-49d4-91be-e600d8e2e7c4 |  | checkpoint | Interconnecting cables correctly installed and protected
checkpoint-status | 8ec6033b-5a02-4f32-9087-91cd93972c3d |  | checkpoint | Plans marked up for As Builts and 2nd fix grille locations
checkpoint-group | e638ed24-9d28-4dc9-8d26-6f45c4a022c2 |  | section | Second Fix Ext Fan
checkpoint-status | b2fdaea4-7289-442a-82aa-082fabc1d478 |  | checkpoint | Grilles installed square and level
checkpoint-status | a5ec845e-724b-4d6f-937a-5bb228ad9f74 |  | checkpoint | Flexible ducts taped then cable tied to grilles/boots
checkpoint-status | 3bcccbe0-09d3-4a33-a6a8-5c47c4470cd3 |  | checkpoint | Boots sealed to grilles
checkpoint-status | 40c12c9f-fccc-4ad7-96dc-b26b30cb8299 |  | checkpoint | Fans/Filters/Dampers/Access Panels etc all still accessible for maintenance
checkpoint-status | 28461bd6-c4c1-4377-99e4-1d8d181d188c |  | checkpoint | Controllers fitted off
checkpoint-status | 52a8775b-b4fa-4468-8141-00fd94003d8d |  | checkpoint | Power fitted off
checkpoint-status | 565ae8af-da6f-4e8b-a4d9-3d3c1ff635f5 |  | checkpoint | Area left clean and tidy, fingerprints removed
checkpoint-status | 45604dcb-1b5d-4530-a57d-32e5b0d3a980 |  | checkpoint | Plant and controllers labelled
checkpoint-group | cab13d0f-7d91-4f8a-8ede-2c9e2e53f5e5 |  | section | Commission Ext Fan
checkpoint-status | 18a49a57-e68d-4728-8ebb-f9a5ac38d342 |  | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
checkpoint-status | de0c1756-1410-4256-ba54-51cc1feec740 |  | checkpoint | Electrical testing complete
checkpoint-status | b943ee2c-9399-4b0d-a348-53e025728686 |  | checkpoint | COC issued
checklist-sectioned | c2144b71-00fc-40b7-a488-80455f34abdf |  | checklist | Split HW |  |  |  |  | Yes | Split HW | 85f8deee-8d9a-405e-9dce-77ddbf858401
checkpoint-group | ba7e7ce1-fbc8-4a2e-8db5-dfbbccefa8e3 |  | section | Pre-Start HW
checkpoint-status | 2d9da7b0-354a-43cd-91e2-46e402c73c72 |  | checkpoint | Area clear, access good, enough space for install
checkpoint-status | 5da09642-c451-4cf6-9847-13ecb4158659 |  | checkpoint | Area/base ready for outdoor unit
checkpoint-status | 66b653b0-5e4d-406f-8dea-8c1a06cab3f5 |  | checkpoint | Any required drains for outdoor unit in place
checkpoint-status | 5e692fe5-ac38-4221-8b17-16dcd2deab94 |  | checkpoint | Pipework route all clear, penetrations complete
checkpoint-status | d922e4e0-e8f2-4fbe-bc5d-f63507b1436b |  | checkpoint | Nogs in place
checkpoint-status | 8e3598f3-17b0-4092-b2a7-f9d23c6a48aa |  | checkpoint | Drain 1m from Indoor unit location by plumber
checkpoint-group | 1768f3ec-82b7-48f2-9bfa-a6634a5d3bfb |  | section | First Fix HW
checkpoint-status | 77640eb0-df59-43f6-a5f3-290fee20c383 |  | checkpoint | Pipework Insulated complete length
checkpoint-status | 7935ff3e-2478-4a66-90e9-cb38e5ce4242 |  | checkpoint | Drain installed and insulated
checkpoint-status | eb982ab3-42b9-4c4a-a5e7-9769b6177cf8 |  | checkpoint | Supply cable installed correctly, protected and secured
checkpoint-status | c688d5f6-63fb-4477-8bd2-c9beaa50a90e |  | checkpoint | Interconnecting cables correctly installed and protected
checkpoint-group | ebc5a48e-a4d7-4cb6-9cd3-1a69c9791152 |  | section | Second Fix HW
checkpoint-status | ad7d9763-69e9-4701-90b3-5e1e1560b360 |  | checkpoint | System pressure checked and still holding 1st fix pressure
checkpoint-status | 8b29fa31-0872-4f2c-bd9a-b7ffbc158859 |  | checkpoint | Indoor unit secure, level and tight to wall
checkpoint-status | ff8805a5-2d16-4613-aee1-9450abe81604 |  | checkpoint | Correct Indoor unit installed
checkpoint-status | 9fcd79d2-4baa-43a1-83d5-0255131f2906 |  | checkpoint | Outdoor unit secure and level
checkpoint-status | 6fb7608c-c231-4505-b919-2174c9ff737c |  | checkpoint | Correct Outdoor unit installed
checkpoint-status | a0391a5c-8ba5-4736-bb3f-35608acdb65b |  | checkpoint | Indoor unit serial no. recorded
checkpoint-status | 536e43a5-6364-4a47-abee-8a920a7bdf3f |  | checkpoint | Outdoor Unit serial no. recorded
checkpoint-status | 21b37bbf-982e-4e99-80ce-256612f30318 |  | checkpoint | Area left clean and tidy, fingerprints removed
checkpoint-group | 7dd83865-950c-4414-9411-d209aa4cdf4e |  | section | Commission
checkpoint-status | b3525aae-a8b1-4a64-8285-f63bb5817f4f |  | checkpoint | Installer confirmed commissioned and paperwork submitted
checkpoint-status | 8739864f-f8c0-48b0-aeb3-c39bd5b67c22 |  | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
checkpoint-status | a17dd38f-dde7-46a5-91a9-947416103d6c |  | checkpoint | Electrical testing complete
checklist-flat | d54e753c-0e78-44b9-b80a-dc1b08a7b864 |  | checklist | Pre-commencement checks |  |  |  |  | Yes | Pre-commencement checks | 8d6688b6-d409-49d9-aff7-53c2e3991c8f
checkpoint-status | 175c273d-b45e-48ca-bdb8-33b049e64ccb |  | checkpoint | Quality Management Plan Completed, Agreed and Attached
checkpoint-status | 17a73d14-171e-4725-b2de-c4c17dc222e4 |  | checkpoint | Inspection & Test Plan Completed, Agreed & Attached
checkpoint-status | a6d58314-abda-43a5-9d08-15270c3a62c5 |  | checkpoint | Relevant Breakdown & Checklist Setup on Conqa & Reviewed by Main Contractor
checkpoint-status | 03cf4f88-2bab-4bbd-9e53-17863a9c3fd9 |  | checkpoint | Conqa Setup & Project Team Trained & Given Access
checkpoint-status | fef95f0f-ccec-43f4-a6f5-372d80be82ad |  | checkpoint | Review Access Granted to Main Contractor & Relevant Parties
checkpoint-status | ff12aed5-8407-46c7-a0d0-cf0772e59919 |  | checkpoint | Matrix/Insight Setup (if required)
checklist-sectioned | dc6ceccf-f93d-4b6a-8bbc-3d20fbc5aaa1 |  | checklist | Jet Pulse Fan |  |  |  |  | Yes | Jet Pulse Fan | 98286f25-47e8-45a0-bfad-3d6cb4e0f6e5
checkpoint-group | 5ed5cc1d-89f7-46fb-aaa5-fe1ffbdd4613 |  | section | Pre-Start SA Fan
checkpoint-status | f5cbb335-dfe1-44c4-873b-136767fe96da |  | checkpoint | Area clear, access good, enough space for install
checkpoint-status | 42263a70-f446-4a95-947d-c4af248bd9f4 |  | checkpoint | Duct Route clear, Penetrations complete
checkpoint-status | 5ee8bb96-e9f2-43c5-ab18-e43f57d2d95e |  | checkpoint | Nogs/Supports in place
checkpoint-group | da136fbb-8a3f-4697-b4d1-c1b35c2c7b94 |  | section | First Fix SA Fan
checkpoint-status | 57284dfa-31cc-471e-96e3-72826cc1e6e5 |  | checkpoint | Fan installed straight and level and correct orientation.
checkpoint-status | 9455eb90-c52d-48ae-8bbe-b2165cc6925b |  | checkpoint | Correct Fan installed
checkpoint-status | 44de78bb-de45-4bf2-bcc7-8814e828659f |  | checkpoint | Fan serial No. recorded
checkpoint-status | fbfb2a6c-fe52-4c7b-af01-c5c9af2f8409 |  | checkpoint | Fan seismically braced and vibration isolated
checkpoint-status | 91804b91-d614-4fc3-aaa6-1729d221bb60 |  | checkpoint | Supply cable installed correctly, protected and secured
checkpoint-status | 8e400563-8da4-4d03-9687-c7d2e60d9b3f |  | checkpoint | Interconnecting cables correctly installed and protected
checkpoint-status | 366d01f0-4246-4662-ab38-e811a7bd11fb |  | checkpoint | CO sensor installed
checklist-flat | 10846f47-1932-4fa5-aa26-79e270c7b401 |  | checklist | Completion documents |  |  |  |  | Yes | Completion documents | e9238ab0-e3b0-413e-9bdf-5eebc17b86f5
checkpoint-status | be47ea6f-096c-42e7-877c-69eab7da2db0 |  | checkpoint | O&M
checkpoint-status | 96afe1a6-bda8-4d51-82a7-c7c5e68dd901 |  | checkpoint | PS3 Mechanical Service - BCO10328723
checkpoint-status | 9f89bb39-0132-4eac-86f8-4df209004e69 |  | checkpoint | Carbon Monitor & Fantech Checksheet
checkpoint-status | 887d610f-2429-495a-a30c-b3db13a022e5 |  | checkpoint | HVAC - As built
checkpoint-status | 5cdb375e-3461-4660-9bfe-b7e94748ade5 |  | checkpoint | PS3 HVAC - BCO10328723
checkpoint-status | c05f9fc1-0cc5-4e81-9c9a-cb43ef6042aa |  | checkpoint | Electrical Safety Certification
checkpoint-status | 7e3cfb2b-7684-498a-822c-6de568d3a7ab |  | checkpoint | PS4 Seismic Support - BCO10328723