## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | SWMS Checklist |  |  |  |  | Yes | SWMS Checklist | 14f03b2b-6ea9-47ea-853f-3c5cb2a9fc59
checkpoint-status |  |  | checkpoint | SWMS doc uploaded and details enterred below
text | 0f3eb545-ffc3-5133-bff4-ac2b1eb6514d |  | textbox | Name
text | aa6a72ba-b112-5dc9-867b-6b786cfe5eca |  | textbox | Date
checklist-flat |  |  | checklist | Fix 2 ITP |  |  |  |  | Yes | Fix 2 ITP | 29ba4acd-0561-48b8-b4b3-f18c63ea23b2
checkpoint-status |  |  | checkpoint | Only approved fixtures installed
checkpoint-status |  |  | checkpoint | Products checked and have no imperfections
checkpoint-status |  |  | checkpoint | Fixtures installed as per approved drawing locations
checkpoint-status |  |  | checkpoint | No cross-connection on all water lines
checkpoint-status |  |  | checkpoint | Hot water correct temperature & Hot water tempering valve set to 50c +/-5c)
checkpoint-status |  |  | checkpoint | DDA Hot water correct temperature & Hot water tmv set to 42c +/-2c)
checkpoint-status |  |  | checkpoint | Water pressure acceptable 350kpa - 500kpa
checkpoint-status |  |  | checkpoint | Checked all drainage is working correctly wth no leaks
checkpoint-status |  |  | checkpoint | Cleaned out all strainers
checkpoint-status |  |  | checkpoint | Commissioned all fixtures
checkpoint-status |  |  | checkpoint | Final check for any leaks
checkpoint-status |  |  | checkpoint | Area clean - sign off and photos attached below
checklist-flat |  |  | checklist | Hydraulic Pressure Test Record Checklist |  |  |  |  | Yes | Hydraulic Pressure Test Record Checklist | 3ecd9d11-3f1f-4425-8ba4-54a0bac6b37f
checkpoint-status |  |  | checkpoint | Details entered below
text | 982a52a1-0844-5cc3-af72-d59c7b4e10d0 |  | textbox | Description of system being tested
text | 8190c82e-c7f3-5ff3-887f-023ce31d065d |  | textbox | Nominal Working Pressure (KPA)
text | 4cc2967a-b9bb-5182-ba24-f1dddfd0544c |  | textbox | Max Test Pressure (KPA)
text | 07cea4ae-66a3-5a28-b8bb-0a26ba80dd54 |  | textbox | Test Type (Hydro/Air)
text | ddb3401a-15c6-54cf-b56d-2ce4be82c7c6 |  | textbox | Gauges Calibration
text | bd2d9802-8c39-5c1a-be3a-cd6b0cae101f |  | textbox | Time at test
text | 418aa139-ae5d-5be7-8247-d88a7a40596b |  | textbox | Time at test completion
text | 7774688a-c716-566b-bcad-546efe2ec962 |  | textbox | Pressure at completion
text | 2e5347b4-65df-52e9-b972-03bcc0df3f51 |  | textbox | Duration of Pressure Test
checkpoint-status |  |  | checkpoint | Transplumb and witness signoff attached below
holdpoint |  |  | signoff | Request signoff
checklist-flat |  |  | checklist | Fix 1 ITP |  |  |  |  | Yes | Fix 1 ITP | 70dc899a-3a05-4b1c-a846-125d701b876a
checkpoint-status |  |  | checkpoint | Working to an approved drawing
checkpoint-status |  |  | checkpoint | Setout is correct as per current approved drawings
text | 14ada7dc-95c4-5fa9-927e-5862e6e87f44 |  | textbox | Drawing no. & Revision
checkpoint-status |  |  | checkpoint | No cross-connection on all water lines
checkpoint-status |  |  | checkpoint | Support and fixings checked (water hammer/silicone) and in order
checkpoint-status |  |  | checkpoint | All lines new and existing capped for testing
checkpoint-status |  |  | checkpoint | Pressure tested waterlines 1500kpa for 30 mins with start photo attached below
checkpoint-status |  |  | checkpoint | Pressure tested waterlines 1500kpa for 30 mins with finish photo attached below
checkpoint-status |  |  | checkpoint | Fixture waste points heights and centres doubled checked before wall sign off
checkpoint-status |  |  | checkpoint | All suspended drainage has been supported as per AS3500 Requirements
checkpoint-status |  |  | checkpoint | All suspended drainage been flow tested and has no leaks
checkpoint-status |  |  | checkpoint | Please supply photos of all water and waste completetd installations
checkpoint-status |  |  | checkpoint | Area clean & works signed off below
checklist-flat |  |  | checklist | Transplumb General Works ITP |  |  |  |  | Yes | Transplumb General Works ITP | 7181bbf0-b57f-48c8-8f25-7382d65fcf62
checkpoint-status |  |  | checkpoint | Client notified of works to be carried out
button | 240106f7-32a1-5618-be2d-31e1603f486c |  | button | Do any of the works require pressure testing on completion | Yes,No
checkpoint-status |  |  | checkpoint | All requested works completed
checkpoint-status |  |  | checkpoint | Area clean & works signed off below
checklist-flat |  |  | checklist | Transplumb Roofing ITP |  |  |  |  | Yes | Transplumb Roofing ITP | 7da042d9-1888-4cde-b03b-f9625ca9216d
checkpoint-status |  |  | checkpoint | Working to an approved drawing
checkpoint-status |  |  | checkpoint | Only approved materials installed
checkpoint-status |  |  | checkpoint | All fixings correctly installed as per AS 3500
checkpoint-status |  |  | checkpoint | Boxgutters/sump/downpipes installed and clipped correctly as per AS 3500
checkpoint-status |  |  | checkpoint | Flashings installed correctly and siliconed
checkpoint-status |  |  | checkpoint | Testing carried out where possible
checkpoint-status |  |  | checkpoint | Area clean & works signed off below
checklist-flat |  |  | checklist | Take 5 Checklist |  |  |  |  | Yes | Take 5 Checklist | b77b6bea-46d0-4dcc-9846-34acd36f6f13
checkpoint-status |  |  | checkpoint | Task details entered below
text | 1a33097f-a620-5d4d-8cf8-417cefbf70b7 |  | textbox | Task
checkpoint-no-status |  |  | checkpoint | If any of the below are 'Fail' (no) - make yourself aquainted with site requirements before starting work
checkpoint-status |  |  | checkpoint | Have you completed a site induction?
checkpoint-status |  |  | checkpoint | Do you know the site’s health and safety rules?
checkpoint-status |  |  | checkpoint | Are you familiar with security arrangements and the system for reporting incidents, near misses and hazards?
checkpoint-status |  |  | checkpoint | Are you familiar with the emergency facilities and evacuation procedure/route for the site?
checkpoint-status |  |  | checkpoint | Do you have access to appropriate emergency and first aid equipment?
checkpoint-status |  |  | checkpoint | Have you asked the person in charge about all relevant hazards?
checkpoint-no-status |  |  | checkpoint | If any of the below are 'Fail' (no) - follow up with person in charge to ensure your safety
checkpoint-status |  |  | checkpoint | If the work involves a high risk task (such as work at heights, hot-work, confined spaces), has a safe work method statement or job safety analysis been completed?
checkpoint-status |  |  | checkpoint | Do you have the correct procedures, equipment and PPE to do the work safely?
checkpoint-status |  |  | checkpoint | Has equipment that requires a lock/tag-out and/or power that requires isolation/containment been completed?
checkpoint-status |  |  | checkpoint | Is there appropriate separation of vehicles and people during the proposed work?
checkpoint-status |  |  | checkpoint | Is all required electrical/mechanical equipment in a safe condition?
checkpoint-status |  |  | checkpoint | Are all hazardous and/or dangerous goods/substances used and stored according to their material safety data sheets?
checkpoint-status |  |  | checkpoint | Have you consulted with all fellow workers about the task to be completed and the safe way to do it?
checkpoint-status |  |  | checkpoint | Have you got a safe way of getting in and out of your work area?
checkpoint-status |  |  | checkpoint | Have any manual handling risks been identified and assessed?
checkpoint-no-status |  |  | checkpoint | Any additional site specifc hazards or requirements commented below
checklist-flat |  |  | checklist | Events QA ITP |  |  |  |  | Yes | Events QA ITP | c6ad93d6-58a6-48ab-829f-3dcce2b5d4bb
checkpoint-status |  |  | checkpoint | Kitchen layout is correct as per current drawings issued by client
checkpoint-status |  |  | checkpoint | Kitchen layout is correct as per current drawings issued by client
checkpoint-status |  |  | checkpoint | Do all gas appliances have the minimum 500mm clearance from combustible surfaces?
checkpoint-status |  |  | checkpoint | Do all gas appliances have an isolation valve installed and is valve in good condition?
checkpoint-status |  |  | checkpoint | Have all gas appliances been fixed in position?
checkpoint-status |  |  | checkpoint | Are gas flexible hoses installed off the floor?
checkpoint-status |  |  | checkpoint | Have all gas flexible hoses been installed with slack for expansion?
checkpoint-status |  |  | checkpoint | Are the gas LPG bottles installed with the minimum 1500mm clearance from an ignition source and secured to the base plate with chain?
checkpoint-status |  |  | checkpoint | Have all gas appliance been commissioned? Are they working as intended?
checkpoint-status |  |  | checkpoint | Has all tiger tail been installed neatly free of deformation in hoses?
checkpoint-status |  |  | checkpoint | Are all sinks,basins and appliance waste points connected?
checkpoint-status |  |  | checkpoint | Are all sinks, basin and appliance water points connected?
checkpoint-status |  |  | checkpoint | Is hot water unit connected and working as required?
checkpoint-status |  |  | checkpoint | Is macerator unit connected and working as required?
checkpoint-status |  |  | checkpoint | Are sullage tanks and sewer connections in place and connected as required?
checkpoint-status |  |  | checkpoint | All water points have been checked for cross connections
checkpoint-status |  |  | checkpoint | All water pipe has been installed neatly
checkpoint-status |  |  | checkpoint | All water and waste has been checked for leaks and repaired as required
checkpoint-status |  |  | checkpoint | Have all excess plumbing materials been removed from kitchen ready for handover?
checklist-flat |  |  | checklist | Transplumb Variations |  |  |  |  | Yes | Transplumb Variations | e3f950c3-a79a-4a35-9456-e11de2ebfb43
checkpoint-status |  |  | checkpoint | Variation details entered below
text | e76a3ad9-ad2c-51d7-8481-7454765ac768 |  | textbox | Variation Name
text | 769c37c9-1eb8-5055-835a-dac6d0cf7e89 |  | textbox | Variation Description
checkpoint-status |  |  | checkpoint | Materials & Labour Breakdown - Names, Hours & Materials Quantities entered in comments below
checkpoint-status |  |  | checkpoint | Final signoff - any supporting docs and client signature attached below
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | Transplumb Drainage BG ITP |  |  |  |  | Yes | Transplumb Drainage BG ITP | fc7edb0c-678f-4a7b-a44a-c4eae796840f
checkpoint-status |  |  | checkpoint | Working to an approved drawing
checkpoint-status |  |  | checkpoint | Setout is correct as per current approved drawings
checkpoint-status |  |  | checkpoint | Pipe bedding materials comply (as per AS 3500)
checkpoint-status |  |  | checkpoint | Grades, fittings & joints installed to standards
checkpoint-status |  |  | checkpoint | Inspection & Testing carried out prior to backfill
checkpoint-status |  |  | checkpoint | Sealed any open ends
checkpoint-status |  |  | checkpoint | Backfill & compact trenches to code requirements
checkpoint-status |  |  | checkpoint | CCTV on completion
checkpoint-status |  |  | checkpoint | Area clean & works signed off below