## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Take 5 Checklist |  |  |  |  | Yes | Take 5 Checklist | 5782120b-0cf1-4d55-90d2-d8a3ea6bb2a3
checkpoint-status |  |  | checkpoint | Task details entered below
text | 0fd08658-1990-5703-8fd4-49bc100fd85f |  | textbox | Task
checkpoint-no-status |  |  | checkpoint | If any of the below are 'Fail' (no) - make yourself aquainted with site requirements before starting work
checkpoint-status |  |  | checkpoint | Have you completed a site induction?
checkpoint-status |  |  | checkpoint | Do you know the site’s health and safety rules?
checkpoint-status |  |  | checkpoint | Are you familiar with security arrangements and the system for reporting incidents, near misses and hazards?
checkpoint-status |  |  | checkpoint | Are you familiar with the emergency facilities and evacuation procedure/route for the site?
checkpoint-status |  |  | checkpoint | Do you have access to appropriate emergency and first aid equipment?
checkpoint-status |  |  | checkpoint | Have you asked the person in charge about all relevant hazards?
checkpoint-no-status |  |  | checkpoint | If any of the below are 'Fail' (no) - follow up with person in charge to ensure your safety
checkpoint-status |  |  | checkpoint | If the work involves a high risk task (such as work at heights, hot-work, confined spaces), has a safe work method statement or job safety analysis been completed?
checkpoint-status |  |  | checkpoint | Do you have the correct procedures, equipment and PPE to do the work safely?
checkpoint-status |  |  | checkpoint | Has equipment that requires a lock/tag-out and/or power that requires isolation/containment been completed?
checkpoint-status |  |  | checkpoint | Is there appropriate separation of vehicles and people during the proposed work?
checkpoint-status |  |  | checkpoint | Is all required electrical/mechanical equipment in a safe condition?
checkpoint-status |  |  | checkpoint | Are all hazardous and/or dangerous goods/substances used and stored according to their material safety data sheets?
checkpoint-status |  |  | checkpoint | Have you consulted with all fellow workers about the task to be completed and the safe way to do it?
checkpoint-status |  |  | checkpoint | Have you got a safe way of getting in and out of your work area?
checkpoint-status |  |  | checkpoint | Have any manual handling risks been identified and assessed?
checkpoint-no-status |  |  | checkpoint | Any additional site specifc hazards or requirements commented below
checklist-flat |  |  | checklist | SWMS Checklist |  |  |  |  | Yes | SWMS Checklist | fbadff39-5789-4075-bdee-c12b86decc2a
checkpoint-status |  |  | checkpoint | SWMS doc uploaded and details enterred below
text | bc288195-8f95-548f-9097-0f9875a7daa9 |  | textbox | Name
text | a31a71c2-e809-5d4e-99af-ac8e3c24f8da |  | textbox | Date
checklist-flat |  |  | checklist | Fix 2 ITP |  |  |  |  | Yes | Fix 2 ITP | fde70b8d-f37d-4ae5-bdbd-db6d7da9604a
checkpoint-status |  |  | checkpoint | Only approved fixtures installed
checkpoint-status |  |  | checkpoint | Products checked and have no imperfections
checkpoint-status |  |  | checkpoint | Fixtures installed as per approved drawing locations
checkpoint-status |  |  | checkpoint | No cross-connection on all water lines
checkpoint-status |  |  | checkpoint | Hot water correct temperature & Hot water tempering valve set to 50c +/-5c)
checkpoint-status |  |  | checkpoint | DDA Hot water correct temperature & Hot water tmv set to 42c +/-2c)
checkpoint-status |  |  | checkpoint | Water pressure acceptable 350kpa - 500kpa
checkpoint-status |  |  | checkpoint | Checked all drainage is working correctly wth no leaks
checkpoint-status |  |  | checkpoint | Cleaned out all strainers
checkpoint-status |  |  | checkpoint | Commissioned all fixtures
checkpoint-status |  |  | checkpoint | Final check for any leaks
checkpoint-status |  |  | checkpoint | Area clean - sign off and photos attached below
checklist-flat |  |  | checklist | Fix 1 ITP |  |  |  |  | Yes | Fix 1 ITP | fe873d09-4e36-48f5-8848-bec11d82c4c4
checkpoint-status |  |  | checkpoint | Working to an approved drawing
checkpoint-status |  |  | checkpoint | Setout is correct as per current approved drawings
text | 1865a16a-82fc-5112-aa0e-78e0708b66e5 |  | textbox | Drawing no. & Revision
checkpoint-status |  |  | checkpoint | No cross-connection on all water lines
checkpoint-status |  |  | checkpoint | Support and fixings checked (water hammer/silicone) and in order
checkpoint-status |  |  | checkpoint | All lines new and existing capped for testing
checkpoint-status |  |  | checkpoint | Pressure tested waterlines 1500kpa for 30 mins with start photo attached below
checkpoint-status |  |  | checkpoint | Pressure tested waterlines 1500kpa for 30 mins with finish photo attached below
checkpoint-status |  |  | checkpoint | Fixture waste points heights and centres doubled checked before wall sign off
checkpoint-status |  |  | checkpoint | All suspended drainage has been supported as per AS3500 Requirements
checkpoint-status |  |  | checkpoint | All suspended drainage been flow tested and has no leaks
checkpoint-status |  |  | checkpoint | Please supply photos of all water and waste completetd installations
checkpoint-status |  |  | checkpoint | Area clean & works signed off below