## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | 2641cadf-92eb-499a-8fbb-750f777b562d |  | checklist | Bulkhead Area |  |  |  |  | Yes | Bulkhead Checklist QA | 06dec20b-c594-4991-a41f-7632c9fc03d3
checkpoint-group | f36c6093-e19d-48ce-a650-c52558de09ed |  | section | Bulkhead Prestart
checkpoint-status | c7fc3b61-f54f-4b62-9dfc-00f70f489d15 |  | checkpoint | Purlin installation complete
checkpoint-status | 5d010b06-59dd-4b37-b19f-c54c11272476 |  | checkpoint | Batten direction considered for bulkhead lining orientation and fire rated requirements
checkpoint-status | 99bcbd99-d6ad-4216-904c-3012bc0a13c8 |  | checkpoint | Correct materials and quantities on site
checkpoint-status | bc36a203-dc11-4b63-93da-f345f00ec606 |  | checkpoint | Enough transformer ladders on site
checkpoint-status | ed91d194-58ab-43d2-9f62-90d98752c83a |  | checkpoint | General Comments and Queries
checkpoint-group | 8cb7d865-9686-4ceb-a9a0-7744b2710e46 |  | section | Bulkhead Post Checks
checkpoint-status | 785562b1-ce3b-4cc7-b65f-1900b905a192 |  | checkpoint | Bulkhead complete
checkpoint-status | 4538cb0f-f78c-4f22-b7c4-7e68f60b6159 |  | checkpoint | Sides of bulkhead fixed directly to purlin with Tek screws
checkpoint-status | 976c1134-1e4d-4ef2-b828-b5b5a761cd1d |  | checkpoint | No missing clips, solid hangers and strong backs, these are installed using Tek screws
checkpoint-status | 625b7a0b-cef9-410d-a771-d0b8306c3294 |  | checkpoint | Battens are positioned at correct centres for bulkhead lining
checkpoint-status | d19bd38b-024c-4153-b0a9-8b380189a261 |  | checkpoint | Any additional angle required for fixing points installed
checkpoint-status | 0635ed70-b1cc-4066-a979-5c84bbe98345 |  | checkpoint | Site clean and tidy
checkpoint-status | 843bbe2c-077e-40f3-b8c2-b3c6d63867fc |  | checkpoint | General Comments and Queries
checklist-sectioned | 00823e83-a5ad-4e98-8eae-f4033ee10ae5 |  | checklist | Steel Stud checks |  |  |  |  | Yes | Steel Stud checks | 24d45d07-3de6-4b88-882e-cdd45738fd69
checkpoint-group | a739e47c-646d-489a-a1df-b27677793f81 |  | section | Steel Stud Prestart
checkpoint-status | acd8a264-b582-412a-9b01-ce59c3d89f73 |  | checkpoint | Is there a framing layout plan and does it have all necessary details and measurements
checkpoint-status | d0e4e35f-0933-4c8e-b731-fd2eba6f3ee9 |  | checkpoint | Is there a wall type plan and is it clear what walls are needing to be built
checkpoint-status | e2b596c8-80d0-40b3-befe-8e2e7a0a4419 |  | checkpoint | Do we have a door schedule/ door openings
checkpoint-status | 00405209-479e-457e-9609-4fa9ce18188b |  | checkpoint | Is there top connection detail
checkpoint-status | f13c4b18-9ab3-409c-8689-fa133b92be41 |  | checkpoint | Are all services completed and finished
checkpoint-status | 6e5de74c-d440-4825-b06a-81aacd2e79b8 |  | checkpoint | Is the floor clear
checkpoint-status | 52fedc6b-7257-4b48-b942-cd32f639c461 |  | checkpoint | Do we have a clear run and is there anything stopping us from proceeding
checkpoint-status | d67f93bc-5423-4393-857b-833fed8b413e |  | checkpoint | Do we have enough DPC
holdpoint | 8f1e73ba-d3f4-43ba-a462-b3b95b27454c |  | signoff | Area OK to proceed
checkpoint-group | c022a157-694a-4502-8d1c-de2b1cfaf98d |  | section | Steel Stud Post Checks
checkpoint-status | 6682f1ef-ee29-4213-9ad9-4d247a8e0e07 |  | checkpoint | Have we done a check with a level and straight edge
checkpoint-status | b4615fd3-0059-4ff8-a349-b87d8f6c2637 |  | checkpoint | Have we put building square in all internal corners
checkpoint-status | ab94e6f0-aa96-43a7-aea0-6b3d52bd18f9 |  | checkpoint | Have we checked all door openings are correct
checkpoint-status | c621fdc3-02c1-4bc6-acfa-6a4c7d3a0e3e |  | checkpoint | Have we checked all walls are parallel
checkpoint-status | 44f56804-5c25-42d9-9bd8-4b972657b92e |  | checkpoint | Have we installed DPC to all walls
checkpoint-status | 013a0d5c-ef31-4d71-8227-9ba09b0771c4 |  | checkpoint | Do all internal corner junctions have appropriate fixings for plasterboard
checkpoint-status | 4c9ca7b3-8bf6-4bbb-b6f0-057991058665 |  | checkpoint | Have we left appropriate gap for deflection head
checkpoint-status | 89585e61-f1d6-4c3b-85ce-ee158aedd9da |  | checkpoint | Are all materials removed from unit and rubbish taken to bin
holdpoint | 7baa7a60-a76a-4ca5-a5c3-26702c360d73 |  | signoff | Request Signoff
checklist-sectioned | ab248801-f4b3-4f53-b422-7789da9b40f9 |  | checklist | Interior Painting checks |  |  |  |  | Yes | Interior Painting checks | 372ffe91-6964-42a0-a8d9-2a029ddec7c1
checkpoint-group | 5b91451a-7dc8-49af-a6f9-1377f5bc0988 |  | section | Interior Painting Prestart
checkpoint-status | ca35820c-d7ae-42e0-8ed4-ad05a6b5a2af |  | checkpoint | Square stop
checkpoint-status | ba75e3b8-b5f2-4972-ae5b-2ef7d349b0b9 |  | checkpoint | Internal returns
checkpoint-status | 0f220c3f-1792-408a-91e0-196f84ce2cbb |  | checkpoint | Behind cupboards
checkpoint-status | 63f5db07-af1c-4051-9387-00108aff220b |  | checkpoint | Dust in corner top and bottom
checkpoint-status | 337e6d25-1c11-44be-bbe8-1d0964ffde5f |  | checkpoint | Wave in square stop
checkpoint-status | 4fed7382-20ae-4b44-9d5b-55b531920732 |  | checkpoint | Around meters
checkpoint-status | 5b2aa837-117a-4877-8d21-16a272640181 |  | checkpoint | Bathroom shower bottoms
checkpoint-status | 86b6093a-0798-4deb-939e-fbddb8f70691 |  | checkpoint | Switches and plugs cut outs
checkpoint-status | 18f861a7-ad0c-4f2e-8d59-10b7f2ce62c3 |  | checkpoint | Do we require mobile scaffold?
checkpoint-status | af3fbced-98f6-465d-a5e0-a9e7f276492b |  | checkpoint | If yes, have we allowed for it?
checkpoint-status | cda3a63c-ae71-43f9-9c52-d2222d76b885 |  | checkpoint | If yes, has it been quoted or is it a variation?
checkpoint-status | 82b068f8-bcc3-484b-8073-609fae62ae78 |  | checkpoint | Scaffold safe to use/set up safely
checkpoint-status | 460992c9-a4e6-41f5-99f9-9f153a5b7a6e |  | checkpoint | Lumps and bumps
checkpoint-status | 813d8479-c270-4f87-b6b8-dacf94ca1446 |  | checkpoint | General Comments and Queries
holdpoint | 1549ba8a-11e7-4b8a-bdca-2e14534eea8e |  | signoff | Area Ready to Begin
checkpoint-group | 534920e4-f5db-4c2b-9116-f38322fdaba0 |  | section | Interior Painting Post Checks
checkpoint-status | 4c469788-869f-4685-8bc2-dbf280a7b114 |  | checkpoint | Walls
checkpoint-status | fcf2c9a2-6e54-47c5-8d36-4a0c83cd107d |  | checkpoint | Ceilings
checkpoint-status | 2dbe0a73-3fd3-4a3d-b246-8cc91dd80fc0 |  | checkpoint | Doors
checkpoint-status | 9aaa60fa-c144-4300-93b2-ee69c8429365 |  | checkpoint | Trims
checkpoint-status | a6495d3e-bda5-4bd1-8856-ab77bdb34054 |  | checkpoint | Skirting
checkpoint-status | 323edc41-8270-4716-ac36-47f0b4e16dc2 |  | checkpoint | Windows
checkpoint-status | 17a750ee-780b-4866-8185-96d4d1c1da47 |  | checkpoint | Site left clean and tidy
checkpoint-status | c9af2ea2-b65f-4824-ab7d-a0fe19ce5572 |  | checkpoint | Paint to be left on site
checkpoint-status | 56335b57-b97c-4a85-a461-21b58a5d8280 |  | checkpoint | General Comments and Queries
holdpoint | a52e807f-6f7a-4f93-837b-b0716856fe62 |  | signoff | Request Signoff
checklist-sectioned | ed48b637-8ba9-4508-afb3-640d6367caf0 |  | checklist | Interior Painting QA |  |  |  |  | Yes | SYS - Interior Painting QA | 3cf2d739-3e46-47df-9533-cfe686dc1c70
checkpoint-group | f45db81c-06f6-4240-a381-8ddd52c5adea |  | section | Interior Painting Prestart
checkpoint-status | 561235da-2692-4953-b1af-e1607cf477aa |  | checkpoint | Sqaure stop
checkpoint-status | a2b90e62-987a-4740-a74b-e43b3852242d |  | checkpoint | Internal returns
checkpoint-status | 33c0c81e-3be9-44fb-8fd0-fbf5b5e5f01e |  | checkpoint | Behind cupboards
checkpoint-status | 91ed1245-526e-46e2-868c-5d490ba3c466 |  | checkpoint | Dust in corner top and bottom
checkpoint-status | 3f3a7273-699f-47b6-862e-c5f9932d9406 |  | checkpoint | Wave in square stop
checkpoint-status | 23b29974-789e-4a81-bb2f-a57b47dae2d6 |  | checkpoint | Around meters
checkpoint-status | e3d0fe8f-1e4e-41a8-b3a8-63c2f34de659 |  | checkpoint | Bathroom shower bottoms
checkpoint-status | df0ac560-b557-4dcc-bd8f-d03467c02d71 |  | checkpoint | Switches and plugs cut outs
checkpoint-status | e46bc174-2ad1-4288-a2a3-1fb9af29c94a |  | checkpoint | Do we require mobile scaffold?
checkpoint-status | f3dbc80e-d31c-41a8-87c9-d3234c4d57eb |  | checkpoint | If yes, have we allowed for it?
checkpoint-status | ffafe78e-3152-4079-917b-369551f78224 |  | checkpoint | If yes, has it been quoted or is it a variation?
checkpoint-status | 3b094714-88d9-4546-811e-ec3c7099d5a7 |  | checkpoint | Scaffold safe to use/set up safely
checkpoint-status | 3ddccd0c-4751-4180-99cb-9fce2493705a |  | checkpoint | Lumps and bumps
checkpoint-status | 5a209b6b-9d21-402a-8fd5-221c57082edc |  | checkpoint | General Comments and Queries
holdpoint | 459a9281-a824-4eca-99d6-d33c5fb473ed |  | signoff | Area Ready to Begin
checkpoint-group | 69642060-9d1c-436a-bb55-8e68148340ab |  | section | Interior Painting Post Checks
checkpoint-status | e8d65da9-48ec-489e-9d7a-f41ec801c8a7 |  | checkpoint | Walls
checkpoint-status | befc1bd4-819b-4bd3-b8a8-b16afbe6b6b7 |  | checkpoint | Ceilings
checkpoint-status | 54ec3bd5-4dad-4210-a73c-ecdbb75eaec1 |  | checkpoint | Doors
checkpoint-status | fa1cb242-3c92-4fe7-b1ab-3660820dc53b |  | checkpoint | Trims
checkpoint-status | 36d9e246-6d1b-4ade-967e-ded572f805b6 |  | checkpoint | Skirting
checkpoint-status | 1a7a215d-bfff-474a-bd88-97c465d481f8 |  | checkpoint | Windows
checkpoint-status | 73905344-35d6-416d-a168-ff03e67f653c |  | checkpoint | Site left clean and tidy
checkpoint-status | e89c9750-1114-4791-bd1e-2c7538999af9 |  | checkpoint | Paint to be left on site
checkpoint-status | 65d1858c-21d9-4552-840e-7e30b0d31176 |  | checkpoint | General Comments and Queries
holdpoint | 31e72e97-8182-44dc-bbf7-56a326683a56 |  | signoff | Request Signoff
checklist-sectioned | b4934568-e417-4f09-ba9b-8f1528bb5267 |  | checklist | Stopping QA |  |  |  |  | Yes | Stopping QA | 3fb93e90-4fd2-4e37-b68e-8d9ede0e8efa
checkpoint-group | 190e1244-9367-4136-bfb5-912cc6706835 |  | section | Stopping Prestart
checkpoint-status | 2dbaca71-14ad-45fc-912d-49bea0fd6817 |  | checkpoint | Do we require mobile scaffold?
checkpoint-status | da49ff39-cb6b-4b03-8d1d-7eac72b79813 |  | checkpoint | If yes, have we allowed for it?
checkpoint-status | c5414013-4b24-4ac2-931e-e125f0ef80be |  | checkpoint | If yes, has it been quoted or is it a variation?
checkpoint-status | 90cd01e1-ea07-43bd-8de1-a33f2b335307 |  | checkpoint | Scaffold safe to use/set up safely
checkpoint-status | 7c7c98a4-9ac9-4467-9c11-f8f7ed79188d |  | checkpoint | Bracing walls fixed correctly
checkpoint-status | 204dc8f7-0035-4f83-abf6-6c547ba8d6a2 |  | checkpoint | No proud screws
checkpoint-status | cb1db19e-3518-4be7-b812-977bc7f39bce |  | checkpoint | No overdriven screws
checkpoint-status | 12bf7949-10e6-41e6-89f1-e45f5ce09cba |  | checkpoint | Backblocking of joins as per Troake Backblocking guidelines
checkpoint-status | 69f4b686-f3a4-4242-8ad5-3bccb91b6740 |  | checkpoint | All areas of broken GIB dug out and ready for pre-filling
checkpoint-status | aed55be7-0fd5-4de2-adfe-66364b0889bc |  | checkpoint | Sheets layout correct and in consideration of critical light
checkpoint-status | f6a93e3e-a10d-4260-925a-c5dc866d1bd8 |  | checkpoint | Grooved liners fitted correctly if present
checkpoint-status | d90de173-723f-4d46-b1d9-4c20ed01675a |  | checkpoint | All joins as per GIB site Guide above windows and doors etc
checkpoint-status | 475ffcdf-8542-4631-a4f3-1107caf299b9 |  | checkpoint | General Comments and Queries
holdpoint | 4511c99a-1439-4c3d-9233-18804c242e92 |  | signoff | Area Ready for Stopping
checkpoint-group | 6abf090c-5b87-4e4e-ac74-4af91c772347 |  | section | Stopping Post Checks
checkpoint-status | 0dce3e1f-d0ee-4a5d-9bca-22f8b21f5085 |  | checkpoint | All work completed to GIB® Site Guidelines
checkpoint-status | fbc5d6b6-cce4-457b-a3a7-b63b0b3f8873 |  | checkpoint | Screws adequately covered
checkpoint-status | 776897c7-cd31-4f37-bed2-2922af0dd7b3 |  | checkpoint | Joints flat and level
checkpoint-status | 00ad6448-44aa-40eb-a9e4-7228e5630841 |  | checkpoint | Square stop and corner joints square/ straight to the eye
checkpoint-status | df898c14-70fc-4e09-9260-d0a7cb4c0578 |  | checkpoint | GIB® Cove joints acceptable
checkpoint-status | 5b6964a7-7ee9-4e92-8eb2-055bd8a6354e |  | checkpoint | Floors scraped clean
checkpoint-status | fb27c42a-47d1-4a76-9a7e-17fbbef767b1 |  | checkpoint | All slimlines, J-moulds, negative detail or any other finishing completed plumb, level square and straight to the eye
checkpoint-status | 737672b4-8e2c-4754-97b5-23ded8018a8d |  | checkpoint | Light check complete
checkpoint-status | becef61c-66ea-4ff3-8b5e-a7973e4b1f3c |  | checkpoint | Materials to be picked up from site
checkpoint-status | 3e2f9d63-d889-4610-8036-27033d062f17 |  | checkpoint | Site left clean and tidy (attach photos)
checkpoint-status | cedfa7a6-b639-4a07-9b58-e4a5bd741ee3 |  | checkpoint | General Comments and Queries
holdpoint | 4bfbd36b-5d96-46aa-9291-20f6f54980f6 |  | signoff | Request Signoff
checklist-sectioned | 83beddcf-4814-4a69-aa5b-de0e7b71e647 |  | checklist | Insulation QA |  |  |  |  | Yes | Insulation QA | 478d022a-222d-423e-857a-afb5b98874cb
checkpoint-group | 6cd43f8e-aa87-43ab-b247-523921bbb76b |  | section | Insulation Prestart
checkpoint-status | 4eede55f-e5fb-4cc5-95c2-1e3504bdcb00 |  | checkpoint | Metal Ceiling Grid Completed
checkpoint-status | 365db4c5-9e88-49fe-95bc-2e83804f93a1 |  | checkpoint | All nogs installed as required
checkpoint-status | 9623c01c-d78e-4dae-8d5b-3b79e5856da2 |  | checkpoint | Electrical wiring completed
checkpoint-status | 8c94e943-d4b3-405d-bddf-51a9ab183cb5 |  | checkpoint | Plumbing completed
checkpoint-status | 1fd5f4c3-fd3a-4af6-b3e8-d3b52249af87 |  | checkpoint | Which walls and ceilings are to be insulated?
checkpoint-status | d32aa2db-8c1d-41f6-bc97-9e0f7d7aff46 |  | checkpoint | Do we require mobile scaffold?
checkpoint-status | 31d50c77-4d2a-4328-bc2c-fc5c1be81bcb |  | checkpoint | If yes, have we allowed for it?
checkpoint-status | 6139e71c-4e8e-4b2c-888e-5a1e2decfd20 |  | checkpoint | If yes, has it been quoted or is it a variation?
checkpoint-status | a729d48a-882b-41c2-8fd3-14c3b90229cf |  | checkpoint | Scaffold safe to use/set up safely
checkpoint-status | ffbe2831-5615-443c-a49e-5f72bca53d75 |  | checkpoint | Garage included or excluded?
checkpoint-status | 03d1a169-77dd-4e69-a8bb-7abc6f261370 |  | checkpoint | Any noise reduction batts to walls or midfloors
checkpoint-status | 6d418661-460b-4cb7-8dd0-760ebc0721da |  | checkpoint | Site clean and tidy
checkpoint-status | 310f8d36-31f7-4f43-8142-737b5f1136c8 |  | checkpoint | All left over materials and rubbish removed
checkpoint-status | 83b62faa-38f7-4a1f-a03e-cd777311b10d |  | checkpoint | General Comments and Queries
holdpoint | cf70a015-4391-45d5-9074-4df350ab4194 |  | signoff | Work completed as per spec
checkpoint-group | 123e70c3-ec12-4308-919a-7fa58dbff268 |  | section | Insulation Post Check
checkpoint-status | 4613f761-a45c-4242-9bd8-741f62cfe417 |  | checkpoint | Ceiling Batts installed correctly and no gaps left
checkpoint-status | b2951bca-2658-48af-b859-1666939770aa |  | checkpoint | Wall batts installed correctly and no gaps left
checkpoint-status | 2d2f8f74-b17a-442f-b1a8-5f6810b607f4 |  | checkpoint | No proud insulation?
checkpoint-status | a20a4c65-b67f-4ab1-b3a6-9f41c61cfa76 |  | checkpoint | Insulation cut around (not over) pipes etc to prevent bulging of sheets
checkpoint-status | 16496e91-157b-4c21-83fd-7cb1bb12a09a |  | checkpoint | Noise reduction batts installed to walls or midfloors
checkpoint-status | 20e10ed8-b452-414a-ac15-6b38fb96bd21 |  | checkpoint | Site clean and tidy ready for next trade?
checkpoint-status | 05259f8a-399b-4724-a21c-2bd00f1f4be8 |  | checkpoint | General Comments and Queries
holdpoint | 7b6d7613-d938-4f84-a8b2-a19061fe6637 |  | signoff | Request signoff
checklist-sectioned | 2c13d301-d624-4536-8775-8f8edfe10d50 |  | checklist | Bulkhead Lining |  |  |  |  | Yes | Bulkhead Lining Checklist QA | 479a6967-991f-4b96-9ec0-528676e10025
checkpoint-group | 4f03c71c-58f5-49d1-aa35-b39ea0adc9ed |  | section | Bulkhead Lining Prestart
checkpoint-status | 3c06bfcf-3690-4b35-85a9-43f39a8a6af1 |  | checkpoint | Roofing and waterproofing complete
checkpoint-status | f2a076ff-5c3d-4880-8dca-41e51080997c |  | checkpoint | Timber nogging complete
checkpoint-status | c4262c3d-f2c4-445d-ac85-afde3acc9b88 |  | checkpoint | Bulkhead has been installed with correct centres for fire rated fixing
checkpoint-status | f2206370-61a5-4c66-a31e-be903d614253 |  | checkpoint | No missing fixings, clips or supports
checkpoint-status | 773f4ea2-f09b-4c8f-babc-49aa9482ec46 |  | checkpoint | Fyreline board and GIB grabbers are on site ready for install
checkpoint-status | 098a72e6-ce3d-4fcf-b1c2-a626c0943df7 |  | checkpoint | Site clean and tidy of excess materials
checkpoint-status | aee3ff74-ebd9-406e-8e7e-5d7470869f42 |  | checkpoint | General Comments and Queries
checkpoint-group | 0a85a90a-1d75-4ef9-b857-166a8abff781 |  | section | Bulkhead Lining Post Checks
checkpoint-status | 51a45e6f-36a5-45a7-835f-95f273f13be4 |  | checkpoint | All work completed to GIB Site Guidelines
checkpoint-status | f9557588-6cd0-4d01-9237-54886b9627e0 |  | checkpoint | All work completed to GIB Fire Rated Systems, screwed off to manufacturers specifications and have been checked against plan
checkpoint-status | 4fc949ba-a581-4e35-9998-be49b39f4ef9 |  | checkpoint | First layer of bulkhead has been fire sealed
checkpoint-status | a80fb3ae-a31d-4926-9ccb-e50b533e6101 |  | checkpoint | Second layer of bulkhead has been fire stopped
checkpoint-status | 2ce3434d-8fe5-4d42-a2d6-8e70a2737dbc |  | checkpoint | Site left clean and tidy
checkpoint-status | 83256c57-4f4b-445b-8b91-2a0e3f1bdf93 |  | checkpoint | General Comments and Queries
checklist-flat | 905ad6c6-b432-412d-9804-b087c6bbbaff |  | checklist | Precommencement checks |  |  |  |  | Yes | Precommencement checks | 6ea5bff0-8b82-4a36-8df9-5014e8b2a450
checkpoint-status | cc51abb7-09b0-4904-883a-611bb2ac076b |  | checkpoint | Quality Management Plan Completed, Agreed & Attached
checkpoint-status | 7185ec5e-1687-4b43-b55a-14a2306621f6 |  | checkpoint | Inspection & Test Plan Completed, Agreed & Attached
checkpoint-status | 70ffe6cb-61a6-41d4-8587-83032c6359c2 |  | checkpoint | Relevant Breakdown & Checklists Setup on Conqa & Reviewed by Main Contractor
checkpoint-status | 35b3dd64-3148-48ee-9cac-0d847e7f159b |  | checkpoint | Conqa Setup & Project Team Trained & Given Access
checkpoint-status | 91c0d556-d042-4e0f-b042-48cbc781f1fe |  | checkpoint | Review Access Granted to Main Contractor & Relevant Parties
checkpoint-status | a98cbe22-7d06-4680-b4f0-31bb6ac73f3f |  | checkpoint | Matrix/Insights Setup (if required)
checklist-sectioned | 6230541d-b11f-414e-a715-1db5d1a2c4bb |  | checklist | Insultation checks |  |  |  |  | Yes | Insultation checks | 81137eaf-d06b-4992-9e48-0e4c6a53930c
checkpoint-group | 0813ecc6-a872-4ca7-bdde-cba71c84c195 |  | section | Insulation Prestart
checkpoint-status | c3564db3-8941-4eb8-8fa1-e21e0f6ad5d7 |  | checkpoint | Metal Ceiling Grid Completed
checkpoint-status | 464baf46-0c4a-46b4-aed7-027d39e4c6d1 |  | checkpoint | All nogs installed as required
checkpoint-status | 7ae0ab05-314f-460c-9d0d-05f69150c799 |  | checkpoint | Electrical wiring completed
checkpoint-status | 6dbc9853-9a30-4d56-9ae7-5da9f6916834 |  | checkpoint | Plumbing completed
checkpoint-status | 3b981797-7a34-4813-b916-54fbfa55b20d |  | checkpoint | Which walls and ceilings are to be insulated?
checkpoint-status | b691dcbb-5f43-466b-bb3b-e25b05103d0b |  | checkpoint | Garage included or excluded?
checkpoint-status | dca336a4-8754-4ac1-88c1-1508c300fd5f |  | checkpoint | Any noise reduction batts to walls or midfloors
checkpoint-status | 07db4642-e177-4c00-beaf-7e0aaff917e5 |  | checkpoint | Site clean and tidy
checkpoint-status | ea7b0a2b-f45d-42bc-9635-b4951fe3a33c |  | checkpoint | All left over materials and rubbish removed
checkpoint-status | e1477e6f-d946-4890-8a0d-540907b4e95c |  | checkpoint | General Comments and Queries
holdpoint | 25814d92-f93a-4eac-b521-1e70cbd67990 |  | signoff | Work completed as per spec
checkpoint-group | 1ba64ea7-5810-4d8e-aece-b037b3940765 |  | section | Fixing Prestart
checkpoint-status | d6a350e4-e866-4d7b-8f84-21489de9f644 |  | checkpoint | Exterior Cladding complete
checkpoint-status | dca922b8-07b4-4225-abd3-0eb76e24fadd |  | checkpoint | Joinery installed
checkpoint-status | a70a6ec4-6333-4e90-97b6-dd81a9cd60a2 |  | checkpoint | Doors liners installed including cavity sliders
checkpoint-status | b62fa338-3a94-4b78-94ce-64a6a4ccf263 |  | checkpoint | Grooved jams big enough (12mm for 10mm and 15mm for 13mm) on doors and windows
checkpoint-status | afc36274-9bf0-4417-95a6-1dfa8016f677 |  | checkpoint | Walls checked to be level and planed if necessary with no protruding nogs
checkpoint-status | 77245fea-d19a-48f9-ab58-ee1f1ac70e94 |  | checkpoint | Metal ceiling battens running in the same direction and in consideration of critical light
checkpoint-status | 5c075abe-06e1-49df-8b2f-2c5f293be756 |  | checkpoint | No missing hangers or clips on Metal ceiling battens
checkpoint-status | 04f6ee52-f753-415b-a6fe-1e5d72c84d57 |  | checkpoint | No proud screws on any of the metal ceiling battens or wall strapping
checkpoint-status | 41dbe6fc-7820-4ab2-97db-992fe9665c9d |  | checkpoint | Wall angle fixed off completely and corners fixed
checkpoint-status | 81f6f9da-b310-4387-89b9-0f1a6b56b354 |  | checkpoint | All battens secure
checkpoint-status | 99704f0b-421d-48b8-81b2-7051013855b0 |  | checkpoint | Beam framing checked and acceptable
checkpoint-status | ef69221b-c60f-4a95-a596-15530d438ab0 |  | checkpoint | Batten joins offset
checkpoint-status | 8d0d44b1-e4fa-4e66-978b-1bb817941ad6 |  | checkpoint | Brace walls have brackets or straps at each end of the element
checkpoint-status | df433118-aa1d-4fa0-81e5-1d380612182b |  | checkpoint | Services installed completely
checkpoint-status | fe57cc66-aa72-4043-920a-548395581a45 |  | checkpoint | Site clean and tidy of excess materials
checkpoint-status | ec7e7e60-2448-42cf-8039-3dd886ea07cb |  | checkpoint | Do we require mobile scaffold?
checkpoint-status | 545526a3-5fa5-4c54-986f-18347c0eb9cb |  | checkpoint | If yes, have we allowed for it?
checkpoint-status | ad276241-2e4c-4bef-8c95-c4011449cbba |  | checkpoint | If yes, has it been quoted or is it a variation?
checkpoint-status | 4eb2b4be-45ff-42a8-88e4-8c2fd1573c72 |  | checkpoint | Scaffold safe to use/ set up safely
checkpoint-status | e9139516-71f0-43dd-ad48-1f3a2bec211f |  | checkpoint | General Comments and Queries
holdpoint | f1a4e4b9-f714-4f73-8891-64d02e6546d6 |  | signoff | Work Completed as per Spec
checkpoint-group | 664ed142-76d2-4dbf-a483-3e4370210edb |  | section | Insulation Post Checks
checkpoint-status | a849384d-1e23-47b8-ba97-45d22d2aaf7c |  | checkpoint | Ceiling Batts installed correctly and no gaps left
checkpoint-status | 45236d8a-4b0f-4c6a-bb33-7558542346ab |  | checkpoint | Wall batts installed correctly and no gaps left
checkpoint-status | 12172e09-79c3-439d-a7f0-d5989dfd5b1f |  | checkpoint | No proud insulation?
checkpoint-status | 22aad7cb-7d6e-48f9-9537-c69c8d885af5 |  | checkpoint | Insulation cut around (not over) pipes etc to prevent bulging of sheets
checkpoint-status | 0a298c5d-909d-43ce-92ab-1f780512568b |  | checkpoint | Noise reduction batts installed to walls or midfloors
checkpoint-status | 9dc84672-a9cf-4a9f-88f7-fc1adc18470f |  | checkpoint | Site clean and tidy
checkpoint-status | b3d40c3d-97b8-45c8-99a2-75a162e2770b |  | checkpoint | Do we require mobile scaffold?
checkpoint-status | 8c359dd9-b240-46df-800e-3d309d1dee6d |  | checkpoint | If yes, have we allowed for it?
checkpoint-status | 1d1681a6-5fc4-4cd2-b20c-1221acc9f391 |  | checkpoint | If yes, has it been quoted or is it a variation?
checkpoint-status | 3f852e2c-c350-4990-93a6-df47b422976f |  | checkpoint | Scaffold safe to use/set up safely
checkpoint-status | 406d0bec-a334-444f-906c-cababbfb57e1 |  | checkpoint | All left over materials and rubbish removed?
checkpoint-status | a9fb9fa7-9a77-4ec5-9112-f0bc81e57f87 |  | checkpoint | Site clean and tidy ready for next trade?
checkpoint-status | e7afc0b0-c688-4347-90d8-e0fa526b0461 |  | checkpoint | General Comments and Queries
holdpoint | 231293f5-187e-49e3-8d99-7191e2db1fff |  | signoff | Request signoff
checkpoint-group | 4788e708-3208-4f25-bf15-cffcfe950d7c |  | section | Fixing Post Checks
checkpoint-status | 171e3cd9-2357-49e3-8695-6005aae6b8fc |  | checkpoint | All work completed to GIB® Site Guidelines
checkpoint-status | 1d4d2209-5039-4483-86e1-4c4009eec1a2 |  | checkpoint | Fire rating, bracing elements and wet areas are screwed off to manufacturers specifications and have been checked against plan
checkpoint-status | 26c0df2c-e793-4654-a130-1b5f379f7d05 |  | checkpoint | All sheets have had centre screws on packers
checkpoint-status | 60e6afc4-ffae-42fe-b504-29494cf72b91 |  | checkpoint | Butt joins, ceiling taper edges and stairwell taper edges are back blocked as per Troake Guidelines
checkpoint-status | 7683a6e6-ef1c-4158-8a97-4412e886e2bc |  | checkpoint | Pipes are market on the face of the sheet. Wires within nailing distance marked
checkpoint-status | b66e2250-9e81-49c6-8394-f780b40e82a8 |  | checkpoint | All plugs and penetrations have been marked on the floor and have been cut neatly and correctly
checkpoint-status | c4152f23-e9b5-43c5-bb5b-4253f1b488a5 |  | checkpoint | All plasterboard correctly fitted into rebated jambs
checkpoint-status | aa4a79fa-11e9-4114-9f18-7658449f7f50 |  | checkpoint | All sheets 5-10mm above floor (unless specified)
checkpoint-status | d59566de-4c69-460f-b1b6-f3d72b2df893 |  | checkpoint | Back block stick and centre screws removed
checkpoint-status | db7353db-5981-4f02-b370-e41b85d54f3c |  | checkpoint | Site left clean and tidy (attach photos)
checkpoint-status | 98115f66-4029-4717-8e4b-5c656dc80041 |  | checkpoint | Site Hazard Checklist Completed (attach photos)
checkpoint-status | 4513003d-7f85-4e7b-97ea-9ff3cd9a66e5 |  | checkpoint | General Comments and Queries
holdpoint | 229aed83-fc21-4e5c-a83c-1e59fd2c965c |  | signoff | Request Signoff
checklist-sectioned | 2bf33fdf-e91a-4d69-aaa3-ef019f4f62dc |  | checklist | Fixing QA |  |  |  |  | Yes | Fixing QA | 857d9a64-d823-4d26-b4dd-7beedbe6a94e
checkpoint-group | 6961080f-673f-4d64-b1d7-97e23db8c8a6 |  | section | Fixing Prestart
checkpoint-status | a95a3d4c-8e48-48ae-afd8-2782802db1c8 |  | checkpoint | Exterior Cladding complete
checkpoint-status | e0b664ca-1da4-4a97-8044-a23114c158e8 |  | checkpoint | Joinery installed
checkpoint-status | 7dbeaa8f-98bf-4055-9aee-db273060e1f7 |  | checkpoint | Doors liners installed including cavity sliders
checkpoint-status | 68212369-a7e1-4efd-b6b2-6305416d918b |  | checkpoint | Grooved jams big enough (12mm for 10mm and 15mm for 13mm) on doors and windows
checkpoint-status | cefbab7c-6c7b-48ea-b897-ad0d001c6cf6 |  | checkpoint | Walls checked to be level and planed if necessary with no protruding nogs
checkpoint-status | b237b9f5-3dbb-4575-b4ba-b7de6072ce90 |  | checkpoint | Metal ceiling battens running in the same direction and in consideration of critical light
checkpoint-status | 6f8a5b16-7560-4bb0-852c-34733d22b24f |  | checkpoint | No missing hangers or clips on Metal ceiling battens
checkpoint-status | 826430b0-3d26-4f05-a2be-f1987c7fc054 |  | checkpoint | No proud screws on any of the metal ceiling battens or wall strapping
checkpoint-status | b06aaa3c-a663-41a4-91be-e2bf568c3e96 |  | checkpoint | Wall angle fixed off completely and corners fixed
checkpoint-status | b49ed157-3d9e-41eb-a95d-abbf634f1c57 |  | checkpoint | All battens secure
checkpoint-status | ade77728-9a9a-412c-b813-2776010b3ea0 |  | checkpoint | Beam framing checked and acceptable
checkpoint-status | 5446aecd-2ef6-411b-afaf-6e79575a13a9 |  | checkpoint | Batten joins offset
checkpoint-status | f47e5239-63a2-43ac-872d-47de6cb5349d |  | checkpoint | Brace walls have brackets or straps at each end of the element
checkpoint-status | 0c7a8999-7785-46cd-84f8-928a18d06a87 |  | checkpoint | Services installed completely
checkpoint-status | d4d8d2fd-c709-4b08-9f6e-c235750056fb |  | checkpoint | Site clean and tidy of excess materials
checkpoint-status | d9a5e5f1-f142-422a-bcff-ffbc171b7c73 |  | checkpoint | Do we require mobile scaffold?
checkpoint-status | 990afdc3-08d8-4482-b6ef-71773fb2ae99 |  | checkpoint | If yes, have we allowed for it?
checkpoint-status | 0fee1f38-cacc-4824-936d-7551660a3e79 |  | checkpoint | If yes, has it been quoted or is it a variation?
checkpoint-status | 50937301-e492-4779-9b5e-a33230ac17d4 |  | checkpoint | Scaffold safe to use/ set up safely
checkpoint-status | 86d22ab9-0c37-4a7b-8729-09d94454e6ad |  | checkpoint | General Comments and Queries
holdpoint | 2048a43a-4941-43f4-84da-d8eef56c023f |  | signoff | Work Completed as per Spec
checkpoint-group | 5ebf4648-1c8c-445f-80eb-9f82c8511e18 |  | section | Fixing Post Checks
checkpoint-status | ef017e35-fe23-4d41-936f-40e41f91db23 |  | checkpoint | All work completed to GIB® Site Guidelines
checkpoint-status | 3c8e3d87-dc0c-43c7-a213-7242ed676732 |  | checkpoint | Fire rating, bracing elements and wet areas are screwed off to manufacturers specifications and have been checked against plan
checkpoint-status | 9daa8f2f-485c-4f93-b22c-41957684524f |  | checkpoint | All sheets have had centre screws on packers
checkpoint-status | 34772c68-7c8e-4d2f-94a9-3602f0fc1baf |  | checkpoint | Butt joins, ceiling taper edges and stairwell taper edges are back blocked as per Troake Guidelines
checkpoint-status | 5594563a-06c1-4490-827e-23d2a9f458ee |  | checkpoint | Pipes are market on the face of the sheet. Wires within nailing distance marked
checkpoint-status | 30369158-e408-4229-bc00-f44a3514fd74 |  | checkpoint | All plugs and penetrations have been marked on the floor and have been cut neatly and correctly
checkpoint-status | 4566cda3-24bf-413d-bd9a-418f83fd7d33 |  | checkpoint | All plasterboard correctly fitted into rebated jambs
checkpoint-status | a885c2e7-b705-4bd7-b4c4-332cd94beaf4 |  | checkpoint | All sheets 5-10mm above floor (unless specified)
checkpoint-status | bd39567e-df22-4df4-8b7e-e42fea018631 |  | checkpoint | Back block stick and centre screws removed
checkpoint-status | cd6e92e6-4d45-49d3-b469-44c5c215dcd6 |  | checkpoint | Site left clean and tidy (attach photos)
checkpoint-status | 7efd65fa-0491-46af-9f9b-607829f5241b |  | checkpoint | Site Hazard Checklist Completed (attach photos)
checkpoint-status | 2655febf-0a3c-4432-b4a8-5aad0b2aa28f |  | checkpoint | General Comments and Queries
holdpoint | d86b8603-23e9-447b-84a1-c725ed5d6436 |  | signoff | Request Signoff
checklist-sectioned | f57ec235-0577-4e33-8869-d5775f878002 |  | checklist | Exterior Painting QA V2 |  |  |  |  | Yes | Exterior Painting QA V2 | 892fa57b-e43d-4be4-a7ae-da03ca3004fe
checkpoint-group | 8531a0ba-d96a-46be-a3b1-528495b4916a |  | section | PrePaint QA
checkpoint-status | 54e5fff3-8d30-413b-bbc2-334ef0623ea7 |  | checkpoint | Square stop
checkpoint-status | 68759b88-e837-4cbc-91a1-d8423ce09205 |  | checkpoint | Internals returns
checkpoint-status | 01716686-08fc-4786-8c97-7a51142a82a7 |  | checkpoint | Behind cupboards
checkpoint-status | 4f2ccce3-f1d6-425c-9909-28ad28cf1431 |  | checkpoint | Dust in corner top and bottom
checkpoint-status | f57ead42-b9f4-4c21-986a-0186f3b8e6e1 |  | checkpoint | Wave in square stop
checkpoint-status | 7517fafb-d24e-4a59-9604-d7985d1eaa17 |  | checkpoint | Around meters
checkpoint-status | 91fecd1c-be8f-4410-af5f-4d04bc7b7d5d |  | checkpoint | Bathroom shower bottoms
checkpoint-status | 0f634606-0ebe-4c61-bfc2-dc8404fa1c34 |  | checkpoint | Switchers and plugs cut outs
checkpoint-status | a68231f0-a3f5-4a73-a7f1-e4c5add66074 |  | checkpoint | Lumps and bumps
checkpoint-group | ebb7f01a-71e1-443c-8aa3-adb44a6b0f2d |  | section | Paint Sign off
checkpoint-status | 752f29fd-4c8a-47cd-ab34-4097cb2b9339 |  | checkpoint | Soffits
checkpoint-status | 675aabf4-7b88-4599-80dd-1acb139b0c62 |  | checkpoint | Weatherboards
checkpoint-status | 100455fe-2b95-4914-b7af-40f9ba75fc8f |  | checkpoint | Painted edge last weatherboard
checkpoint-status | 93168551-3cbc-4978-9915-f543b895dec8 |  | checkpoint | Gaps
checkpoint-status | 1813315c-229c-4ae2-8c6a-56636075c9cd |  | checkpoint | Substrate Dirt and Grit Free
checkpoint-status | a21de35e-1a2f-465d-8526-53863fd3706a |  | checkpoint | Site left clean and tidy?
checkpoint-status | f6c63787-2b95-4efe-a5f5-2cbc16edf1cb |  | checkpoint | Paint to be left on site?
checkpoint-status | be0162d2-fb18-45c1-a122-f57ed6bd4710 |  | checkpoint | Job 100% Complete?
checkpoint-status | 5492f4b2-7de1-4fe0-b64c-96095ff27a82 |  | checkpoint | Approved for subcontractor payment
checklist-sectioned | 6279f717-b947-4466-aa96-7f8c234b2749 |  | checklist | Insulation Qa |  |  |  |  | Yes | Insulation QA | 8b011848-0633-4201-b41b-1480e023dff4
checkpoint-group | 63cbd669-4a49-45df-9024-ace88e27c488 |  | section | Insulation Prestart
checkpoint-status | 4db53c79-3c4a-4d25-b1fa-88d970a3b5c1 |  | checkpoint | Metal Ceiling Grid Completed
checkpoint-status | 3aec5708-0a78-4e9e-a53b-b9afcd9bb825 |  | checkpoint | All nogs installed as required
checkpoint-status | 8c3b0c7f-9b27-4a47-8668-e56b6ddee640 |  | checkpoint | Electrical wiring completed
checkpoint-status | dc77b5bf-38ac-473e-aa2b-7c2bec317351 |  | checkpoint | Plumbing completed
checkpoint-status | 0cd6e493-bcce-40f7-9013-6d0cf2a8c4f0 |  | checkpoint | Which walls and ceilings are to be insulated?
checkpoint-status | a8c97540-0372-474b-b787-8e44a93a86f2 |  | checkpoint | Garage included or excluded?
checkpoint-status | 551bc96b-8049-43b3-bb4d-1f490a3195c2 |  | checkpoint | Any noise reduction batts to walls or midfloors
checkpoint-status | cb41dab8-43b4-4531-9399-f37be45e7a23 |  | checkpoint | Site clean and tidy
checkpoint-status | c2a10674-527e-4220-9b88-6c685dcb4e77 |  | checkpoint | All left over materials and rubbish removed
checkpoint-status | 0b817c90-2aed-47b8-8f93-36a5a91f5911 |  | checkpoint | General Comments and Queries
holdpoint | 5672f64b-9902-44c3-818f-0d7a71ba2b01 |  | signoff | Work completed as per spec
checkpoint-group | ae3e57bf-8a92-45e3-9ad0-3a8da23330d2 |  | section | Insulation Post Checks
checkpoint-status | 24a076f5-1c33-434e-bd77-1d78822ee9af |  | checkpoint | Ceiling Batts installed correctly and no gaps left
checkpoint-status | cc2ce7dc-0b43-45fd-80b3-acaa9bbd7975 |  | checkpoint | Wall batts installed correctly and no gaps left
checkpoint-status | 9da8f06c-7a85-435d-94a6-dbe7f758a80b |  | checkpoint | No proud insulation?
checkpoint-status | 3d326a14-d6bc-4795-8f21-978cf457253e |  | checkpoint | Insulation cut around (not over) pipes etc to prevent bulging of sheets
checkpoint-status | 325f9ab0-55a0-4af9-81aa-1879b33ac709 |  | checkpoint | Noise reduction batts installed to walls or midfloors
checkpoint-status | 3bad2a89-6513-467f-a03f-2b98f90183fc |  | checkpoint | Site clean and tidy
checkpoint-status | 221b4293-5751-4c6f-89be-ccdf0f4968f1 |  | checkpoint | Do we require mobile scaffold?
checkpoint-status | f0c64863-3d47-4b5e-a9cb-aafeb02c261a |  | checkpoint | If yes, have we allowed for it?
checkpoint-status | b6d5f788-7acb-4a88-8222-2ab42355928f |  | checkpoint | If yes, has it been quoted or is it a variation?
checkpoint-status | 5094be90-4b2f-4bdd-8bd2-0560e0cd1bca |  | checkpoint | Scaffold safe to use/set up safely
checkpoint-status | df4fa2fc-09cc-4ece-b4ee-fb495d48d9e6 |  | checkpoint | All left over materials and rubbish removed?
checkpoint-status | 8a3bd00a-0a91-44a9-87f5-6a294b4029a0 |  | checkpoint | Site clean and tidy ready for next trade?
checkpoint-status | 5945eab7-1a95-47d5-a3c5-6299c98af194 |  | checkpoint | General Comments and Queries
holdpoint | de830f0b-f9d7-48ef-ab7a-51ebf327eefd |  | signoff | Request signoff
checklist-sectioned | 7153a79b-aba8-4e81-97a8-e63e43f00728 |  | checklist | Grid QA |  |  |  |  | Yes | Grid QA | 8db4b425-70ab-4e1d-9e15-cc91c287e6f1
checkpoint-group | 3096b56f-2ae1-4c87-af7b-9557896ed29e |  | section | Grid Prestart
checkpoint-status | 57db80dc-0524-454c-b1e5-ce08345b0d18 |  | checkpoint | Batten direction discussed and considered for critical light
checkpoint-status | 0a41a561-bc3c-4ccb-ac05-d14d1e6acf86 |  | checkpoint | Nogging requested from/by builders
checkpoint-status | 80d92e0c-c3c4-40be-b123-3a180a4da983 |  | checkpoint | Firewalls considered? i.e. Wall angle left off if IT Wall is full height
checkpoint-status | 4bcb31af-5305-4653-ab87-dd75d73c8812 |  | checkpoint | Tiling (Wall angle in shower)
checkpoint-status | ae3f810d-f038-4a17-9a5e-313ea389e87a |  | checkpoint | System considered and accounted for and all material ordered
checkpoint-status | 00530ba6-ce1b-402f-984d-f542d523477f |  | checkpoint | Walls straight and true for wall angle
checkpoint-status | 4d1d169a-b344-4923-9dc5-15ba7fb2f7c9 |  | checkpoint | Bulkheads considered where required
checkpoint-status | 80f1ee2e-5464-4433-89fb-e2a934eb71c3 |  | checkpoint | All services in
checkpoint-status | c0ba6069-9c58-419d-a8c8-cb647d7aee1d |  | checkpoint | All building work completed so work can begin
checkpoint-status | 18a3437f-5a93-4f72-b87c-1fcaa3bf202d |  | checkpoint | Site clean and tidy for start
checkpoint-status | 5b763643-2759-4705-8747-fddf7840347c |  | checkpoint | Do we require mobile scaffold?
checkpoint-status | 800e6074-4274-458b-9d0c-ed2d9487ca32 |  | checkpoint | If yes, have we allowed for it?
checkpoint-status | d28e1af9-3d87-4e4b-b0a0-b38658eb8931 |  | checkpoint | If yes, has it been quoted or is it a variation?
checkpoint-status | 8f2858d6-16b5-4e48-8eab-9a2427f115a9 |  | checkpoint | Scaffold safe to use/set up safely
checkpoint-status | 2ad6d159-6a39-497d-b199-b417a472935c |  | checkpoint | General Comments and Queries
holdpoint | ba5b9363-fe70-4d65-8859-82d7c7f54b73 |  | signoff | Area OK to proceed
checkpoint-group | eb6849e4-c113-450f-86f3-d1fbcfcd8ec0 |  | section | Grid Post Checks
checkpoint-status | 0c4b4069-4336-4474-886e-a863c3f61057 |  | checkpoint | Ceiling grid complete
checkpoint-status | 1ecae3be-ccc4-4c29-8e7b-dd8b949be5a2 |  | checkpoint | Earth strapping
checkpoint-status | d99a53eb-d3dd-47d7-ac23-71dead451e04 |  | checkpoint | Bulkhead's formed where required and plumb, level & square
checkpoint-status | 4e893ce2-e1df-46c0-bcfb-16e2418e171a |  | checkpoint | Tiling (Wall angle in shower)
checkpoint-status | 0b484d55-d6fe-4e28-a112-8a5e7d68be19 |  | checkpoint | Battens all running in the same direction and correct orientation for critical light/ sheet layout
checkpoint-status | 3a88fcb9-7a10-4371-8df0-b1ed874dc8c7 |  | checkpoint | Batten joins offset
checkpoint-status | 24091da0-8977-4534-81bf-7e0f149a02fc |  | checkpoint | Joins Flush
checkpoint-status | 3e1b40ed-6bbc-4f95-9387-a595fda0915e |  | checkpoint | No missing hangers or clips
checkpoint-status | c76de59a-26f7-4054-9a54-2c237b41fb96 |  | checkpoint | Corners fixed correctly
checkpoint-status | 7b218910-dfb3-41c2-b7d7-4ec698fc4c40 |  | checkpoint | Wall angle straight and true
checkpoint-status | 4d188065-ecc4-4f9f-9b0f-53f15d312466 |  | checkpoint | Is angle the right way to supply top fixings for plasterboard?
checkpoint-status | 7222e8e6-7ca9-49af-81ef-523b4da89e3b |  | checkpoint | Correct screw placing and clips screwed off properly
checkpoint-status | 8fe23a79-0134-4f28-aed7-94b316bb0a37 |  | checkpoint | No proud screws or fixings
checkpoint-status | 92bc0e49-bebc-4976-8365-bfa89943717f |  | checkpoint | Site clean and tidy
checkpoint-status | 482eed52-9aac-46ef-9bac-b5ca4b617294 |  | checkpoint | Is there any gear that needs to be collected from Site? Can this be removed in the van? If not schedule pickup
checkpoint-status | 48f6ae23-7bc4-46f3-87e3-e18d57c4b8b4 |  | checkpoint | General Comments and Queries
holdpoint | e7f09e0c-6e13-45c7-b4d1-e1ec580f1cec |  | signoff | Request Signoff
checklist-sectioned | fb3d06a5-e296-41e8-ac12-2f38edb3322d |  | checklist | Steel Stud QA |  |  |  |  | Yes | Steel Stud QA | 9b5f24a6-1323-4ffb-9aca-ab220fa2c31d
checkpoint-group | 2afbf066-d266-4c44-a5e0-dedaec478869 |  | section | Steel Stud Prestart
checkpoint-status | 61294b1a-241f-4b73-af09-7b98c5b788d6 |  | checkpoint | Is there a framing layout plan and does it have all necessary details and measurements
checkpoint-status | dda3621f-0493-4112-b7fd-45c5e085a80e |  | checkpoint | Is there a wall type plan and is it clear what walls are needing to be built
checkpoint-status | 5e871094-b769-4a11-957d-6c9660e8a456 |  | checkpoint | Do we have a door schedule/ door openings
checkpoint-status | 76df2d5d-a77c-4953-92bb-1d2212bc517d |  | checkpoint | Is there top connection detail
checkpoint-status | 6c8075ab-d867-4c1f-b965-d1b1ad23a4e8 |  | checkpoint | Are all services completed and finished
checkpoint-status | ad692f39-4bc3-4e91-bf8a-81782e49f6e0 |  | checkpoint | Is the floor clear
checkpoint-status | 929d2621-a88a-47f7-a8a8-820ba0fe3b01 |  | checkpoint | Do we have a clear run and is there anything stopping us from proceeding
checkpoint-status | cab4b7d3-b42c-4028-92cc-8be7a3f278a1 |  | checkpoint | Do we have enough DPC
holdpoint | 79520ff0-abeb-4902-8272-4b7d1bac3194 |  | signoff | Area OK to proceed
checkpoint-group | 47c890f9-a131-43d8-abf0-74ffeae2d224 |  | section | Steel Stud Post Checks
checkpoint-status | 28678e45-0022-4396-a2e5-6e35be21e763 |  | checkpoint | Have we done a check with a level and straight edge
checkpoint-status | 1d323ba9-9340-4804-b90a-4894c6b1b430 |  | checkpoint | Have we put building square in all internal corners
checkpoint-status | d5e617bc-3a85-4632-8ac8-17fbed8f5deb |  | checkpoint | Have we checked all door openings are correct
checkpoint-status | 7d4161c8-bf6f-47c3-bb71-dd0c31d47606 |  | checkpoint | Have we checked all walls are parallel
checkpoint-status | 3bdf4f6d-443f-483e-8f90-f4fe687ef94b |  | checkpoint | Have we installed DPC to all walls
checkpoint-status | c6f07d6d-80d1-49c6-a983-e0d3bb1113b5 |  | checkpoint | Do all internal corner juntions have appropriate fixings for plasterboard
checkpoint-status | b2b7a6d9-7173-4908-8db0-8c35506666bc |  | checkpoint | Have we left appropriate gap for deflection head
checkpoint-status | 8aa4cf9a-d384-46a1-9eb0-5b2c7494fa07 |  | checkpoint | Are all materials removed from unit and rubbish taken to bin
holdpoint | 511cc3ea-c62b-4543-a40f-1ba652477053 |  | signoff | Request Signoff
checklist-sectioned | ae09bc0f-be10-4a5a-9db7-981710469ffd |  | checklist | Interior Painting QA |  |  |  |  | Yes | Interior Painting QA V2 | e04250b8-25c6-49c0-8a59-710b2dcc3f9e
checkpoint-group | e67fd87f-b91b-4a55-94cb-8b551866c18c |  | section | Interior Painting Prestart
checkpoint-status | ff400139-4f83-43e8-b70d-f904ceee2aa4 |  | checkpoint | Sqaure stop
checkpoint-status | d06912b8-c32f-4972-8d03-2332e0c31b4d |  | checkpoint | Internal returns
checkpoint-status | 5bdc94b2-1c64-4179-bc3f-81930a6b23c2 |  | checkpoint | Behind cupboards
checkpoint-status | 99cd33a9-fae3-4120-be16-d7ac1cb13acd |  | checkpoint | Dust in corner top and bottom
checkpoint-status | 3b178334-7419-43d5-b025-6b43a114774f |  | checkpoint | Wave in square stop
checkpoint-status | 14d107ec-4799-4a1c-8cf6-19d72beb580d |  | checkpoint | Around meters
checkpoint-status | cfeea056-3f5c-4a9c-bc3d-4dd9ea423115 |  | checkpoint | Bathroom shower bottoms
checkpoint-status | 209b42f1-00b8-40bd-a233-3f8c691a20a3 |  | checkpoint | Switches and plugs cut outs
checkpoint-status | 751756bd-3c37-4022-ad8a-12f13ab7234d |  | checkpoint | Do we require mobile scaffold?
checkpoint-status | a7e4bdf5-5a16-4927-9ec8-70958737f8b0 |  | checkpoint | If yes, have we allowed for it?
checkpoint-status | 976d2833-fd28-43c8-ae8d-b40d5cb90133 |  | checkpoint | If yes, has it been quoted or is it a variation?
checkpoint-status | 02a63949-e5f5-4f56-8331-5fb1225d722d |  | checkpoint | Scaffold safe to use/set up safely
checkpoint-status | 4153dd8e-467b-4865-96b5-3d15b3d1d4c9 |  | checkpoint | Lumps and bumps
checkpoint-status | bd527075-5582-4680-8310-74144c28703f |  | checkpoint | General Comments and Queries
checkpoint-group | 9b341767-9e1b-41d4-ba30-08098f662486 |  | section | Interior Painting Post Checks
checkpoint-status | 4cb10e98-3e25-4395-b478-0c7a2831b4c1 |  | checkpoint | Walls
checkpoint-status | f84b0e2b-7b1b-4d88-aad8-a1d9f5df5b9f |  | checkpoint | Ceilings
checkpoint-status | 82c1f047-63de-4958-b8d8-612ed2826570 |  | checkpoint | Doors
checkpoint-status | e8cb4ad9-7d4d-4e0d-a15f-cfc1cf643567 |  | checkpoint | Trims
checkpoint-status | 81d91146-1e80-4ab0-b111-d91f0f4169bd |  | checkpoint | Skirting
checkpoint-status | d4e672eb-6ad1-45d6-af76-d10ac7300c0d |  | checkpoint | Windows
checkpoint-status | 330f4991-3387-4333-8545-c5f638a1b0be |  | checkpoint | Site left clean and tidy
checkpoint-status | df32f468-4d5f-48e4-ae27-b9ba5e61b8bc |  | checkpoint | Paint to be left on site
checkpoint-status | c49652bc-1fc6-4a55-9736-9fd64250cb55 |  | checkpoint | General Comments and Queries
checkpoint-status | 78b373f1-04b5-4401-8414-73ff266ac95e |  | checkpoint | Approved for subcontractor payment