## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Stopping QA |  |  |  |  | Yes | Stopping QA | 0956ce2d-1efd-442f-8d6a-6d2349e4f079
checkpoint-group |  |  | section | Stopping Prestart
checkpoint-status |  |  | checkpoint | Do we require mobile scaffold?
checkpoint-status |  |  | checkpoint | If yes, have we allowed for it?
checkpoint-status |  |  | checkpoint | If yes, has it been quoted or is it a variation?
checkpoint-status |  |  | checkpoint | Scaffold safe to use/set up safely
checkpoint-status |  |  | checkpoint | Bracing walls fixed correctly
checkpoint-status |  |  | checkpoint | No proud screws
checkpoint-status |  |  | checkpoint | No overdriven screws
checkpoint-status |  |  | checkpoint | Backblocking of joins as per Troake Backblocking guidelines
checkpoint-status |  |  | checkpoint | All areas of broken GIB dug out and ready for pre-filling
checkpoint-status |  |  | checkpoint | Sheets layout correct and in consideration of critical light
checkpoint-status |  |  | checkpoint | Grooved liners fitted correctly if present
checkpoint-status |  |  | checkpoint | All joins as per GIB site Guide above windows and doors etc
checkpoint-status |  |  | checkpoint | General Comments and Queries
holdpoint |  |  | signoff | Area Ready for Stopping
checkpoint-group |  |  | section | Stopping Post Checks
checkpoint-status |  |  | checkpoint | All work completed to GIB® Site Guidelines
checkpoint-status |  |  | checkpoint | Screws adequately covered
checkpoint-status |  |  | checkpoint | Joints flat and level
checkpoint-status |  |  | checkpoint | Square stop and corner joints square/ straight to the eye
checkpoint-status |  |  | checkpoint | GIB® Cove joints acceptable
checkpoint-status |  |  | checkpoint | Floors scraped clean
checkpoint-status |  |  | checkpoint | All slimlines, J-moulds, negative detail or any other finishing completed plumb, level square and straight to the eye
checkpoint-status |  |  | checkpoint | Light check complete
checkpoint-status |  |  | checkpoint | Materials to be picked up from site
checkpoint-status |  |  | checkpoint | Site left clean and tidy (attach photos)
checkpoint-status |  |  | checkpoint | General Comments and Queries
holdpoint |  |  | signoff | Request Signoff
checklist-sectioned |  |  | checklist | Steel Stud QA |  |  |  |  | Yes | Steel Stud QA | 201156b4-1bbf-4a91-a813-6a952ce99585
checkpoint-group |  |  | section | Steel Stud Prestart
checkpoint-status |  |  | checkpoint | Is there a framing layout plan and does it have all necessary details and measurements
checkpoint-status |  |  | checkpoint | Is there a wall type plan and is it clear what walls are needing to be built
checkpoint-status |  |  | checkpoint | Do we have a door schedule/ door openings
checkpoint-status |  |  | checkpoint | Is there top connection detail
checkpoint-status |  |  | checkpoint | Are all services completed and finished
checkpoint-status |  |  | checkpoint | Is the floor clear
checkpoint-status |  |  | checkpoint | Do we have a clear run and is there anything stopping us from proceeding
checkpoint-status |  |  | checkpoint | Do we have enough DPC
holdpoint |  |  | signoff | Area OK to proceed
checkpoint-group |  |  | section | Steel Stud Post Checks
checkpoint-status |  |  | checkpoint | Have we done a check with a level and straight edge
checkpoint-status |  |  | checkpoint | Have we put building square in all internal corners
checkpoint-status |  |  | checkpoint | Have we checked all door openings are correct
checkpoint-status |  |  | checkpoint | Have we checked all walls are parallel
checkpoint-status |  |  | checkpoint | Have we installed DPC to all walls
checkpoint-status |  |  | checkpoint | Do all internal corner junctions have appropriate fixings for plasterboard
checkpoint-status |  |  | checkpoint | Have we left appropriate gap for deflection head
checkpoint-status |  |  | checkpoint | Are all materials removed from unit and rubbish taken to bin
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | Pre-Commencement Checks |  |  |  |  | Yes | Pre-Commencement Checks | 2b69c621-67a1-493c-8fc7-c6a8f988c5bc
checkpoint-status |  |  | checkpoint | Quality Management Plan Completed, Agreed & Attached
checkpoint-status |  |  | checkpoint | Inspection & Test Plan Completed, Agreed & Attached
checkpoint-status |  |  | checkpoint | Relevant Breakdown & Checklists Setup on Conqa & Reviewed by Main Contractor
checkpoint-status |  |  | checkpoint | Conqa Setup & Project Team Trained & Given Access
checkpoint-status |  |  | checkpoint | Review Access Granted to Main Contractor & Relevant Parties
checkpoint-status |  |  | checkpoint | Matrix/insights Setup (if required)
checklist-sectioned |  |  | checklist | Insulation QA |  |  |  |  | Yes | Insulation QA | 2f4cfa7d-687f-4a14-ba68-6a07b63cc230
checkpoint-group |  |  | section | Insulation Prestart
checkpoint-status |  |  | checkpoint | Metal Ceiling Grid Completed
checkpoint-status |  |  | checkpoint | All nogs installed as required
checkpoint-status |  |  | checkpoint | Electrical wiring completed
checkpoint-status |  |  | checkpoint | Plumbing completed
checkpoint-status |  |  | checkpoint | Which walls and ceilings are to be insulated?
checkpoint-status |  |  | checkpoint | Garage included or excluded?
checkpoint-status |  |  | checkpoint | Any noise reduction batts to walls or midfloors
checkpoint-status |  |  | checkpoint | Site clean and tidy
checkpoint-status |  |  | checkpoint | All left over materials and rubbish removed
checkpoint-status |  |  | checkpoint | General Comments and Queries
holdpoint |  |  | signoff | Work completed as per spec
checkpoint-group |  |  | section | Insulation Post Checks
checkpoint-status |  |  | checkpoint | Ceiling Batts installed correctly and no gaps left
checkpoint-status |  |  | checkpoint | Wall batts installed correctly and no gaps left
checkpoint-status |  |  | checkpoint | No proud insulation?
checkpoint-status |  |  | checkpoint | Insulation cut around (not over) pipes etc to prevent bulging of sheets
checkpoint-status |  |  | checkpoint | Noise reduction batts installed to walls or midfloors
checkpoint-status |  |  | checkpoint | Site clean and tidy
checkpoint-status |  |  | checkpoint | Do we require mobile scaffold?
checkpoint-status |  |  | checkpoint | If yes, have we allowed for it?
checkpoint-status |  |  | checkpoint | If yes, has it been quoted or is it a variation?
checkpoint-status |  |  | checkpoint | Scaffold safe to use/set up safely
checkpoint-status |  |  | checkpoint | All left over materials and rubbish removed?
checkpoint-status |  |  | checkpoint | Site clean and tidy ready for next trade?
checkpoint-status |  |  | checkpoint | General Comments and Queries
holdpoint |  |  | signoff | Request signoff
checklist-flat |  |  | checklist | B03 Defects |  |  |  |  | Yes | B03 Defects | 4fce2a5d-5221-41a8-9c89-00f8e8d0a26a
checkpoint-status |  |  | checkpoint | Living/Kitchen
checkpoint-status |  |  | checkpoint | Common Areas
checkpoint-status |  |  | checkpoint | Bedroom 1
checkpoint-status |  |  | checkpoint | Bedroom 2
checkpoint-status |  |  | checkpoint | Toilet
checkpoint-status |  |  | checkpoint | Bathroom
checklist-sectioned |  |  | checklist | Fixing QA |  |  |  |  | Yes | Fixing QA | 6fb11ca0-a043-4181-b3d9-2d4da3f44942
checkpoint-group |  |  | section | Fixing Prestart
checkpoint-status |  |  | checkpoint | Exterior Cladding complete
checkpoint-status |  |  | checkpoint | Joinery installed
checkpoint-status |  |  | checkpoint | Doors liners installed including cavity sliders
checkpoint-status |  |  | checkpoint | Grooved jambs big enough (12mm for 10mm and 15mm for 13mm) on doors and windows
checkpoint-status |  |  | checkpoint | Walls checked to be level and planed if necessary with no protruding nogs
checkpoint-status |  |  | checkpoint | Metal ceiling battens running in the same direction and in consideration of critical light
checkpoint-status |  |  | checkpoint | No missing hangers or clips on Metal ceiling battens
checkpoint-status |  |  | checkpoint | No proud screws on any of the metal ceiling battens or wall strapping
checkpoint-status |  |  | checkpoint | Wall angle fixed off completely and corners fixed
checkpoint-status |  |  | checkpoint | All battens secure
checkpoint-status |  |  | checkpoint | Beam framing checked and acceptable
checkpoint-status |  |  | checkpoint | Batten joins offset
checkpoint-status |  |  | checkpoint | Brace walls have brackets or straps at each end of the element
checkpoint-status |  |  | checkpoint | Services installed completely
checkpoint-status |  |  | checkpoint | Site clean and tidy of excess materials
checkpoint-status |  |  | checkpoint | Do we require mobile scaffold?
checkpoint-status |  |  | checkpoint | If yes, have we allowed for it?
checkpoint-status |  |  | checkpoint | If yes, has it been quoted or is it a variation?
checkpoint-status |  |  | checkpoint | Scaffold safe to use/ set up safely
checkpoint-status |  |  | checkpoint | General Comments and Queries
holdpoint |  |  | signoff | Work Completed as per Spec
checkpoint-group |  |  | section | Fixing Post Checks
checkpoint-status |  |  | checkpoint | All work completed to GIB® Site Guidelines
checkpoint-status |  |  | checkpoint | Fire rating, bracing elements and wet areas are screwed off to manufacturers specifications and have been checked against plan
checkpoint-status |  |  | checkpoint | All sheets have had centre screws on packers
checkpoint-status |  |  | checkpoint | Butt joins, ceiling taper edges and stairwell taper edges are back blocked as per Troake Guidelines
checkpoint-status |  |  | checkpoint | Pipes are market on the face of the sheet. Wires within nailing distance marked
checkpoint-status |  |  | checkpoint | All plugs and penetrations have been marked on the floor and have been cut neatly and correctly
checkpoint-status |  |  | checkpoint | All plasterboard correctly fitted into rebated jambs
checkpoint-status |  |  | checkpoint | All sheets 5-10mm above floor (unless specified)
checkpoint-status |  |  | checkpoint | Back block stick and centre screws removed
checkpoint-status |  |  | checkpoint | Site left clean and tidy (attach photos)
checkpoint-status |  |  | checkpoint | Site Hazard Checklist Completed (attach photos)
checkpoint-status |  |  | checkpoint | General Comments and Queries
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | Report |  |  |  |  | Yes | Report | 9a647504-a40a-4ce0-8bf2-59bdb6bafeff
checkpoint-status |  |  | checkpoint | Engineer Inspection report
checkpoint-status |  |  | checkpoint | Inspection comments and Remedial items Actioned
holdpoint |  |  | signoff | Raise Remedial/Request Signoff
checklist-sectioned |  |  | checklist | Grid QA |  |  |  |  | Yes | Grid QA | a3984f8e-3258-4cab-889a-364cc51d84c7
checkpoint-group |  |  | section | Grid Prestart
checkpoint-status |  |  | checkpoint | Batten direction discussed and considered for critical light
checkpoint-status |  |  | checkpoint | Nogging requested from/by builders
checkpoint-status |  |  | checkpoint | Firewalls considered? i.e. Wall angle left off if IT Wall is full height
checkpoint-status |  |  | checkpoint | Tiling (Wall angle in shower)
checkpoint-status |  |  | checkpoint | System considered and accounted for and all material ordered
checkpoint-status |  |  | checkpoint | Walls straight and true for wall angle
checkpoint-status |  |  | checkpoint | Bulkheads considered where required
checkpoint-status |  |  | checkpoint | All services in
checkpoint-status |  |  | checkpoint | All building work completed so work can begin
checkpoint-status |  |  | checkpoint | Site clean and tidy for start
checkpoint-status |  |  | checkpoint | Do we require mobile scaffold?
checkpoint-status |  |  | checkpoint | If yes, have we allowed for it?
checkpoint-status |  |  | checkpoint | If yes, has it been quoted or is it a variation?
checkpoint-status |  |  | checkpoint | Scaffold safe to use/set up safely
checkpoint-status |  |  | checkpoint | General Comments and Queries
holdpoint |  |  | signoff | Area OK to proceed
checkpoint-group |  |  | section | Grid Post Checks
checkpoint-status |  |  | checkpoint | Ceiling grid complete
checkpoint-status |  |  | checkpoint | Earth strapping
checkpoint-status |  |  | checkpoint | Bulkhead's formed where required and plumb, level & square
checkpoint-status |  |  | checkpoint | Tiling (Wall angle in shower)
checkpoint-status |  |  | checkpoint | Battens all running in the same direction and correct orientation for critical light/ sheet layout
checkpoint-status |  |  | checkpoint | Batten joins offset
checkpoint-status |  |  | checkpoint | Joins Flush
checkpoint-status |  |  | checkpoint | No missing hangers or clips
checkpoint-status |  |  | checkpoint | Corners fixed correctly
checkpoint-status |  |  | checkpoint | Wall angle straight and true
checkpoint-status |  |  | checkpoint | Is angle the right way to supply top fixings for plasterboard?
checkpoint-status |  |  | checkpoint | Correct screw placing and clips screwed off properly
checkpoint-status |  |  | checkpoint | No proud screws or fixings
checkpoint-status |  |  | checkpoint | Site clean and tidy
checkpoint-status |  |  | checkpoint | Is there any gear that needs to be collected from Site? Can this be removed in the van? If not schedule pickup
checkpoint-status |  |  | checkpoint | General Comments and Queries
holdpoint |  |  | signoff | Request Signoff
checklist-sectioned |  |  | checklist | Interior Painting QA |  |  |  |  | Yes | Interior Painting QA | bd91414a-4c7b-4c6b-a6b2-fc9d1366d9cc
checkpoint-group |  |  | section | Interior Painting Prestart
checkpoint-status |  |  | checkpoint | Square stop
checkpoint-status |  |  | checkpoint | Internal returns
checkpoint-status |  |  | checkpoint | Behind cupboards
checkpoint-status |  |  | checkpoint | Behind Laundry tub
checkpoint-status |  |  | checkpoint | Dust in corner top and bottom
checkpoint-status |  |  | checkpoint | Wave in square stop
checkpoint-status |  |  | checkpoint | Around meters
checkpoint-status |  |  | checkpoint | Bathroom shower bottoms
checkpoint-status |  |  | checkpoint | Switches and plugs cut outs
checkpoint-status |  |  | checkpoint | Do we require mobile scaffold?
checkpoint-status |  |  | checkpoint | If yes, have we allowed for it?
checkpoint-status |  |  | checkpoint | If yes, has it been quoted or is it a variation?
checkpoint-status |  |  | checkpoint | Scaffold safe to use/set up safely
checkpoint-status |  |  | checkpoint | Lumps and bumps
checkpoint-status |  |  | checkpoint | General Comments and Queries
holdpoint |  |  | signoff | Area Ready to Begin
checkpoint-group |  |  | section | Interior Painting Post Checks
checkpoint-status |  |  | checkpoint | Walls
checkpoint-status |  |  | checkpoint | Ceilings
checkpoint-status |  |  | checkpoint | Doors
checkpoint-status |  |  | checkpoint | Trims
checkpoint-status |  |  | checkpoint | Skirting
checkpoint-status |  |  | checkpoint | Windows
checkpoint-status |  |  | checkpoint | Site left clean and tidy
checkpoint-status |  |  | checkpoint | Paint to be left on site
checkpoint-status |  |  | checkpoint | General Comments and Queries
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | B03 Defects (Common Areas) |  |  |  |  | Yes | B03 Defects (Common Areas) | d57b2d47-d6dc-46a8-98df-84ad434a9886
checkpoint-no-status |  |  | checkpoint | Add photos and comments as required
checklist-flat |  |  | checklist | Completion documents |  |  |  |  | Yes | Completion documents | e62d4eeb-e977-4ee0-bd37-581684ccacdb
checkpoint-status |  |  | checkpoint | PS3 Fire Protection - Interior Surface Finishes
checkpoint-status |  |  | checkpoint | PS3 Fire Stopping of the fire rated wall and Ceilings
checkpoint-status |  |  | checkpoint | PS3 Plasterboard
checkpoint-status |  |  | checkpoint | Material Schedule
checkpoint-status |  |  | checkpoint | Record of Building Work
checkpoint-status |  |  | checkpoint | Other documents