## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | b31e0f50-f326-4abd-a055-361c711f77be |  | checklist | Insulation QA |  |  |  |  | Yes | Insulation QA | 0fc2a0ad-3193-4862-8832-7d1a85bddc79
checkpoint-group | 88ef827e-4e44-403a-9675-7017c2449c0a |  | section | Insulation Prestart
checkpoint-status | 3cba6979-6305-4c89-a094-79dcd487b006 |  | checkpoint | Metal Ceiling Grid Completed
checkpoint-status | 3d024842-8fc6-4b72-967c-802af9c53a62 |  | checkpoint | All nogs installed as required
checkpoint-status | 34bd55fb-8238-4764-b3af-0e96bf936254 |  | checkpoint | Electrical wiring completed
checkpoint-status | 7e0c5ea8-6858-4169-a7de-f65683fc2e54 |  | checkpoint | Plumbing completed
checkpoint-status | 042de99c-2a81-4dac-9c09-11293aef8026 |  | checkpoint | Which walls and ceilings are to be insulated?
checkpoint-status | 19bdcdd9-f041-46c6-abd1-e01d16827b68 |  | checkpoint | Garage included or excluded?
checkpoint-status | f3217f11-50c1-43f9-a1b5-51114df5ef29 |  | checkpoint | Any noise reduction batts to walls or midfloors
checkpoint-status | e84511e8-7d7a-43df-8068-bf7b54eacdb2 |  | checkpoint | Site clean and tidy
checkpoint-status | 02bb512a-8a1e-4f5e-a3d6-e3ab7bea9922 |  | checkpoint | All left over materials and rubbish removed
checkpoint-status | f591826c-4558-41fe-9188-afb19f84b4ec |  | checkpoint | General Comments and Queries
holdpoint | 25e6d9ab-afc5-46d8-afdd-867f836849b7 |  | signoff | Work completed as per spec
checkpoint-group | 6287134e-c533-437c-83ff-c074d4f0af50 |  | section | Insulation Post Checks
checkpoint-status | 162c5a0d-3fe1-40fd-bc50-43b6bb11d10d |  | checkpoint | Ceiling Batts installed correctly and no gaps left
checkpoint-status | d062b367-67ea-48ae-9e38-11d7e89b55d2 |  | checkpoint | Wall batts installed correctly and no gaps left
checkpoint-status | 95411f05-2e6d-499e-a666-006cd3dff006 |  | checkpoint | No proud insulation?
checkpoint-status | af500794-c55f-4490-9123-2cd3ebe1965c |  | checkpoint | Insulation cut around (not over) pipes etc to prevent bulging of sheets
checkpoint-status | f1154c28-dd23-4b07-8313-64eec20e0edb |  | checkpoint | Noise reduction batts installed to walls or midfloors
checkpoint-status | 5f1e4d44-9c61-46b5-948e-d9775dfeabd6 |  | checkpoint | Site clean and tidy
checkpoint-status | ee611de5-11d6-4d01-ba0b-b848a1e91cfb |  | checkpoint | Do we require mobile scaffold?
checkpoint-status | 30978030-237c-43bf-81cc-e20144b005b7 |  | checkpoint | If yes, have we allowed for it?
checkpoint-status | 28e396c9-52f2-47cb-9565-b0108e805c25 |  | checkpoint | If yes, has it been quoted or is it a variation?
checkpoint-status | 327a8864-d2d8-4aaf-80bc-a0bd2529d1d8 |  | checkpoint | Scaffold safe to use/set up safely
checkpoint-status | a51984b1-0c94-47de-a961-0e7c14d6a988 |  | checkpoint | All left over materials and rubbish removed?
checkpoint-status | 3f48720f-6955-447c-8d3b-a3b4bd0aee0a |  | checkpoint | Site clean and tidy ready for next trade?
checkpoint-status | 3eb608d7-73b7-4426-8400-84b71766a277 |  | checkpoint | General Comments and Queries
holdpoint | 6ac84548-69b6-4eb8-b4df-06d6d30d766e |  | signoff | Request signoff
checklist-sectioned | 7b158fb1-8cf9-45fa-9d78-355f7ec60d51 |  | checklist | Interior Painting QA |  |  |  |  | Yes | SYS - Interior Painting QA | 294ad9bc-5902-4330-9291-54fdc6da35c6
checkpoint-group | cc5b7d5f-f47b-4327-b62b-2971f935b4f3 |  | section | Interior Painting Prestart
checkpoint-status | 7996f573-8cd1-4a4d-b305-caa22d1f4b9e |  | checkpoint | Square stop
checkpoint-status | 41357389-5574-4904-af0d-8fbcc9f09c51 |  | checkpoint | Internal returns
checkpoint-status | 478c9b45-8542-4388-8aed-da046b3c8e43 |  | checkpoint | Behind cupboards
checkpoint-status | 8b87e000-05d3-48f5-bfba-e5c3a572f7e1 |  | checkpoint | Dust in corner top and bottom
checkpoint-status | 883e9b50-59ff-42c5-8738-a182d3b2e71d |  | checkpoint | Wave in square stop
checkpoint-status | 63610d12-8e94-4249-86fc-939a7303a958 |  | checkpoint | Around meters
checkpoint-status | 1b22cc94-3883-417e-bf6c-815ed7e40810 |  | checkpoint | Bathroom shower bottoms
checkpoint-status | 433507da-4caa-4740-b786-e2736692175d |  | checkpoint | Switches and plugs cut outs
checkpoint-status | 20d3db10-0b16-4db4-b1a8-e0e5dd6e6025 |  | checkpoint | Do we require mobile scaffold?
checkpoint-status | 7fb85152-66bd-465c-8df5-f20d906545e6 |  | checkpoint | If yes, have we allowed for it?
checkpoint-status | 738fc8df-e62e-4280-8d4e-30305bc85e23 |  | checkpoint | If yes, has it been quoted or is it a variation?
checkpoint-status | 13c5c867-8a6e-4862-9a41-ed6cb9e30356 |  | checkpoint | Scaffold safe to use/set up safely
checkpoint-status | 4dd7ec0f-e16d-4c35-93e9-178e7d906a59 |  | checkpoint | Lumps and bumps
checkpoint-status | 0784cdde-8208-4fd7-a65d-052dd011723a |  | checkpoint | General Comments and Queries
holdpoint | 8e0efbee-e048-4939-a8fe-6e99dd87426a |  | signoff | Area Ready to Begin
checkpoint-group | 2ecf1057-efa8-473e-98cf-89aadbdf41a9 |  | section | Interior Painting Post Checks
checkpoint-status | 05b8de9e-fda5-4b1e-94b4-b1a44b29a39d |  | checkpoint | Walls
checkpoint-status | 483ec8c9-e5f5-47c5-84be-b4c21d7c8a98 |  | checkpoint | Ceilings
checkpoint-status | 26194326-31a1-49f1-9654-b6116114130b |  | checkpoint | Doors
checkpoint-status | c2cf682e-434e-40f6-ab20-84be95f75f5f |  | checkpoint | Trims
checkpoint-status | 5e30df01-f221-4ab2-8a11-c300acb1f5e6 |  | checkpoint | Skirting
checkpoint-status | 371125b7-2f0c-4680-baeb-68c21f79c4eb |  | checkpoint | Windows
checkpoint-status | e5850cf2-fa64-4eeb-aca6-d735cb736cac |  | checkpoint | Site left clean and tidy
checkpoint-status | 2239d2ea-4e4e-4930-91d5-8a404b088321 |  | checkpoint | Paint to be left on site
checkpoint-status | ef097f11-9c1c-449c-a362-5e3d3e5b4a82 |  | checkpoint | General Comments and Queries
holdpoint | fd454126-76b3-4372-ba5c-87dbebefe70a |  | signoff | Request Signoff
checklist-sectioned | 021a547d-1a1f-4023-85c5-d8b2a837e449 |  | checklist | Grid QA |  |  |  |  | Yes | Grid QA | 39ee1e7b-7781-44ec-804e-856bc1bbd456
checkpoint-group | cc164514-74d3-46e3-94bf-292865e57801 |  | section | Grid Prestart
checkpoint-status | 29066d04-154c-4f9b-afab-03848ca7d25d |  | checkpoint | Batten direction discussed and considered for critical light
checkpoint-status | 925cd6bc-6b3a-438a-848e-86b428841d63 |  | checkpoint | Nogging requested from/by builders
checkpoint-status | 933145d2-5df1-4400-84cf-f4023381fc95 |  | checkpoint | Firewalls considered? i.e. Wall angle left off if IT Wall is full height
checkpoint-status | 34c74b61-ced9-4c8a-9065-dd3ff3f33948 |  | checkpoint | Tiling (Wall angle in shower)
checkpoint-status | 1c836568-5c40-40ce-aaaf-913f12a57d5a |  | checkpoint | System considered and accounted for and all material ordered
checkpoint-status | ebd74286-dee2-4d61-a956-459655848a0f |  | checkpoint | Walls straight and true for wall angle
checkpoint-status | dc953cd2-0d98-4839-9d2c-76de60f74212 |  | checkpoint | Bulkheads considered where required
checkpoint-status | d42c733c-10b9-4844-a8a1-1d3845165bed |  | checkpoint | All services in
checkpoint-status | 736bb66c-5c76-4235-b4a5-beeb5f26800c |  | checkpoint | All building work completed so work can begin
checkpoint-status | 03c85ea5-29f4-457b-a3b6-8e785a8e4a1a |  | checkpoint | Site clean and tidy for start
checkpoint-status | 7406d14e-a628-4b92-8028-2528eb5f8ee4 |  | checkpoint | Do we require mobile scaffold?
checkpoint-status | ae1e6d75-7ec1-4a83-8409-f523890e0f14 |  | checkpoint | If yes, have we allowed for it?
checkpoint-status | 1c082ff6-6123-4f90-9ae5-b3ef89a6205f |  | checkpoint | If yes, has it been quoted or is it a variation?
checkpoint-status | f881874c-9258-41d6-bb40-2b645ddf0e0c |  | checkpoint | Scaffold safe to use/set up safely
checkpoint-status | 389ba7f4-e439-4ed1-82fb-35976badef36 |  | checkpoint | General Comments and Queries
holdpoint | 064b0a46-bbd9-49b3-9e88-56fd08ecaaf6 |  | signoff | Area OK to proceed
checkpoint-group | 1d8189f4-2177-43dc-b388-d2ba7bc2942d |  | section | Grid Post Checks
checkpoint-status | 154c544c-072d-4794-a63e-759f0f37ae9e |  | checkpoint | Ceiling grid complete
checkpoint-status | 8118dd5b-7ec9-458a-8671-2c14d4ebaa14 |  | checkpoint | Earth strapping
checkpoint-status | 013b45cf-3412-46ee-a454-1da552804bcf |  | checkpoint | Bulkhead's formed where required and plumb, level & square
checkpoint-status | 22e842a2-573d-456e-840e-6062c6ce52dc |  | checkpoint | Tiling (Wall angle in shower)
checkpoint-status | aba4494e-7fa1-4937-b4b8-c094fffdd822 |  | checkpoint | Battens all running in the same direction and correct orientation for critical light/ sheet layout
checkpoint-status | 2c9c3203-4f95-4453-9013-d53695185964 |  | checkpoint | Batten joins offset
checkpoint-status | 59d43d25-b51b-4157-b335-2883876135bc |  | checkpoint | Joins Flush
checkpoint-status | 37fc07c9-ed51-424e-926a-6a5883d08acd |  | checkpoint | No missing hangers or clips
checkpoint-status | c8b2e9c3-5e17-4d39-a53d-bc6b3a7e287a |  | checkpoint | Corners fixed correctly
checkpoint-status | c3fc482c-b549-4c43-a9d8-d7353a03de7d |  | checkpoint | Wall angle straight and true
checkpoint-status | 52c78249-dbc3-4e21-81bf-24695ec59086 |  | checkpoint | Is angle the right way to supply top fixings for plasterboard?
checkpoint-status | 889ed5d3-70bf-420b-ac93-d5b0db584fe9 |  | checkpoint | Correct screw placing and clips screwed off properly
checkpoint-status | 9c160813-c6dd-443f-887b-6d93ad9bc66f |  | checkpoint | No proud screws or fixings
checkpoint-status | c80e7326-9f41-4bc8-bfdc-a5d6cb50afb5 |  | checkpoint | Site clean and tidy
checkpoint-status | 545c6dac-4711-447b-aa62-f0a5b4d44c81 |  | checkpoint | Is there any gear that needs to be collected from Site? Can this be removed in the van? If not schedule pickup
checkpoint-status | 5e276ed1-1d94-4d75-a31b-8adfe904ebfe |  | checkpoint | General Comments and Queries
holdpoint | 25ac13fe-bb32-4c0f-b43f-8d373f6ab1bd |  | signoff | Request Signoff
checklist-sectioned | 118e41c7-2fd9-46a9-a48a-d9db9e9292f9 |  | checklist | Stopping QA |  |  |  |  | Yes | Stopping QA | 3a618e0b-d175-46b1-b3e7-fd38da1edd0a
checkpoint-group | 7252cbd3-4be8-48d6-b86e-16531017ea5c |  | section | Stopping Prestart
checkpoint-status | 8247df07-fd89-47d5-9d59-49348d8ada35 |  | checkpoint | Do we require mobile scaffold?
checkpoint-status | 549bc45e-b81c-452a-ba0d-ce3098cd2a5d |  | checkpoint | If yes, have we allowed for it?
checkpoint-status | 3f6098cd-c906-40f0-b860-48ea464e445a |  | checkpoint | If yes, has it been quoted or is it a variation?
checkpoint-status | e427c2a2-14f6-456b-ae0c-514f5d7d449e |  | checkpoint | Scaffold safe to use/set up safely
checkpoint-status | 32437dc8-2464-4431-9539-22f64ba5b6f6 |  | checkpoint | Bracing walls fixed correctly
checkpoint-status | 64411a45-3580-4d68-a7aa-2b56a23d96ba |  | checkpoint | No proud screws
checkpoint-status | 9386a42e-a5d6-4614-a9d6-d92186d55db9 |  | checkpoint | No overdriven screws
checkpoint-status | 5b8f3e83-e3cb-4326-9771-24a52b769c93 |  | checkpoint | Backblocking of joins as per Troake Backblocking guidelines
checkpoint-status | 34a3256a-810f-4e09-b08b-32c19545ebf6 |  | checkpoint | All areas of broken GIB dug out and ready for pre-filling
checkpoint-status | f51cfae5-8c31-4078-8004-26193a1e65bf |  | checkpoint | Sheets layout correct and in consideration of critical light
checkpoint-status | 63e4ccc2-6671-49aa-909a-978f9e6cbbb8 |  | checkpoint | Grooved liners fitted correctly if present
checkpoint-status | 23217e03-311f-45de-ab72-c6864a7c8988 |  | checkpoint | All joins as per GIB site Guide above windows and doors etc
checkpoint-status | 6eb99446-4dc3-4938-b9f6-c41e9c0f3043 |  | checkpoint | General Comments and Queries
holdpoint | 6b823fe4-547f-4844-8c31-d309accc9b5d |  | signoff | Area Ready for Stopping
checkpoint-group | 7f979980-c8fe-4c77-9ed5-2ecb79d3f99c |  | section | Stopping Post Checks
checkpoint-status | c541b278-d184-4996-9096-462038934676 |  | checkpoint | All work completed to GIB® Site Guidelines
checkpoint-status | c3266739-6785-4566-b1ef-551ffe187d9f |  | checkpoint | Screws adequately covered
checkpoint-status | a555b2a0-cca1-4ebc-929a-5506ec4095ee |  | checkpoint | Joints flat and level
checkpoint-status | f3375960-73c3-483d-b7eb-a4c1c9159e69 |  | checkpoint | Square stop and corner joints square/ straight to the eye
checkpoint-status | 3aac709b-3845-4686-a316-34ffc2c46aa7 |  | checkpoint | GIB® Cove joints acceptable
checkpoint-status | 819b149f-80b9-49d3-bf80-6ba6d25a38f3 |  | checkpoint | Floors scraped clean
checkpoint-status | 10abea8b-c156-43da-9384-173365515b1e |  | checkpoint | All slimlines, J-moulds, negative detail or any other finishing completed plumb, level square and straight to the eye
checkpoint-status | 5a129dcb-abe5-480b-b290-3bcd6f29c851 |  | checkpoint | Light check complete
checkpoint-status | 0215350f-6e18-4faf-b88c-13ee69834d73 |  | checkpoint | Materials to be picked up from site
checkpoint-status | c905a0ec-343e-4b08-b272-9b2f8aa85787 |  | checkpoint | Site left clean and tidy (attach photos)
checkpoint-status | 60ec7180-41c4-4c6e-8438-5369dfb479a9 |  | checkpoint | General Comments and Queries
holdpoint | 3aa4fb46-58d1-4fd7-9cca-8156c7366308 |  | signoff | Request Signoff
checklist-sectioned | fb6bd75c-dc7a-4729-9e76-b6a4692ab199 |  | checklist | Steel Stud QA |  |  |  |  | Yes | SYS - Steel Stud QA | 4a87d0c7-5f70-47b4-ab3f-ffce49a639ce
checkpoint-group | 97139a8f-1210-4069-90d0-7cf5ed5b4710 |  | section | Steel Stud Prestart
checkpoint-status | fb9ff78a-513b-4ee0-8f72-1c6e4a83589e |  | checkpoint | Is there a framing layout plan and does it have all necessary details and measurements
checkpoint-status | 81f2ab31-8322-43f2-bd8f-bd9200f61074 |  | checkpoint | Is there a wall type plan and is it clear what walls are needing to be built
checkpoint-status | 8f45858a-4691-4a9a-8a08-cb1a19635a28 |  | checkpoint | Do we have a door schedule/ door openings
checkpoint-status | 25e40474-eef7-443a-84ff-cac93cf1c133 |  | checkpoint | Is there top connection detail
checkpoint-status | 349ff644-9a45-4760-92b3-571ce204d20a |  | checkpoint | Are all services completed and finished
checkpoint-status | 272c51ce-d124-4e9e-b035-2c773d74468c |  | checkpoint | Is the floor clear
checkpoint-status | 43d00fa2-5834-4179-8474-546ed9f31d00 |  | checkpoint | Do we have a clear run and is there anything stopping us from proceeding
checkpoint-status | 83a52f40-cbd7-4090-ab79-bd5f0f5f77c9 |  | checkpoint | Do we have enough DPC
holdpoint | 09c6ed29-f403-4840-a95d-a46fd932117e |  | signoff | Area OK to proceed
checkpoint-group | 4d8a5479-73b7-4573-90da-36d61a7d5a4d |  | section | Steel Stud Post Checks
checkpoint-status | f5b7962b-00ef-43d9-99aa-2eda6e436ef9 |  | checkpoint | Have we done a check with a level and straight edge
checkpoint-status | b8f67282-152e-43c4-917e-c9f91062b5df |  | checkpoint | Have we put building square in all internal corners
checkpoint-status | c1fc5655-d3a2-46c2-9297-328732acc098 |  | checkpoint | Have we checked all door openings are correct
checkpoint-status | 599ceb19-b0cf-419f-9773-a9aa1dc18f7a |  | checkpoint | Have we checked all walls are parallel
checkpoint-status | 2248be49-34fc-4a32-9555-5c078f62cbf0 |  | checkpoint | Have we installed DPC to all walls
checkpoint-status | 9e0b619c-49fb-4293-a494-9775c3f3eb42 |  | checkpoint | Do all internal corner junctions have appropriate fixings for plasterboard
checkpoint-status | 1bf7e064-a29c-4c2b-9c05-331332378bfc |  | checkpoint | Have we left appropriate gap for deflection head
checkpoint-status | a0f4175d-500b-4ae8-a02d-2e1490d3fd77 |  | checkpoint | Are all materials removed from unit and rubbish taken to bin
holdpoint | 9e4b8551-6fa8-41e5-8e1b-db095c97a7a5 |  | signoff | Request Signoff
checklist-sectioned | 68ca1078-0def-4410-a643-9d9f4e0a7f21 |  | checklist | Steel Stud QA |  |  |  |  | Yes | Steel Stud QA v1 | 65d1b5ce-b941-4e4b-95fc-0f20fbf3e252
checkpoint-group | fd78c805-ae5e-4dde-86db-c4e37aad5253 |  | section | Steel Stud Prestart
checkpoint-status | 0d05ffc1-5dce-4f08-86dd-b77dbafee3a9 |  | checkpoint | Is there a framing layout plan and does it have all necessary details and measurements
checkpoint-status | 6607279e-5f08-4a58-a801-1e0e1e61e314 |  | checkpoint | Is there a wall type plan and is it clear what walls are needing to be built
checkpoint-status | 2d501a94-8b30-40c0-b4e0-f1edfb687a9e |  | checkpoint | Do we have a door schedule/ door openings
checkpoint-status | 6a4c06c4-bbd2-459d-a6c7-c3fd3e223828 |  | checkpoint | Is there top connection detail
checkpoint-status | 928521d6-930c-4fb9-91ef-d408de98afdb |  | checkpoint | Are all services completed and finished
checkpoint-status | 24430366-e06f-4895-8ea7-a797b6698a3b |  | checkpoint | Is the floor clear
checkpoint-status | b6d7a305-9c40-440a-a071-67207166adeb |  | checkpoint | Do we have a clear run and is there anything stopping us from proceeding
checkpoint-status | 90ad6058-ec73-4518-9db1-985fceaba168 |  | checkpoint | Do we have enough DPC
holdpoint | 081feea9-f28e-42cc-a917-a497b8c66ab6 |  | signoff | Area OK to proceed
checkpoint-group | 154005b3-9ca6-4f88-bda5-b61b2b984996 |  | section | Steel Stud Post Checks
checkpoint-status | 62c923e4-f2d8-488b-9d8a-279f861275da |  | checkpoint | Have we done a check with a level and straight edge
checkpoint-status | 35bdf8fa-224f-42cd-8e11-ba56cd44a506 |  | checkpoint | Have we put building square in all internal corners
checkpoint-status | f6d3f29c-8e89-44a9-a64f-dcd4a27b20ae |  | checkpoint | Have we checked all door openings are correct
checkpoint-status | 61891c95-2e21-4b2b-9e3a-08aa2f52a7bc |  | checkpoint | Have we checked all walls are parallel
checkpoint-status | b1f7c99e-198b-4ea7-9ee4-981f686348fd |  | checkpoint | Have we installed DPC to all walls
checkpoint-status | 2ef31a05-29f8-4b64-b755-9918148bb9fc |  | checkpoint | Do all internal corner junctions have appropriate fixings for plasterboard
checkpoint-status | 2b970c73-2ad5-476c-bdda-441e30dca52f |  | checkpoint | Have we left appropriate gap for deflection head
checkpoint-status | c88eb53e-fe81-4d9a-aeff-163fd35135bf |  | checkpoint | Have all noggs been checked and in the appropriate places?
holdpoint | 64be30a8-d541-4d94-89a9-645135b1afd1 |  | signoff | Request Sign Off
checklist-sectioned | 7b299383-1298-46bd-a5e5-28840c59f2cd |  | checklist | Barrierline QA |  |  |  |  | Yes | SYS - Barrierline QA | 82e02ebc-2cdf-4583-83af-dde1ebd6c3aa
checkpoint-group | 6b8ba92f-41ab-42d7-9baf-f981f2ea387f |  | section | Barrier line Prestart
checkpoint-status | 3e8f4821-df1d-4bfa-bd01-4a6e66ede736 |  | checkpoint | Has the first wall been installed/ erected in the correct position on the slab?
checkpoint-status | 2f0910e3-3471-405d-8a38-77de0a939680 |  | checkpoint | Have the two strips of GIB Fyreline been fixed between the top of the stud and the additional layer of GIB Fyreline to timber infill
checkpoint-status | 3386ca1b-4bf2-4d68-a2d2-8948c9b46b42 |  | checkpoint | Does the metal angle protrude over the cavity gap distance, to sit perpendicular to the Barrier line plasterboard
checkpoint-status | 3d4c4f0d-db7c-4855-8da5-1c516966fb10 |  | checkpoint | Does the inside framing have correctly spaced studs and nogs for fixing GIB Clips and GIB Wall Straps
checkpoint-status | dc1a1a07-5bba-471c-9ed8-3dd4402e45f1 |  | checkpoint | Any extra nogging required to fix GIB Clips
checkpoint-status | f5ab0e3e-3169-4609-a1ad-fc97f57085d2 |  | checkpoint | Concrete floor level to an acceptable standard where the bottom Barrier line perimeter track will be fixed
checkpoint-status | 5e5fea0f-5fbb-4a7e-ae66-625efaa07979 |  | checkpoint | General Comments and Queries
holdpoint | 50397554-94e0-4609-80c9-5d7c159b11ac |  | signoff | First steel stud wall complete and ready for Barrier line installation
checkpoint-group | 90151b65-cd74-4859-903f-ab8e69b423b5 |  | section | Barrier line Post Checks
checkpoint-status | e854a6c2-88b8-4048-88a3-5427e57ec87e |  | checkpoint | Has the specified cavity gap distance been met?
checkpoint-status | d8b17ab2-97c5-40fa-bb5e-40f36431688c |  | checkpoint | H-studs installed every 600mm centres?
checkpoint-status | c848e67f-5ec9-4aa5-85ca-fba2421be435 |  | checkpoint | Do the Barrier line sheets fit tightly into the H-studs?
checkpoint-status | 24bae553-1394-47e4-9555-b571f12d4768 |  | checkpoint | Are the ends and top of the IT wall capped with 140 perimeter channel
checkpoint-status | f11bef46-0ec8-40ca-8750-ef9c38bed196 |  | checkpoint | Has the second metal angle been fixed and sealed with Fire/ Acoustic sealant
checkpoint-status | 732fa4be-6de6-4fb2-bedc-b17d2fc9d5aa |  | checkpoint | Deflection head gap been allowed for
checkpoint-status | 6f5b3e6b-8b33-4402-af02-4fdccd410cc1 |  | checkpoint | GIB Wall Clips fixed to both sides of the H-studs
checkpoint-status | f8691623-5089-4647-8fa7-1099c14d3a53 |  | checkpoint | Two GIB Wall straps fixed at wall ends
checkpoint-status | 4de8150c-f097-4a94-84a5-fcdbb07ac250 |  | checkpoint | General Comments and Queries
holdpoint | 21612477-2198-4e9e-bf25-b1766dbbd622 |  | signoff | Request Signoff
checklist-sectioned | de2e9b35-710c-4b4b-9740-5452f48d02d4 |  | checklist | Interior Painting QA |  |  |  |  | Yes | Interior Painting QA V2 | 8a61a934-ac0e-4a76-aa7c-eda20b520fd3
checkpoint-group | 4642592d-7506-464b-b823-872577cf65e1 |  | section | Interior Painting Prestart
checkpoint-status | 088e7b09-a4c7-4c07-9a34-e5de623f55df |  | checkpoint | Sqaure stop
checkpoint-status | 87e2e0b3-ff2f-4084-ab56-f28b7204d812 |  | checkpoint | Internal returns
checkpoint-status | ae96ae60-352b-4846-acde-be950689f0bf |  | checkpoint | Behind cupboards
checkpoint-status | 247e16a8-22aa-42f2-9860-6635598ac30c |  | checkpoint | Dust in corner top and bottom
checkpoint-status | 90882f7a-2f17-4f23-8d71-e9bb0071fed4 |  | checkpoint | Wave in square stop
checkpoint-status | 396ee974-dd4b-49ba-83bd-a06801664f22 |  | checkpoint | Around meters
checkpoint-status | 6d8f21a8-b1c2-4a8c-aaef-476ad7727086 |  | checkpoint | Bathroom shower bottoms
checkpoint-status | 1592c8e9-d0fd-426f-8495-e12090ba661f |  | checkpoint | Switches and plugs cut outs
checkpoint-status | 1b774d32-2f24-4e02-ae62-9a10f7cc5b3f |  | checkpoint | Do we require mobile scaffold?
checkpoint-status | 22703787-d29d-49ed-98e5-cd5fa6d5de91 |  | checkpoint | If yes, have we allowed for it?
checkpoint-status | a28ec579-4d3b-411f-b607-c93e319c7c33 |  | checkpoint | If yes, has it been quoted or is it a variation?
checkpoint-status | c525eb5e-99eb-4311-8e39-ed1e4d1d7a33 |  | checkpoint | Scaffold safe to use/set up safely
checkpoint-status | 74530846-1950-4a8b-8343-3d7deb946edf |  | checkpoint | Lumps and bumps
checkpoint-status | 2b3fbebb-7591-46bb-87d6-2cce7f5f5880 |  | checkpoint | General Comments and Queries
checkpoint-group | ffb7c2d6-90a3-4628-9e5f-3d0ca9456e6a |  | section | Interior Painting Post Checks
checkpoint-status | 4363dde9-1596-48e0-b8d8-d8d5dfc0d1d6 |  | checkpoint | Walls
checkpoint-status | 84d4a117-0ee6-4490-864e-583c60be01e8 |  | checkpoint | Ceilings
checkpoint-status | 235a1c51-bcd0-4101-aba1-cc86f8d630a3 |  | checkpoint | Doors
checkpoint-status | fc2f2fc5-088b-4737-8432-65a9519d6446 |  | checkpoint | Trims
checkpoint-status | 5e380881-e4b9-4a3c-9309-d9674b3ab801 |  | checkpoint | Skirting
checkpoint-status | 37bb8eb1-ee09-4cd6-a18a-eecfb6728532 |  | checkpoint | Windows
checkpoint-status | dab23ba5-db50-461b-ad97-93f9b25f5b6a |  | checkpoint | Site left clean and tidy
checkpoint-status | 6e8014e5-2f0a-4bb2-8898-07db78066382 |  | checkpoint | Paint to be left on site
checkpoint-status | 4cfda75d-2465-4222-b2a8-61c21af91a77 |  | checkpoint | General Comments and Queries
checkpoint-status | 8a7a5040-3484-4542-b14b-4aa340d17cea |  | checkpoint | Approved for subcontractor payment
checklist-sectioned | 7fafe5c4-0e4f-4d33-a44f-f43150b6f5b0 |  | checklist | Insulation QA |  |  |  |  | Yes | Fixing QA | bddb7273-88f4-40b7-ad85-0bb4bd7dfc3c
checkpoint-group | 4df18f92-3a70-4f1a-b9d1-8d9f623062ad |  | section | Fixing Prestart
checkpoint-status | 0048f4e5-8809-409e-b00c-e8d0c0b993d3 |  | checkpoint | Exterior Cladding complete
checkpoint-status | 12fa6c94-8b19-43c5-b83d-328e1774e60f |  | checkpoint | Joinery installed
checkpoint-status | 85300855-2b84-4357-98fd-e914777c73fa |  | checkpoint | Doors liners installed including cavity sliders
checkpoint-status | 7a9a0600-a30c-41fc-a5d8-e4c5dd8cb4c9 |  | checkpoint | Grooved jams big enough (12mm for 10mm and 15mm for 13mm) on doors and windows
checkpoint-status | b7edd0ab-fe62-4f0e-8350-0dd9770a85c7 |  | checkpoint | Walls checked to be level and planed if necessary with no protruding nogs
checkpoint-status | b0420ce8-73ff-4e79-ba5d-ae05ab4b06b7 |  | checkpoint | Metal ceiling battens running in the same direction and in consideration of critical light
checkpoint-status | 39dfcf22-2191-4448-881e-4c87c066094e |  | checkpoint | No missing hangers or clips on Metal ceiling battens
checkpoint-status | 8d415ae8-4e1e-4eee-abb7-d19c22d5ef4a |  | checkpoint | No proud screws on any of the metal ceiling battens or wall strapping
checkpoint-status | 4f43e812-c3df-4a21-85ad-23cd6fdfa060 |  | checkpoint | Wall angle fixed off completely and corners fixed
checkpoint-status | c9b16262-7d55-476a-88ac-22c07b8b5085 |  | checkpoint | All battens secure
checkpoint-status | 4a1b627f-9579-4f78-bcbd-d6801d6db027 |  | checkpoint | Beam framing checked and acceptable
checkpoint-status | dc248e4b-cfdf-4355-a8a4-f3395b3bc79b |  | checkpoint | Batten joins offset
checkpoint-status | 1192376c-ed77-41c2-8f58-0e006b48ab74 |  | checkpoint | Brace walls have brackets or straps at each end of the element
checkpoint-status | 6614b4f3-1347-42cb-9f9c-c7a82067b7fe |  | checkpoint | Services installed completely
checkpoint-status | 411c3b5c-a8f9-4f25-b8ea-6ac9c0dd66ce |  | checkpoint | Site clean and tidy of excess materials
checkpoint-status | e4d3b434-baa0-421f-b9cf-9044d8739765 |  | checkpoint | Do we require mobile scaffold?
checkpoint-status | 64820cb9-466b-41cd-929e-32cc1c15be53 |  | checkpoint | If yes, have we allowed for it?
checkpoint-status | 36810b07-3bac-4b23-85e4-060a0eb99a58 |  | checkpoint | If yes, has it been quoted or is it a variation?
checkpoint-status | a3ce5bc5-77cc-414b-87fd-749c3bc4e712 |  | checkpoint | Scaffold safe to use/ set up safely
checkpoint-status | b14dd7ae-7643-405a-9806-fc88852a42cf |  | checkpoint | General Comments and Queries
holdpoint | d138cb7f-51c7-40e7-997c-c04c3ad8f8b3 |  | signoff | Work Completed as per Spec
checkpoint-group | 31b05f1b-4d63-4862-9d43-bd92b4ad4b83 |  | section | Fixing Post Checks
checkpoint-status | 3a04953f-2e90-4586-b2a6-2d8948296a83 |  | checkpoint | All work completed to GIB® Site Guidelines
checkpoint-status | b9565c27-2ba0-4591-92c9-da4a301f1372 |  | checkpoint | Fire rating, bracing elements and wet areas are screwed off to manufacturers specifications and have been checked against plan
checkpoint-status | 46f3e20b-c55a-408e-b576-386336a737e5 |  | checkpoint | All sheets have had centre screws on packers
checkpoint-status | 1f9a16fa-f0f1-437d-be18-d3027c18089d |  | checkpoint | Butt joins, ceiling taper edges and stairwell taper edges are back blocked as per Troake Guidelines
checkpoint-status | f1d4b652-a1b2-4acc-a602-d92bc4942417 |  | checkpoint | Pipes are market on the face of the sheet. Wires within nailing distance marked
checkpoint-status | 7ec6278e-7a39-4ac4-a29e-c70d4fa235be |  | checkpoint | All plugs and penetrations have been marked on the floor and have been cut neatly and correctly
checkpoint-status | 1e2c8b69-e827-4092-9798-6bb16da6cbd1 |  | checkpoint | All plasterboard correctly fitted into rebated jambs
checkpoint-status | 28feaa47-0811-490c-bf6d-255d613a2f0a |  | checkpoint | All sheets 5-10mm above floor (unless specified)
checkpoint-status | a40a987d-8c19-4602-ab08-1cc9e681e166 |  | checkpoint | Back block stick and centre screws removed
checkpoint-status | 174fa3b5-bead-42f7-b756-4465f05ca256 |  | checkpoint | Site left clean and tidy (attach photos)
checkpoint-status | 89edcab9-4719-4758-9037-3e4ec4ba73fb |  | checkpoint | Site Hazard Checklist Completed (attach photos)
checkpoint-status | fdac96cf-8eab-4531-850b-d9f0a1ae44b2 |  | checkpoint | General Comments and Queries
holdpoint | ebae0727-0983-4f3d-a9f4-badc319bf023 |  | signoff | Request Signoff
checklist-sectioned | 4125e545-e6e2-4749-ad2c-abbb1ee74f2b |  | checklist | Exterior Painting QA V2 |  |  |  |  | Yes | Exterior Painting QA V2 | cc4d27ba-7424-4112-b5ed-df25f303355e
checkpoint-group | 4e1f6fe0-e168-4657-8d70-f29b66cbd243 |  | section | PrePaint QA
checkpoint-status | 9450a13d-2668-4645-863b-045081132cb0 |  | checkpoint | Square stop
checkpoint-status | 1e4babd1-da9d-456d-bdf4-b0cc50de7a61 |  | checkpoint | Internals returns
checkpoint-status | 30eef358-d485-4b3d-806e-f3c9424ba7f3 |  | checkpoint | Behind cupboards
checkpoint-status | 8f1c023d-fca1-438f-a16c-26e02d392d8b |  | checkpoint | Dust in corner top and bottom
checkpoint-status | cb161a65-f88a-4f45-acac-efeffb048607 |  | checkpoint | Wave in square stop
checkpoint-status | 337e7e4a-4e95-44d0-a828-58bff57f1563 |  | checkpoint | Around meters
checkpoint-status | 1fe01650-aaeb-4ba1-a862-85064f612c0b |  | checkpoint | Bathroom shower bottoms
checkpoint-status | 05469090-fe2c-4bd3-bb43-2e09ee03fd94 |  | checkpoint | Switchers and plugs cut outs
checkpoint-status | 6fb19918-6d5b-4aaa-b8bb-1481f02dca80 |  | checkpoint | Lumps and bumps
checkpoint-group | fc2532f6-3b44-4fa6-b706-9cae8aa526a4 |  | section | Paint Sign off
checkpoint-status | c484c630-11d1-4915-955c-d32fbdba54a4 |  | checkpoint | Soffits
checkpoint-status | 7f6e73b1-6156-46c6-a4bf-3f9332736a7b |  | checkpoint | Weatherboards
checkpoint-status | fd4e5873-5cf9-40dd-82f6-04affa44f51b |  | checkpoint | Painted edge last weatherboard
checkpoint-status | 50c0ea5c-1e3e-4ce2-9c49-555d2ce6499b |  | checkpoint | Gaps
checkpoint-status | b84061e8-29fa-4367-9762-7ae4e67a2b2b |  | checkpoint | Substrate Dirt and Grit Free
checkpoint-status | 4e9a978e-941c-49d4-8ad5-7506cf5fdf57 |  | checkpoint | Site left clean and tidy?
checkpoint-status | 66cb9edc-570a-495b-b9af-545417d5b87a |  | checkpoint | Paint to be left on site?
checkpoint-status | 02ee2555-1efd-4dd2-9544-a4fd59500fc4 |  | checkpoint | Job 100% Complete?
checkpoint-status | 4f6f7c53-c4ac-43ab-a7d2-c310b0cc00c1 |  | checkpoint | Approved for subcontractor payment
checklist-sectioned | 2cf61d62-012b-471f-a1cd-e48b8078c599 |  | checklist | Barrierline QA |  |  |  |  | Yes | Barrierline QA v1 | ebb9f323-6e30-4da3-8288-678ae7a71b0d
checkpoint-group | 1cc5b8be-0b05-4248-a5ed-da8d3f7f17d6 |  | section | Barrier line Prestart
checkpoint-status | 08654213-d281-4156-817f-7a2bf498d2a9 |  | checkpoint | Has the first wall been installed/ erected in the correct position on the slab?
checkpoint-status | f08ea262-ea7c-45df-8fc6-5dae956e590f |  | checkpoint | Have the two strips of GIB Fyreline been fixed between the top of the stud and the additional layer of GIB Fyreline to timber infill
checkpoint-status | 2689b384-4955-4cc8-8ab3-a1994b401181 |  | checkpoint | Does the metal angle protrude over the cavity gap distance, to sit perpendicular to the Barrier line plasterboard
checkpoint-status | 4df4ca71-c981-4b00-a8dc-14306b911a0f |  | checkpoint | Does the inside framing have correctly spaced studs and nogs for fixing GIB Clips and GIB Wall Straps
checkpoint-status | 80651d22-1113-4f7a-8f01-1c2bb35ae4ab |  | checkpoint | Any extra nogging required to fix GIB Clips
checkpoint-status | 48f18045-4dc9-412d-91c5-309741115ab0 |  | checkpoint | Concrete floor level to an acceptable standard where the bottom Barrier line perimeter track will be fixed
checkpoint-status | 4ec14af9-8809-436c-889d-a7393919fbc0 |  | checkpoint | General Comments and Queries
holdpoint | f51a20e1-e35b-4983-a747-9bbcbe33f216 |  | signoff | First steel stud wall complete and ready for Barrier line installation
checkpoint-group | cbdce299-7c3c-4ac2-a55a-acb3e4d7c4c4 |  | section | Barrier line Post Checks
checkpoint-status | d4a2c494-afac-4598-ba41-c17a4114145d |  | checkpoint | Has the specified cavity gap distance been met?
checkpoint-status | ac8981e1-f2ce-483e-a760-157dbf90b3cc |  | checkpoint | H-studs installed every 600mm centres?
checkpoint-status | eba8e0d2-63e5-4844-8874-728d8e2eb474 |  | checkpoint | Do the Barrier line sheets fit tightly into the H-studs?
checkpoint-status | 84a93cac-66ee-4e3f-b16c-e188dae1ee66 |  | checkpoint | Are the ends and top of the IT wall capped with 140 perimeter channel
checkpoint-status | 45513603-d6ec-4f64-bce7-c05ba7a7ddda |  | checkpoint | Has one side of the GIB® Rondo® 140 Perimeter Channel been sealed to floor slab with fire/acoustic sealant?
checkpoint-status | dbc05fc1-751e-4bff-9910-29aa6fd0dc5b |  | checkpoint | Has the second metal angle been fixed and sealed with Fire/ Acoustic sealant
checkpoint-status | e3a08e04-bac8-46b2-acb3-3abc222ba190 |  | checkpoint | Deflection head gap been allowed for
checkpoint-status | 241a2433-d5d9-40bc-a4f2-ce6511c98de1 |  | checkpoint | GIB Wall Clips fixed to both sides of the H-studs
checkpoint-status | 29584c8d-0495-4715-a286-a32be2bd60c0 |  | checkpoint | Two GIB Wall straps fixed at wall ends
checkpoint-status | 407f2b83-c70c-4438-9fc1-3ff88db6921f |  | checkpoint | General Comments and Queries
holdpoint | 28968282-b7ca-45bb-93a7-be40a9cdbe23 |  | signoff | Request Signoff