## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Fixing QA |  |  |  |  | Yes | Fixing QA | 2000963d-3982-44b9-a7b8-d882ed191bc9
checkpoint-group |  |  | section | Fixing Prestart
checkpoint-status |  |  | checkpoint | Exterior Cladding complete
checkpoint-status |  |  | checkpoint | Joinery installed
checkpoint-status |  |  | checkpoint | Door liners installed including cavity sliders
checkpoint-status |  |  | checkpoint | Grooved jams big enough (12mm for 10mm and 15mm for 13mm) on doors and windows
checkpoint-status |  |  | checkpoint | Walls checked to be level and planed if necessary with no proding nogs
checkpoint-status |  |  | checkpoint | Metal ceiling battens running in same direction and in consideration of critical light
checkpoint-status |  |  | checkpoint | No missing hangers or clips on Metal Ceiling battens
checkpoint-status |  |  | checkpoint | No proud screws on any of the metal ceiling battens or wall strapping
checkpoint-status |  |  | checkpoint | Wall angle fixed off completely and corners fixed
checkpoint-status |  |  | checkpoint | All battens secure
checkpoint-status |  |  | checkpoint | Beam framing checked and acceptable
checkpoint-status |  |  | checkpoint | Batten joins offset
checkpoint-status |  |  | checkpoint | Brace walls have brackets or straps at each end of the element
checkpoint-status |  |  | checkpoint | Services installed completely
checkpoint-status |  |  | checkpoint | Site clean and tidy of excess materials
checkpoint-status |  |  | checkpoint | Do we require mobile scaffold?
checkpoint-status |  |  | checkpoint | If yes, have we allowed for it?
checkpoint-status |  |  | checkpoint | If yes, has it been quoted or is it a variation?
checkpoint-status |  |  | checkpoint | Scaffold safe to use/set up safely
checkpoint-status |  |  | checkpoint | General Comments and Queries
holdpoint |  |  | signoff | Work completed as per spec
checkpoint-group |  |  | section | Fixing Post Checks
checkpoint-status |  |  | checkpoint | All work completed to GIB® Site Guidelines
checkpoint-status |  |  | checkpoint | Fire rating, bracing elements and wet areas are screwed off to manufacturers specifications and have been checked against plan
checkpoint-status |  |  | checkpoint | All sheets have had centre screws on packers.
checkpoint-status |  |  | checkpoint | Butt joins, ceiling taper edges and stairwell taper edges are back blocked as per Troake Guidelines.
checkpoint-status |  |  | checkpoint | Pipes are marked on the face of the sheet. Wires within nailing distance marked.
checkpoint-status |  |  | checkpoint | All plugs and penetrations have been marked on the floor and have been cut neatly and correctly.
checkpoint-status |  |  | checkpoint | All plasterboard correctly fitted into rebated jambs.
checkpoint-status |  |  | checkpoint | All sheets 5-10mm above floor (unless specified)
checkpoint-status |  |  | checkpoint | Back block stick and centre screws removed
checkpoint-status |  |  | checkpoint | Site left clean and tidy (attach photos)
checkpoint-status |  |  | checkpoint | Site Hazard Checklist Completed (attach photos)
checkpoint-status |  |  | checkpoint | General Comments and Queries
holdpoint |  |  | signoff | Request signoff
checklist-sectioned |  |  | checklist | Stopping QA |  |  |  |  | Yes | Stopping QA | fa80d705-7bda-4979-a158-08b2ffaa5408
checkpoint-group |  |  | section | Stopping Prestart
checkpoint-status |  |  | checkpoint | Do we require mobile scaffold?
checkpoint-status |  |  | checkpoint | If yes, have we allowed for it?
checkpoint-status |  |  | checkpoint | If yes, has it been quoted or is it a variation?
checkpoint-status |  |  | checkpoint | Scaffold safe to use/set up safely
checkpoint-status |  |  | checkpoint | Bracing walls fixed correctly
checkpoint-status |  |  | checkpoint | No proud scews
checkpoint-status |  |  | checkpoint | No overdriven screws
checkpoint-status |  |  | checkpoint | Backblocking of joins as per Troake Backblocking guidelines
checkpoint-status |  |  | checkpoint | All areas of broken GIB dug out and ready for pre-filling
checkpoint-status |  |  | checkpoint | Sheet layout correct and in consideration of critical light
checkpoint-status |  |  | checkpoint | Grooved liners fitted correctly if present
checkpoint-status |  |  | checkpoint | All joins as per GIB site Guide above windows and doors etc
checkpoint-status |  |  | checkpoint | General Comments and Queries
holdpoint |  |  | signoff | Area ready for stopping
checkpoint-group |  |  | section | Stopping Post Check
checkpoint-status |  |  | checkpoint | All work completed to GIB® Site Guidelines
checkpoint-status |  |  | checkpoint | Screws adequately covered
checkpoint-status |  |  | checkpoint | Joints flat and level
checkpoint-status |  |  | checkpoint | Square stop and corner joints square/ straight to the eye
checkpoint-status |  |  | checkpoint | GIB® Cove joints
checkpoint-status |  |  | checkpoint | Site left clean and tidy
checkpoint-status |  |  | checkpoint | Floors scraped clean
checkpoint-status |  |  | checkpoint | All slimlines, J-moulds, negative detail or any other finishing systems completed plumb, level square and straight to the eye
checkpoint-status |  |  | checkpoint | Light check complete
checkpoint-status |  |  | checkpoint | Materials to be pickedup from site
checkpoint-status |  |  | checkpoint | Site left clean and tidy, attach photos
checkpoint-status |  |  | checkpoint | General Comments and Queries
holdpoint |  |  | signoff | Request signoff
checklist-sectioned |  |  | checklist | Interior Painting QA |  |  |  |  | Yes | Interior Painting QA | 6b753720-cf62-4b42-981d-142dfa03cddb
checkpoint-group |  |  | section | Interior Painting Prestart
checkpoint-status |  |  | checkpoint | Square stop
checkpoint-status |  |  | checkpoint | Internals returns
checkpoint-status |  |  | checkpoint | Behind cupboards
checkpoint-status |  |  | checkpoint | Dust in corner top and bottom
checkpoint-status |  |  | checkpoint | Wave in square stop
checkpoint-status |  |  | checkpoint | Around meters
checkpoint-status |  |  | checkpoint | Bathroom shower bottoms
checkpoint-status |  |  | checkpoint | Switchers and plugs cut outs
checkpoint-status |  |  | checkpoint | Do we require mobile scaffold?
checkpoint-status |  |  | checkpoint | If yes, have we allowed for it?
checkpoint-status |  |  | checkpoint | If yes, has it been quoted or is it a variation?
checkpoint-status |  |  | checkpoint | Scaffold safe to use/set up safely
checkpoint-status |  |  | checkpoint | Lumps and bumps
checkpoint-status |  |  | checkpoint | General Comments and Queries
holdpoint |  |  | signoff | Area ready to begin
checkpoint-group |  |  | section | Interior Painting Post Checks
checkpoint-status |  |  | checkpoint | Walls
checkpoint-status |  |  | checkpoint | Ceilings
checkpoint-status |  |  | checkpoint | Doors
checkpoint-status |  |  | checkpoint | Trims
checkpoint-status |  |  | checkpoint | Skirting
checkpoint-status |  |  | checkpoint | Windows
checkpoint-status |  |  | checkpoint | Site left clean and tidy
checkpoint-status |  |  | checkpoint | Paint to be left on site
checkpoint-status |  |  | checkpoint | General Comments and Queries
holdpoint |  |  | signoff | Request signoff
checklist-flat | 7787bc48-d36f-4769-ab50-4fecc825c89f |  | checklist | Defects |  |  |  |  | Yes | Add Defects | 6a8a610e-a12e-4699-a256-0d38d09af81b
checkpoint-status | 79dcd694-0b1a-488b-9224-ba78b331f992 |  | checkpoint | Item 1
checkpoint-status | 5a1efa05-5bb1-4902-818a-ee295e7e9fae |  | checkpoint | Item 2
checkpoint-status | 28313726-fda2-4d82-9169-09e905616b4b |  | checkpoint | Item 3
checkpoint-status | 3b9f9121-c6a6-4d11-8850-b9043c887e95 |  | checkpoint | Item 4
checkpoint-status | dbc9a0b7-21be-4d16-a035-4be9edd5328a |  | checkpoint | Item 5
checkpoint-status | 172f6e2d-4cae-4624-9095-8130c786b7b4 |  | checkpoint | Item 6
checkpoint-status | 5d2a8fe3-b439-4f07-8f4f-1be5487d173f |  | checkpoint | Item 7
checkpoint-status | 1903eea6-db7b-4389-9461-90847e8ba686 |  | checkpoint | Item 8
checkpoint-status | c2090606-3f1d-482c-8688-48ed4dbd950a |  | checkpoint | Item 9
checkpoint-status | ac31353f-4adc-4d28-99f5-59fd166916d4 |  | checkpoint | Item 10
checkpoint-status | a2f12d50-3489-4bd3-9fb0-af6853a28bad |  | checkpoint | Item 11
checkpoint-status | d259021f-3f29-408f-99a3-5501c538465b |  | checkpoint | Item 12
checkpoint-status | a620ab27-3153-4b73-914c-2229a9a0a0aa |  | checkpoint | Item 13
checkpoint-status | c57b2a33-fe1d-4104-92d2-0c9b7c2cac27 |  | checkpoint | Item 14
checkpoint-status | 565e484f-4fbd-48c9-9583-3f9c0ae5df5c |  | checkpoint | Item 15
checkpoint-status | 74da9e1d-f2e0-4945-a0c6-208ccef90603 |  | checkpoint | Item 16
checkpoint-status | bc120340-b64b-4c26-b4af-0274085ff6c6 |  | checkpoint | Item 17
checkpoint-status | a3122549-6d84-400b-86fb-c83ce6edad5f |  | checkpoint | Item 18
checkpoint-status | b3219a96-17f1-4021-af81-cb202454f038 |  | checkpoint | Item 19
checkpoint-status | acc44c60-d245-4ede-900c-87f55a205cc7 |  | checkpoint | Item 20
checkpoint-status | f9f4cc8a-d44a-495c-a053-565a5060707a |  | checkpoint | Item 21
checkpoint-status | 28b023d1-3e83-430d-aa8d-3d4f18a65a7e |  | checkpoint | Item 22
checkpoint-status | 85e9f5f7-5847-4a84-b279-a197b7fc6621 |  | checkpoint | Item 23
checkpoint-status | 925939d4-7dab-4ef2-8f23-24351a4cf2c4 |  | checkpoint | Item 24
checkpoint-status | aec44139-1a5e-4237-a9e2-bf356182d706 |  | checkpoint | Item 25
checklist-sectioned |  |  | checklist | Grid Install |  |  |  |  | Yes | Grid QA | de5506be-2d64-475f-9722-f75b11e682b9
checkpoint-group |  |  | section | Grid Prestart
checkpoint-status |  |  | checkpoint | Batten direction discussed and considered for critical light
checkpoint-status |  |  | checkpoint | Nogging requested from/by builders
checkpoint-status |  |  | checkpoint | Firewalls Considered? i.e. Wall angle left off if IT Wall is full height
checkpoint-status |  |  | checkpoint | Tiling (Wall angle in shower)
checkpoint-status |  |  | checkpoint | System considered and accounted for and all material ordered
checkpoint-status |  |  | checkpoint | Walls straight and true for wall angle
checkpoint-status |  |  | checkpoint | Site clean and tidy for start
checkpoint-status |  |  | checkpoint | Bulkheads considered where required
checkpoint-status |  |  | checkpoint | All services in
checkpoint-status |  |  | checkpoint | All building work completed so work can begin
checkpoint-status |  |  | checkpoint | Do we require mobile scaffold?
checkpoint-status |  |  | checkpoint | If yes, have we allowed for it?
checkpoint-status |  |  | checkpoint | If yes, has it been quoted or is it a variation?
checkpoint-status |  |  | checkpoint | Scaffold safe to use/set up safely
checkpoint-status |  |  | checkpoint | General Comments and Queries
holdpoint |  |  | signoff | Area ok to proceed
checkpoint-group |  |  | section | Grid Post Checks
checkpoint-status |  |  | checkpoint | Ceiling Grid Complete
checkpoint-status |  |  | checkpoint | Earth Strapping
checkpoint-status |  |  | checkpoint | Bulkhead’s formed where required and plumb, level & square
checkpoint-status |  |  | checkpoint | Tiling (Wall angle in shower)
checkpoint-status |  |  | checkpoint | Battens all running in the same direction and correct orientation for critical light/ sheet layout
checkpoint-status |  |  | checkpoint | Batten joins offset
checkpoint-status |  |  | checkpoint | Joins Flush
checkpoint-status |  |  | checkpoint | No missing hangers or clips
checkpoint-status |  |  | checkpoint | Corners fixed correctly
checkpoint-status |  |  | checkpoint | Wall angle straight and true
checkpoint-status |  |  | checkpoint | Is angle the right way to supply top fixings for plasterboard?container
checkpoint-status |  |  | checkpoint | Correct Screw Placing and clips screwed off properly
checkpoint-status |  |  | checkpoint | No proud screws or fixings
checkpoint-status |  |  | checkpoint | Site clean and tidy
checkpoint-status |  |  | checkpoint | Is there any gear that needs to be collected from site? Can this be removed in the van? If not schedule pickup.
checkpoint-status |  |  | checkpoint | General Comments and Queries
holdpoint |  |  | signoff | Request signoff
checklist-sectioned |  |  | checklist | Exterior Painting QA |  |  |  |  | Yes | Exterior Painting QA | 0b67a676-2357-432d-ac92-580fe5ef1128
checkpoint-group |  |  | section | Exterior Painting Prestart
checkpoint-status |  |  | checkpoint | Do we require access/scaffold?
checkpoint-status |  |  | checkpoint | If yes, have we allowed for it?
checkpoint-status |  |  | checkpoint | If yes, has it been quoted or is it a variation?
checkpoint-status |  |  | checkpoint | Lumps and bumps
checkpoint-status |  |  | checkpoint | General Comments and Queries
holdpoint |  |  | signoff | Area ready to begin
checkpoint-group |  |  | section | Exterior Painting Post Checks
checkpoint-status |  |  | checkpoint | Soffits
checkpoint-status |  |  | checkpoint | Weatherboards
checkpoint-status |  |  | checkpoint | Gaps
checkpoint-status |  |  | checkpoint | Substrate Dirt and Grit Free
checkpoint-status |  |  | checkpoint | Site left clean and tidy
checkpoint-status |  |  | checkpoint | Paint to be left on site
checkpoint-status |  |  | checkpoint | General Comments and Queries
holdpoint |  |  | signoff | Job 100% Complete
checklist-sectioned |  |  | checklist | Insulation QA |  |  |  |  | Yes | Insulation QA | 3ff58f35-e82f-4109-9549-6d59243e3d08
checkpoint-group |  |  | section | Insulation Prestart
checkpoint-status |  |  | checkpoint | Metal Ceiling Grid Completed
checkpoint-status |  |  | checkpoint | All nogs installed as required
checkpoint-status |  |  | checkpoint | Electrical wiring completed
checkpoint-status |  |  | checkpoint | Plumbing completed
checkpoint-status |  |  | checkpoint | Which walls and ceilings are to be insulated?
checkpoint-status |  |  | checkpoint | Do we require mobile scaffold?
checkpoint-status |  |  | checkpoint | If yes, have we allowed for it?
checkpoint-status |  |  | checkpoint | If yes, has it been quoted or is it a variation?
checkpoint-status |  |  | checkpoint | Scaffold safe to use/set up safely
checkpoint-status |  |  | checkpoint | Garage included or excluded?
checkpoint-status |  |  | checkpoint | Any noise reduction batts to walls or midfloors
checkpoint-status |  |  | checkpoint | Site clean and tidy
checkpoint-status |  |  | checkpoint | All left over materials and rubbish removed
checkpoint-status |  |  | checkpoint | General Comments and Queries
holdpoint |  |  | signoff | Work completed as per spec
checkpoint-group |  |  | section | Insulation Post Check
checkpoint-status |  |  | checkpoint | Ceiling Batts installed correctly and no gaps left
checkpoint-status |  |  | checkpoint | Wall batts installed correctly and no gaps left
checkpoint-status |  |  | checkpoint | No proud insulation?
checkpoint-status |  |  | checkpoint | Insulation cut around (not over) pipes etc to prevent bulging of sheets
checkpoint-status |  |  | checkpoint | Noise reduction batts installed to walls or midfloors
checkpoint-status |  |  | checkpoint | Site clean and tidy ready for next trade?
checkpoint-status |  |  | checkpoint | General Comments and Queries
holdpoint |  |  | signoff | Request signoff