## Structure
Job Name: 105070 - Aria Bay Stage 2
Main area/First click | Level/2nd click | Apartment/3rd click | checklist needed
Main Bulding
GF
|  | Aprt 1 | checklist | Framed Baluster Checklist
|  | Aprt 2 | checklist | Framed Baluster Checklist
|  | Aprt 3 | checklist | Framed Baluster Checklist
|  | Aprt 4 | checklist | Framed Baluster Checklist
|  | Aprt 5 | checklist | Framed Baluster Checklist
|  | Aprt 6 | checklist | Framed Baluster Checklist
|  |  | checklist | Full Hight Screens
|  | Aprt 7 | checklist | Framed Baluster Checklist
|  |  | checklist | Full Hight Screens
|  | Aprt 8 | checklist | Framed Baluster Checklist
|  | Café Stairs | checklist | Framed Baluster Checklist | checklist | Stairs (add to previous if required)
|  | Aprt 01/02 Corridoor | checklist | Stairs (add to previous if required)
Level 1
|  | Aprt 101 | checklist | Framed Baluster Checklist
|  |  | checklist | Full Hight Screens
|  | Aprt 102 | checklist | Framed Baluster Checklist
|  |  | checklist | Full Hight Screens
|  | Aprt 103 | checklist | Framed Baluster Checklist
|  | Aprt 104 | checklist | Framed Baluster Checklist
|  | Aprt 105 | checklist | Framed Baluster Checklist
|  |  | checklist | Full Hight Screens
|  | Aprt 106 | checklist | Framed Baluster Checklist
|  |  | checklist | Full Hight Screens
|  | Aprt 107 | checklist | Framed Baluster Checklist
|  | Aprt 108 | checklist | Framed Baluster Checklist
|  | Aprt 109 | checklist | Framed Baluster Checklist
|  | Aprt 110 | checklist | Framed Baluster Checklist
|  | Aprt 111 | checklist | Framed Baluster Checklist
|  |  | checklist | Full Hight Screens
|  | Aprt 112 | checklist | Framed Baluster Checklist
|  |  | checklist | Full Hight Screens
|  | Aprt 113 | checklist | Framed Baluster Checklist
|  | Aprt 114 | checklist | Framed Baluster Checklist
|  | Aprt 115 | checklist | Framed Baluster Checklist
|  | Aprt 103/104 Corridoor | checklist | Stairs (add to previous if required)
Level 2
|  | Aprt 201 | checklist | Framed Baluster Checklist
|  |  | checklist | Full Hight Screens
|  | Aprt 202 | checklist | Framed Baluster Checklist
|  |  | checklist | Full Hight Screens
|  | Aprt 203 | checklist | Framed Baluster Checklist
|  | Aprt 204 | checklist | Framed Baluster Checklist
|  | Aprt 205 | checklist | Framed Baluster Checklist
|  |  | checklist | Full Hight Screens
|  | Aprt 206 | checklist | Framed Baluster Checklist
|  |  | checklist | Full Hight Screens
|  | Aprt 207 | checklist | Framed Baluster Checklist
|  | Aprt 208 | checklist | Framed Baluster Checklist
|  | Aprt 209 | checklist | Framed Baluster Checklist
|  | Aprt 210 | checklist | Framed Baluster Checklist
|  | Aprt 211 | checklist | Framed Baluster Checklist
|  |  | checklist | Full Hight Screens
|  | Aprt 212 | checklist | Framed Baluster Checklist
|  |  | checklist | Full Hight Screens
|  | Aprt213 | checklist | Framed Baluster Checklist
|  | Aprt 214 | checklist | Framed Baluster Checklist
Level 3
|  | Aprt 301 | checklist | Framed Baluster Checklist
|  |  | checklist | Full Hight Screens
|  | Aprt 302 | checklist | Framed Baluster Checklist
|  |  | checklist | Full Hight Screens
|  | Aprt 303 | checklist | Framed Baluster Checklist
|  | Aprt 304 | checklist | Framed Baluster Checklist
|  | Aprt 305 | checklist | Framed Baluster Checklist
|  |  | checklist | Full Hight Screens
|  | Aprt 306 | checklist | Framed Baluster Checklist
|  |  | checklist | Full Hight Screens
|  | Aprt 307 | checklist | Framed Baluster Checklist
|  | Aprt 308 | checklist | Framed Baluster Checklist
|  | Aprt 309 | checklist | Framed Baluster Checklist
|  | Aprt 310 | checklist | Framed Baluster Checklist
|  | Aprt 311 | checklist | Framed Baluster Checklist
|  |  | checklist | Full Hight Screens
|  | Aprt 312 | checklist | Framed Baluster Checklist
|  |  | checklist | Full Hight Screens
|  | Aprt 313 | checklist | Framed Baluster Checklist
Level 4
|  | Aprt 401 | checklist | Framed Baluster Checklist
|  |  | checklist | Full Hight Screens
|  | Aprt 402 | checklist | Vertical Safa Slat
|  | Aprt 403 | checklist | Framed Baluster Checklist
|  |  | checklist | Full Hight Screens
|  | Aprt 404 | checklist | Framed Baluster Checklist
|  | Aprt 405 | checklist | Framed Baluster Checklist
|  |  | checklist | Full Hight Screens
|  |  | checklist | Vertical Safa Slat
|  | Aprt 406 | checklist | Framed Baluster Checklist
|  |  | checklist | Full Hight Screens
|  |  | checklist | Vertical Safa Slat
Stairs and Handrails
Stair 1
|  | Flight 1 | checklist | Framed Baluster Checklist | checklist | Stairs (add to previous if required)
|  | Flight 2 | checklist | Framed Baluster Checklist | checklist | Stairs (add to previous if required)
|  | Flight 3 | checklist | Framed Baluster Checklist | checklist | Stairs (add to previous if required)
|  | Flight 4 | checklist | Framed Baluster Checklist | checklist | Stairs (add to previous if required)
|  | Flight 5 | checklist | Framed Baluster Checklist | checklist | Stairs (add to previous if required)
|  | Flight 6 | checklist | Framed Baluster Checklist | checklist | Stairs (add to previous if required)
|  | Flight 7 | checklist | Framed Baluster Checklist | checklist | Stairs (add to previous if required)
|  | Flight 8 | checklist | Framed Baluster Checklist | checklist | Stairs (add to previous if required)
Stair 2
|  | Flight 1 | checklist | Framed Baluster Checklist | checklist | Stairs (add to previous if required)
|  | Flight 2 | checklist | Framed Baluster Checklist | checklist | Stairs (add to previous if required)
|  | Flight 3 | checklist | Framed Baluster Checklist | checklist | Stairs (add to previous if required)
|  | Flight 4 | checklist | Framed Baluster Checklist | checklist | Stairs (add to previous if required)
|  | Flight 5 | checklist | Framed Baluster Checklist | checklist | Stairs (add to previous if required)
|  | Flight 6 | checklist | Framed Baluster Checklist | checklist | Stairs (add to previous if required)
|  | Flight 7 | checklist | Framed Baluster Checklist | checklist | Stairs (add to previous if required)
|  | Flight 8 | checklist | Framed Baluster Checklist | checklist | Stairs (add to previous if required)
Link Building
GF
|  | Ramp | checklist | Stairs (add to previous if required)
Level 1
|  | Ramp | checklist | Stairs (add to previous if required)

## Checklists
type | name | values
checklist | Frameless Glass Checklist
checkpoint | Work area acceptable & approval to start work
label | PS1 read and understood
label | PS1 Document number as by Engineer
label | Latest drawings available, checked and referenced
label | Relevant drawings & revisions for reference:
checkpoint | Fixing Details checked
select | Fixing Substrate Type | Wood, Concrete, Steel
checkpoint | Setout as per CAD drawings
checkpoint | Position materials and mark drill points
text | Drill depth
select | Threaded Rod/Coach Screw/Bolt Size | 6mm, 8mm, 10mm, 12mm, 14mm
select | Length of Rod/Coach Screw/Bolt Size | 80mm, 90mm, 100mm, 110mm, 120mm, 130mm, 140mm, 150mm, 160mm, 170mm, 180mm, 190mm, 200mm,210mm, 220mm
select | Epoxy Type | Ramset C6, Ramset CX801, Sika Supergrip 2 hour, Zink Galvanising Spray Paint
checkpoint | Neoprene Gasket Installed as per PS1
checkpoint | Install Spacers, Backing Channel and Clamps
checkpoint | Confirm Plumb/level/Square final positions
checkpoint | Install Glass, wedges and glazing rubbers as per PS1
checkpoint | Install Front covers, Inner and Top Rail and End Caps
checkpoint | All work completed, reviewed and approved
label | Area left clean & tidy (Photo Required)
label | Works meet PS1 specifications
checklist | Framed Baluster Checklist
checkpoint | Work area acceptable & approval to start work
label | PS1 read and understood
label | PS1 Document number as by Engineer
label | Latest drawings available, checked and referenced
label | Relevant drawings & revisions for reference:
checkpoint | Fixing Details checked
select | Fixing Substrate Type | Wood, Concrete, Steel
checkpoint | Setout as per CAD drawings
checkpoint | Position materials and mark drill points
text | Drill depth
select | Threaded Rod/Coach Screw/Bolt Size | 6mm, 8mm, 10mm, 12mm, 14mm
select | Length of Rod/Coach Screw/Bolt Size | 80mm, 90mm, 100mm, 110mm, 120mm, 130mm, 140mm, 150mm, 160mm, 170mm, 180mm, 190mm, 200mm,210mm, 220mm
select | Epoxy Type | Ramset C6, Ramset CX801, Sika Supergrip 2 hour, Zink Galvanising Spray Paint
checkpoint | Neoprene Gasket Installed as per PS1
checkpoint | Install posts and Panels
checkpoint | Confirm Plumb/level/Square final positions
checkpoint | Install Inner and Top Rail and Endcaps
checkpoint | All work completed, reviewed and approved
label | Area left clean & tidy (Photo Required)
label | Works meet PS1 specifications
checklist | Postless Baluster Checklist
checkpoint | Work area acceptable & approval to start work
label | PS1 read and understood
label | PS1 Document number as by Engineer
label | Latest drawings available, checked and referenced
label | Relevant drawings & revisions for reference:
checkpoint | Fixing Details checked
select | Fixing Substrate Type | Wood, Concrete, Steel
checkpoint | Setout as per CAD drawings
checkpoint | Position materials and mark drill points
text | Drill depth
select | Threaded Rod/Coach Screw/Bolt Size | 6mm, 8mm, 10mm, 12mm, 14mm
select | Length of Rod/Coach Screw/Bolt Size | 80mm, 90mm, 100mm, 110mm, 120mm, 130mm, 140mm, 150mm, 160mm, 170mm, 180mm, 190mm, 200mm,210mm, 220mm
select | Epoxy Type | Ramset C6, Ramset CX801, Sika Supergrip 2 hour, Zink Galvanising Spray Paint
checkpoint | Neoprene Gasket Installed as per PS1
checkpoint | Install Spacers and Backing Channel
checkpoint | Confirm Plumb/level/Square final positions
checkpoint | Install Panels
checkpoint | Install Inner and Top Rail and Endcaps
checkpoint | All work completed, reviewed and approved
label | Area left clean & tidy (Photo Required)
label | Works meet PS1 specifications
checklist | Frameless Glass arena point Checklist
checkpoint | Work area acceptable & approval to start work
label | PS1 read and understood
label | PS1 Document number as by Engineer
label | Latest drawings available, checked and referenced
label | Relevant drawings & revisions for reference:
checkpoint | Fixing Details checked
select | Fixing Substrate Type | Wood, Concrete, Steel
checkpoint | Setout as per CAD drawings
checkpoint | Position materials and mark drill points
text | Drill depth
select | Threaded Rod/Coach Screw/Bolt Size | 6mm, 8mm, 10mm, 12mm, 14mm
select | Length of Rod/Coach Screw/Bolt Size | 80mm, 90mm, 100mm, 110mm, 120mm, 130mm, 140mm, 150mm, 160mm, 170mm, 180mm, 190mm, 200mm,210mm, 220mm
select | Epoxy Type | Ramset C6, Ramset CX801, Sika Supergrip 2 hour, Zink Galvanising Spray Paint
checkpoint | Neoprene Gasket Installed as per PS1
checkpoint | Install Spacers,
checkpoint | Confirm Plumb/level/Square final positions
checkpoint | Install Glass, wedges and glazing rubbers as per PS1
checkpoint | All work completed, reviewed and approved
label | Area left clean & tidy (Photo Required)
label | Works meet PS1 specifications
checklist | Framed and Semi-Framed Glass Checklist
checkpoint | Work area acceptable & approval to start work
label | PS1 read and understood
label | PS1 Document number as by Engineer
label | Latest drawings available, checked and referenced
label | Relevant drawings & revisions for reference:
checkpoint | Fixing Details checked
select | Fixing Substrate Type | Wood, Concrete, Steel
checkpoint | Setout as per CAD drawings
checkpoint | Position materials and mark drill points
text | Drill depth
select | Threaded Rod/Coach Screw/Bolt Size | 6mm, 8mm, 10mm, 12mm, 14mm
select | Length of Rod/Coach Screw/Bolt Size | 80mm, 90mm, 100mm, 110mm, 120mm, 130mm, 140mm, 150mm, 160mm, 170mm, 180mm, 190mm, 200mm,210mm, 220mm
select | Epoxy Type | Ramset C6, Ramset CX801, Sika Supergrip 2 hour, Zink Galvanising Spray Paint
checkpoint | Neoprene Gasket Installed as per PS1
checkpoint | Install posts
checkpoint | Confirm Plumb/level/Square final positions
checkpoint | Install Glass, wedges and glazing rubbers as per PS1
checkpoint | Install Inner and Top Rail and Endcaps
checkpoint | All work completed, reviewed and approved
label | Area left clean & tidy (Photo Required)
label | Works meet PS1 specifications
checklist | Stairs (add to previous if required)
checkpoint | Install J-Mounts, Leada Rail and End Caps
checkpoint | Silicone gaps, Confirm not bigger than 2mm
checkpoint | All work completed, reviewed and approved
checklist | Arena point hand rails
checkpoint | Install J-Mounts, Leada Rail and End Caps
checkpoint | Ends fixed to wall and polished
checkpoint | All work completed, reviewed and approved
checklist | Full Hight Screens
checkpoint | Work area acceptable & approval to start work
label | PS1 read and understood
label | PS1 Document number as by Engineer
label | Latest drawings available, checked and referenced
label | Relevant drawings & revisions for reference:
checkpoint | Fixing Details checked
select | Fixing Substrate Type | Wood, Concrete, Steel
checkpoint | Setout as per CAD drawings
checkpoint | Position materials and mark drill points
text | Drill depth
select | Threaded Rod/Coach Screw/Bolt Size | 6mm, 8mm, 10mm, 12mm, 14mm
select | Length of Rod/Coach Screw/Bolt Size | 80mm, 90mm, 100mm, 110mm, 120mm, 130mm, 140mm, 150mm, 160mm, 170mm, 180mm, 190mm, 200mm,210mm, 220mm
select | Epoxy Type | Ramset C6, Ramset CX801, Sika Supergrip 2 hour, Zink Galvanising Spray Paint
checkpoint | Neoprene Gasket Installed as per PS1
checkpoint | Install posts and Panels
checkpoint | Confirm Plumb/level/Square final positions
checkpoint | Install Inner and Top Rail and Endcaps
checkpoint | All work completed, reviewed and approved
label | Area left clean & tidy (Photo Required)
label | Works meet PS1 specifications
checklist | Vertical Safa Slat
checkpoint | Work area acceptable & approval to start work
label | PS1 read and understood
label | PS1 Document number as by Engineer
label | Latest drawings available, checked and referenced
label | Relevant drawings & revisions for reference:
checkpoint | Fixing Details checked
select | Fixing Substrate Type | Wood, Concrete, Steel
checkpoint | Setout as per CAD drawings
checkpoint | Position materials and mark drill points
text | Drill depth
select | Threaded Rod/Coach Screw/Bolt Size | 6mm, 8mm, 10mm, 12mm, 14mm
select | Length of Rod/Coach Screw/Bolt Size | 80mm, 90mm, 100mm, 110mm, 120mm, 130mm, 140mm, 150mm, 160mm, 170mm, 180mm, 190mm, 200mm,210mm, 220mm
select | Epoxy Type | Ramset C6, Ramset CX801, Sika Supergrip 2 hour, Zink Galvanising Spray Paint
checkpoint | Neoprene Gasket Installed as per PS1
checkpoint | Install posts and Panels
checkpoint | Confirm Plumb/level/Square final positions
checkpoint | Install Inner and Top Rail and Endcaps
checkpoint | All work completed, reviewed and approved
label | Area left clean & tidy (Photo Required)
label | Works meet PS1 specifications
checklist | Aircon Unit Covers
checkpoint | Work area acceptable & approval to start work
label | PS1 read and understood
label | PS1 Document number as by Engineer
label | Latest drawings available, checked and referenced
label | Relevant drawings & revisions for reference:
checkpoint | Fixing Details checked
select | Fixing Substrate Type | Wood, Concrete, Steel
checkpoint | Setout as per CAD drawings
checkpoint | Position materials and mark drill points
text | Drill depth
select | Threaded Rod/Coach Screw/Bolt Size | 6mm, 8mm, 10mm, 12mm, 14mm
select | Length of Rod/Coach Screw/Bolt Size | 80mm, 90mm, 100mm, 110mm, 120mm, 130mm, 140mm, 150mm, 160mm, 170mm, 180mm, 190mm, 200mm,210mm, 220mm
select | Epoxy Type | Ramset C6, Ramset CX801, Sika Supergrip 2 hour, Zink Galvanising Spray Paint
checkpoint | Neoprene Gasket Installed as per PS1
checkpoint | Install posts and Panels
checkpoint | Confirm Plumb/level/Square final positions
checkpoint | Install Inner and Top Rail and Endcaps
checkpoint | All work completed, reviewed and approved
label | Area left clean & tidy (Photo Required)
label | Works meet PS1 specifications

## Checklist word meaning
checkpoint = | pass/fail/N/A
label = | additional text on a checkpoint
text = | empty text box
button = | up to 3 boxes you can select
select = | drop down with multiple options to select
bool = | tick box