## Precast
INSPECTION & TEST PLAN
|  | Contract Name: | [6 empty] | Rev: | Originator | Date | Approved | Date
|  | Tauhara Field facilities |  |  | Hold Point (H) | Verify (V) |  |  | 0 | Cameron Hinge | 2022-03-19
[5 empty] | Submit (S) | Review (R) |  |  | 1 | JD | 2022-03-26
Approve(A)
TASK | SPECIFICATION REFERENCE | TEST REQUIRED | INSPECTION BY | TASK TIMING OR TASK FREQUENCY | ACCEPTANCE CRITERIA | UCCL Signature | Client Signature | UCCL | Client | DATE | COMMENTS
PRECAST INSTALLATION
Preplanning | UC Temp works procedure | Construction sequence, Precast propping temporary works design, Lifting inserts required, Site Access Plan, Storage Plan, Lift Plan. | UCCL | Prior to installation | Certified TW's design, Method statement |  |  | W | R
Survey setout | IFC drawings, Shop drawings | Setout pins to determine line and level of precast elements | UCCL | Prior to installation | Survey Data / Report |  |  | W | S
Verticality and positional alignment | Locate precast items to the following tolerances: Plan: ± 10mm Vertical: ± 1mm/metre Panel Joint width: ± 1mm/metre; but no panel joint shall be less than 10mm, or more than 20mm (unless indicated otherwise on drawings) Above tolerance can be increased but should not be more than the values mentioned in NZS3109. | Check verticality of the precast elements are within spec tolerance | UCCL | During installation | Signoff the ITP |  |  | W | S
Propping precast units | Certified TW's design, Precast to be installed per Approved Code of Practice for the Safe Handling, Transportation and Erection of Pre-Cast Concrete | Check props have been installed per temporary works design. | UCCL | Before releasing crane | Permit to load |  |  | R | S
Grouting / waterproofing / joint sealing / | IFC drawings | Drossbach ducts to be filled with concrete of the element they are to be incorporated within. | UCCL | During installation | Signoff the ITP |  |  | W | S
POST-CONSTRUCTION
As Built Survey | Compliance to IFC Drawings / Shop Drawings. | Survey As-Built Drawings | UCCL | Completion | As built drawing/ report |  |  | S | R
Completion Inspection | The construction defects completed (excluding only Snagging Defects have been rectified). | Completion inspection on the structure by Constructors and Designers | UCCL | At the completion of the construction of each element | Project requirements and relevant specification / Records. |  |  | S | H